## Prj Legend
MTEP16 MISO Transmission Expansion Plan 2016 |  | Appendices A, B
Project Table Field Legend
Appendix A contains projects which are being or have been approved by MISO Board of Directors.
Transmission Owners are obligated to make a good faith effort to construct projects in Appendix A.
Appendix B projects have been reviewed by MISO staff for need and effectivenes.
Project table has blue highlighted header. A project may have multiple facilties.
Facility table has beige highlighted header. A project's facilities may have different in service dates.
Project Table Field Legend
Field | Description
Target Appendix | Target appendix for the MTEP16 planning cycle. "A in MTEP16" projects were reviewed and approved in MTEP16. This column also indicates what projects were approved in prior MTEPs that are not yet in service.
App AB | Appendix the project is in. B>A for projects moving during this planning cycle.
Region | MISO Planning Region: Central, East, West or South
Geographic Location by TO Member System | Project geographic location by Transmission Owner member systems
PrjID | Project ID: MISO project identifier
Project Name | Project name (short name)
Project Description | A description of the project's components
State 1 | State project is located or first state if in multiple states
State 2 | If applicable, the second state the project is located
Allocation Type per FF | Project Type per Attachment FF of Tariff. BaseRel is Baseline Reliability, GIP is Generator Interconnection Project, TDSP is Transmission Delivery Service Project, MEP is Market Efficiency Project, MVP is Multi Value Project, Other is none of the above. Preliminary project allocation types may be designated for projects in Appendix B
Share Status | Cost allocation status for projects in Appendix A or moving to Appendix A in current planning cycle. Projects are Shared, Not Shared or Excluded. Preliminary sharing designations may be input for Appendix B projects
Other Type | Indicates the project driver behind Other type projects.
Estimated Cost | Total estimated project cost from Facility table
Expected ISD (Min/Max) | Dates when project is expected to be in service. Min and Max dates. Expected ISD are in Facility table.
Max kV | Maximum facility voltage in project. Summary information from Facility table
Min kV | Minimum facility voltage in project. Summary information form Facility table
Transmission Project Category | Bottom-Up, Top-Down or Externally Driven per BPM-020 r15 section 2.3

## MTEP16_AppAB_Projects
MTEP16 MISO Transmission Expansion Plan 2016 | [18 empty] | Appendices A, B
Appendices A, B: Project Table 10/03/2016
Target Appendix | App AB | Planning Region | Geographic Location by TO Member System | PrjID | Prj_Rec_Date | Member_ID | Project Name | Project Description | State 1 | State2 | Allocation Type per FF | Share Status | Other Type | Estimated Cost | Expected ISD (Min) | Expected ISD (Max) | Max kV | Min kV | Transmission Project Category
A in MTEP16 | B>A | Central | AmerenIL | 3005 | 2016-04-28 | AMRN38 | S. Belleville-Tilden Terminal Equipment Upgrade | Baldwin 138 kV Substation - Construct a 5 position 138 kV ring bus at Baldwin Substation (5 - 3000 A, 40 kA PCBs). Build a 138 kV double-circuit line between Baldwin Substation and the tap to the South Belleville-Tilden 1526 138 kV line by rebuilding 2 miles of existing single-circuit 138 kV line to double-circuit capability, both circuits to have 2000 A summer emergency capability. | IL | IL | Other |  | Reliability | 3400000 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | Central | AmerenIL | 7820 | 2015-12-14 |  | Hennepin-Kewanee-6101 Reconductoring | Upgrade terminal equipment at Hennepin terminal. | IL | IL | Other |  | Condition | 300000 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | Central | AmerenIL | 7860 | 2015-09-11 |  | Effingham 138-Effingham NW Increase Ground Clearance | Effingham 138-Effingham, Northwest 138 kV Line - Elevate 2.72 miles of 954 kcmil ACSR conductor to permit operation at 120 degrees C. Upgrade terminal equipment at Effingham 138 Substation. | IL | IL | BaseRel |  |  | 2000000 | 2016-06-01 | 2016-06-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | Central | AmerenIL | 7869 | 2016-05-23 |  | Alsey Tap (Ballard) Breaker Station | Install 138 kV breaker station near tap to the PPI Alsey Plant on the Jersesyville, Northwest-Meredosia-1 138 kV line. May be an ultimate 6-breaker ring bus. | IL | IL | Other |  | Reliability | 6626495 | 2016-05-01 | 2016-05-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | Central | AmerenIL | 9261 | 2016-05-23 |  | Searitt Breaker Station | Build a 3-breaker 138 kV ring bus (Searitt Breaker Station) adjacent to the N. Decatur-Latham-1566 138 kV line near the planned Enbridge Pumping Station. Buld a radial 138 kV line to the new customer substation. | IL | IL | Other |  | Reliability | 4563667 | 2016-06-01 | 2017-12-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | Central | AmerenIL | 9722 | 2016-08-09 |  | Frederick, North 138-69 kV Transformer Replacement | Replace existing 138-69 kV transformer bank with 112 MVA unit. | IL | IL | Other |  | Distribution |  | 2016-10-03 | 2016-10-03 | 138 | 69 | Bottom-up
A in MTEP16 | B>A | Central | AmerenIL | 9726 | 2016-02-02 |  | Fogarty 138-34.5 kV Transformer Connection | Provide 138 kV connection to supply 138-34.5 kV transformer | IL | IL | Other |  | Distribution | 1726448 | 2018-06-01 | 2018-06-01 | 138 | 34.5 | Bottom-up
A in MTEP16 | B>A | Central | AmerenIL | 9727 | 2016-05-23 |  | Wakefield Substation | Establish 138 kV ring bus; connect to South Bloomington-Clinton-1372 line to supply Wakefield Substation | IL | IL | Other |  | Distribution | 7430056 | 2019-06-01 | 2019-06-01 | 138 | 34.5 | Bottom-up
A in MTEP16 | B>A | Central | AmerenIL | 9736 | 2016-01-13 |  | East Quincy-Hamilton-4 Reconductoring | Replace existing conductor | IL | IL | Other |  | Condition | 8315916 | 2016-05-01 | 2016-05-01 | 138 | 138 | Bottom-up
A in MTEP16 | B>A | Central | AmerenIL | 9741 | 2016-03-11 |  | E. Collinsville-Porter Road Terminal Equipment Upgrade | Upgrade terminal equipment at Porter Road | IL | IL | Other |  | Reliability | 50000 | 2016-05-24 | 2016-05-24 | 138 | 138 | Bottom-up
A in MTEP16 | B>A | Central | AmerenIL | 9845 | 2015-09-14 |  | Gallatin 138 kV Ring Bus | Construct 138 kV ring bus | IL | IL | Other |  | Distribution | 5621250 | 2017-05-01 | 2017-05-01 | 138 | 69 | Bottom-up
A in MTEP16 | B>A | Central | AmerenIL | 9853 | 2016-08-09 |  | Mt. Vernon, West Terminal Equipment | Upgrade terminal equipment in Prairie State-Mt. Vernon, West position | IL | IL | Other |  | Condition |  | 2017-06-01 | 2017-06-01 | 345 | 345 | Bottom-up
A in MTEP16 | B>A | Central | AmerenIL | 9869 | 2016-08-09 |  | Havana-Springfield 138 kV Upgrade | Upgrade terminal equipment | IL | IL | Other |  | Condition |  | 2017-06-01 | 2017-06-01 | 138 | 138 | Bottom-up
A in MTEP16 | B>A | Central | AmerenIL | 9873 | 2016-08-09 |  | Edwards 138-69 kV Transformer Addition | Install 138-69 kV Transformer | IL | IL | Other |  | Distribution |  | 2016-12-01 | 2016-12-01 | 138 | 69 | Bottom-up
A in MTEP16 | B>A | Central | AmerenIL | 10884 | 2016-03-11 |  | Roxford Substation - Replace 345/138 kV Transformer | Roxford 345/138 kV Substation - Replace 345/138 kV, 560 MVA transformer with a 700 MVA unit, and install a 3000 A, 50 kA PCB to place the transformer on its own position at Roxford Substation. | IL | IL | BaseRel |  |  | 3611589 | 2016-05-23 | 2016-05-23 | 345 | 138 | Bottom-up
A in MTEP16 | B>A | Central | AmerenIL | 10904 | 2016-03-18 |  | Brokaw-Gibson City South-1582 Reconductoring | Rebuild to 1200 A summer emergency capability. Upgrade line terminal equipment at Gibson City South Substation. | IL | IL | Other |  | Condition | 10318299 | 2016-12-01 | 2016-12-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | Central | AmerenIL | 11063 | 2016-04-19 |  | Rising-North Champaign-1592 Terminal Upgrade | Upgrade terminal equipment at Rising Substation on the Rising-North Champaign-1592 138 kV line position. | IL | IL | Other |  | Condition | 1747553 | 2016-12-01 | 2016-12-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | Central | AmerenMO | 10483 | 2015-12-16 |  | Cape-Kelso-2 and Kelso-Miner-2 - Increase Ground Clearance | Increase ground clearance to and perform line hardware verification to permit operation at 120 degrees C. Upgrade terminal equipment at Cape, Kelso, and Miner Substations. | MO | MO | Other |  | Condition | 5586082 | 2016-12-01 | 2016-12-01 | 161 | 161 | Bottom-up
A in MTEP16 | B>A | Central | AmerenMO | 10604 | 2016-08-09 |  | Page-Sioux-4 Reconductoring | Replace 14.28 miles of 2-300 kcmil Copper conductor with conductor matching or exceeding the capability of the rest of the line (954 kcmil ACSR conductor) | MO | MO | Other |  | Condition |  | 2016-12-01 | 2016-12-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | Central | CWLD | 10162 | 2016-06-16 |  | McBaine Line Terminal Upgrades | Upgrade McBaine-McBaine Tap line to 249 MVA (300501 bus). Replace a switch (from 600 A to 1200 A) and a wave trap (from 600 A to 2000 A). Limiting element will be conductor at 895 A = 249 MVA. | MO | MO | Other |  | Reliability | 50000 | 2016-03-01 | 2016-03-01 | 161 |  | Bottom-up
A in MTEP16 | B>A | Central | DEI | 2873 | 2015-10-06 | DIN0216 | Danville E. 69kV looped feed | Construct new Danville East substation near HRH hospital - single 22.4MVA transformer - 6945 ckt to be looped through | IN | IN | Other |  | Distribution | 990000 | 2018-06-01 | 2018-06-01 | 69 | 12 | Bottom-up
A in MTEP16 | B>A | Central | DEI | 9834 | 2015-10-30 | AMIN1055 | Noblesville to Tipton W. 230kV Rebuild | Noblesville to Tipton West 23008 ckt: Replace all single/H-frame pole structures with steel poles, reconductor with 954ACSR45X7 OVAL / OPGW and build Switching Station with 3-2000A line switches near existing Carmel 146th St. junction. | IN | IN | Other |  | Condition | 12079985 | 2018-12-31 | 2018-12-31 | 230 |  | Bottom-up
A in MTEP16 | B>A | Central | DEI | 9850 | 2016-08-03 | AMIN1129 | Lebanon Prairie Crk. 69kV Switching Station | New Lebanon Prairie Crk. 69kV Switching Station to be inserted in the 6983 ckt. | IN | IN | Other |  | Distribution | 3518244 | 2017-12-31 | 2017-12-31 | 69 |  | Bottom-up
A in MTEP16 | B>A | Central | DEI | 9854 | 2015-09-17 | AMIN1407 | Speed 138kV - Brkr Replacements | Speed 138kV - Replace OCB 13850, 13857, 13869, 13881, 138138 TIE and obsolete relays on CIR 13850, 13857, 13881. | IN | IN | Other |  | Condition | 2264125 | 2017-12-31 | 2017-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | Central | DEI | 9855 | 2015-11-30 | TIN1422 | Columbus North Brkr / Relay Replacements | Columbus North: Replace OCB 6975, 6929, 69230-1, 6950 and obsolete relays on CIR 6929, 6950, 6975, 6982. Also replace relays on CIR 23019. | IN | IN | Other |  | Condition | 2711016 | 2020-12-31 | 2020-12-31 | 230 | 69 | Bottom-up
A in MTEP16 | B>A | Central | DEI | 9856 | 2015-09-14 | TIN1406 | Walton 230-69kV Brkr Replacements | Walton: Replace OCB 69 KV CAP BK, 69230-1, 69110, 69 KV TRANSFER, 6927, 6987, 23020-21. | IN | IN | Other |  | Condition | 3303866 | 2017-12-31 | 2017-12-31 | 230 | 69 | Bottom-up
A in MTEP16 | B>A | Central | DEI | 9858 | 2016-01-25 | TIN1469 | Bedford 345 Brkr / Xfmr Replacements | Bedford 345: Replace 345/138kV Bank 7; Replace relays on CIR 6995, 13829, 13837, 34506, 34521. Replace all 69kV and 138kV Oil Circuit Breakers. | IN | IN | Other |  | Condition | 12078813 | 2018-12-31 | 2018-12-31 | 345 | 69 | Bottom-up
A in MTEP16 | B>A | Central | DEI | 9888 | 2015-09-14 | TIN1528 | MiddleFork to Deer Crk. Jct. 69kV rebuild | Rebuild 6988 ckt. from MiddleFork sub to deadend 879/1041-01 and from Deer Cr Jct to 879/1046. 477acsr@120C w/ OPGW - 187 wood poles to be replaced with light duty steel. | IN | IN | Other |  | Condition | 4860632 | 2017-12-31 | 2017-12-31 | 69 |  | Bottom-up
A in MTEP16 | B>A | Central | DEI | 9889 | 2015-09-14 | TIN1530 | Sharpsville to Kokomo SE 69kV rebuild | Rebuild 69174 ckt. from Sharpsville sub to Kokomo SE. 477acsr@120C w/ OPGW - 174 wood poles to be replaced with light duty steel. | IN | IN | Other |  | Condition | 4287945 | 2017-12-31 | 2017-12-31 | 69 |  | Bottom-up
A in MTEP16 | B>A | Central | DEI | 9890 | 2015-09-14 | TIN1536 | Gibson Sta. to Merom Sta. 345kV Deadend Structures | Gibson to Merom: Install (10) double deadend structures in the 34511 ckt. | IN | IN | Other |  | Condition | 4433734 | 2017-12-31 | 2017-12-31 | 345 |  | Bottom-up
A in MTEP16 | B>A | Central | DEI | 9891 | 2015-09-14 | TIN1534 | Flat Rock to Hope Jct. 69kV Pole Replacements | Flat Rock to Hope Jct. 6975 ckt. pole replacements (45), replace line switches at both ends. Transfer existing conductor to new poles. | IN | IN | Other |  | Condition | 1087274 | 2016-12-31 | 2016-12-31 | 69 |  | Bottom-up
A in MTEP16 | B>A | Central | DEI | 9892 | 2016-07-22 | TIN1533 | Lewis Crk. to Flat Rock 69kV Pole Replacements | Lewis Crk. to Flat Rock 6975 ckt. pole replacements (100), replace line switches at Lewis Crk with 1200A. Transfer existing conductor to new poles. | IN | IN | Other |  | Condition | 1875342 | 2018-12-31 | 2018-12-31 | 69 |  | Bottom-up
A in MTEP16 | B>A | Central | DEI | 9893 | 2015-09-14 | TIN1581 | Shelbyville Northeast CB and Relay Replacements | Shelbyville Northeast - Replace CIR 6946, 6976, 69183, 13803, 13865 relays, replace OCBs 6946, 6976, 69183, 69138-1, 13803, replace Bank 1 ground switch with circuit switcher, and station battery. | IN | IN | Other |  | Condition | 3511433 | 2017-06-01 | 2017-06-01 | 138 | 69 | Bottom-up
A in MTEP16 | B>A | Central | DEI | 9897 | 2015-09-15 | DIN1393 | River Ridge Gateway 138-12kV New Sub. | River Ridge Gateway 138-12kV Sub. to be inserted in the 13857 ckt. between Clark Maritime and HE Northport | IN | IN | Other |  | Distribution | 1000000 | 2018-06-01 | 2018-06-01 | 138 | 12 | Bottom-up
A in MTEP16 | B>A | Central | DEI | 9905 | 2015-11-30 | TIN1529 | Sharpsville to Windfall Jct. 69kV rebuild | Rebuild 69174 from Sharpsville sub to Windfall Jct - 477acsr@120C w/ OPGW - 81 wood poles to be replaced with light duty steel. Replace (3) Windfall Jct switches with 1200A. Install new motor mechs on 69-1 and 69-3 at Windfall Junction. | IN | IN | Other |  | Condition | 2179983 | 2017-12-31 | 2017-12-31 | 69 |  | Bottom-up
A in MTEP16 | B>A | Central | DEI | 9914 | 2015-10-26 | TIN1609 | Mohawk to Lee Hanna 69kV rebuild | Rebuild 5.84 mile 69kV - 69130 ckt. from Mohawk to Mohawk Ind. Jct to Lee Hanna Jct with 954ACSR@120C - replace (2) Lee Hanna Jct line switches with 1200A | IN | IN | Other |  | Condition | 3741298 | 2017-06-01 | 2017-06-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | Central | DEI | 9926 | 2016-07-22 | DIN1620 | Spelterville 138-34kV Sub Expansion | Spelterville: expand sub footprint, Install 138/34kV 60MVA Bank | IN | IN | Other |  | Condition | 1000000 | 2018-12-31 | 2018-12-31 | 138 | 34 | Bottom-up
A in MTEP16 | B>A | Central | DEI | 10144 | 2015-09-30 | TIN1640 | Cayuga Station 230kV Breakers Replace | Cayuga Gen. Sta.: Replace existing 230kV OCBs 23011-03, 23013-11,230B9-13 and associated disconnect switches. New brkrs will be 3000 amp, 63KIA with 3000A disc switches. | IN | IN | BaseRel |  |  | 1536000 | 2017-12-31 | 2017-12-31 | 230 |  | Bottom-up
A in MTEP16 | B>A | Central | DEI | 11343 | 2016-08-10 | TIN1923 | Lafayette SE to General Foods Jct 13808 Reconductor | Lafayette SE to General Foods Jct 13808 Reconductor: rebuild 0.64 mile of 138kV line with 954acsr@120C | IN | IN | BaseRel |  |  | 1060000 | 2018-06-01 | 2018-06-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | Central | IPL | 9220 | 2015-06-23 |  | Parker Substation Breaker Replacements | Replacement of three (3) 138 kV breakers at Parker Substation; Two line breakers for the 132-07 and 132-17 transmission lines and a bus-tie breaker. | IN | IN | BaseRel |  |  |  | 2018-12-31 | 2018-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | Central | IPL | 9221 | 2015-06-23 |  | Southport Substation Breaker Replacement | Replacement of one (1) 138 kV breaker at Southport Substation; One line breaker for the 132-29 transmission line. | IN | IN | BaseRel |  |  |  | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | Central | IPL | 9222 | 2015-06-23 |  | Thompson 138 kV Substation Breaker Replacements | Replacement of three (3) 138 kV breakers at Thompson 138 kV Substation; Two line breakers for the 132-68 and 132-77 transmission lines and a bus-tie breaker. | IN | IN | BaseRel |  |  |  | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | Central | IPL | 9223 | 2015-06-23 |  | River Road Substation Breaker Replacement | Replacement of one (1) 138 kV breaker at River Road Substation; One bus-tie breaker. | IN | IN | BaseRel |  |  |  | 2018-12-31 | 2018-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | Central | IPL | 9602 | 2015-09-03 |  | Mooresville Substation Breaker Replacements | Replacement of three (3) 138 kV breakers at Mooresville Substation; Two (2) line breakers for the 132-84 and 132-24 lines and a bus-tie breaker. | IN | IN | BaseRel |  |  |  | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | Central | IPL | 11123 | 2016-04-26 |  | Guion Relay Addition | Addition of redundant bus differential (87) relay at Guion 345 kV south bus section. | IN | IN | BaseRel |  |  |  | 2017-07-15 | 2017-07-15 | 345 |  | Bottom-up
A in MTEP16 | B>A | Central | IPL | 11523 | 2016-08-17 |  | Stout CT - Stout North Line Rating Upgrade | Increase line rating from 322 to 345 MVA | IN | IN | Other |  | Reliability |  | 2021-06-30 | 2021-06-30 | 138 |  | Bottom-up
A in MTEP16 | B>A | Central | IPL | 11643 | 2016-08-10 |  | Replace Failed Stout Auto | Replace Failed Stout Auto | IN | IN | Other |  | Condition |  | 2017-06-01 | 2017-06-01 | 345 |  | Bottom-up
A in MTEP16 | B>A | Central | PPI | 9564 | 2015-09-14 | 2016-12,38,39,43 | Turris Tap Breaker Station, Turris-Athens 138 kV, Athens 138/69 kV station | Construct Turris tap 138 kV 4-breaker station, Turris-Athens 138 kV transmission line, Athens 138/69 kV substation, Athens Tap 69 kV switching station | IL | IL | Other |  | Reliability | 16297000 | 2019-12-01 | 2020-12-01 | 138 | 69 | Bottom-up
A in MTEP16 | B>A | Central | Vectren | 4393 | 2016-08-10 | 2013SIGE7 | Y67-2 Dubois - Huntingburg Rebuild | Rebuild and Reconductor approx. 3.5 miles of 69 kV | IN | IN | Other |  | Distribution | 2625000 | 2018-12-31 | 2018-12-31 | 69 |  | Bottom-up
A in MTEP16 | B>A | Central | Vectren | 9940 | 2016-04-01 | 2016SIGE1 | Elliott Dist Sub and Y52 69kV Line Loop | New Distribution Substation with 9.375MVA 69kV/12kV transformer and Y52 69kV loop from Elliott sub to Sunbeam sub for load growth | IN | IN | Other |  | Distribution | 1350000 | 2015-12-31 | 2015-12-31 | 69 | 12 | Bottom-up
A in MTEP16 | B>A | Central | Vectren | 9942 | 2016-06-16 | 2016SIGE2 | Z85 138kV Line Relocation for Road Widening | Public Roadway relocation of 1.25 miles of Z85 138kV line | IN | IN | Other |  | Relocation | 1200000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | Central | Vectren | 9946 | 2016-08-10 | 2016SIGE11 | Adams Substation for Distribution | 69kV/12kV distribution substation to serve customer load (Y65). | IN | IN | Other |  | Distribution | 2100000 | 2018-12-31 | 2018-12-31 | 138 | 12 | Bottom-up
A in MTEP16 | B>A | Central | Vectren | 9948 | 2016-08-25 | 2016SIGE11 | Y56 69kV Line Rebuild from Pelzer to Chrisney | 69kV line Y56 rebuild from Pelzer to Chrisney substations. | IN | IN | Other |  | Distribution | 6800000 | 2019-12-31 | 2019-12-31 | 69 |  | Bottom-up
A in MTEP16 | B>A | Central | Vectren | 9952 | 2016-08-25 | 2016SIGE13 | Y43 Berry Plastics Sub Loop Feed | Berry Plastics Substation loop feed (69kV Y43). | IN | IN | Other |  | Distribution | 300000 | 2018-12-31 | 2018-12-31 | 69 |  | Bottom-up
A in MTEP16 | B>A | East | CETO | 9543 | 2016-03-30 |  | Stamping Plant 138 kV Circuit Breaker Replacement | Increase short-circuit capacity of the 177 and 188 circuit breakers | MI | MI | BaseRel |  |  | 560000 | 2016-06-30 | 2016-06-30 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | CETO | 9544 | 2015-09-14 |  | CE Annual Breaker Replacement Program - 2017 | CE Breaker Replacement Program - 2017 | MI | MI | Other |  | Condition | 1240000 | 2017-12-31 | 2017-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | CETO | 9545 | 2015-09-14 |  | CE Annual Breaker Replacement Program - 2016 | Breaker Replacement Program for 2016 | MI | MI | Other |  | Condition | 1380000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | CETO | 9859 | 2015-09-14 |  | CE Line Equipment Replacement Program - 2016 | Replace cross arms, insulators, guying, and switches as needed to maintain the lines' condition | MI | MI | Other |  | Condition | 160000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | CETO | 9860 | 2015-09-14 |  | CE Line Equipment Replacement Program - 2017 | Replace cross arms, insulators, guying, and switches as needed to maintain the lines' condition | MI | MI | Other |  | Condition | 160000 | 2017-12-31 | 2017-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | CETO | 9861 | 2015-09-14 |  | CE Pole Replacement Program - 2016 | Replace damaged or defective poles with new poles | MI | MI | Other |  | Condition | 360000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | CETO | 9862 | 2015-09-14 |  | CE Pole Replacement Program - 2017 | Replace damaged or defective poles with new poles | MI | MI | Other |  | Condition | 680000 | 2017-12-31 | 2017-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | CETO | 9863 | 2015-09-14 |  | CE Line Sag Remediation - 2016 | Install poles or replace spans of conductor to remediate sag limits | MI | MI | Other |  | Reliability | 400000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | CETO | 9865 | 2015-09-14 |  | CE Relay Replacement Program - 2016 | Replace electromechanical and/or defective relays with new digital relays | MI | MI | Other |  | Condition | 240000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | CETO | 9866 | 2015-09-14 |  | CE Relay Replacement Program - 2017 | Replace electromechanical and/or defective relays with new digital relays | MI | MI | Other |  | Condition | 480000 | 2017-12-31 | 2017-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | CETO | 9868 | 2015-09-14 |  | CE Substation Equipment Replacements - 2016 | Replace damaged or defective substation equipment, not including breakers or relays, with new equipment | MI | MI | Other |  | Condition | 560000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | CETO | 9870 | 2015-09-14 |  | CE Substation Equipment Replacements - 2017 | Replace damaged or defective substation equipment, not including breakers or relays, with new equipment | MI | MI | Other |  | Condition | 500000 | 2017-12-31 | 2017-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | CETO | 9871 | 2016-05-20 |  | Edenville-Edenville Jct 138 kV Line Rebuild - North | Rebuild the north portion of the Edenville-Edenville Jct 138 kV Line, approximately 9.8 miles, utilizing 138 kV single circuit construction and 336.4 ACSR conductor. | MI | MI | Other |  | Condition | 4170000 | 2017-12-31 | 2017-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | CETO | 9872 | 2016-05-20 |  | Edenville-Edenville Jct 138 kV Line Rebuild - South | Rebuild the south portion of the Edenville-Edenville Jct 138 kV Line, approximately 2.0 miles, utilizing 138 kV single circuit construction and 336.4 ACSR conductor. | MI | MI | Other |  | Condition | 850000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | CETO | 9874 | 2015-09-14 |  | Cole Creek Spur 138 kV Line Rebuild | Rebuild the Cole Creek-Cole Creek Jct 138 kV Line, approximately 4.7 miles, utilizing 138 kV single circuit construction and 795 ACSR conductor. | MI | MI | Other |  | Condition | 1960000 | 2017-12-31 | 2017-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | CETO | 9875 | 2016-09-30 |  | Chase 138 kV Bus Rebuild | Rebuild the 138 kV portion of Chase Substation to a three breaker ring bus | MI | MI | Other |  | Reliability | 3200000 | 2017-12-31 | 2017-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | CETO | 9878 | 2015-09-14 |  | Vrooman - Complete 138 kV Bus | Complete the 138 kV bus as a ring by adding one 138 kV breaker | MI | MI | Other |  | Reliability | 800000 | 2018-06-01 | 2018-06-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | CETO | 10046 | 2015-09-17 |  | Beaver Creek Customer Interconnection | Consumers Energy has received a request to connect a new load near Grayling. Construct a 138 kV three breaker ring bus at Beaver Creek Substation. Replace relaying at Higgins Substation. | MI | MI | Other |  | Distribution | 3500000 | 2018-03-01 | 2018-03-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | CETO | 10763 | 2016-05-04 |  | J392 Generation Upgrades-CE | Add a wavetrap and upgrade relaying at Emmet Substation to accommodate the addition of a dual-pilot relay scheme on the Emmet-Livingston 138 kV Line. | MI | MI | GIP |  |  | 874000 | 2016-06-17 | 2016-06-17 | 138 |  | Externally-Driven
A in MTEP16 | B>A | East | ITCT | 9685 | 2015-09-10 | ITC_15_016 | Jacob - St. Clair 120 kV Sag Remediation | Remediate the Sag Limit on Jacob-St. Clair 120 kV to 292 MVA (1405 Amp) | MI | MI | BaseRel |  |  | 139000 | 2019-12-31 | 2019-12-31 | 120 |  | Bottom-up
A in MTEP16 | B>A | East | ITCT | 9692 | 2015-09-10 | ITC_15_022 | Seneca - Spokane 120 kV Sag Remediation | Remediate the Sag Limit on Seneca-Spokane 120 kV to 283 MVA (1362 Amp) | MI | MI | BaseRel |  |  | 339000 | 2018-12-31 | 2018-12-31 | 120 |  | Bottom-up
A in MTEP16 | B>A | East | ITCT | 9883 | 2015-09-14 | ITC_15_025 | Ironton 120 kV-Install Two Line Breakers | Install two 120 kV breakers to terminate the two River Rouge–Ironton 120 kV connections at Ironton | MI | MI | BaseRel |  |  | 910000 | 2019-12-31 | 2019-12-31 | 120 |  | Bottom-up
A in MTEP16 | B>A | East | ITCT | 9884 | 2016-09-30 | ITC_15_015 | Belle River - Pontiac 345 kV Sag Remediation | Raise the Sag Limit on Belle River-Pontiac 345 kV to 1414 MVA (2366 Amp) | MI | MI | Other |  | Reliability | 340000 | 2019-12-31 | 2019-12-31 | 345 |  | Bottom-up
A in MTEP16 | B>A | East | ITCT | 9887 | 2016-09-30 | ITC_15_019 | Pontiac - Wixom 345 kV Sag Remediation | Raise the Sag Limit on Pontiac-Wixom 345 kV to 1185 MVA (1983 Amp) | MI | MI | Other |  | Reliability | 305000 | 2019-12-31 | 2019-12-31 | 345 |  | Bottom-up
A in MTEP16 | B>A | East | ITCT | 9900 | 2015-09-15 | ITC_15_020 | River Rouge - Ironton #2 120 kV Sag Remediation | Raise the Sag Limit on River Rouge-Ironton #2 120 kV to 271 MVA (1304 Amps) | MI | MI | BaseRel |  |  | 340000 | 2018-12-31 | 2018-12-31 | 120 |  | Bottom-up
A in MTEP16 | B>A | East | ITCT | 9902 | 2015-09-15 | ITC_15_030 | Sterling 120 kV Ring Bus | Install a new 120 kV bus and one 120 kV breaker to convert Sterling to a ring bus. Also move the Sterling transformer #201 connection to the new bus and install a disconnect switch on the low side. Breaker “HT” will become the bus-tie between bus #101 and #104 | MI | MI | BaseRel |  |  | 1100000 | 2018-12-31 | 2018-12-31 | 120 |  | Bottom-up
A in MTEP16 | B>A | East | ITCT | 9994 | 2015-12-04 | ITC_15_007 | Custer - Monroe 120 kV Line Rebuild | Rebuild the entire Custer – Monroe 120 kV line. Pre-build it to 230 kV construction to facilitate possible future 230 kV expansion in southern Michigan. Replace all existing structures and conductor with new double-circuit structures that are designed for bundled 954 ACSR 54/7 conductor and install this conductor along with an OPGW path. Also, upgrade terminal equipment at Custer and Monroe | MI | MI | BaseRel |  |  | 14500000 | 2019-12-31 | 2019-12-31 | 120 |  | Bottom-up
A in MTEP16 | B>A | East | ITCT | 9998 | 2015-09-15 |  | 2017 ITCT Asset Replacement Program | Replace aging and outdated equipment on a cycle that will ensure each piece of equipment is replaced near its expected end of life. Modern equipment can improve reliability, use state of the art technology, and typically will allow for longer maintenance intervals. New equipment is also commonly equipped with better monitoring and alarming functionality giving improved remote supervision. All of this will help to reduce overall maintenance costs | MI | MI | Other |  | Reliability | 47970000 | 2017-12-31 | 2017-12-31 | 345 | 120 | Bottom-up
A in MTEP16 | B>A | East | ITCT | 9999 | 2015-09-15 |  | 2018 ITCT Asset Replacement Program | Replace aging and outdated equipment on a cycle that will ensure each piece of equipment is replaced near its expected end of life. Modern equipment can improve reliability, use state of the art technology, and typically will allow for longer maintenance intervals. New equipment is also commonly equipped with better monitoring and alarming functionality giving improved remote supervision. All of this will help to reduce overall maintenance costs. | MI | MI | Other |  | Reliability | 53250000 | 2018-12-31 | 2018-12-31 | 345 | 120 | Bottom-up
A in MTEP16 | B>A | East | ITCT | 10000 | 2015-09-15 |  | 2019 ITCT Asset Replacement Program | Replace aging and outdated equipment on a cycle that will ensure each piece of equipment is replaced near its expected end of life. Modern equipment can improve reliability, use state of the art technology, and typically will allow for longer maintenance intervals. New equipment is also commonly equipped with better monitoring and alarming functionality giving improved remote supervision. All of this will help to reduce overall maintenance costs. | MI | MI | Other |  | Reliability | 53310000 | 2019-12-31 | 2019-12-31 | 345 | 120 | Bottom-up
A in MTEP16 | B>A | East | ITCT | 10010 | 2016-03-23 |  | ITCT Customer Interconnections - Year 2019 | Customer interconnection requests and retirements. | MI | MI | Other |  | Distribution | 2000000 | 2019-12-31 | 2019-12-31 | 120 |  | Bottom-up
A in MTEP16 | B>A | East | ITCT | 10243 | 2015-10-16 |  | Navarre 120 kV Breakers HX Replacement | Upgrade the existing Navarre 120 kV breaker HX to have an interrupting capability of 50 kA. | MI | MI | Other |  | Reliability | 70000 | 2018-06-30 | 2018-06-30 | 120 |  | Bottom-up
A in MTEP16 | B>A | East | ITCT | 10270 | 2016-09-30 | ITC_15_053 | Apache – Seneca 120 kV Sag Remediation | The proposed solution is to remediate the sag limit on the Apache – Seneca 120 kV line to 230 MVA (1107 Amp). | MI | MI | BaseRel |  | Reliability | 202000 | 2018-12-31 | 2018-12-31 | 120 |  | Bottom-up
A in MTEP16 | B>A | East | ITCT | 10425 | 2016-09-14 |  | J340 Generation Interconnection | Rebuild 5.3 miles of the existing 120 kV Cosmo tap to double circuit steel poles, relocate the Harvest Wind tap point, and string 954 ACSR to create the new J340-Harvest Wind-Grassmere 120 kV line. Expand the Grassmere station and install 1-345 kV breaker, a 345/120 kV transformer, and a 120 kV breaker on the low side of the transformer to tie in the new line. | MI | MI | GIP | Shared |  | 15150000 | 2017-09-01 | 2017-09-01 | 345 | 120 | Externally-Driven
A in MTEP16 | B>A | East | ITCT | 10723 | 2016-02-10 |  | Skylark | ITC will install 2-120 kV line breakers and 2-120 kV section breakers with associated disconnects at Skylark, and loop the 120 kV Northeast-Sloan line in and out. OPGW will be added on the new Northeast-Skylark and Sloan-Skylark 120 kV lines, and relay upgrades will occur at Sloan and Northeast. | MI | MI | Other |  | Distribution | 5395000 | 2017-12-01 | 2017-12-01 | 120 |  | Bottom-up
A in MTEP16 | B>A | East | ITCT | 10923 | 2016-03-21 |  | ITCT Pole Top Switch Additions/Replacement Program 2017 | Installing, or replacing as appropriate, pole-top switches at tap points of circuits will provide the operational flexibility to sectionalize parts of the line to isolate faults or perform maintenance work on it without having to shut down the entire circuit. | MI | MI | Other |  | Reliability | 2400000 | 2016-12-31 | 2016-12-31 | 120 |  | Bottom-up
A in MTEP16 | B>A | East | ITCT | 10924 | 2016-03-21 |  | ITCT Pole Top Switch Additions/Replacement Program 2018 | Installing, or replacing as appropriate, pole-top switches at tap points of circuits will provide the operational flexibility to sectionalize parts of the line to isolate faults or perform maintenance work on it without having to shut down the entire circuit. | MI | MI | Other |  | Reliability | 2400000 | 2018-12-31 | 2018-12-31 | 120 |  | Bottom-up
A in MTEP16 | B>A | East | ITCT | 11003 | 2016-04-12 | ITC_16_001 | Mercury Interconnection | Construct a new 120 kV,3 breaker substation and install approx. 0.8 miles of new double circuit structures to loop the existing Artic-Crestwood 120 kV line into the new substation. Install approx. 4.7 miles of OPGW (fiber) on the Arctic-Ranger line and upgrade relaying at Crestwood and Ranger. | MI | MI | Other |  | Distribution | 10100000 | 2017-12-01 | 2017-12-01 | 120 |  | Bottom-up
A in MTEP16 | B>A | East | ITCT | 11043 | 2016-09-30 | ITC_13_052 | Relay Modifications at Monroe to Accommodate PJM Y1-069 Lallendorf Generator Interconnection | Perform necessary relay modifications and install a new wave trap at Monroe in order to accommodate the PJM generator interconnection request ID# Y1-069 (in the PJM queue) which involves the construction of a new 799 MW natural gas generation facility in First Energy. | MI | MI | GIP | Shared |  | 250000 | 2016-04-04 | 2016-04-04 | 345 |  | Externally-Driven
A in MTEP16 | B>A | East | ITCT | 11443 | 2016-09-30 |  | Ranger Interconnection Request | ITC to install 2-3000 A, 120 kV, 40 kA min. int. capability, line breakers at existing Ranger Station. DTE to replace existing transformers with 40 MVA 120/13.2 kV transformers. Upgrades will support 50MW of new load at Ranger, and 37 MW of load relocated from Ford Engineering distribution station. Trainers on the River Rouge - Warren #2 line will also be upgraded to prevent overload. | MI | MI | Other |  | Distribution | 2173000 | 2017-12-01 | 2017-12-01 | 120 |  | Bottom-up
A in MTEP16 | B>A | East | ITCT | 11583 | 2016-09-14 |  | J301 Generation Interconnection | TO Interconnection Facilities and Network Upgrades associated with the J301 generation interconnection project. This includes a new 345 kV, 3-breaker substation fed by looping the 345 kV Bauer-Ringle line. | MI | MI | GIP | Shared |  | 9497000 | 2017-09-01 | 2017-09-01 | 345 |  | Externally-Driven
A in MTEP16 | B>A | East | ITCT | 11584 | 2016-09-30 |  | J308 Generation Interconnection | 345 kV, 3 Breaker Substation with relay upgrades and 0.1 miles of dbl ckt 345 kV to new substation (tapping greenwood-rapson) | MI | MI | GIP | Shared |  | 9421000 | 2016-09-01 | 2017-09-01 | 345 |  | Externally-Driven
A in MTEP16 | B>A | East | ITCT | 11603 | 2016-09-14 |  | J321 Generation Interconnection | The J321 TOIFs and NUs include a new 345 kV, 3-breaker substation in a ring bus configuration, and loop the Greenwood-Rapson #2 345 kV line into the new substation. | MI | MI | GIP | Shared |  | 9366000 | 2017-09-01 | 2017-09-01 | 345 |  | Externally-Driven
A in MTEP16 | B>A | East | ITCT | 11604 | 2016-09-14 |  | J419 Generation Interconnection | Network Upgrades and TOIFs associated with the J419 project. These include extending bus 103 and installing a 120 kV breaker with associated disconnects at Milan substation. | MI | MI | GIP | Shared |  | 803000 | 2018-06-30 | 2018-06-30 | 120 |  | Externally-Driven
A in MTEP16 | B>A | East | METC | 2809 | 2015-10-02 | 87 | Garfield Avenue – Hemphill 138 kV Rebuild | Rebuild a ~9.5 mile-long portion of 336 ACSR conductor utilizing 1431 ACSR conductor on double-circuit, 138 kV structures, relocate a portion of the Weadock – Hemphill 138 kV line to the other side of the new structures. | MI | MI | BaseRel |  |  | 11000000 | 2019-12-31 | 2019-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | METC | 3133 | 2015-09-15 | METC_15_022 | Bell Road - Cornell 138 kV Rebuild | Rebuild a ~4.3 mile-long portion of the Claremont – Cornell 2 line between Bell Road and Cornell. | MI | MI | BaseRel |  |  | 4350000 | 2019-12-31 | 2019-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | METC | 9422 | 2016-09-30 | METC_15_017 | Coldwater Interconnection phase 1 | METC would construct a 138 kV, 4-breaker substations configured into a ring bus (Newton), and build a 3 mile. 138 kV, single circuit, line on new right-of-way between Michigan Ave and Newton substations. | MI | MI | Other |  | Distribution | 12310000 | 2017-04-01 | 2018-06-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | METC | 9695 | 2015-09-10 | METC_15_028 | Bullock 138 kV Terminal Equipment Upgrade (Dow Corning Line) | Upgrade terminal equipment at Bullock on the Dow Corning 138 kV line | MI | MI | BaseRel |  |  | 300000 | 2018-12-31 | 2018-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | METC | 9705 | 2015-09-10 | METC_15_024 | Alma - Regal #2 138 kV Sag Remediation | Remediate the sag limit on the Alma – Regal 2 138 kV line to a minimum of 208 MVA / 871 Amps | MI | MI | BaseRel |  |  | 200000 | 2018-12-31 | 2018-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | METC | 9876 | 2015-10-14 | METC_15_027 | Karn - Manning 138 kV Sag Remediation | Remediate the sag limit on the Karn - Manning 138 kV line to a minimum of 396 MVA / 1657 Amps and upgrade terminal equipment at Karn | MI | MI | BaseRel |  |  | 620000 | 2018-12-31 | 2018-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | METC | 9932 | 2015-09-15 | METC_14_026 | Karn - Saginaw River 138 kV Line Rebuild | Rebuild a ~2.7 mile-long portion of six-wired 3/0 copper conductor utilizing 1431 ACSR conductor on single-circuit, 138 kV structures, remediate the sag limit on the existing 1431 ACSR conductor to a minimum of 412 MVA / 1724 Amps, and upgrade terminal equipment at both Karn and Saginaw River stations | MI | MI | BaseRel |  |  | 8500000 | 2019-12-31 | 2019-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | METC | 9945 | 2015-09-15 |  | 2017 METC Asset Replacement Program | Replace aging and outdated equipment on a cycle that will ensure each piece of equipment is replaced near its expected end of life. Modern equipment can improve reliability, use state of the art technology, and typically will allow for longer maintenance intervals. New equipment is also commonly equipped with better monitoring and alarming functionality giving improved remote supervision. All of this will help to reduce overall maintenance costs. | MI | MI | Other |  | Condition | 54276000 | 2017-12-31 | 2017-12-31 | 345 | 138 | Bottom-up
A in MTEP16 | B>A | East | METC | 9956 | 2015-09-15 |  | 2018 METC Asset Replacement Program | Replace aging and outdated equipment on a cycle that will ensure each piece of equipment is replaced near its expected end of life. Modern equipment can improve reliability, use state of the art technology, and typically will allow for longer maintenance intervals. New equipment is also commonly equipped with better monitoring and alarming functionality giving improved remote supervision. All of this will help to reduce overall maintenance costs | MI | MI | Other |  | Condition | 49398000 | 2018-12-31 | 2018-12-31 | 345 | 138 | Bottom-up
A in MTEP16 | B>A | East | METC | 9959 | 2016-03-23 |  | METC Customer Interconnections - Year 2019 | Customer interconnection requests and retirements. | MI | MI | Other |  | Distribution | 2500000 | 2017-12-31 | 2017-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | METC | 9960 | 2015-09-15 |  | 2019 METC Asset Replacement Program | Replace aging and outdated equipment on a cycle that will ensure each piece of equipment is replaced near its expected end of life. Modern equipment can improve reliability, use state of the art technology, and typically will allow for longer maintenance intervals. New equipment is also commonly equipped with better monitoring and alarming functionality giving improved remote supervision. All of this will help to reduce overall maintenance costs. | MI | MI | Other |  | Condition | 49398000 | 2019-12-31 | 2019-12-31 | 345 | 138 | Bottom-up
A in MTEP16 | B>A | East | METC | 9972 | 2016-06-16 |  | METC Four Mile Control Relocation Project | Replace METC relaying and controls at Four Mile Substation. Locate the new relaying and controls in a new dedicated METC control center. Install dedicated METC AC and DC systems. | MI | MI | Other |  | Relocation | 3520000 | 2017-12-31 | 2017-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | METC | 9975 | 2016-06-16 |  | METC Verona Control Relocation | Replace METC relaying and controls at Verona Substation. Locate the new relaying and controls in a new dedicated METC control center. Install dedicated METC AC and DC systems. | MI | MI | Other |  | Relocation | 2940000 | 2017-12-31 | 2017-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | METC | 9978 | 2015-09-15 |  | Eureka 138 kV Breaker Replacement | Replace the Eureka 138 kV circuit switcher 256 with a synchronous breaker that has a continuous rating of 3000 amp and a minimum interrupting capability of 40 kA. | MI | MI | BaseRel |  |  | 510000 | 2018-06-30 | 2018-06-30 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | METC | 9984 | 2015-09-15 |  | Tittabawassee 345 kV Breaker 38H9 Replacement | The proposed solution is to replace the Tittabawassee 345 kV breaker 38H9 with a breaker that has a continuous rating of 3000 amp and a minimum interrupting capability of 40 kA. | MI | MI | BaseRel |  |  | 790000 | 2018-06-30 | 2018-06-30 | 345 |  | Bottom-up
A in MTEP16 | B>A | East | METC | 10286 | 2016-07-18 | METC_12_001 | Campbell 138 kV Remove Circuit Breaker 588 Sparing Capability | Remove the Campbell 508 disconnect switch. Modify the relaying to remove 588 breaker sparing capability. | MI | MI | Other |  | Reliability | 88000 | 2018-12-31 | 2018-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | METC | 10323 | 2016-09-30 |  | Coldwater Phase 2 Wagner | Install a new 138 kV, 3 breaker substation (tentatively named Wagner) in a ring bus configuration in Union City, MI. Loop the existing 138 kV Alder Creek-Batavia line into Wagner, and modify relaying at Batavia to accommodate the new substation. Construct an approx. 13 mile, 138 kV line between Wagner and Newton on 138 kV, single circuit, steel poles. | MI | MI | Other |  | Distribution | 34409000 | 2018-05-31 | 2018-05-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | METC | 10384 | 2015-11-23 | METC_15_018 | Verona - Barnum Creek Jct. 138 kV Sag Remediation | Fully remediate the sag limit on the 266.8 ACSR conductor from the Verona – Barnum Creek Jct. section of the Verona – Batavia 138 kV circuit to the conductor rating of 730 Amps / 174 VMVA (summer emergency) using new future double circuit (FDC) structures capable of supporting 954 ACSR in order to facilitate a rebuild of this circuit in the near future. | MI | MI | BaseRel |  |  | 1070000 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | METC | 10743 | 2016-09-30 |  | Covert Gen Interconnection (PJM-T94) | Phase 1 to construct a new control house at Palisades substation and replace the relaying associated with positions RH25 and FH27. Install OPGW on the new Palisades-Segreto #1 345 kV line and remove the METC SCADA equipment at Covert. | MI | MI | GIP | Shared |  | 3605000 | 2015-09-30 | 2015-09-30 | 345 |  | Externally-Driven
A in MTEP16 | B>A | East | METC | 10744 | 2016-09-14 |  | J392 Generation Interconnection | Wolverine will construct the Stand Alone Network Upgrades which include the new 4 row, 11 breaker, 138 kV Van Tyle substation, laid out in a breaker and a half design. Ownership of these upgrades will be transferred to METC upon completion of the construction. METC will loop the 138 kV Livingston-Stover line into Van Tyle, and rebuild the new Livingston-Van Tyle line to double circuit structures, with OPGW being added to the new poles. 1431 ACSR conductor will be installed on both sides of the new structures to create Livingston-Van Tyle #1 and #2. A duel pilot relaying scheme will be installed on the Livingston-Emmett 138 kV line, and the Livingston substation will be expanded to include 2 new rows, and 5 additional breakers, on the 138 kV breaker and a half sub. Relaying upgrades will also occur at Gaylord. | MI | MI | GIP | Shared |  | 18087200 | 2016-05-06 | 2016-06-11 | 138 |  | Externally-Driven
A in MTEP16 | B>A | East | METC | 11243 | 2016-05-13 | METC_15_019 | Verona - Barnum Creek Jct. 138 kV Rebuild | Rebuild the Verona – Barnum Creek Jct. section of the Verona – Batavia 138 kV circuit using 954 ACSR and OGPW on new 230 kV future double circuit structures. Replace PTS 3186. Upgrade terminal equipment at the Verona station. Also reconductor approximately 0.6 miles of the Verona – Foundry 138 kV circuit where it shares common structures with the Verona – Batavia 138 kV circuit. | MI | MI | BaseRel |  |  | 13300000 | 2018-05-31 | 2018-05-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | METC | 11683 | 2016-09-30 |  | Barnum Creek–Alder Creek 138kV Sag Remediation | Remediate Sag on the Barnum Creek Jct. – Alder Creek 138 kV section up to the conductor rating of 174 MVA (730 Amp.). | MI | MI | BaseRel |  |  | 400000 | 2018-05-31 | 2018-05-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | METC | 11684 | 2016-09-30 |  | Alder Creek–Wagner 138kV Sag Remediation | Remediate Sag on the Alder Creek – Wagner 138 kV section up to the conductor rating of 174 MVA (730 Amp.). | MI | MI | BaseRel |  |  | 365000 | 2018-05-31 | 2018-05-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | METC | 11704 | 2016-09-30 |  | Denso J.–Vrooman 138kV Sag Remediation | Remediate the sag limit on the Denso J.–Vrooman 138 kV section to at least 150 MVA (628 Amp). | MI | MI | BaseRel |  |  | 195000 | 2018-05-31 | 2018-05-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | East | WPSC | 4385 | 2015-11-23 | BP-FV | Burnips to Fairview | Burnips to Fairview Rebuild | MI | MI | Other |  | Reliability | 3500000 | 2018-12-31 | 2018-12-31 | 69 |  | Bottom-up
A in MTEP16 | B>A | East | WPSC | 9899 | 2016-07-07 | RW-SV Rebuild | Redwood to Scottville Rebuild | Rebuild the Redwood to Scottville 69kV line, install new poles and hardware with 795ACSS conductor | MI | MI | Other |  | Reliability | 10500000 | 2018-12-01 | 2018-12-31 | 69 |  | Bottom-up
A in MTEP16 | B>A | East | WPSC | 9913 | 2015-09-15 | 2017 Battery Bank Replacement Project | 2017 Battery Bank Replacement Project | This project replaces battery banks and chargers that have reached the end of their useful life at transmission stations. | MI | MI | Other |  | Condition | 70000 | 2017-12-31 | 2017-12-31 | 69 |  | Bottom-up
A in MTEP16 | B>A | East | WPSC | 9915 | 2015-09-15 | OE Relay Upgrade | Oden Relay Upgrade | Upgrade the relaying on the Oden-Emmet terminal | MI | MI | Other |  | Condition | 35000 | 2017-12-31 | 2017-12-31 | 69 |  | Bottom-up
A in MTEP16 | B>A | East | WPSC | 11023 | 2016-04-11 |  | J392 Generator Interconnection | Upgrades determined in the FEB2015 DPP studies to connect J392. Wolverine to construct the following: -Advance 138kV station and 138/69kV transformer -Gaylord 138kV 4 breaker ring bus to accommodate 3rd line into the station (2016) -Gaylord 138kV 6 breaker ring bus and 2nd 138/69KV transformer (2018) -Upgrades to Elmira, Deer Lake and Alpine distribution subs from 69kV to 138kV operation -Conversion of existing Gaylord - Advance 69kV line to 138kV operation, new lines will be Gaylord - Van Tyle and Van Tyle to Advance -Rebuild of Gaylord - Livingston 138kV line to 795ACSS | MI | MI | GIP |  |  | 13980072 | 2016-04-30 | 2018-10-31 | 138 | 13.09 | Externally-Driven
A in MTEP16 | B>A | South | AECC | 9662 | 2015-10-13 |  | Harrison South Transformer Upgrade | Upgrade the autotransformer at the Harrison South 161/69 kV substation. The four single phase 5.6 MVA, 161/69 kV transformers will be replaced with the three phase 27.5 MVA, 161/69 kV autotransformer from the Black Rock 161/69 kV substation. | AR | AR | Other |  | Distribution | 600000 | 2017-01-01 | 2017-01-01 | 161 |  | Bottom-up
A in MTEP16 | B>A | South | AECC | 9663 | 2015-10-13 |  | Tap EAI Newport - Balch 161 kV line: Construct South Newport 161/13.2 kV substation | Construct 20 MVA, 161/13.2 kV substation under EAI Newport - Parkin 161 kV line. The load for this substation will be transferred from the Newport and Cherokee Acres distribution delivery points. Once the load is transferred the two distribution delivery points will no longer be needed. Edit: POD/substation name will likely be changed from South Newport to Newport East. | AR | AR | Other |  | Distribution | 500000 | 2017-07-01 | 2017-07-01 | 161 | 13.2 | Bottom-up
A in MTEP16 | B>A | South | AECC | 10204 | 2016-05-06 |  | Tap EAI Moses to Bailey 161kV line, Construct 161/13.2kV Hunter North substation | Tap EAI Moses to Bailey 161kV line, Construct 161/13.2kV Hunter North substation | AR | AR | Other |  | Reliability | 500000 | 2018-06-01 | 2018-06-01 | 161 |  | Bottom-up
A in MTEP16 | B>A | South | AECC | 10205 | 2015-11-12 |  | Bee Branch to Damascus 161kV transmission line, 161/13.2kV substation | Build 6.8 mile 161kV line from the existing AECC Bee Branch substation to the proposed Damascus substation, add 161kV line breaker, build 161/13.2kV Damascus substation. | AR | AR | Other |  | Distribution | 8000000 | 2017-02-28 | 2017-02-28 | 161 |  | Bottom-up
A in MTEP16 | B>A | South | AECC | 10206 | 2016-05-06 |  | Clinton West to Partain 161kV line, 161/69kV Partain substation | Build 5 position ring bus at the AECC Clinton West substation, Build 14 mile 161kV line from the existing Clinton West substation to the proposed Partain substation, Build 3 position ring bus at the proposed Partain substation, Build the proposed Partian 161/69kV substation. | AR | AR | Other |  | Reliability | 27000000 | 2020-12-01 | 2020-12-01 | 161 | 69 | Bottom-up
A in MTEP16 | B>A | South | AXLA | 10122 | 2015-10-15 | AXLA PRJ_01_MTEP16 | Hunter - Downtown 138 kV Reconductor | Reconductor the existing Hunter - Downtown 138kV transmission line | LA | LA | Other |  | Reliability | 340000 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | South | AXLA | 10123 | 2015-10-15 | AXLA PRJ_02_MTEP16 | Prescott - Sterkx 138 kV Recondutor | Reconductor the existing Prescott - Sterkx 138kV transmission line | LA | LA | Other |  | Reliability | 490000 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | South | CLECO | 9542 | 2015-09-11 | 19944 | Dolet Hills Mine Line Tap | Tap the existing 230 kV line from Dolet Hills to Mansfield Compressor to serve existing load which is moving its operations. | LA | LA | Other |  | Reliability | 5000000 | 2016-12-01 | 2016-12-01 | 230 |  | Bottom-up
A in MTEP16 | B>A | South | CLECO | 9713 | 2015-09-11 |  | Dolet Hills Breaker Replacements | Replace one of the 345 kV Breakers at Dolet Hills due to aging equipment and trouble maintaining existing breakers. | LA | LA | Other |  | Reliability | 294580 | 2016-11-01 | 2016-11-01 | 345 |  | Bottom-up
A in MTEP16 | B>A | South | CLECO | 9715 | 2015-09-11 |  | Wax Lake Cap Switcher Replacements | Replaces existing MOS 8374 & 8373 with Cap Switcher at Wax Lake | LA | LA | Other |  | Reliability | 406013 | 2016-10-01 | 2016-10-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | South | CLECO | 10983 | 2016-04-04 |  | Hopkins Breaker Addition | Add a second Breaker in Series with Hopkins Breaker 8061. | LA | LA | Other |  | Reliability | 300000 | 2017-05-01 | 2017-05-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-AR | 4665 | 2015-09-28 | 12-EAI-019 | Mabelvale: Replace 500-115 Autos | Upgrade both Mabelvale 500/115 kV autotransformers to 598MVA. | AR | AR | BaseRel |  |  | 17417000 | 2017-12-01 | 2017-12-01 | 500 | 115 | Bottom-up
A in MTEP16 | B>A | South | Entergy-AR | 7942 | 2016-08-23 | 15-EAI-004 | Mayflower - Morgan: Rebuild 115kV line | Mayflower - Morgan: Rebuild 115kV line | AR | AR | BaseRel |  |  | 4877301 | 2019-06-01 | 2019-06-01 | 115 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-AR | 7944 | 2015-09-16 | 15-EAI-007 | Stuttgart Ricuskey - Stuttgart Ind: Rebuild 115kV line | Stuttgart Ricuskey - Stuttgart Ind: Upgrade 115kV line to 176MVA | AR | AR | GIP |  |  | 2526158 | 2018-01-30 | 2018-01-30 | 115 |  | Externally-Driven
A in MTEP16 | B>A | South | Entergy-AR | 9673 | 2015-09-09 | 16-EAI-002 | El Dorado Install 2nd 500/115 Autotransformer | Install 2nd-598MVA 500/115 kV autotransformer at El Dorado EHV. | AR | AR | BaseRel |  |  | 16446045 | 2018-06-01 | 2018-06-01 | 500 | 115 | Bottom-up
A in MTEP16 | B>A | South | Entergy-AR | 9691 | 2015-09-24 | 16-EAI-009 | Lonoke East 115kV: 20.5MVAR Capacitor Bank | Install new 20.5 MVAR Capacitor bank on Lonoke East 115 kV. | AR | AR | BaseRel |  |  | 1456861 | 2017-06-01 | 2017-06-01 | 115 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-AR | 9693 | 2015-09-10 | 16-EAI-014 | Pleasant Hill: Add tertiary reactors | Add three 30 MVAR reactors on the tertiary windings of the 500/161/13.8 kV transformer at the Pleasant Hill EHV substation to maintain the voltages within the limits defined in the Entergy Local Planning Criteria. | AR | AR | BaseRel |  |  | 2184660 | 2017-10-01 | 2017-10-01 | 500 | 161 | Bottom-up
A in MTEP16 | B>A | South | Entergy-AR | 9696 | 2016-09-28 | 16-AI-017 | Newport 161 kv: Address Newport Flicker Issues | Build a breaker switching station "Mallory" near Newport Industrial and re-terminate the Newport-Swifton, Newport - Newport Industrial and Newport Industrial - Newport Air Base 161kV lines into Mallory. The 3.5 mile long line Newport - Mallory should be upgraded to a minimum of 545MVA (1956 Amps). | AR | AR | BaseRel |  |  | 15150000 | 2018-06-01 | 2018-06-01 | 161 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-AR | 9697 | 2015-09-10 | 16-EAI-001 | Trumann-Trumann West: Upgrade existing 161kV line | Re-build 6.5 mile long line to a minimum rating of 1300A. | AR | AR | BaseRel |  |  | 12115000 | 2018-06-01 | 2018-06-01 | 161 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-AR | 9698 | 2016-02-03 | 16-EAI-006 | El Dorado East - El Dorado Jackson 115kV rebuild | Upgrade El Dorado East - El Dorado Jackson 115 kV line to minimum 1300A. | AR | AR | BaseRel |  |  | 4926295 | 2018-06-01 | 2018-06-01 | 115 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-AR | 9703 | 2015-09-10 | 16-EAI-007 | Bono: New 161kV Substation | Build new 161kV substation to support load growth. | AR | AR | Other |  | Distribution | 9380200 | 2017-10-01 | 2017-10-01 | 161 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-AR | 9704 | 2015-09-10 | 16-EAI-008 | London North: New 161kV Substation | Construct new London North 161kV substation | AR | AR | Other |  | Distribution | 9244000 | 2017-10-01 | 2017-10-01 | 161 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-AR | 9707 | 2015-09-10 | 16-EAI-011 | Camden Maguire115kV: Reconfigure station | Reconfigure Camden Maguire 115 kV substation so that a single bus failure will not open all the elements in the Camden Maguire substation. Some potential configurations are double bus double breaker, breaker and a half, and ring bus. The final configuration will be decided during project scoping. | AR | AR | BaseRel |  |  | 5772470 | 2017-06-01 | 2017-06-01 | 115 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-AR | 9708 | 2015-09-10 | 16-EAI-004 | ISES 161kV: Reconfigure station | Reconfigure the Independence 161 kV station to a breaker-and-a-half configuration or a double bus/double breaker configuration to help eliminate area thermal and voltage violations. | AR | AR | BaseRel |  |  | 9100851 | 2017-10-01 | 2017-10-01 | 161 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-AR | 9709 | 2015-09-10 | 16-EAI-012 | Mabelvale 115kV: Reconfigure Station | Reconfigure the Mabelvale 115 kV substation so that a single bus tie breaker failure will not open all the elements in the Mabelvale 115 kV substation. Some potential configurations are double bus double breaker, breaker and a half, and ring bus. The final configuration will be decided during project scoping. | AR | AR | BaseRel |  |  | 17446076 | 2019-06-01 | 2019-06-01 | 115 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-AR | 10044 | 2015-09-17 | 16-EAI-018 | Goodwin Road 115 kV: New SS for GIA J348 | Construct a new 115 kV 3 breaker ring bus switching station named Goodwin Road on the Stuttgart Ricuskey - Almyra 115 kV line. | AR | AR | GIP |  |  | 10064000 | 2018-01-30 | 2018-01-30 | 115 |  | Externally-Driven
A in MTEP16 | B>A | South | Entergy-AR | 11483 | 2016-06-30 | 16-EAI-023 | Benton Hurricane Lake 115 kV: New point-of-delivery | Cut-in new wholesale delivery point on River Ridge - Mabelvale 115 kV line | AR | AR | Other |  | Reliability | 1589494 | 2017-05-01 | 2017-05-01 | 115 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 4634 | 2015-09-11 | 13-ELL-006 | Ninemile to Westwego 115 kV: Reconductor Line | Reconductor the existing Ninemile to Westwego115 kV line to achieve a minimum rating of320 MVA and upgrade terminal equipment at Ninemile and Westwego line bays to achieve the minimum rating of 320 MVA. | LA | LA | BaseRel |  |  | 9026000 | 2018-06-01 | 2018-06-01 | 115 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 4639 | 2015-09-13 | 14-ELL-006 | Ninemile to Harvey2 115 kV: Reconductor line and change station limiting elements | Reconductor the existing Ninemile to Harvey2 115 kV line to achieve a minimum rating of320 MVA and upgrade terminal equipment at Ninemile and Harvey2 line bays to achieve the minimum rating of 320 MVA. | LA | LA | BaseRel |  |  | 15121000 | 2018-06-01 | 2018-06-01 | 115 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 7949 | 2016-05-10 | 15-EGL-010 | Solac 230-69 kV: Upgrade Both Autos | Replace both 230/69 kV AT with 300MVA | LA | LA | BaseRel |  |  | 8457000 | 2018-06-01 | 2018-06-01 | 230 | 69 | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 7950 | 2015-11-06 | 15-EGL-011 | East Broad to Ford 69 kV line: Reconductor line | Re-conductor East Broad to Ford 69 kV line | LA | LA | BaseRel |  |  | 1474000 | 2018-06-01 | 2018-06-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 7952 | 2015-09-13 | 15-EGL-012 | Contraband to Solac 69 kV line: Reconductor line | Re-conductor Contraband to Solac 69 kV line | LA | LA | BaseRel |  |  | 4125000 | 2018-06-01 | 2018-06-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9682 | 2015-09-10 | 16-ELN-001 | Vienna - Trussell Crossing: Upgrade line | Upgrade the Vienna - Trussell Crossing 115 kV to a minimum of 260MVA. | LA | LA | BaseRel |  |  | 8823757 | 2020-06-01 | 2020-06-01 | 115 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9684 | 2015-11-06 | 16-ELN-004 | Cadeville: New distribution substation | Construct a new 115 kV substation in the Cadeville area to serve area load | LA | LA | Other |  | Distribution | 41643000 | 2018-06-01 | 2018-06-01 | 115 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9686 | 2015-09-10 | 16-ELN-005 | Lake Providence: New distribution substation | Construct a new radial 115 kV transmission line to the Lake Providence area to serve area load. | LA | LA | Other |  | Distribution | 31830074 | 2020-06-01 | 2020-06-01 | 115 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9690 | 2015-09-10 | 16-ELN-010 | Hodge: Replace existing substation | Construct a new 230 kV substation to serve area load in the Hodge area. | LA | LA | Other |  | Distribution | 14121450 | 2018-12-01 | 2018-12-01 | 230 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9763 | 2015-09-13 | 16-EGL-004 | Baker to Blount 69kV: Reconductor Line | Upgrade the rating on the Baker to Blount 69 kV line. This includes recondutor and upgrading station equipment. | LA | LA | BaseRel |  |  | 5182000 | 2018-06-01 | 2018-06-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9765 | 2015-09-13 | 16-EGL-006 | Harelson to Line 369 Tap 69 kV: Reconductor Line | Reconductor the Harelson to Line 369 Tap 69 kV line. | LA | LA | BaseRel |  |  | 3165000 | 2018-12-01 | 2018-12-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9770 | 2015-09-13 | 16-EGL-011 | Goosport to L673 TP 69 kV: Upgrade Station Equipment | Upgrade the substation equipment at Goosport to increase the rating of the line. | LA | LA | BaseRel |  |  | 145205 | 2016-11-18 | 2016-11-18 | 69 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9771 | 2015-09-13 | 16-EGL-012-1 | SWLA69IP Phase 1: Construct Jefferson Davis 138/69 kV Substation | Construct new Jefferson Davis 138/69 kV substation. | LA | LA | BaseRel |  |  | 76570000 | 2019-06-01 | 2019-06-01 | 138 | 69 | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9772 | 2015-09-13 | 16-EGL-012-2 | SWLA69IP Phase 1: Colonial Welsh TP to Jefferson Davis 138 kV: Construct 138 kV line | Construct a new line from Colonial Welsh Tap to the new Jefferson Davis 138 kV station. | LA | LA | BaseRel |  |  |  | 2019-06-01 | 2019-06-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9773 | 2015-09-13 | 16-EGL-012-3 | SWLA69IP Phase 1: Jefferson Davis to Carter Construct 69 kV line | Build a new 69 kV line from Jefferson Davis to Carter substation | LA | LA | BaseRel |  |  |  | 2019-06-01 | 2019-06-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9774 | 2016-03-11 | 16-EGL-012-4 | SWLA69IP Phase 1: Jefferson Davis to Compton Construct 69 kV line | Construct 5 miles of double circuit 69 kV with a conductor rating of at least 880 A to a cut in point on 69 kV L-13 two miles south of the existing Compton 69 kV substation. Rebuild 2 miles of 69 kV L-13 from new cut in point to Compton with a conductor rating of at least 880 A. | LA | LA | BaseRel |  |  |  | 2019-06-01 | 2019-06-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9775 | 2015-09-13 | 16-EGL-012-5 | SWLA69IP Phase 1: Derouen 69 kV Cut into L-11 | Cut the Derouen 69 kV substation in and out of Line 11. | LA | LA | BaseRel |  |  |  | 2019-06-01 | 2019-06-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9776 | 2015-09-13 | 16-EGL-012-6 | SWLA69IP Phase 1: Lawtag 69 kV Cut into L-13 & Close NO @ L-13A | Cut line number 13 in and out of the Lawtag 69 kV substation. Also, close the normally open point on line number 13A. | LA | LA | BaseRel |  |  |  | 2019-06-01 | 2019-06-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9777 | 2015-09-13 | 16-EGL-012-7 | SWLA69IP Phase 1: Welsh 69 kV Cut into L-13A | Cut the Welsh 69 kV substation in and out of line 13A. | LA | LA | BaseRel |  |  |  | 2019-06-01 | 2019-06-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9778 | 2015-09-13 | 16-EGL-012-8 | SWLA69IP Phase 1: Colonial Welsh TP to Jefferson Davis 138 kV Reconductor | Reconductor the Colonial Welsh Tap to Jefferson Davis 138 kV line. | LA | LA | BaseRel |  |  |  | 2019-06-01 | 2019-06-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9779 | 2015-09-13 | 16-EGL-013 | SWLA69IP Phase 2: Carter to Serpent 69 kV Reconductor | Reconductor the Carter to Serpent 69 kV line. | LA | LA | BaseRel |  |  | 19235078 | 2018-12-01 | 2018-12-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9780 | 2015-09-13 | 16-EGL-014 | SWLA69IP Phase 3: Compton to Elton 69 kV Reconductor | Reconductor Comton to Elton 69 kV line. | LA | LA | BaseRel |  |  | 12782000 | 2019-12-01 | 2019-12-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9782 | 2015-09-13 | 16-EGL-016 | SWLA69IP Phase 4: Lake Arthur 69 kV Move NO Point | Move the normally open point at the Lake Arthur 69 kV substation. | LA | LA | BaseRel |  |  |  | 2022-06-01 | 2022-06-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9786 | 2015-10-21 | 16-EGL-020 | Nelson 138 kV: Add L-274 to Breaker-and-a-half Scheme | Add L-274, L-654, L-656 and L-698 to the double bus double breaker scheme at Nelson. | LA | LA | Other |  | Reliability | 1142000 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9787 | 2015-09-13 | 16-EGL-021 | Air Products to Giegy 138kV: Upgrade Substation Equipment | Upgrade substation equipment on the Air Products and Giegy terminals to increase the rating of the line. | LA | LA | BaseRel |  |  | 300000 | 2016-06-01 | 2016-06-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9788 | 2015-09-13 | 16-EGL-022 | Port Barre 69 kV: Install Cap Bank | Install a capacitor bank at the Port Barre substation. | LA | LA | BaseRel |  |  | 786000 | 2018-06-01 | 2018-06-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9790 | 2015-12-03 | 16-EGL-026 | Swisco 138 kV: Construct New Substation | Construct a new substation to serve area load. | LA | LA | Other |  | Distribution | 8191000 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9791 | 2015-09-13 | 16-EGL-027 | Thompson Road 230 kV: Construct New Substation | Construct a new substation to serve area load. | LA | LA | Other |  | Distribution | 9252000 | 2018-06-01 | 2018-06-01 | 230 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9792 | 2015-09-13 | 16-EGL-028 | Lowe Grout Road 138 kV: Construct New Substation | Construct a new substation to serve area load. | LA | LA | Other |  | Distribution | 6989000 | 2019-06-01 | 2019-06-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9794 | 2016-09-14 | 16-EGL-032 | Repapco to Port Hudson Station 230 kV: Upgrade Substation Equipment | Upgrade substation equipment at on the Repapco to Port Hudson 230 kV line. | LA | LA | BaseRel |  |  | 101000 | 2018-06-01 | 2018-06-01 | 230 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9795 | 2015-09-13 | 16-EGL-033 | Nesser 69 kV: New Cap Bank | Add a capacitor bank to the Nesser 69 kV substation. | LA | LA | BaseRel |  |  | 1053000 | 2017-12-01 | 2017-12-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9801 | 2015-09-13 | 16-ELL-004 | North Norco 115 kV: Add Cap Bank | Add a capacitor bank to the North Norco substation. | LA | LA | BaseRel |  |  | 1826000 | 2017-12-01 | 2017-12-01 | 115 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9805 | 2015-09-13 | 16-ENO-001 | Patterson to Pontchartrain Park 115 kV: Reconductor Line | Reconductor the Patterson to Pontchartrain Park 115 kV line | LA | LA | BaseRel |  |  | 11851000 | 2018-12-01 | 2018-12-01 | 115 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9847 | 2015-09-14 | 16-EGL-030-1 | EGSL Underrated Breaker Project: Mossville 69 kV Breaker 17985 | Breaker number 17985 at the Mossville 69 kV substation will be replace due to the short circuit analysis. | LA | LA | Other |  | Reliability | 700000 | 2017-12-01 | 2017-12-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9848 | 2015-09-14 | 16-EGL-030-2 | EGSL Underrated Breaker Project: Mossville 69 kV Breaker 17995 | Breaker 17995 at the Mossville 69 kV substation will be replaced due to the short circuit analysis. | LA | LA | Other |  | Reliability |  | 2017-12-01 | 2017-12-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 9849 | 2015-09-14 | 16-EGL-030-3 | EGSL Underrated Breaker Project: Carlyss 69 kV Breaker 7840 | Breaker number 7840 at the Carlyss 69 kV substation will be replace due to the short circuit analysis. | LA | LA | Other |  | Reliability |  | 2017-12-01 | 2017-12-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 10008 | 2016-06-22 | 15-EGL-023 | Nelson to Menena 230 kV: Construct New Line | Construct new 230 kV line from Nelson to Menena. | LA | LA | BaseRel |  |  | 15500000 | 2020-06-01 | 2020-06-01 | 230 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 10223 | 2015-11-17 | 16-ELN-011 | LAGEN Holly Ridge new substation | Construct a new 115/13.8 kV distribution serving substation on the Oak Ridge - Dunn 115 kV transmission line in North Central Louisiana. | LA | LA | Other |  | Distribution | 254833 | 2016-12-31 | 2016-12-31 | 115 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 10583 | 2016-01-12 | 16-EGL-037 | Coly 230 kV: Add Breaker | Add a breaker at the Coly 230 kV substation. | LA | LA | Other |  | Reliability | 1692865 | 2018-06-01 | 2018-06-01 | 230 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 10584 | 2016-01-12 | 16-EGL-038 | Tiger 230 kV: Add Breaker | Add a 230 kV breaker at the Tiger substation. | LA | LA | Other |  | Reliability | 1692865 | 2018-06-01 | 2018-06-01 | 230 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 10585 | 2016-01-12 | 16-EGL-039 | Harelson 230 kV: Add Breaker | Add a breaker at the Harelson 230 kV substation. | LA | LA | Other |  | Reliability | 1692865 | 2018-06-01 | 2018-06-01 | 230 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 10588 | 2016-03-01 | 16-ELL-010 | Fleur 230 kV Substation: New Substation | Construct a new 230 kV substation on the Oakville to Alliance 230 kV transmission line. This substation will be the primary feed to a customer in the area. Load will move from other substations in the area. Rebuild the Ninemile to Barataria 115 kV line. | LA | LA | Other |  | Distribution | 42705000 | 2018-12-31 | 2018-12-31 | 230 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 10591 | 2016-01-12 | 16-EGL-041 | Willow Glen 500/138 kV Auto: Adjust Taps | Changing the position of the de-energized tap changer to 500kV (3/C) from 487.5kV (2/B). | LA | LA | Other |  | Reliability | 15027 | 2016-06-01 | 2016-06-01 | 500 | 138 | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 10623 | 2016-06-22 | 16-EGL-042 | Sadie 230 kV: Construct New Substation | Construct a new 230 kV substation on the PPG to Rosebluff 230 kV line. | LA | LA | Other |  | Distribution | 24814742 | 2018-06-01 | 2018-06-01 | 230 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 10624 | 2016-06-22 | 16-EGL-043 | Big Lake 230 kV: Construct New Substation | Construct a new 230 kV substation on the Vincent to Graywood 230 kV line. | LA | LA | Other |  | Distribution | 28000000 | 2019-06-01 | 2019-06-01 | 230 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 11423 | 2016-06-22 | 16-EGL-044 | Menena 230 kV: Construct New Substation | Industrial Customer Connection This is a customer driven project to install a new 230 kV substation on the PPG to Rosebluff 230 kV line. | LA | LA | Other |  | Reliability | 7290000 | 2017-12-01 | 2017-12-01 | 230 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 12016 | 2016-09-13 |  | Upgrade Minden - Sarepta 115 kV Terminal Equipment | Upgrade line terminal equipment on Minden – Sarepta 115kV to increase the MVA rating to 176MW | LA | LA | Other |  | Economic | 1900000 | 2020-01-01 | 2020-01-01 | 115 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-LA | 12017 | 2016-09-13 |  | Southeast Louisiana Project | Construction a new 230 kV substation called Churchill. Construction of approximately 26 miles of new 230 kV transmission line connecting the existing 230 kV Waterford substation to the Churchill 230 kV substation crossing the Down Stream Gypsy load pocket interface. Re-configuration of the existing Waterford to Ninemile and Ninemile to Estelle 230 kV lines into the Churchill 230 kV substation and out to the existing Ninemile 230 kV substation to provide access to the strong sources at the Ninemile substation. Add a breaker at the Michoud 115 kV substation to address the findings during the reliability no-harm robustness analysis. | LA | LA | Other |  | Economic | 87656751 | 2022-01-01 | 2022-01-01 | 230 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-MS | 9822 | 2015-09-14 | 16-EMI-001 | Harper 115 kV new switching station | Construct a new 115 kV breaker switching station. | MS | MS | Other |  | Reliability | 5300000 | 2018-12-01 | 2018-12-01 | 115 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-MS | 9833 | 2015-09-14 | 16-EMI-007 | Greenville North Install 2nd Capacitor | Install 2nd 20.5 MVAR capacitor bank at Greenville North 115 kV. | MS | MS | BaseRel |  |  | 1185857 | 2018-06-01 | 2018-06-01 | 115 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-MS | 9839 | 2015-09-14 | 16-EMI-005 | Reconfigure Gerald Andrus 230 kV line terminals | Reterminate Ray Braswell 230 kV line circuit into Bagby line bay. This project will be completed as part of the pre-planned Madison/Hinds Improvement Project as the scope of that project is replacing the necessary breakers at the Gerald Andrus 230 kV. | MS | MS | BaseRel |  |  | 310000 | 2018-03-01 | 2018-03-01 | 230 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-MS | 9949 | 2015-09-15 |  | Cloverdale 115kV Delivery Point | The Cloverdale DP will be served from the existing Entergy IP to Johns Manville 115kV transmission line via a looped transmission feed into a new switching station to be constructed at the DP site. | MS | MS | Other |  | Distribution | 900000 |  |  | 115 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-MS | 9955 | 2015-09-15 |  | Steiner 115kV Delivery Point | The Steiner DP will be located approximately 1.6 miles northeast of the existing Shaw Switching Station and will be served from Entergy's existing 115kV Cleveland to Shaw transmission line via a looped transmission feed. This DP will require installation of a new switching station with motor operated switches and other miscellaneous upgrades to accommodate the new 115kV looped service. | MS | MS | Other |  | Distribution | 810000 |  |  | 115 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-MS | 10863 | 2016-03-08 | 16-EMI-013 | Attala - Conehoma Creek: Upgrade line | Upgrade line rating of Attala - Conehoma Creek 115 kV line to minimum 1303A. | MS | MS | BaseRel |  |  | 1716001 | 2017-06-01 | 2017-06-01 | 115 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-MS | 10864 | 2016-09-14 | 16-EMI-014 | Pelahatchie - Morton: Upgrade line | Upgrade the Pelahatchie - Morton 115 kV line to 1303 A. | MS | MS | BaseRel |  |  | 5593224 | 2017-12-31 | 2017-12-31 | 115 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-MS | 10865 | 2016-09-14 | 16-EMI-015 | Morton - Forest Ind 115 kV (Southern Company Tie): Upgrade line | Upgrade approximately 9 miles of 115 kV line between Morton and Forest Ind (to the Southern Company tie point) to minimum 1303 A. | MS | MS | BaseRel |  |  | 10987197 | 2018-06-01 | 2018-06-01 | 115 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-MS | 10943 | 2016-09-14 | 16-EMI-016 | Norrel Road: Construct new 230 kV substation | Construct new 230 kV substation on the Clinton Industrial - Gerald Andrus (new Tinnin substation will be cut-in during 2017-2018) 230 kV line. | MS | MS | Other |  | Distribution | 9197916 | 2019-06-01 | 2019-06-01 | 230 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-MS | 11623 | 2016-08-09 | 16-EMI-017 | Gallman: Install 115 kV transmission breakers | Install transmission breakers at Gallman 115 kV substation. | MS | MS | Other |  | Reliability | 2988936 | 2016-12-31 | 2016-12-31 | 115 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-MS | 11705 | 2016-08-09 | 16-EMI-018 | Wynndale 115 kV: Install distribution transformers | Install 2x115/13.8 kV distribution transformers in the Wynndale substation. | MS | MS | Other |  | Distribution | 7789909 | 2017-12-31 | 2017-12-31 | 115 | 13.8 | Bottom-up
A in MTEP16 | B>A | South | Entergy-MS | 11783 | 2016-09-27 | 16-EMI-019 | McAdams Upgrade Autotransformers | Remove and replace the both a banks of autotransformers with new autotransformers with a minimum rating of at least 750 MVA per bank. Replace the existing spare single phase auto and re-configure the bus so that is usable for either bank. Add 1 – 35 MVAR reactor to autotransformer bank # 2, so there are 4 reactors for each autotransformer bank. | MS | MS | BaseRel |  |  | 12633990.04 | 2020-06-01 | 2020-06-01 | 500 | 230 | Bottom-up
A in MTEP16 | B>A | South | Entergy-MS | 12015 | 2016-09-13 |  | Lakeover 500/230 kV XFMR | Relocate existing 500/230 kV transformer from McAdams to Lakeover | MS | MS | Other |  | Economic | 6700000 | 2020-01-01 | 2020-01-01 | 500 | 230 | Bottom-up
A in MTEP16 | B>A | South | Entergy-TX | 4620 | 2016-05-10 | 12-ETI-006 | Kolbs 230 kV - Add capacitor bank | Kolbs Substation: Add two 86.4 MVAR 230 kV capacitor banks | TX | TX | BaseRel |  |  | 3000000 | 2017-06-01 | 2017-06-01 | 230 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-TX | 7930 | 2016-06-22 | 15-ETI-008 | Heights 230 kV: Construct New Substation | Construct new 230 kV substation for load growth in the Woodlands area to offload the New Caney 138 kV substation. New substation will be tapped into 230 kV line between China and Porter. | TX | TX | Other |  | Distribution | 14208000 | 2019-06-01 | 2019-06-01 | 230 | 34.5 | Bottom-up
A in MTEP16 | B>A | South | Entergy-TX | 9806 | 2016-09-14 | 16-ETI-001 | Bryan 138-69 kV: Replace Autos & Reconfigure 138 & 69 kV Bus | Replace the 2 138/69 kV autotransformers at the Bryan substation and reconfigure the 69 kV and 138 kV buses. | TX | TX | BaseRel |  |  | 8268000 | 2019-06-01 | 2019-06-01 | 138 | 69 | Bottom-up
A in MTEP16 | B>A | South | Entergy-TX | 9807 | 2015-09-13 | 16-ETI-002 | Pintail 138 kV: Construct new Switching Substation | Expand an existing substation to include breakers and switchs. This will allow a normally open point to be closed. | TX | TX | Other |  | Distribution | 9524000 | 2018-12-01 | 2018-12-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-TX | 9808 | 2015-09-14 | 16-ETI-005 | Kirbyville 69 kV: Add Cap Bank | Add a new capacitor bank to the Kirbyville 69 kV substation. | TX | TX | BaseRel |  |  | 1000000 | 2018-06-01 | 2018-06-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-TX | 9809 | 2015-09-14 | 16-ETI-007 | Hull to Sour Lake 69 kV: Reconductor Line | Reconductor the Hull to Sout Lake 69 kV line. | TX | TX | BaseRel |  |  | 30759000 | 2019-06-01 | 2019-06-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-TX | 9810 | 2015-09-14 | 16-ETI-008 | Raywood to Daisetta 69 kV: Reconductor Line | Reconductor the Raywood to Daisetta 69 kV line. | TX | TX | BaseRel |  |  | 8655000 | 2019-12-01 | 2019-12-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-TX | 9812 | 2015-09-14 | 16-ETI-014-1 | PARIP Garden 230 kV: Construct New 230 kV Substation | Port Arthur Reliability Improvement Plan: Cut the Sabine to China 230 kV line and the Nederland to Mid County 230 kV line into a new 230 kV substation named Garden. | TX | TX | BaseRel |  |  | 65835000 | 2019-06-01 | 2019-06-01 | 230 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-TX | 9813 | 2015-09-14 | 16-ETI-014-2 | PARIP Garden to Legend 230 kV: Construct New Line | Port Arthur Reliability Improvement Plan: Construct a new line from the new Garden substation to the new Legend substation. | TX | TX | BaseRel |  |  |  | 2019-06-01 | 2019-06-01 | 230 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-TX | 9814 | 2016-05-10 | 16-ETI-014-3 | PARIP Legend 230 kV: Construct New Substation | Port Arthur Reliability Improvement Plan: Construct a new substation and cut in 230 kV line 829(Port Acres to Keith Lake). The new substation will be named Legend. | TX | TX | BaseRel |  |  |  | 2019-06-01 | 2019-06-01 | 230 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-TX | 9817 | 2015-09-14 | 16-ETI-016 | Helbig 230 kV: Reconfigure Bus | Reconfigure the bus work at the Helbig 230 kV substation to represent a ring bus. | TX | TX | BaseRel |  |  | 7196000 | 2018-12-01 | 2018-12-01 | 230 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-TX | 9818 | 2016-09-14 | 16-ETI-017 | Stowell to Himex 69 kV: Convert to 138 kV | Convert the Stowell to Himex 69 kV line to 138 kV. The line is already built to 138 kV standards. | TX | TX | BaseRel |  |  | 13600000 | 2019-06-01 | 2019-06-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-TX | 9852 | 2015-09-14 | 16-ETI-018 | Grimes 345/138 kV: Install Breakers on Low Side of AT2 | Install breakers on the low side of autotransformer number 2 at the Grimes 345/138 kV substation. | TX | TX | BaseRel |  |  | 1142000 | 2017-06-01 | 2017-06-01 | 345 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-TX | 10823 | 2016-03-01 | 16-ETI-021 | Moscow 138 kV: Construct New Substation | Construct a new 138 kV substation on L-411 Corrigan Bulk to Kickapoo 138 kV line to serve an industrial customer. | TX | TX | Other |  | Distribution | 7004002 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | South | Entergy-TX | 11363 | 2016-08-09 | 16-ETI-023 | Hartburg 500 kV: Reconfigure Line Bays | Re-position the line bays of line L-800 (Hartburg-Cottonwood 500 kV Circuit 1) and line L-547 (Hartburg-Cypress 500 kV line) at Hartburg 500 kV substation. | TX | TX | BaseRel |  |  | 2000000 | 2017-06-01 | 2017-06-01 | 500 |  | Bottom-up
A in MTEP16 | B>A | South | LAFA | 8821 | 2015-08-21 |  | Northeast to Peck | 69kv line connecting Northeast station to Peck station. | LA | LA | Other |  | Distribution | 4230000 | 2019-12-31 | 2019-12-31 | 69 |  | Bottom-up
A in MTEP16 | B>A | South | SMEPA | 9957 | 2016-04-27 |  | Origis Solar Project Substation | The Origis Energy solar plant will tap SMEPA's existing 69kV Line 42 (Sumrall to Rawls Springs) approximately 5.6 miles from Sumrall with a new 69kV switching station and a 69/26.4 kV GSU. Line 42 and 43 (Columbia to Sumrall) will be uprated to a higher conductor temperature via structural change outs to support the generation addition. OPGW will also be installed for communications. | MS | MS | GIP |  |  | 1590000 | 2017-03-23 | 2017-03-23 | 69 | 26.4 | Externally-Driven
A in MTEP16 | B>A | South | SMEPA | 9969 | 2016-05-08 |  | Origis Solar Project Transmission Rebuilds | The Origis Energy solar plant will tap SMEPA's existing 69kV Line 42 (Sumrall to Rawls Springs) approximately 5.6 miles from Sumrall with a new 69kV switching station and a 69/26.4 kV GSU. Line 42 and 43 (Columbia to Sumrall) will be uprated to a higher conductor temperature via structural change outs to support the generation addition. OPGW will also be installed for communications. | MS | MS | GIP |  |  | 4782000 |  |  | 69 |  | Externally-Driven
A in MTEP16 | B>A | West | ATC | 3190 | 2016-02-02 | PR05190 | Rebuild Sunset Point-Winneconne 69 kV | Rebuild line Y-103 from Sunset Point to Winneconne to SN/SE = 200/300 deg F | WI | WI | Other |  | Reliability | 3868404 | 2016-04-29 | 2016-04-29 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 7583 | 2016-07-13 | PR04985 | Rebuild Lone Rock - Boscobel 69 kV | Rebuild Y-124 from Lone Rock to Boscobel with T2-4/0 ACSR. Inlcudes partial rebuild of Y-78 Lone Rock - Richland Center | WI | WI | Other |  | Condition | 41848961 | 2015-12-31 | 2018-12-31 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 7983 | 2015-09-15 | PR05247 | Install 138/69 kV Canal Breakers | Install Canal 138-69 kV transformer high/low side breaker additions | WI | WI | Other |  | Distribution | 5100000 | 2017-06-01 | 2017-06-01 | 138 | 69 | Bottom-up
A in MTEP16 | B>A | West | ATC | 7985 | 2015-09-18 | PR04578 F3720 WO:69613 | Install 138 kV Canal Redundant Bus Differentials | This project consists of installing redundant bus differential protection on the two Canal 138-kV buses. The project will install two new dual SEL-487B bus differential relay panels. | WI | WI | Other |  | Distribution | 221116 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 8442 | 2015-10-13 | PR05503 | Replace Arnott 138/69 kV Transformer | Asset maintenance, Replace the Arnott 138-69 kV Tr with 60 MVA unit | WI | WI | Other |  | Reliability | 4545000 | 2016-12-31 | 2016-12-31 | 138 | 69 | Bottom-up
A in MTEP16 | B>A | West | ATC | 8640 | 2015-09-15 |  | Upgrade City Limits Bus 138 kV | Replace bus conductors at City Limits | WI | WI | Other |  | Reliability | 500000 | 2017-12-31 | 2017-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 8841 | 2015-03-16 | PR04988 | Rebuild Finger Rd - Canal 69 KV | This project is a Asset Management driven project to rebuild the main section of J-10 from Finger Road to Beardsley to Canal. The tapped lines off of J-10 and East Krok to Beardsley are not included in this scope. No substation work is included in scope. | WI | WI | Other |  | Reliability | 74000000 | 2019-12-01 | 2019-12-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 9423 | 2016-08-17 | PR04968, F3633 & F363 WO: 069403-55, | Rebuild 115KV Line B-106 Plover - Whiting Avenue Substation | Rebuild line B-106 (Plover-Okray-Whiting 115) using existing conductor 795 ACSR. | WI | WI | BaseRel |  |  | 6217603 | 2019-12-01 | 2019-12-01 | 115 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 9896 | 2015-09-15 |  | Lyndon Substation | Install 2 line breakers to sectionalize. | WI | WI | Other |  | Distribution | 3100000 | 2015-12-31 | 2015-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 9911 | 2015-09-15 | PR#5981 | Maes Substation 138 kV | Maes substation: Install 2 line breakers to sectionalize. | WI | WI | Other |  | Distribution | 1800000 | 2016-04-22 | 2016-04-22 | 138 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 9917 | 2016-06-10 | PR04727, PR04726, F3576, WO064898 | Bloomington Substation 69kV | Install SCADA controlled breakers to sectionalize. | WI | WI | Other |  | Distribution | 1600000 | 2016-12-31 | 2016-12-31 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 9918 | 2015-09-15 | PR#6143 | Red Maple Substation 138kV | Install a bus tie breaker. | WI | WI | Other |  | Distribution | 1200000 | 2016-06-01 | 2016-06-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 9921 | 2015-09-15 | PR#6142 | Birchwood Substation 138kV | Install a bus tie breaker. | WI | WI | Other |  | Distribution | 700000 | 2017-12-31 | 2017-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 9923 | 2015-09-15 |  | Mukwanago Substation 138kV | Install line breaker on line 67K61. | WI | WI | Other |  | Distribution | 600000 | 2017-12-01 | 2017-12-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 9934 | 2016-07-13 | PR07285 | Upgrade Oak Creek - Hayes 138-kV line | Oak Creek - Hayes 138-kV line 811 upgrade and reconfiguration | WI | WI | Other |  | Reliability | 21000000 | 2018-06-30 | 2018-06-30 | 138 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 9938 | 2015-09-15 | PR04754 | Replace Sunset Point 138-69 kV Transformer | Replace 138/69KV power transformer with 100MVA continuous top rated transformer. | WI | WI | Other |  | Reliability | 6000000 | 2016-12-01 | 2016-12-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 9944 | 2015-09-15 |  | Replace Erdman T31 Transformer | Replace Erdman T31 Transformer. | WI | WI | Other |  | Reliability | 6000000 | 2017-12-31 | 2017-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 9954 | 2015-12-03 | PR07375 | Replace Lost Dauphin T1 Transformer | Replace Lost Dauphin T1 Transformer. | WI | WI | Other |  | Reliability | 6700000 | 2018-12-01 | 2018-12-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 9958 | 2015-09-15 |  | Replace East Krok Transformer | Replace East Krok Transformer. | WI | WI | Other |  | Reliability | 2500000 | 2017-12-31 | 2017-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 9961 | 2015-09-15 |  | Replace Nelson Dewey T31/T32 Transformers | Replace Nelson Dewey T31/T32 Transformers. | WI | WI | Other |  | Reliability | 6000000 | 2018-12-31 | 2018-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 9977 | 2016-07-13 |  | Rebuild 69KV Line J-88 Goodman - Caldron Falls Substation | Rebuild 69KV Line J-88 Goodman - Caldron Falls Substation. | WI | WI | Other |  | Condition | 35000000 | 2020-06-30 | 2020-06-30 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 9986 | 2016-02-12 | PR07410 | Rebuild 138KV Line 762 Port Washington - Saukville Substation | Rebuild 138KV Line 762 Port Washington - Saukville Substation. | WI | WI | BaseRel |  |  | 15000000 | 2021-12-31 | 2021-12-31 | 138 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 10403 | 2016-05-04 | PR07285,F4849, WO 602023 | Re-rate Kegonsa - Sun Prairie (Y-81) 69kV Line | Re-rate Y -81 69kV line between Kegonsa - Sun Prairie. | WI | WI | Other |  | Reliability | 5000000 | 2017-04-21 | 2017-04-21 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 10404 | 2016-05-04 | PR07333,F4812, WO601919 | Re-rate 9 Mile - Detour (6950) 69kV Line | Re-rate Approximately 56.87 miles (6950) 69kV Line between 9 Mile - Detour substations. | MI | MI | Other |  | Reliability | 7000000 | 2017-03-17 | 2017-03-17 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 10484 | 2015-12-16 | PR07373 | Construct Eaton 138 kV T- D | Construct a new ATC 138KV loop through at Eaton Substation. | WI | WI | Other |  | Distribution | 2500000 | 2019-06-01 | 2019-06-01 | 138 | 24.9 | Bottom-up
A in MTEP16 | B>A | West | ATC | 10485 | 2015-12-16 | PR007372 | Construct Bay Ridge 138 kV T- D | Construct a new ATC 138KV loop through at Bay Ridge Substation. | WI | WI | Other |  | Distribution | 2000000 | 2022-06-01 | 2022-06-01 | 138 | 24.9 | Bottom-up
A in MTEP16 | B>A | West | ATC | 10543 | 2016-01-05 | PR07390 | Construct T-D Escanaba North Substation | Construct T-D Escanaba North Substation (GOAB) | MI | MI | Other |  | Distribution | 1000000 | 2017-01-01 | 2017-01-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 10563 | 2016-01-12 | PR07397 | Construct T -D Oakview Substation | Construct T -D Oakview Substation | WI | WI | Other |  | Distribution | 4900000 | 2018-06-01 | 2018-06-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 10589 | 2016-01-12 | PR07388 | Rerate Whitcomb - Tigerton Tap 69kV | Rerate Whitcomb - Tigerton Tap 69kV | WI | WI | Other |  | Reliability | 1400000 | 2017-06-09 | 2017-06-09 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 10603 | 2016-01-13 | PR07299 | Construct T - D Springwater Substation | Construct T - D Springwater Substation. | WI | WI | Other |  | Distribution | 7100000 | 2019-12-31 | 2019-12-31 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 10643 | 2016-02-12 | PR07400 | Construct T - D St. Martins Substation | St Martins Bus Expansion, Bus-tie Breaker Addition, Line Relocation, and T-D Transformer Addition. | WI | WI | Other |  | Distribution | 2300000 | 2017-01-01 | 2018-01-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 10683 | 2016-02-02 | PR07394 | Uprate Lone Rock - Richland Center 69kV Line | Uprate Lone Rock - Richland Center to max operating temperature. | WI | WI | Other |  | Reliability | 1700000 | 2017-06-09 | 2017-06-09 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 10684 | 2016-02-02 | PR07396 | Construct T - D Ellinwood Substation | T-D distribution transformer addition at Ellinwood Substation. | WI | WI | Other |  | Distribution | 100000 | 2017-06-01 | 2017-06-01 | 138 | 24.9 | Bottom-up
A in MTEP16 | B>A | West | ATC | 10685 | 2016-02-02 | PR07393 | Construct T - D Tomahawk Substation | Tomahawk Substation bus-tie breaker addition and T-D distribution transformer addition. | WI | WI | Other |  | Distribution | 700000 | 2017-06-01 | 2017-06-01 | 115 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 10686 | 2016-02-02 | PR07392 | Construct T - D Roosevelt Road Substation | ATC bus expansion and T-D distribution transformer addition. | WI | WI | Other |  | Distribution | 200000 | 2018-06-01 | 2018-06-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 10703 | 2016-02-08 | PR07050 | Replace Jefferson SS 138 kV Circuit Breakers | Replace Jefferson SS 138 kV Circuit Breakers and replace 138kV capacitor bank. | WI | WI | Other |  | Distribution | 2200000 | 2016-11-15 | 2016-11-15 | 138 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 11223 | 2016-07-13 | PR07437, F4934, WO602202 | Construct T - D Townhall Substation | New T-D Townhall Substation - GOAB on Y-32 and approx. 2 miles of new 69 kV ROW. | WI | WI | Other |  | Distribution | 3900000 | 2017-06-01 | 2017-06-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | ATC | 11224 | 2016-07-13 | PR07471 | Construct T - D White Lake Substation | White Lake Distribution Transformer Addition and ATC Line Breaker Addition. | WI | WI | Other |  | Distribution | 908000 | 2017-11-01 | 2017-11-01 | 138 |  | Bottom-up
A in MTEP16 | B>A | West | CFU-PMEU | 11383 | 2016-06-15 | Pella RRHD | J329 Network Upgrades | Network upgrades associated with J329 for substations in Pella Iowa. | IA | IA | GIP |  |  | 1043700 | 2017-08-01 | 2017-08-01 | 69 |  | Externally-Driven
A in MTEP16 | B>A | West | GRE | 7884 | 2015-03-30 | 203079 | Riverview 345/115/69 kV Substation | Construct the new Riverview 345/115/69 kV substation directly off the CapX 345 kV line between the Melrose East and Millwood 69 kV substations. The transformers will be a 448 MVA, 345/115 kV transformer and a 70 MVA 115/69 MVA transformer. This substation will initially have two 345 line terminating breakers, a single 345 kV breaker on the high side of the transformer, two 69 kV line termination breakers in addition to a low side 69 kV breaker. The substation should be designed for future development and be laid out for nine 345 breaker (3 rows of 345 kV breakers in a breaker and half scheme), six 115 kV (2 rows of 115 kV breakers in a breaker and half scheme), and four 69 kV breakers in a straight bus configuration. | MN | MN | Other |  | Reliability | 20051684 | 2018-12-10 | 2018-12-10 | 345 | 69 | Bottom-up
A in MTEP16 | B>A | West | GRE | 7896 | 2015-03-30 | 202987 | Fish Trap Pumping Station | Construct a new 115 kV transmission line from the Dog Lake to Scearcyville (#24 Line) 115 kV transmission line to Koch Pipeline's new Fish Trap pumping substation (approximately 20 miles). | MN | MN | Other |  | Reliability | 10855000.26 | 2017-08-31 | 2017-08-31 | 115 | 115 | Bottom-up
A in MTEP16 | B>A | West | GRE | 10423 | 2015-12-01 | 20418 | Randolph Distribution Substation | Construct approximately 0.25 mile in and out 115 kV line from the NSP 0822 line (Empire to Colville). | MN | MN | Other |  | Distribution | 525000 | 2017-03-30 | 2017-03-30 | 115 |  | Bottom-up
A in MTEP16 | B>A | West | GRE | 10424 | 2015-12-01 | 20559 | Savage Distribution Substation | Construct approximately 0.5 mile in and out 115 kV line from the NSP 5539 line (Black Dog to Blue Lake). | MN | MN | Other |  | Distribution | 1000000 | 2017-10-31 | 2017-10-31 | 115 |  | Bottom-up
A in MTEP16 | B>A | West | GRE | 11463 | 2016-07-25 | 204473 | C023 - Stanton 31RB3 | Jumper replacement inside Stanton Substation at 230 kV breaker 31RB3. | ND | ND | GIP |  |  | 33033 | 2016-11-01 | 2016-11-01 | 230 |  | Externally-Driven
A in MTEP16 | B>A | West | GRE, MP | 4378 | 2016-08-11 | 202970 | Menahga Area Project | Build Hubbard to Blueberry to Red Eye 115 kV | MN | MN | Other |  | Distribution | 29360748.68 | 2017-04-01 | 2020-09-01 | 115 | 34.5 | Bottom-up
A in MTEP16 | B>A | West | ITCM | 9664 | 2015-09-09 | Guthrie-Panora 34 to 69 Conv | Guthrie-White Pole Rd-Panora 34 to 69 kV Conversion | Convert 34.5 kV system between Guthrie - White Pole Rd (new breaker station) - Menlo - Redfield - Panora - Guthrie to 69 kV operation | IA | IA | Other |  | Condition | 3385176 | 2017-12-31 | 2017-12-31 | 69 | 69 | Bottom-up
A in MTEP16 | B>A | West | ITCM | 9665 | 2015-09-09 | PCI-Oak Hill 34 to 69 Conv | PCI-Oak Hill 34 to 69 kV Conv | Convert 34.5 kV system between PCI and Oak Hill to 69 kV operation | IA | IA | Other |  | Condition | 33600 | 2017-12-31 | 2017-12-31 | 69 | 69 | Bottom-up
A in MTEP16 | B>A | West | ITCM | 9666 | 2015-09-09 | Emerald Isle-Beverly 34 to 69 kV Conv | Emerald Isle-Beverly 34 to 69 kV Conv | Convert 34.5 kV system between Beverly and Emeral Isle to 69 kV operation. | IA | IA | Other |  | Condition | 5114718 | 2018-12-31 | 2018-12-31 | 69 | 69 | Bottom-up
A in MTEP16 | B>A | West | ITCM | 9667 | 2015-09-09 | Wapello Reliability Rebuild | Wapello County Substation Reliability Rebuild | Rebuild the Wapello County 161kV to breaker and 1/2 design and upgrade the 69 kV ring bus. | IA | IA | BaseRel |  |  | 10115465 | 2017-12-31 | 2017-12-31 | 161 | 69 | Bottom-up
A in MTEP16 | B>A | West | ITCM | 9668 | 2015-09-11 | CR-North Liberty-Hills | Cedar Rapids-North Liberty area-Hills Upgrades | Add a new Hills area 345/161kV source and upgrade the 161 and 69kV systems in the North Liberty area. This includes a new North Liberty 161/69kV substation also. | IA | IA | BaseRel |  |  | 75440438 | 2019-12-31 | 2025-12-31 | 345 | 69 | Bottom-up
A in MTEP16 | B>A | West | ITCM | 9669 | 2015-11-18 | St. Ansgar Industrial | St. Ansgar Industrial Substation | New 69kV/distribution substation. Tap 69kV line and install new 69kV breakers for new substation. | IA | IA | Other |  | Distribution | 2508817 | 2017-11-11 | 2017-11-17 | 69 | 69 | Bottom-up
A in MTEP16 | B>A | West | ITCM | 9670 | 2015-09-09 | Columbus Junction Breaker add | Columbus Junction 69 kV Breaker Addition | Add 69 kV breaker at the Columbus Junction substation. | IA | IA | Other |  | Distribution | 932101 | 2020-12-31 | 2020-12-31 | 69 | 69 | Bottom-up
A in MTEP16 | B>A | West | ITCM | 9671 | 2015-09-09 | Amber Creamery Capacitor | Amber Creamery 69 kV Capacitor | Add a 69 kV cap bank at the Amber Creamery substation. | IA | IA | Other |  | Reliability | 515076 | 2016-12-31 | 2016-12-31 | 69 | 69 | Bottom-up
A in MTEP16 | B>A | West | ITCM | 9672 | 2015-09-09 | 76th AVE SW | 76th AVE SW Substation | ITC will need to construct a new four (4) terminal, four (4) breaker 69 kV substation southeast of the city of Cedar Rapids, Iowa in order to eliminate the coordination and system protection issues. The existing PCI – Tharp 69 kV transmission line will need to be tapped and re-routed into the new substation. The existing Prairie Creek Ckt. 0210 will need to be re-routed and terminated into the new substation when the area is converted as well. A 13.2 MVAR capacity bank will be installed at the new substation to provide voltage support for the area. | IA | IA | Other |  | Condition | 4056304 | 2019-12-31 | 2019-12-31 | 69 | 69 | Bottom-up
A in MTEP16 | B>A | West | ITCM | 9706 | 2015-09-10 | Huntley 69 kV Maintenance | Huntley 69 kV Maintenance | Relocate the 161/69 kV T1 transformer and replace the 161/69 kV T2 transformer with the Adams 161/69 kV 75 MVA transformer and the 69 kV breakers at the new proposed Huntley substation. | MN | IA | Other |  | Reliability | 9055247 | 2016-12-31 | 2016-12-31 | 161 | 69 | Bottom-up
A in MTEP16 | B>A | West | ITCM | 9711 | 2015-10-19 | Traer 161 kV Ring Bus | Traer 161 kV Ring Bus | Convert the Traer 161 kV to a ring bus design. | IA | IA | BaseRel |  |  | 5065882 | 2017-12-31 | 2017-12-31 | 161 | 161 | Bottom-up
A in MTEP16 | B>A | West | ITCM | 9712 | 2015-09-10 |  | BGS Substation Upgrades | Modify the Burlington Generating Station’s substation for increased reliability and to accommodate the required NERC PRC-005 maintenance testing of the BGS relaying schemes. Replace 161 kV circuit switcher 1272 with a breaker to isolate the BGS - Denmark #2 161 kV line from 161/69 kV T2 transformer. The 69 kV motor-operated switches will be replaced with 69 kV main circuit breakers to create separately relayed 161/69 kV transformer and 69 kV bus sections. Additional three-phase 161 kV voltage transformers will be added. A new control enclosure will be added outside the BGS power plant. All ITC relaying will be replaced and be installed in this new enclosure. The existing schemes in the BGS plant control room will be retired and removed. | IA | IA | BaseRel |  |  | 3114346 | 2017-06-01 | 2017-06-01 | 161 | 69 | Bottom-up
A in MTEP16 | B>A | West | ITCM | 9714 | 2015-09-11 | Doud-Lyon 34 to 69 kV Conv | Doud-Lyon 34 to 69 kV Conv | Construct a new 69 kV breaker station near Lyon with 3 line terminals. The station should be laid out to accommodate a future additional breaker position for an Alliant Energy distribution transformer. Re-connect or extend 69 kV taps to the connected distribution substations and convert to 69 kV operation from the new station near Lyon to Doud. | IA | IA | Other |  | Condition | 4638479 | 2019-12-31 | 2019-12-31 | 69 | 69 | Bottom-up
A in MTEP16 | B>A | West | ITCM | 9901 | 2015-11-18 | Mount Ayr 69 kV Sub Rebuild | Mount Ayr 69 kV Substation Rebuild | Complete rebuild of the substation with all new equipment was proposed. Due to space limitations at the existing site, a new Kneedler (Mt. Ayr) 69kV breaker station will be constructed just north of the Mt. Ayr site. The existing 8.1MVAr cap will be replaced with a 3-stage 8.4MVAr (25.2MVAr total) capacitor bank at the Kneedler sub site. | IA | IA | Other |  | Condition | 4944594 | 2018-12-31 | 2018-12-31 | 69 | 69 | Bottom-up
A in MTEP16 | B>A | West | ITCM | 9904 | 2015-09-15 | Appanoose Co 161 kV Rebuild | Appanoose Co 161 kV Rebuild | ITC will replace it with a unit equipped with a Load Tap Changer (LTC). The 100 MVA (equipped with a LTC) 161:69kV transformer at Fernald will be relocated to Appanoose County after the MGS upgrades are completed. In addition, to increase reliability, ITC will rebuild the existing 161kV bus to a ring configuration. | IA | IA | BaseRel |  |  | 4944594 | 2019-12-31 | 2019-12-31 | 161 | 69 | Bottom-up
A in MTEP16 | B>A | West | ITCM | 9907 | 2015-09-15 | Summit to Dovray 69 kV Rebuild | Summit to Dovray 69 kV Rebuild | Phase 1: Rebuild ~12.9 miles of old line to new T2-4/0 ACSR | MN | MN | Other |  | Condition | 9162091 | 2022-12-31 | 2022-12-31 | 69 | 69 | Bottom-up
A in MTEP16 | B>A | West | ITCM | 9908 | 2015-09-15 | Dovray to Fulda 69 kV Rebuild | Dovray to Fulda 69 kV Rebuild | Rebuild ~14.5 miles of old line to new T2-4/0 ACSR | MN | MN | Other |  | Condition | 9410124 | 2023-12-31 | 2023-12-31 | 69 | 69 | Bottom-up
A in MTEP16 | B>A | West | ITCM | 9910 | 2015-09-15 | Fulda to Heron Lake 69 kV Rebuild | Fulda to Heron Lake 69 kV Rebuild | Rebuild ~20.14 miles of old line to new T2-4/0 ACSR | MN | MN | Other |  | Condition | 14976652 | 2024-12-31 | 2024-12-31 | 69 | 69 | Bottom-up
A in MTEP16 | B>A | West | ITCM | 9937 | 2015-09-15 | J233 Network Upgrades | J233-Network Upgrades | Replace existing 161/69 kV transformers with 150 MVA units at Fernald, Jasper, and Newton substations. Uprate the Marshalltown-Blairstown Junction 115 kV line to 90 MVA; Uprate the Jasper to Laurel161 kV to 361 MVA; remove sag limit from Jasper to Newton 161 kV line to allow operation at 276 MVA; Rebuild ITCM's portion of the Newton to Prairie City 69 kVwith T2-4/0 ACSR to allow operation at MEC's rating of 40 MVA | IA | IA | GIP |  |  | 17740415 | 2015-09-15 | 2017-03-30 | 161 | 69 | Externally-Driven
A in MTEP16 | B>A | West | ITCM | 9939 | 2015-09-15 | H009-Jasper-Aurora 69 kV | H009-Jasper-Aurora 69 kV | Rebuild Jasper to Aurora Heights 69 kV with T2-477 ACSR | IA | IA | GIP |  |  | 3720000 | 2016-12-31 | 2016-12-31 | 69 | 69 | Externally-Driven
A in MTEP16 | B>A | West | ITCM | 9941 | 2015-09-15 | H021-Traer-Traer Tap 69 kV | H021-Traer-Traer Tap 69 kV | Upgrade Traer to Trear Tap 69 kV | IA | IA | GIP |  |  | 293449 | 2016-06-01 | 2016-06-01 | 69 | 69 | Externally-Driven
A in MTEP16 | B>A | West | ITCM | 9985 | 2015-09-15 | Newhall-Williamsburg 161 kV | Newhall-Williamsburg 161 kV Rebuild | Rebuild Williamsburg 115kV tap to 161kV | IA | IA | Other |  | Condition | 40174153 | 2018-12-31 | 2018-12-31 | 161 | 161 | Bottom-up
A in MTEP16 | B>A | West | ITCM | 9988 | 2015-09-15 | Newhall 161 kV Breaker Station | Newhall 161 kV Breaker Station | Construct a new 3 position 161kV breaker station | IA | IA | Other |  | Condition | 8090882 | 2018-12-31 | 2018-12-31 | 161 | 161 | Bottom-up
A in MTEP16 | B>A | West | ITCM | 10022 | 2015-09-15 | PCI-Mt.Vernon-Lisbon-76thAVE Conv | PCI-Mt.Vernon-Lisbon-76th AVE Conv | ITC will be converting the PCI to Mt. Vernon to Lisbon North to 76th Ave. substation from 34.5 kV operation to 69 kV operation. To accommodate the conversion, a 69 kV breaker and associated equipment will be installed at the PCI substation, two (2) 69 kV breakers and associated equipment will be installed at the Lisbon North substation, approximately 0.6 mile of new 69 kV transmission line will be constructed to complete the PCI to 76th Ave circuit and OPGW will need to be installed. | IA | IA | Other |  | Condition | 5793932 | 2019-12-31 | 2019-12-31 | 69 | 69 | Bottom-up
A in MTEP16 | B>A | West | ITCM | 10023 | 2015-09-17 | ITCM Asset Blanket | ITC Midwest Asset Replacement Program | Equipment that is past its expected design life, utilizes outdated functionality or whose failure rates and maintenance have increased potential for misoperations and higher maintenance costs associated with their ongoing use. | IA,MN,IL | IA,MN,IL | Other |  | Condition | 111600000 | 2017-12-31 | 2019-12-31 | 345 | 69 | Bottom-up
A in MTEP16 | B>A | West | ITCM | 10024 | 2015-09-15 | Cust Interconnet Blanket | ITCM Customer Interconnects with short lead time | These projects are being done at the request of an interconnection customer in order to facilitate new load, re-distribute existing load, improve the performance of the sub-transmission and distribution systems, or to accommodate a new Transmission-to-Transmission connection request. | IA,MN,IL | IA,MN,IL | Other |  | Distribution | 2000000 | 2019-12-31 | 2019-12-31 | 345 | 69 | Bottom-up
A in MTEP16 | B>A | West | ITCM | 10268 | 2015-10-28 | DBQ 8th ST dist TRFs | Dubuque 8th Street Distribution Transformer Upgrades | This project consists of the ITC work required to allow for the replacement of the two 69/distribution transformers at the 8th Street substation. This project will move the Alliant distribution transformer T-225 position to the existing Sandridge (bkr 253) position & move the ITC owned Sandridge terminal equipment to the former T-255 (bkr 252) position. Alliant will move the T-140 (bkr 257) position to the former North Clinton (bkr 256) position. This project will also require relay upgrades. In addition, the removal of a guyed structure and replace with a new self-supported structure within the substation will be required. | IA | IA | Other |  | Reliability | 1603393 | 2017-04-30 | 2017-04-30 | 69 | 69 | Bottom-up
A in MTEP16 | B>A | West | ITCM | 10269 | 2015-10-30 | Lore-Hickory 161 | Lore-Hickory Creek 161kV Rebuild | Rebuild 6.81 miles of the Lore-Hiclory Creek 161kV line and upgrade the Lore 161kV terminal. | IA | IA | BaseRel |  |  | 12700847 | 2017-12-31 | 2017-12-31 | 161 | 161 | Bottom-up
A in MTEP16 | B>A | West | ITCM | 10303 | 2015-11-05 | Willaimsburg 161kV Temp Conv | Willaimsburg 161kV Temp Conversion | To provide a reliable conversion to 69kV the 34.5kV will need temporary configurations to provide a reliable transition. The Williamsburg 115kV high side will be converted to 161kV. The two aging and miss-matched 115/34.5kV transformers will be replaced with a newer and larger 161/36kV transformer from the Hiawatha Substation. This will provide an increased level of reliability to Williamsburg by serving the high-side from a newly rebuilt and shorter 161kV line compared to an older and longer 115kV line. | IA | IA | Other |  | Reliability | 1204368 | 2017-12-30 | 2017-12-31 | 161 | 34 | Bottom-up
A in MTEP16 | B>A | West | ITCM | 11163 | 2016-08-03 | Devils Creek | Devils Creek | 69 kV customer interconnection near Ft. Madison, IA. Build a new Devils Creek 69kV distributions substation. | IA | IA | Other |  | Distribution | 2026223 | 2017-12-31 | 2017-12-31 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | ITCM | 11164 | 2016-08-03 | Oelwein Hub | Oelwein Hub Distribution Sub | ITCM will form an in and out configuration and install two line breakers at the new substation. | IA | IA | Other |  | Distribution | 6317468 | 2017-04-30 | 2017-04-30 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | ITCM | 11763 | 2016-08-16 | J344 Network Upgrades | J344 Network Upgrades - Irvine Switch Station | To provide a point of interconnection for project J344, a 169 MW wind-powered generating facility, a new 3-terminal, 3-breaker “Irvine” ring bus substation on the Poweshiek to Beacon 161 kV line . The Network Upgrade was required to interconnect the project to the transmission system, and the Network Upgrade was required as a condition of Interconnection Service for project J344. | IA | IA | GIP |  |  | 5537540 | 2017-09-01 | 2017-09-01 | 161 | 161 | Externally-Driven
A in MTEP16 | B>A | West | ITCM, XEL | 11883 | 2016-08-31 |  | Huntley - Wilmarth 345 kV | Huntley to Wilmarth 345 kV Single Ckt Transmission Line - 38.5 miles | MN | MN | MEP | Shared |  | 108000000 | 2022-01-01 | 2022-01-01 | 345 |  | Top-Down
A in MTEP16 | B>A | West | MDU | 4140 | 2015-06-10 | Bowdle | Bowdle Jct | Build a new Bowdle Jct to replace old Bowdle substation | SD | SD | Other |  | Reliability | 5500000 | 2017-06-30 | 2017-06-30 | 115 | 41.6 | Bottom-up
A in MTEP16 | B>A | West | MDU | 9120 | 2015-07-13 |  | Leola | A new 115 kV transmission line from the Ellendale Jct. Substation to a new Leola Jct. 115/41.6 Substation. The new Leola Jct. substation will connect to the existing Ellendale-Bowdle 41.6 kV line. | SD,ND | SD | Other |  | Reliability | 12835000 | 2017-10-31 | 2017-10-31 | 115 | 41.6 | Bottom-up
A in MTEP16 | B>A | West | MDU | 9121 | 2015-06-10 |  | Heskett-Mandan 115 Upgrade | Replace limiting switches in the Heskett substation on the Mandan 115 kV line. | ND | ND | BaseRel |  |  | 125000 | 2016-12-31 | 2016-12-31 | 115 |  | Bottom-up
A in MTEP16 | B>A | West | MDU | 11403 | 2016-06-20 |  | TSR F109/A634 | Reconductor Coyote-Beulah 115 kV line | ND | ND | TDSP |  |  | 350000 | 2015-12-31 | 2015-12-31 | 115 |  | Externally-Driven
A in MTEP16 | B>A | West | MEC | 8108 | 2015-09-15 |  | Sub 73 - Dupont 69 kV Line Upgrade | Replace structures to allow a higher operating temperature for the line. | IA | IA | Other |  | Reliability | 40000 | 2017-06-01 | 2017-06-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | MEC | 8110 | 2015-09-15 |  | Sub 73 - Elvira Tap 69 kV line upgrade | Replace structures on the Sub 73-Elvira 69 kV line to allow a higher operating temperature. | IA | IA | Other |  | Reliability | 50000 | 2017-06-01 | 2017-06-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | MEC | 8112 | 2015-09-15 | G7055 | Buffalo Bill Tap - Elvira Tap 69 kV line upgrade | Replace structures to allow a higher conductor operating temperature. | IA | IA | Other |  | Reliability | 25000 | 2017-06-01 | 2017-06-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | MEC | 9947 | 2015-09-15 |  | Polk City Substation and Lines | Build a new 33 MVA 161-13 kV distribution substation near Polk City, Iowa with 161 kV line taps connecting to the Bittersweet-NE Ankeny 161 kV line. | IA | IA | Other |  | Distribution | 7000000 | 2018-06-01 | 2018-06-01 | 161 | 13 | Bottom-up
A in MTEP16 | B>A | West | MEC | 9973 | 2016-06-07 |  | Manawa Second Transformer | Add a second 33 MVA 161-13 kV transformer at the Manawa Substation. | IA | IA | Other |  | Distribution | 1100000 | 2017-10-01 | 2017-10-01 | 161 | 13 | Bottom-up
A in MTEP16 | B>A | West | MEC | 9976 | 2016-06-07 |  | Avoca transformer 69 kV circuit breaker | Add a 69 kV circuit breaker on the low side of Avoca 161-69 kV transformer 8T1. | IA | IA | Other |  | Reliability | 415000 | 2016-12-01 | 2016-12-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | MEC | 9980 | 2015-09-15 |  | Teakwood 34.5 kV Reactors | Add two 10 MVAr 34.5 kV reactors at Teakwood Substation. | IA | IA | Other |  | Reliability | 850000 | 2016-10-01 | 2016-10-01 | 34.5 |  | Bottom-up
A in MTEP16 | B>A | West | MEC | 9981 | 2015-09-15 |  | Sub 701-Honey Creek 69 kV Line | Rebuild the Sub 701-Honey Creek 69 kV line. | IA | IA | Other |  | Reliability | 3250000 | 2017-06-01 | 2017-06-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | MEC | 9987 | 2015-09-15 |  | Johnston 161-13 kV Substation | Construct a new Johnston 33 MVA 161-13 kV distribution substation. | IA | IA | Other |  | Distribution | 2130000 | 2016-11-30 | 2016-11-30 | 161 | 13 | Bottom-up
A in MTEP16 | B>A | West | MEC | 9992 | 2015-09-15 |  | Lake Cornelia-Coulter 69 kV Upgrade | Replace limiting structures on the Lake Cornelia-Coulter 69 kV line to increase line rating. | IA | IA | Other |  | Reliability | 59000 | 2016-07-01 | 2016-07-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | MEC | 9993 | 2015-09-15 |  | Humboldt East-Thor 69 kV Upgrade | Upgrade the Humboldt East-Thor 69 kV line by replacing limiting structures. | IA | IA | Other |  | Reliability | 61000 | 2016-04-13 | 2016-04-13 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | MEC | 9996 | 2016-09-13 |  | Eagle Grove Second 69-13 kV transformer | Install a second 69-13 kV Transformer at the Eagle Grove Substation | IA | IA | Other |  | Distribution | 2440000 | 2016-12-09 | 2016-12-09 | 69 | 13 | Bottom-up
A in MTEP16 | B>A | West | MEC | 10004 | 2016-09-16 |  | Sub 18 replace transformer 8T3 | Replace 161-69 kV transformer 8T3 at Sub 18 with a 167 MVA unit. | IA | IA | Other |  | Reliability | 1080000 | 2018-06-01 | 2018-06-01 | 161 | 69 | Bottom-up
A in MTEP16 | B>A | West | MEC | 10005 | 2015-09-18 |  | Replace 161 kV Circuit Breaker at Plymouth | Replace 161 kV circuit breaker 9610 at Plymouth Substation | IA | IA | BaseRel |  |  | 264000 | 2015-12-08 | 2015-12-08 | 161 |  | Bottom-up
A in MTEP16 | B>A | West | MEC | 10006 | 2015-09-18 |  | Sycamore Substation: replace three 161 kVK circuit breakers | Replace 161 kV circuit breakers AG805, AG812 and AG816 at Sycamore Substation. | IA | IA | BaseRel |  |  | 685000 | 2016-12-31 | 2016-12-31 | 161 |  | Bottom-up
A in MTEP16 | B>A | West | MEC | 10009 | 2015-09-18 |  | Bondurant: Replace 161 kV circuit breaker | Replace 161 kV circuit breaker AH810 at Bondurant Substation. | IA | IA | BaseRel |  |  | 325000 | 2016-10-31 | 2016-10-31 | 161 |  | Bottom-up
A in MTEP16 | B>A | West | MEC | 10503 | 2015-12-21 | Q1138 | Tate & Lyle Bus Tie Breaker | Add a 161 kV bus tie circuit breaker at Tate & Lyle Substaiton | IA | IA | BaseRel |  |  | 443000 | 2016-10-20 | 2016-10-20 | 161 |  | Bottom-up
A in MTEP16 | B>A | West | MEC | 10663 | 2016-01-29 |  | Willow Creek Substation Expansion | Expand the Willow Creek Substation 161 kV bus to accommodate a new 50 MVA 161-13 kV transformer. Add three new 161 kV circuit breakers and convert the substation to a breaker and one-half configuration. | IA | IA | Other |  | Distribution | 120000 | 2016-12-31 | 2016-12-31 | 161 | 13.2 | Bottom-up
A in MTEP16 | B>A | West | MEC | 10664 | 2016-01-29 |  | 34th Avenue 3rd Transformer | Install a third 161-13 kV 62 MVA transformer and associated equipment at the 34th Ave. NW Substation. | IA | IA | Other |  | Distribution | 90000 | 2016-12-01 | 2016-12-01 | 161 | 13.2 | Bottom-up
A in MTEP16 | B>A | West | MEC | 10803 | 2016-02-29 |  | Sub J Iowa City Reduce Capactor Bank Size | Reduce the size of the existing 161 kV capacitor bank at Sub J Iowa City, from 50.4 MVAR to 37.8 MVAR. The capacitor bank relaying will also be replaced at this time. | IA | IA | BaseRel |  |  | 300000 | 2016-12-01 | 2016-12-01 | 161 |  | Bottom-up
A in MTEP16 | B>A | West | MEC | 10867 | 2016-09-14 |  | J285 Interconnection Facilities | Add one 345 kV circuit breaker position at Obrien County Substation 345 kV ring bus for the J285 generator interconnection. | IA | IA | GIP | Shared |  | 3000000 | 2016-08-15 | 2016-08-15 | 345 |  | Externally-Driven
A in MTEP16 | B>A | West | MEC | 10868 | 2016-09-14 |  | J411 Interconnection Facilities (Ida Co. Substation) | Construct a new three-terminal 345 kV ring bus substation (Ida County Substation), bisecting the Raun-Lehigh 345 kV line for the J411 generator interconnection. Install new transposition structures for the Raun-Ida County and Ida County-Lehigh 345 kV lines. ITC Midwest will have an ownership share of the network transmission facilities. | IA | IA | GIP | Shared |  | 5750000 | 2016-07-15 | 2016-07-15 | 345 |  | Externally-Driven
A in MTEP16 | B>A | West | MEC | 11103 | 2016-05-12 | T90D4 | Black Hawk: Install 2-69 kV Cap Banks | Add two 69 kV, 15 MVAR capacitor banks at Black Hawk Substation. | IA | IA | GIP |  |  | 1180000 | 2016-11-15 | 2016-11-15 | 69 |  | Externally-Driven
A in MTEP16 | B>A | West | MEC | 11143 | 2016-06-07 | T90D9 | Creston-Macksburg 161 kV Uprate | Structure replacements. | IA | IA | GIP |  |  | 175000 | 2016-12-01 | 2016-12-01 | 161 |  | Externally-Driven
A in MTEP16 | B>A | West | MEC | 11144 | 2016-04-27 | T90DK | Sub T(FD): Replace 161 kV Sw 11-817 | Replace 161 kV Switch 11-817 | IA | IA | GIP |  |  | 88000 | 2016-06-24 | 2016-06-24 | 161 |  | Externally-Driven
A in MTEP16 | B>A | West | MEC | 11145 | 2016-06-07 | T905K | Sub T FD-Boone Jct 161 Line Uprate | structure replacements | IA | IA | GIP |  |  | 173000 | 2016-06-30 | 2016-06-30 | 161 |  | Externally-Driven
A in MTEP16 | B>A | West | MEC | 11146 | 2016-04-27 | T90LA | Clarinda-Brooks 161 kV Uprate | structure replacements | IA | IA | GIP |  |  | 200000 | 2017-06-01 | 2017-06-01 | 161 |  | Externally-Driven
A in MTEP16 | B>A | West | MEC | 11203 |  |  | R42 Network Upgrades | Add two new 345 kV circuit breakers and create a ring bus at Lehigh Substation to accommodate Generator Interconnection Project R42 | IA | IA | GIP | Shared |  | 2882000 | 2012-11-01 | 2012-11-01 | 345 |  | Externally Driven
A in MTEP16 | B>A | West | MEC | 11204 |  |  | J191 Network Upgrades | Add a new 345 kV circuit breaker and associated switches at the Rolling Hills Substation to accommodate Generator Interconnection Project J191 | IA | IA | GIP | Shared |  | 754100 | 2011-12-30 | 2011-12-30 | 345 |  | Externally Driven
A in MTEP16 | B>A | West | MEC | 11283 | 2016-07-25 | T90L8 | Clarinda-Maryville 161 kV Uprate | Replace three structures. | IA | IA | GIP |  |  | 100100 | 2017-06-01 | 2017-06-01 | 161 |  | Externally-Driven
A in MTEP16 | B>A | West | MEC | 11284 | 2016-07-25 | T90KU | Clarinda Substation: Replace 161 kV Switch 803L | At Clarinda Substation, on the line terminal to Maryville, install a new 161 kV line disconnect switch, replace associated line drops and jumpers, and remove the existing switch. | IA | IA | GIP |  |  | 80500 | 2017-06-01 | 2017-06-01 | 161 |  | Externally-Driven
A in MTEP16 | B>A | West | MEC | 11285 | 2016-07-25 | T90M4 | Beacon 161 kV Line Drops, Poweshiek | Replace line drops at Beacon Substation on the Beacon–Poweshiek 161 kV line terminal. | IA | IA | GIP |  |  | 25000 | 2017-09-01 | 2017-09-01 | 161 |  | Externally-Driven
A in MTEP16 | B>A | West | MP | 7910 | 2015-09-04 | 5 Line Upgrade | 5 Line Upgrade | Increase capacity of Brainerd - Mud Lake 115 kV Line | MN | MN | BaseRel |  |  | 1900000 | 2019-11-01 | 2019-11-01 | 115 |  | Bottom-up
A in MTEP16 | B>A | West | MP | 7996 | 2015-09-11 | 15 Line Upgrade | 15 Line Upgrade | Rebuild & reconductor Fond Du Lac - Hibbard 115 kV Line | MN | MN | BaseRel |  |  | 5500000 | 2017-12-31 | 2017-12-31 | 115 |  | Bottom-up
A in MTEP16 | B>A | West | MP | 7997 | 2015-09-04 | 15th Ave West | 15th Avenue West Modernization | Rebuild & modernize existing 15th Avenue West Substation, including new 14 kV switchgear, one new 115/14 kV transformer, replace 3 115 kV breakers and other 115 kV equipiment, and miscellaneous site improvements | MN | MN | Other |  | Condition | 10000000 | 2018-05-01 | 2018-12-31 | 115 | 13.8 | Bottom-up
A in MTEP16 | B>A | West | MP | 9064 | 2015-09-08 | Arrowhead Bus Reconfiguration | Arrowhead 115 kV Bus Reconfiguration | Reconfigure Arrowhead 115 kV bus to eliminated 115 MW breaker failure contingency. Cannot have Arrowhead - Colbyville & Arrowhead - Haines Road on adjacent buses | MN | MN | BaseRel |  |  | 600000 | 2017-12-31 | 2017-12-31 | 115 |  | Bottom-up
A in MTEP16 | B>A | West | MP | 9622 | 2015-09-04 | 83 Line Upgrade | 83 Line Upgrade | Replace limiting elements at Boswell & Blackberry to restore 100C rating | MN | MN | Other |  | Reliability | 500000 | 2019-06-01 | 2019-06-01 | 230 |  | Bottom-up
A in MTEP16 | B>A | West | MP | 9623 | 2015-09-04 | 95 Line Upgrade | 95 Line Upgrade | Replace limiting elements at Boswell & Blackberry to restore 100C rating | MN | MN | Other |  | Reliability | 500000 | 2019-06-01 | 2019-06-01 | 230 |  | Bottom-up
A in MTEP16 | B>A | West | MP | 9624 | 2015-09-04 | Bear Creek Transformer | Bear Creek 69/46 kV Transformer | Install 69/46 kV transformer at Great River Energy's existing Bear Creek Substation and remove existing Sandstone 69/46 kV distribution station | MN | MN | Other |  | Condition | 2000000 | 2017-12-31 | 2017-12-31 | 69 | 46 | Bottom-up
A in MTEP16 | B>A | West | MP | 9625 | 2015-09-04 | Nemadji | Nemadji 115 kV Project | New switching station in Gary - Stinson 115 kV Line near Enbridge's Superior Terminal; 115 kV line development around the Superior Terminal | WI | WI | Other |  | Reliability | 8690000 | 2014-12-31 | 2017-12-31 | 115 |  | Bottom-up
A in MTEP16 | B>A | West | MP | 10284 | 2015-10-30 | 28 Line Upgrade | 28 Line Upgrade | Increase emergency rating of Boswell - Canisteo 115 kV Line to at least 150 MVA | MN | MN | BaseRel |  |  | 790000 | 2017-05-01 | 2017-05-01 | 115 |  | Bottom-up
A in MTEP16 | B>A | West | MP | 10383 | 2015-12-02 | Voltage Conversion | Laskin-Tac Harbor Voltage Conversion | Convert Laskin - Tac Harbor 138 kV system to 115 kV and add a 15 MVAr capacitor bank at Dunka Road; coordinated with the Hoyt Lakes Substation Modernization (Project #4426) and Dunka Road Substation (Project #2761) | MN | MN | Other |  | Condition | 2484000 | 2017-07-01 | 2017-12-31 | 115 | 13.8 | Bottom-up
A in MTEP16 | B>A | West | OTP | 9990 | 2016-09-27 |  | Devils Lake East 41.6 kV | Relay upgrades | ND | ND | Other |  | Reliability | 37500 | 2017-12-31 | 2017-12-31 | 41.6 |  | Bottom-up
A in MTEP16 | B>A | West | OTP | 9995 | 2015-12-30 |  | Devils Lake SW 41.6 kV | Relay upgrades | ND | ND | Other |  | Reliability | 37500 | 2017-12-31 | 2017-12-31 | 41.6 |  | Bottom-up
A in MTEP16 | B>A | West | OTP | 10003 | 2016-09-01 |  | Rugby 41.6 kV Breakers | Install four 41.6 kV Breakers in the Rugby area to re-terminate existing OTP-owned 41.6 kV circuits from CPEC-owned Rugby substation to 230 kV delivery. | ND | ND | Other |  | Non - Transferred Facilites | 2000000 | 2016-12-31 | 2016-12-31 | 230 | 41.6 | Bottom-up
A in MTEP16 | B>A | West | OTP | 10007 | 2016-09-21 |  | Max to Ryder 41.6 kV Line Upgrade | The project will start in 2016 and be completed in 2018. The project will replace failing insulation, cross arms and poles identified through patrols and inspections and replace the failing 1/0 ACSR conductor for approximately 34 miles between Max, ND and Ryder, ND. | ND | ND | Other |  | Condition | 2500000 | 2018-12-31 | 2018-12-31 | 41.6 |  | Bottom-up
A in MTEP16 | B>A | West | OTP | 11743 | 2016-09-29 |  | Western ND 41.6 kV Breaker Stations | Western ND 41.6 kV Breaker Stations will consist of 3 Facilities 1. Coleharbor - Single in-line circuit breaker addition 2. Drake - Single in-line circuit breaker addition 3. Granville Jct. - Three circuit breaker addition | ND | ND | Other |  | Non - Transferred Facilites | 1500000 | 2016-12-31 | 2016-12-31 | 41.6 |  | Bottom-up
A in MTEP16 | B>A | West | RPU | 10443 | 2016-02-01 |  | Douglas Trail Substation | New load serving substation (Douglas Trail Substation) will tap RPU's immediately adjacent Q5 161kV transmission line. | MN | MN | Other |  | Distribution | 7000000 | 2017-04-01 | 2017-04-01 | 161 |  | Bottom-up
A in MTEP16 | B>A | West | XEL | 4696 | 2015-10-22 |  | Rebuild Prentice-Medford 69 kV | Rebuild this line to 795 ACSR due to age and condition of the line | WI | WI | Other |  | Condition | 20145714 | 2018-01-31 | 2018-01-31 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | XEL | 10045 | 2015-09-17 |  | City of Chaska Interconnection | Build an in-and-out from double circuit 115 kV just south of Bluff Creek. This in-and-out will serve the City of Chaska’s new distribution substation. New line will 1.7 mi following road from POI to potential new sub | MN | MN | Other |  | Reliability | 3200000 | 2016-06-30 | 2016-06-30 | 115 |  | Bottom-up
A in MTEP16 | B>A | West | XEL | 10062 | 2015-09-18 |  | Tyrone Tap Interconnection | Install a 3-way switch on NSP’s St. Thomas Tap to Boright #2 69 kV line. GRE will then construct a radial line from the tap to serve the new MVEC load. | MN | MN | Other |  | Reliability | 375000 | 2016-06-30 | 2016-06-30 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | XEL | 10063 | 2015-09-18 |  | Rebuild Jackson Co – DPC Merrillan Tap 69 kV | Rebuild 6.1 miles from Jackson Co to DPC Merrillan Tap to 565.3 ACSR/TW. | WI | WI | Other |  | Reliability | 3300000 | 2016-07-30 | 2016-07-30 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | XEL | 10065 | 2015-09-18 |  | Rogers Lake Overstressed Breaker Replacement | Replace the four existing gas 40 kA breakers at Rogers Lake with with gas 63 kA breakers. | MN | MN | Other |  | Condition | 940847 | 2016-04-30 | 2016-04-30 | 115 |  | Bottom-up
A in MTEP16 | B>A | West | XEL | 10066 | 2015-09-18 |  | Southtown Area Upgrades | Upgrade the Southtown-Cedarvale 115 kV line to a minimum of 290 MVA emergency. Upgrade the Southtown-Shepard 115 kV line to a minimum of 270 MVA emergency. Add a 80 MVAR cap to the Hiawatha substation. | MN | MN | BaseRel |  |  | 3495000 | 2016-06-01 | 2017-12-30 | 115 |  | Bottom-up
A in MTEP16 | B>A | West | XEL | 10067 | 2015-09-18 |  | MPC Fossum Interconnection | This project will convert the Prairie Substation to a breaker-in-a-half configuration to accommodate MPC’s Fossum 115 kV interconnection request. Fossum will operate radially. | ND | ND | Other |  | Reliability | 17261500 | 2018-01-01 | 2018-01-01 | 115 |  | Bottom-up
A in MTEP16 | B>A | West | XEL | 10068 | 2015-09-18 |  | Install Baytown 2nd Transformer | Install a 2nd transformer and switchgear at Baytown substation. This will require an in-and-out design at Baytown. | MN | MN | Other |  | Reliability | 1625468 | 2017-06-01 | 2017-06-01 | 115 | 13.8 | Bottom-up
A in MTEP16 | B>A | West | XEL | 10069 | 2015-09-18 |  | Twin Creek Breaker Station | Install a 2 or 3 position 69 kV breaker station - Breakers to Radisson and Osprey/Big Falls - Possible breaker looking toward the Enbridge loads or just switches - Replaces the planned 3-way tap switch on line W3474 that was part of the Enbridge expansion/DPC N-2 retirement plan | WI | WI | Other |  | Reliability | 2866000 | 2019-11-01 | 2019-11-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | XEL | 10071 | 2015-10-22 |  | Prescott Capacity Upgrade | Install second 69/12.47 kV 28 MVA transformer at Prescott, add additional feeders, and install a second 10 MVAR cap bank. | WI | WI | Other |  | Distribution | 1174000 | 2016-09-30 | 2016-09-30 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | XEL | 10072 | 2015-09-18 |  | Dean Lake Third Transformer and Ring Bus | Install a 3rd TR at Dean Lake and add 4 new breakers to complete the ring bus. | WI | MN | Other |  | Distribution | 4904100 | 2016-08-01 | 2016-12-31 | 115 | 13.8 | Bottom-up
A in MTEP16 | B>A | West | XEL | 10073 | 2015-09-18 |  | GIC Monitoring | This project is to install GIC Monitoring at various substations throughout NSPM/NSPW system. Projects will be modeled after the King GIC monitoring pilot program. Transformers will be selected based upon planning study and geographic location. The first substations to have the GIC monitoring installed will be Quarry, Adams, Elm Creek, and Eau Claire. | WI | MN | Other |  | Reliability | 585150 | 2016-04-30 | 2016-12-31 | 345 | 115 | Bottom-up
A in MTEP16 | B>A | West | XEL | 10074 | 2015-09-18 |  | Airport – Rogers Lake 115 kV Rebuild | This project rebuilds the Airport - Rogers Lake 115 kV line due to age and condition. The new line would be built using 795 ACSS conductor. | MN | MN | Other |  | Condition | 4092000 | 2019-05-30 | 2019-05-30 | 115 |  | Bottom-up
A in MTEP16 | B>A | West | XEL | 10075 | 2015-09-18 |  | Waconia 2nd Distribution Transformer | Install a 2nd distribution transformer at Waconia substation and associated feeders. This new transformer will require the 69 kV yard to be converted to an in-and-out configuration. | MN | MN | Other |  | Reliability | 420000 | 2017-12-30 | 2017-12-30 | 69 | 13.8 | Bottom-up
A in MTEP16 | B>A | West | XEL | 10076 | 2015-09-18 |  | West St Cloud – Millwood Tap Rebuild | Rebuild 24 miles of line from West St. Cloud to Millwood Tap. This new line will be built using 477 ACSR conductor. | MN | MN | Other |  | Condition | 10400000 | 2019-05-30 | 2019-05-30 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | XEL | 10077 | 2015-09-18 |  | GRE St. James Interconnection | Install a new three-way switch with load interrupters to accommodate GRE interconnection on line 0714. | MN | MN | Other |  | Reliability | 390800 | 2016-12-01 | 2016-12-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | XEL | 10288 | 2015-10-30 |  | Osprey 69 kV Expansion | Install 69 kV straight bus with 2 additional 69 kV breakers. Reterminate line from Whitetail Tap and Flambeau into Osprey. Rebuild the last 0.4 mies of 69 kV on the Whitetail Tap line to match the rest of the conductor type | WI | WI | Other |  | Reliability | 2880000 | 2018-09-01 | 2018-09-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | XEL | 10289 | 2015-10-30 |  | Elmwood - Eau Galle Rebuild | Rebuild the existing 2/0 conductor to 477 ACSR due to age and condition | WI | WI | Other |  | Condition | 2109095 | 2015-12-01 | 2016-12-01 | 69 |  | Bottom-up
A in MTEP16 | B>A | West | XEL | 10290 | 2015-10-30 |  | Gravel Island Distribution | Install a 28 MVA distribution TR and associated breaker and bus work | WI | WI | Other |  | Distribution | 2983000 | 2017-08-30 | 2017-08-30 | 161 | 12.5 | Bottom-up
A in MTEP16 | B>A | West | XEL | 10291 | 2015-10-30 |  | New LCO Hydro Transformer | Install single 34.5/23.9 kV TR to connect the Lac Courte Oreilles (LCO) hydro facility to the NCP system near Radisson | WI | WI | Other |  | Distribution | 180000 | 2018-12-01 | 2018-12-01 | 34.5 | 23.9 | Bottom-up
B in MTEP16 | B | Central | AmerenIL | 9719 | 2016-09-15 |  | Cahokia Bus-Tie 3-4 Upgrade | Upgrade Bus-Tie 3-4 position to 3000 A capability | IL | IL |  |  |  |  | 2018-06-01 | 2018-06-01 | 138 | 138 | Bottom-up
B in MTEP16 | B | Central | AmerenIL | 9723 | 2015-12-14 |  | Fishhook Breaker Station | Construct 138 kV breaker station in East Quincy-Meredosia-2 138 kV line. | IL | IL |  |  |  |  | 2018-12-31 | 2018-12-31 | 138 | 138 | Bottom-up
B in MTEP16 | B | Central | AmerenIL | 9724 | 2016-09-15 |  | Newton Transformer #1 Retermination. | Relocate Newton 345/138 kV Xfmr #1 345 kV connection point | IL | IL |  |  |  |  | 2018-06-01 | 2018-06-01 | 345 | 138 | Bottom-up
B in MTEP16 | B | Central | AmerenIL | 9729 | 2015-09-11 |  | North Decatur-Clinton Rt.. 54 Upgrade | Reconductor to 1200 A summer emergency capability | IL | IL |  |  |  |  | 2019-06-01 | 2019-06-01 | 138 | 138 | Bottom-up
B in MTEP16 | B | Central | AmerenIL | 9734 | 2015-09-11 |  | North Utica Substation | Construct 138 kV breaker station in North LaSalle-Fox River-1646 138 kV line. | IL | IL |  |  |  |  | 2019-06-01 | 2019-06-01 | 138 | 34.5 | Bottom-up
B in MTEP16 | B | Central | AmerenIL | 9738 | 2016-09-16 |  | Grand Tower-Carbondale Reconductoring | Reconductor to 1200 A summer emergency capability | IL | IL |  |  |  |  | 2025-06-01 | 2025-06-01 | 138 | 138 | Bottom-up
B in MTEP16 | B | Central | AmerenIL | 9739 | 2016-09-16 |  | Carbondale, Northwest-West Frankfort Reconductoring | Reconductor 3.18 miles conductor in the Carbondale-Reeds section with conductor capable of carrying 1200 A under summer emergency conditions. | IL | IL |  |  |  |  | 2025-06-01 | 2025-06-01 | 138 | 138 | Bottom-up
B in MTEP16 | B | Central | AmerenIL | 9740 | 2016-09-16 |  | Grand Tower-Campbell Hill Reconductoring | Reconductor to 1200 A summer emergency capability | IL | IL |  |  |  |  | 2025-06-01 | 2025-06-01 | 138 | 138 | Bottom-up
B in MTEP16 | B | Central | AmerenIL | 9743 | 2015-09-11 |  | Pana, North-Route 51D Reconductoring | Reconductor to 2000 A summer emergency capability | IL | IL |  |  |  |  | 2021-06-01 | 2021-06-01 | 138 | 138 | Bottom-up
B in MTEP16 | B | Central | AmerenIL | 9745 | 2016-09-15 |  | Ramsey Transformer Replacement | Replace existing transformer with 560 MVA unit | IL | IL |  |  |  |  | 2018-06-01 | 2018-06-01 | 345 | 138 | Bottom-up
B in MTEP16 | B | Central | AmerenIL | 9746 | 2016-09-15 |  | Pana, North-Schram City Reconductoring | Reconductor to 1200 A summer emergency capability | IL | IL |  |  |  |  | 2018-06-01 | 2018-06-01 | 138 | 138 | Bottom-up
B in MTEP16 | B | Central | AmerenIL | 9826 | 2016-09-15 |  | Neoga Transformer Addition | Install 2nd. 345/138 kV, 560 MVA Transformer | IL | IL |  |  |  |  | 2018-06-01 | 2018-06-01 | 345 | 138 | Bottom-up
B in MTEP16 | B | Central | AmerenIL | 9832 | 2015-09-14 |  | Casey-Kansas Reconductoring | Reconductor to 3000 A summer emergency capability | IL | IL |  |  |  |  | 2027-06-01 | 2027-06-01 | 345 | 345 | Bottom-up
B in MTEP16 | B | Central | AmerenIL | 9838 | 2015-09-14 |  | Kincaid Terminal Upgrade | Upgrade terminal equipment on Kincaid-Austin 345 kV position. | IL | IL |  |  |  |  | 2022-06-01 | 2022-06-01 | 345 | 345 | Bottom-up
B in MTEP16 | B | Central | AmerenIL | 9840 | 2015-09-14 |  | Washington Street Ring Bus | Install 138 kV Ring Bus | IL | IL |  |  |  |  | 2020-05-01 | 2020-05-01 | 138 | 138 | Bottom-up
B in MTEP16 | B | Central | AmerenIL | 9841 | 2015-09-14 |  | South Bloomington 138-34.5 kV Transformer | Install 112 MVA Transformer | IL | IL |  |  |  |  | 2019-05-01 | 2019-05-01 | 138 | 34.5 | Bottom-up
B in MTEP16 | B | Central | AmerenIL | 9842 | 2015-09-14 |  | Normal East 138-69 kV Transformer | Install 112 MVA Transformer | IL | IL |  |  |  |  | 2020-05-01 | 2020-05-01 | 138 | 69 | Bottom-up
B in MTEP16 | B | Central | AmerenIL | 9843 | 2015-09-14 |  | Normal East 138-34.5 kV Transformer | Install 112 MVA Transformer | IL | IL |  |  |  |  | 2019-05-01 | 2019-05-01 | 138 | 34.5 | Bottom-up
B in MTEP16 | B | Central | AmerenIL | 9844 | 2015-09-14 |  | Normal East-McLean 138 kV Line | Construct 138 kV line | IL | IL |  |  |  |  | 2020-05-01 | 2020-05-01 | 138 | 138 | Bottom-up
B in MTEP16 | B | Central | AmerenIL | 9851 | 2015-09-14 |  | Edwards-Kewanee-7423 Reconductoring | Reconductor Ameren portion to 1200 A summer emergency capability | IL | IL |  |  |  |  | 2019-06-01 | 2019-06-01 | 138 | 138 | Bottom-up
B in MTEP16 | B | Central | AmerenIL | 9857 | 2016-09-13 | AMRN51 | Liberty 345/138 kV Substation | Establish 345/138 kV Substation, connect to 138 kV system in Collinsville-O'Fallon-Highland, Illinois area | IL | IL |  |  |  |  | 2019-06-01 | 2019-06-01 | 345 | 138 | Bottom-up
B in MTEP16 | B | Central | AmerenIL | 10883 | 2016-09-07 |  | Ina Substation 138 kV Breaker Addition | Install 138 kV ring bus | IL | IL |  |  |  |  | 2019-06-01 | 2019-06-01 | 138 | 138 | Bottom-up
B in MTEP16 | B | Central | AmerenIL | 10885 | 2016-09-15 |  | Cahokia-Ridge-2 138 kV Terminal Equipment Upgrade | Upgrade terminal equipment at Cahokia and Ridge Substations. | IL | IL |  |  |  |  | 2018-06-01 | 2018-06-01 | 138 |  | Bottom-up
B in MTEP16 | B | Central | AmerenIL | 10886 | 2016-09-06 |  | South Belleville-Centerville-1586 138 kV Reconductoring | Reconductor approximately 5.6 miles in the 17th Street-Centerville section of south Belleville-Centerville-1586 with conductor capable of carrying 1200 A under summer emergency conditions. | IL | IL |  |  |  |  | 2018-06-01 | 2018-06-01 | 138 |  | Bottom-up
B in MTEP16 | B | Central | AmerenMO | 3020 | 2016-09-15 | AMRN49 | Overton-Columbia Terminal Upgrade | Upgrade terminal equipment at Overton Substation. | MO | MO | BaseRel |  |  |  | 2018-06-01 | 2018-06-01 | 161 | 161 | Bottom-up
B in MTEP16 | B | Central | AmerenMO | 9717 | 2016-05-23 |  | Moberly Terminal Upgrade | Upgrade terminal equipment on Thomas Hill-Moberly-1 161 kV line position. | MO | MO |  |  |  |  | 2040-06-01 | 2040-06-01 | 161 | 161 | Bottom-up
B in MTEP16 | B | Central | AmerenMO | 9721 | 2015-10-14 | AMRN46 | Bland-Tegeler 138 kV Reconductoring | Reconductor line to 1200 A summer emergency capability | MO | MO |  |  |  |  | 2020-06-01 | 2020-06-01 | 138 | 138 | Bottom-up
B in MTEP16 | B | Central | AmerenMO | 9728 | 2015-09-11 |  | Adair Substation Upgrades | Upgrade terminal equipment | MO | MO |  |  |  |  | 2018-11-15 | 2018-11-15 | 161 | 161 | Bottom-up
B in MTEP16 | B | Central | AmerenMO | 9730 | 2016-02-29 |  | Gray Summit Breaker Replacement | Replace overstressed 138 kV breakers. | MO | MO |  |  |  |  | 2019-12-01 | 2019-12-01 | 138 | 138 | Bottom-up
B in MTEP16 | B | Central | AmerenMO | 9731 | 2016-02-29 |  | Marshall Breaker Replacment | Replace overstressed Bus-Tie 3-4 138 kV breaker. | MO | MO |  |  |  |  | 2019-06-01 | 2019-06-01 | 138 | 138 | Bottom-up
B in MTEP16 | B | Central | AmerenMO | 9732 | 2016-05-20 |  | Mason Breaker Replacment | Replace overstressed Bus-Tie 1-2 138 kV breaker. | MO | MO |  |  |  |  | 2021-12-01 | 2021-12-01 | 138 | 138 | Bottom-up
B in MTEP16 | B | Central | AmerenMO | 9733 | 2016-05-23 | AMRN47 | Page Breaker Replacment | Replace overstressed 138 kV breakers | MO | MO |  |  |  |  | 2021-12-01 | 2021-12-01 | 138 | 138 | Bottom-up
B in MTEP16 | B | Central | AmerenMO | 9735 | 2016-05-23 | AMRN48 | Tyson Breaker Replacement | Replace overstressed 138 kV breakers | MO | MO |  |  |  |  | 2021-12-01 | 2021-12-01 | 138 | 138 | Bottom-up
B in MTEP16 | B | Central | AmerenMO | 9824 | 2016-09-15 |  | Huster Terminal Upgrade | Upgrade terminal equipment on Sioux-Huster-3 position. | MO | MO |  |  |  |  | 2017-06-01 | 2017-06-01 | 138 | 138 | Bottom-up
B in MTEP16 | B | Central | AmerenMO | 9825 | 2015-09-14 |  | Osage Terminal Upgrade | Upgrade terminal equipment on Tegeler-Osage-1 position. | MO | MO |  |  |  |  | 2021-06-01 | 2021-06-01 | 138 | 138 | Bottom-up
B in MTEP16 | B | Central | AmerenMO | 9828 | 2015-09-14 | AMRN50 | Joachim-St. Francois-2 and Boyd Branch-St. Francois-1 - Increase Ground Clearance | Increase ground clearance | MO | MO |  |  |  |  | 2022-06-01 | 2022-06-01 | 138 | 138 | Bottom-up
B in MTEP16 | B | Central | AmerenMO | 9830 | 2016-05-23 |  | Meramec-Joachim-2 Reconductoring | Reconductor to 1600 A summer emergency capability | MO | MO |  |  |  |  | 2022-06-01 | 2022-06-01 | 138 | 138 | Bottom-up
B in MTEP16 | B | Central | IPL | 10786 | 2016-02-18 |  | Stout BESS - DPP J401 | New ±20 MVA battery energy storage system at existing Stout substation | IN | IN |  |  |  | 4000 | 2017-12-31 | 2017-12-31 | 138 | 13.8 | Bottom-up
B in MTEP16 | B | Central | PPI | 9563 | 2016-08-12 | 2016-13 | Cronus 138 kV Transmission Lines | Construct two new 138 kV transmission lines from Ameren Illinois's West Tuscola substation to serve new Cronus Fertilizer Plant | IL | IL | Other |  | Reliability | 3600000 | 2017-12-01 | 2017-12-01 | 138 |  | Bottom-up
B in MTEP16 | B | Central | Vectren | 9943 | 2016-05-18 | 2016SIGE14 | Leonard Road 138/69 kV Transformer Addition and Z94 138 kV Line Loop | Leonard Road 138kV/69kV transformer addition and 138kV line Z94 loop. | IN | IN |  |  |  | 3100000 | 2023-12-31 | 2023-12-31 | 138 | 69 | Bottom-up
B in MTEP16 | B | Central | Vectren | 9950 | 2016-08-25 | 2016SIGE15 | Y76 69kV Line Rebuild from New Harmony to Northwest | 69kV (Line Y76) rebuild from New Harmony to Northwest> | IN | IN | Other |  | Condition | 10000000 | 2018-12-31 | 2018-12-31 | 69 |  | Bottom-up
B in MTEP16 | B | Central | Vectren | 9953 | 2016-05-18 | 2016SIGE16 | New Toyota South Distribution Substation | 69kV/12kV distribution substation for load growth. | IN | IN |  |  |  | 2500000 | 2020-12-31 | 2020-12-31 | 138 | 12 | Bottom-up
B in MTEP16 | B | East | CETO | 9879 | 2015-09-14 |  | Moore Road-Vrooman 138 kV Line | Construct a new approximately 22 mile 138 kV line between Moore Road and Vrooman Substations, adding 138 kV circuit breakers to each station. | MI | MI |  |  |  | 22000000 | 2019-06-01 | 2019-06-01 | 138 |  | Bottom-up
B in MTEP16 | B | East | ITCT | 9885 | 2016-09-30 | ITC_15_017 | Jewell - St. Clair #1 345 kV Sag Remediation | Raise the Sag Limit on Jewell-St.Clair 345 kV to 1965 MVA (3288 Amp) | MI | MI | BaseRel |  |  | 5380000 | 2019-12-31 | 2019-12-31 | 345 |  | Bottom-up
B in MTEP16 | B | East | ITCT | 9909 | 2015-09-15 |  | 6-Wire Trenton Channel - Jefferson 120 kV Circuits | Six-wiring the Trenton Channel - Jefferson #4 120 kV and Trenton Channel - Horn - Jefferson 120 kV circuits with the existing decommissioned lines on their common structures. This will also require the construction of approximately 0.16 mile of double circuit 954 ACSR to complete the loop in-and-out of Horn station. Additionally, rebuild approximately 0.2 miles of 954 ACSR conductor to 1431 ACSR on the Jefferson-Riverview #2 120 kV circuit. Also install a 120 kV bus-tie breaker at Jefferson and upgrade station equipment at Trenton Channel, Horn, Jefferson, and Riverview | MI | MI |  |  |  | 2400000 | 2018-12-31 | 2018-12-31 | 120 |  | Bottom-up
B in MTEP16 | B | East | METC | 9864 |  |  | Whiting - Custer 120 kV Rebuild | Rebuild 9.98 miles of 636 ACSR from the Whiting – Custer 120 kV circuit using 1431 ACSR and OPGW on new 230 kV future double circuit structures. Replace limiting equipment at both the Whiting and Custer stations | MI | MI |  |  |  | 14300000 | 2018-06-30 | 2018-06-30 | 120 |  | Bottom-up
B in MTEP16 | B | East | METC | 9880 | 2016-09-30 | METC_15_025 | Claremont - Manning #1 138 kV Sag Remediation | Remediate the sag limit on the Portsmouth Tap – Manning 138 kV section of the Claremont – Manning 1 138 kV line to a minimum of 378 MVA / 1581 Amps, remediate the sag limit on the Claremont – Portsmouth Tap 138 kV section of the Claremont – Manning 1 138 kV line to a minimum of 362 MVA / 1514 Amps, and upgrade terminal equipment at Claremont | MI | MI | BaseRel |  |  | 330000 | 2018-12-31 | 2018-12-31 | 138 |  | Bottom-up
B in MTEP16 | B | East | METC | 9881 | 2016-09-30 | METC_15_026 | Claremont - Manning #2 138 kV Sag Remediation | Remediate the sag limit on the Claremont – Manning 2 138 kV line to a minimum of 369 MVA / 1544 Amps and upgrade terminal equipment at Claremont | MI | MI | BaseRel |  |  | 1400000 | 2018-12-31 | 2018-12-31 | 138 |  | Bottom-up
B in MTEP16 | B | East | METC | 9929 | 2016-09-30 | METC_15_29 | Donaldson Creek - Pere Marquette 138 kV | Build new ~21 mile circuit from Donaldson Creek to Pere Marquette using 954 ACSR and OPGW. Replace equipment at Donaldson Creek, Pere Marquette, and White Lake Stations | MI | MI | BaseRel |  |  | 8700000 | 2019-12-31 | 2019-12-31 | 138 |  | Bottom-up
B in MTEP16 | B | East | WPSC | 9895 | 2015-11-23 | GRX-CT | Graves Crossing to Central Lake Rebuild | Rebuild the Graves Crossing to Central Lake 69kV line, install new poles and hardware with 336ACSR conductor | MI | MI |  |  |  | 3200000 | 2022-12-31 | 2022-12-31 | 69 |  | Bottom-up
B in MTEP16 | B | East | WPSC | 9903 | 2016-09-15 | WC-RG Rebuild | White Cloud to Rogers | Rebuild the White Cloud to Rogers 69kV line, install new poles and hardware with 795ACSS conductor | MI | MI |  |  |  | 18500000 | 2020-12-31 | 2020-12-31 | 69 |  | Bottom-up
B in MTEP16 | B | East | WPSC | 9916 | 2015-09-15 | Fairview Station Upgrade | Fairview Station Upgrade | Fairview station upgrade | MI | MI |  |  |  | 900000 | 2022-12-31 | 2022-12-31 | 69 |  | Bottom-up
B in MTEP16 | B | East | WPSC | 9920 | 2015-09-15 | GRX Station Upgrade | Graves Crossing Station Upgrade | Upgrade the Graves Crossing station | MI | MI |  |  |  | 500000 | 2020-12-31 | 2020-12-31 | 69 |  | Bottom-up
B in MTEP16 | B | East | WPSC | 10264 | 2015-10-28 | Pellston to Cross Village | Pellston to Cross Village Rebuild | Rebuild the Pellston to Cross Village 69kV line, install new poles and hardware with 336ACSR conductor | MI | MI |  |  |  | 3600000 | 2022-12-31 | 2022-12-31 | 138 |  | Bottom-up
B in MTEP16 | B | East | WPSC | 10265 | 2015-10-28 |  | Gaylord Relay Replacement | Gaylord relay replacement - 138kV Livingston line | MI | MI |  |  |  | 35000 | 2019-12-31 | 2019-12-31 | 138 |  | Bottom-up
B in MTEP16 | B | East | WPSC | 10266 | 2016-09-15 |  | East Jordan Station Rebuild | This project will replace the existing equipment at the East Jordan station and upgrade the steel, install new controls, 125v DC battery system and a circuit breaker. | MI | MI |  |  |  | 350000 | 2019-12-31 | 2019-12-31 | 69 |  | Bottom-up
B in MTEP16 | B | East | WPSC | 10267 | 2016-09-15 |  | Black Lake Station Rebuild | Black Lake Station Rebuild | MI | MI |  |  |  | 350000 | 2019-12-31 | 2019-12-31 | 69 |  | Bottom-up
B in MTEP16 | B | South | AECC | 10203 | 2015-10-12 |  | Shaw to Sardis 115kV | 12.00 mile 115kV line from the AECC Shaw substation to the AECC Sardis substation and tie into a proposed 115kV ring bus at the Sardis substation | AR | AR | [6 empty] | 115 |  | Bottom-up
B in MTEP16 | B | South | AECC | 10207 | 2016-07-01 |  | 5 position ring bus at Heber Springs North, 26 mile 161kV line form Heber Springs North to Partain | Build 5 position ring bus at the existing AECC Heber Springs North, build 26 mile 161kV line from the existing Heber Springs North substation to the proposed Partain 161/69kV substation | AR | AR | Other |  | Reliability | 23000000 | 2021-06-01 | 2021-06-01 | 161 |  | Bottom-up
B in MTEP16 | B | South | CLECO | 9718 | 2015-09-11 |  | Ashmore Rd. - Rork 230 kV line | Tap the existing Hineston to Cocodrie 230 kV line 24 miles from Cocodrie at a new 230 kV substation Ashmore Rd. Build a 64 mile 230 kV line from Ashmore Rd. to Rork substation routed through Oakdale, Kinder and Basile for future load growth. | LA | LA |  |  |  | 115000000 |  |  | 230 |  | Bottom-up
B in MTEP16 | B | South | Entergy-AR | 9694 | 2016-05-12 | 16-EAI-003 | Camden Maguire - Smackover 115kV: Rebuild Line | Re-build 14.32 mile long line to a minimum rating of 882A. | AR | AR | BaseRel |  |  | 20706029 | 2024-06-01 | 2024-06-01 | 115 |  | Bottom-up
B in MTEP16 | B | South | Entergy-AR | 9699 | 2016-09-15 | 16-EAI-005 | El Dorado Donan 115kV: Add 1-30MVAR Capacitor Bank | Add one 30 MVAR capacitor bank at El Dorado Donan 115 kV substation | AR | AR |  |  |  | 871182 | 2019-06-01 | 2019-06-01 | 115 |  | Bottom-up
B in MTEP16 | B | South | Entergy-AR | 9700 | 2016-09-14 | 16-EAI-015 | Blakely - Mt. Pine South 115kV: Rebuild Line | Re-building the ~2.92 mile long 115 kV line to a minimum line rating of 259 MVA (1300 Amps) | AR | AR |  |  |  | 3972886 | 2022-06-01 | 2022-06-01 | 115 |  | Bottom-up
B in MTEP16 | B | South | Entergy-AR | 9701 | 2016-09-14 | 16_EAI-010 | Lynch West - NLR Galloway 115kV: Rebuild Line | Upgrade 4.12mi Lynch – NLR Galloway line to a minimum rating of 259 MVA (1300 Amps). Any substation equipment rated below 259 MVA (1300 Amps) needs to be upgraded as well. | AR | AR |  |  |  | 4785896 | 2020-06-01 | 2020-06-01 | 115 |  | Bottom-up
B in MTEP16 | B | South | Entergy-AR | 9702 | 2016-09-14 | 16-EAI-016 | Sylvan Hills - Jacksonville North 115kV: Equipment Upgrade | The line is currently limited to 975 Amps by line bay bus at Sylvan Hills. Upgrading the terminal equipment to a minimum rating of 1200 Amps will eliminate the thermal overloads due to breaker failures. | AR | AR |  |  |  | 26626 | 2018-06-01 | 2018-06-01 | 115 |  | Bottom-up
B in MTEP16 | B | South | Entergy-AR | 9710 | 2015-09-10 | 16-EAI-013 | Little Rock South 115kV: Reconfigure Station | Reconfigure Little Rock South 115 kV station configuration into a double bus double breaker, breaker and a half, or a ring bus configuration. | AR | AR |  |  |  | 5463000 | 2025-06-01 | 2025-06-01 | 115 |  | Bottom-up
B in MTEP16 | B | South | Entergy-AR | 10163 | 2015-10-06 |  | Jonesboro North: Add second 161kV transformer | Craighead Electric Cooperative Corporation (CECC) is splitting the 13.2 kV bus and adding in a second 161 to 13.2 kV transformer. | AR | AR |  |  |  | 800000 | 2017-03-01 | 2017-03-01 | 161 | 13.2 | Bottom-up
B in MTEP16 | B | South | Entergy-LA | 4611 | 2016-09-14 | 16-EGL-024 | Waddill 230-69 kV Substation with reconfigure of 69 kV lines 340 and 749 | Cut the existing 69kV Line 759 Denham Springs to Gloria and the existing 69kV Line 369.3 Gloria to Flannery REA at or near Structure number 92. Also cut the existing 230kV line approximately 7.07 miles from Coly toward Jaguar where it crosses near the same Structure number 92. Construct a new station to bring these lines into a new 230-69kV station. Install a 3 breaker ring bus on the 230kV side and a 5 breaker ring bus on the 69kV side to create a new Flannery area 230-69kV auto-transformer station. The 69kV lines, Gloria to Harelson and Coly to Jones Creek create an intersection. Cut the Harelson to Gloria line 340 at or near structure 73 and cut the Coly to Jones Creek line 749 at or near structure 21. Install a new dead end type structure to reconnect the lines and create Harelson to Jones Creek and Lockhart to Gloria. | LA | LA | BaseRel |  |  | 15859000 | 2026-06-01 | 2026-06-01 | 230 | 69 | Bottom-up
B in MTEP16 | B | South | Entergy-LA | 7970 | 2015-09-10 | 15-ELL-002 | Minden Area Improvement Ph 2 | Construct new 115 kV substation east of Minden REA and cut-in Minden REA to Arcadia 115 kV line and construct new 115 kV lines to cut the Minden to Sailes 115 kV line in and out of the new substation. | LA | LA | BaseRel |  |  | 9592834 | 2026-06-01 | 2026-06-01 | 115 |  | Bottom-up
B in MTEP16 | B | South | Entergy-LA | 9683 | 2016-09-28 | 16-ELN-002 | West Monroe Area 230 kV Reliability Improvement Plan | Install 500/230 kV autotransformer at Perryville 500 kV. Construct double circuit 230 kV and utilize existing 230 kV construct facilities to wind up with Perryville - Selman Field - Rilla 230 kV circuit and Perryville - Dunn 230 kV circuit. Install 230/115 kV autotransformers at Dunn and Rilla. Install 230/69 kV auto at Selman Field. | LA | LA | BaseRel |  |  | 78902650 | 2021-06-01 | 2021-06-01 | 500 | 69 | Bottom-up
B in MTEP16 | B | South | Entergy-LA | 9687 | 2015-09-10 | 16-ELN-006 | Sarepta - Minden 115 kV: Upgrade terminal equipment | Upgrade terminal equipment at Minden 115 kV substation | LA | LA |  |  |  | 553129 | 2022-06-01 | 2022-06-01 | 115 |  | Bottom-up
B in MTEP16 | B | South | Entergy-LA | 9688 | 2016-09-28 | 16-ELN-007 | Dunn - Winnsboro 115 kV: New line | Construct new 230 kV line (energized to 115 kV) from Dunn to Winnsboro. | LA | LA | BaseRel |  |  | 34998093 | 2020-06-01 | 2020-06-01 | 115 |  | Bottom-up
B in MTEP16 | B | South | Entergy-LA | 9689 | 2016-09-28 | 16-ELN-008 | Beekman: New distribution substation | Construct a new 115 kV substation on the North Bastrop - Crossett North 115 kV line. | LA | LA | Other |  | Distribution | 7880989 | 2020-06-01 | 2020-06-01 | 115 |  | Bottom-up
B in MTEP16 | B | South | Entergy-LA | 9764 | 2015-09-13 | 16-EGL-005 | Dixie Baker to Baker 69 kV: Reconductor Line | Upgrade the Dixie Baker to Baker 69 kV line section. This includes a reconductor and upgrading substation equipment. | LA | LA |  |  |  | 2963000 | 2026-06-01 | 2026-06-01 | 69 |  | Bottom-up
B in MTEP16 | B | South | Entergy-LA | 9766 | 2016-09-28 | 16-EGL-007 | Gloria to Flannery REA 69 kV: Reconductor Line | Upgrade the Gloria to Flannery REA 69 kV line section. | LA | LA | BaseRel |  |  | 2020989 | 2019-06-01 | 2019-06-01 | 69 |  | Bottom-up
B in MTEP16 | B | South | Entergy-LA | 9767 | 2015-09-13 | 16-EGL-008 | Harelson to Line 372 Tap 69 kV: Reconductor Line | Reconductor the Harelson to Line 372 Tap 69 kV line. | LA | LA |  |  |  | 5143000 | 2025-06-01 | 2025-06-01 | 69 |  | Bottom-up
B in MTEP16 | B | South | Entergy-LA | 9781 | 2015-09-13 | 16-EGL-015 | SWLA69IP Phase 1: Jennings to Lawtag 69 kV L-13 Reconductor | Reconductor the Jennings to Lawtag line. | LA | LA |  |  |  |  | 2022-06-01 | 2022-06-01 | 69 |  | Bottom-up
B in MTEP16 | B | South | Entergy-LA | 9784 | 2015-09-13 | 16-EGL-018 | Ford to Lake 69 kV: Reconductor Line | Reconductor the Ford to Lake 69 kV line. | LA | LA |  |  |  | 1552000 | 2025-06-01 | 2025-06-01 | 69 |  | Bottom-up
B in MTEP16 | B | South | Entergy-LA | 9789 | 2016-09-28 | 16-EGL-025 | Port Hudson 230-69 kV: Upgrade T6 station equipment | Upgrade substation equipment on the T6 autotransformer to upgrade the element. | LA | LA | Other |  | Reliability | 21435 | 2026-06-01 | 2026-06-01 | 230 | 69 | Bottom-up
B in MTEP16 | B | South | Entergy-LA | 9793 | 2015-09-13 | 16-EGL-031 | Esso to Delmont 230 kV: Reconductor Line | Reconductor the Esso to Delmont 230 kV line. | LA | LA |  |  |  | 2136000 | 2023-06-01 | 2023-06-01 | 230 |  | Bottom-up
B in MTEP16 | B | South | Entergy-LA | 9797 | 2016-09-14 | 16-EGL-036 | Nelson to Lake Charles Bulk 138 kV: Reconductor Line | Reconductor the Nelson to Lake Charles Bulk 138 kV line. | LA | LA |  |  |  | 11416000 | 2023-06-01 | 2023-06-01 | 138 |  | Bottom-up
B in MTEP16 | B | South | Entergy-LA | 9798 | 2016-09-14 | 16-ELL-001 | Gypsy to Claytonia 115 kV: Reconductor Line | Reconductor the Gypsy to Claytonia 115 kV line. | LA | LA |  |  |  | 7366203 | 2020-06-01 | 2020-06-01 | 115 |  | Bottom-up
B in MTEP16 | B | South | Entergy-LA | 9802 | 2016-09-14 | 16-ell-005 | Snakefarm to Labarre 230 kV: Reconductor Line | Reconductor the Snakefarm to Labarre 230 kV line. | LA | LA |  |  |  | 3834000 | 2020-06-01 | 2020-06-01 | 230 |  | Bottom-up
B in MTEP16 | B | South | Entergy-LA | 9803 | 2016-09-14 | 16-ELL-006 | Prospect to Goodhope 230 kV: Reconductor Line | Reconductor the Prospect the Goodhope 230 kV line section. | LA | LA |  |  |  | 697815 | 2020-06-01 | 2020-06-01 | 230 |  | Bottom-up
B in MTEP16 | B | South | Entergy-LA | 9804 | 2016-09-14 | 16-ELL-008 | Avenue C to Paris Tap 115 kV: Reconductor Line | Reconductor the Avenue C to Paris Tap 115 kV line. | LA | LA |  |  |  | 220032 | 2022-06-01 | 2022-06-01 | 115 |  | Bottom-up
B in MTEP16 | B | South | Entergy-MS | 7906 | 2016-09-15 | 15-EMI-004 | Greenwood to Greenwood SS 115 kV: Upgrade line | Upgrade Greenwood - Greenwood SS 115 kV from 70 MVA to at least 239 MVA. | MS | MS | BaseRel |  |  | 13133452 | 2019-06-01 | 2019-06-01 | 115 |  | Bottom-up
B in MTEP16 | B | South | Entergy-MS | 9823 | 2016-09-14 | 16-EMI-002 | Franklin 500 kV reconfig | Reconfigure the Franklin 500 kV EHV substation so that the Franklin - Bogalusa and Franklin - McKnight 500 kV lines do not share a common breaker. | MS | MS |  |  |  | 22435508 | 2020-12-01 | 2020-12-01 | 500 |  | Bottom-up
B in MTEP16 | B | South | Entergy-MS | 9829 | 2015-09-14 | 16-EMI-004 | Ray Braswell 500/115 upgrade 115 kV breakers | Upgrade 2-2500A 115 kV breakers on the low side of the Ray Braswell 500/115 kV autotransformer. | MS | MS |  |  |  | 1153930 | 2019-06-01 | 2019-06-01 | 115 |  | Bottom-up
B in MTEP16 | B | South | Entergy-MS | 9831 | 2016-08-08 | 16-EMI-006 | Tillatoba 230 kV Reconfigure | Reconfigure Tillatoba 230 kV from a single bus single breaker to a multiple protection scheme bus (double bus double breaker) | MS | MS |  |  |  | 5449089 | 2024-06-01 | 2024-06-01 | 230 |  | Bottom-up
B in MTEP16 | B | South | Entergy-MS | 9837 | 2015-09-14 | 16-EMI-010 | South Grenada - Elliott 115 kV: Upgrade line | Upgrade South Grenada - Elliott 115 kV line to 260MVA. | MS | MS |  |  |  | 4961042 | 2022-06-01 | 2022-06-01 | 115 |  | Bottom-up
B in MTEP16 | B | South | Entergy-TX | 9820 | 2015-09-14 | 16-ETI-019 | Hearne to Calvert 69 kV: Reconductor Line | Reconductor the Hearne to Calvert 69 kV line. | TX | TX |  |  |  | 9500000 | 2020-06-01 | 2020-06-01 | 69 |  | Bottom-up
B in MTEP16 | B | South | Entergy-TX | 9821 | 2015-09-14 | 16-ETI-020 | Bryan to College Station Area 138 kV: Construct New Line | Build a new 138 kV line from the Bryan substation to a new substation in the College Station Area. | TX | TX |  |  |  | 31500000 | 2024-06-01 | 2024-06-01 | 138 |  | Bottom-up
B in MTEP16 | B | South | Entergy-TX | 10964 | 2016-04-06 | 16-ETI-022 | Calvert to Hearne 69 kV: Construct New Line | Build a new line from Calvert to Hearne 69kV. | TX | TX |  |  |  |  | 2018-06-01 | 2018-06-01 | 69 |  | Bottom-up
B in MTEP16 | B | South | ETEC | 10081 | 2015-09-18 | SHECO_01_MTEP16 | Fred 138kV Loop Project | Construct new Fred switching station on Dogwood-Warren 138 kV line, construct new 138kV Fred substation, construct new 138 kV line from Fred switching station to new Fred substation, construct new 138kV line from Fred substation to North Buna substation. | TX | TX | [6 empty] | 138 |  | Bottom-up
B in MTEP16 | B | South | ETEC | 10082 | 2015-09-18 | SHECO_02_MTEP16 | Fred 138kV Loop Project Alt_01 | Construct new 138kV Fred substation, construct new 138kV line from Fred substation to the existing North Buna substation, construct new 138kV line from Fred substation to the existing Fork Creek substation | TX | TX | [6 empty] | 138 |  | Bottom-up
B in MTEP16 | B | South | ETEC, Entergy-TX | 10080 | 2016-05-12 | HCEC_01_MTEP16 | Weldon 138kV Tie Line | Construct 138 kV line from existing Mustang Prairie station in AEP-Texas to a new Weldon station to existing Magnolia Groveton station in Entergy-Texas. | TX | TX | Other |  | Distribution |  |  |  | 138 |  | Bottom-up
B in MTEP16 | B | West | ATC | 8443 | 2016-02-01 |  | Replace Rocky Run 345/115 kV T1 Transformer | Replace the thee Rocky Run 345-115 kV transformers with two 500 MVA units. | WI | WI |  |  |  | 22000000 | 2017-12-31 | 2017-12-31 | 345 | 115 | Bottom-up
B in MTEP16 | B | West | ATC | 9925 | 2015-10-05 |  | Tap Stone Lake - Gardner Park 345-kV line | Loop Stone Lake - Gardner Park 345-kV line into new Pershing 345-kV Substation. | WI | WI | BaseRel |  |  | 15000000 | 2018-06-01 | 2018-06-01 | 345 |  | Bottom-up
B in MTEP16 | B | West | ATC | 9928 | 2015-09-15 | PR07179 | Re-rate Council Creek - Tomah Industrial Park (Y-121) 69kV Line | Re-rate 1.2 miles of 69 kV line between Council Creek and Tomah Industrial Park. | WI | WI |  |  |  |  | 2017-11-01 | 2017-11-01 | 69 |  | Bottom-up
B in MTEP16 | B | West | ATC | 9930 | 2016-09-15 | PR07296, 602003, 602026 | Uprate Lost Dauphin - Red Maple 138kV | Lost Dauphin - Red Maple 138-kV line uprate. | WI | WI |  |  |  |  | 2018-12-01 | 2018-12-01 | 138 |  | Bottom-up
B in MTEP16 | B | West | ATC | 9935 | 2015-09-15 | PR05844 | Install Wesmark Substation 2-8 Mvar 69-kV capacitor banks | Wesmark Substation: Install 2-8 Mvar 69-kV capacitor banks. | WI | WI |  |  |  |  | 2020-06-01 | 2020-06-01 | 69 |  | Bottom-up
B in MTEP16 | B | West | ATC | 9968 | 2016-09-14 |  | Rebuild 138KV Line X-6 Portage - Staff Substation | Rebuild 138KV Line X-6 Portage - Staff Substation. | WI | WI |  |  |  |  | 2019-12-31 | 2019-12-31 | 138 |  | Bottom-up
B in MTEP16 | B | West | ATC | 9974 | 2016-09-14 |  | Rebuild 138KV Line X-98 Staff - North Randolph Substation | Rebuild 138KV Line X-98 Staff - North Randolph Substation. | WI | WI |  |  |  |  | 2019-12-31 | 2019-12-31 | 138 |  | Bottom-up
B in MTEP16 | B | West | ATC | 9991 | 2015-09-15 |  | Rebuild Racine 345kV Bus | Rebuild Racine 345kV Bus. | WI | WI |  |  |  |  | 2018-12-31 | 2018-12-31 | 345 |  | Bottom-up
B in MTEP16 | B | West | ATC | 10486 | 2015-12-16 | PR06461 | Rebuild Chaffee Creek - Lincoln Pump Station 69 kV | Rebuild line Y-18 Chaffee Creek - Lincoln Pump Station. | WI | WI |  |  |  |  | 2021-12-31 | 2021-12-31 | 69 |  | Bottom-up
B in MTEP16 | B | West | ATC | 10590 | 2016-08-11 | PR06462 | Rebuild Academy - Columbus 69kV | Rebuild Academy - Columbus (Y-21) 69kV | WI | WI |  |  |  |  | 2023-12-31 | 2023-12-31 | 69 |  | Bottom-up
B in MTEP16 | B | West | ATC, XEL | 10183 | 2016-08-18 |  | Pershing 345 kV Substation | New 345/115 kV substation located near Sheldon Pump on the Stone Lake to Gardner Park 345 kV line. This is a joint Xcel Energy/ATC project with ATC owning the 345 kV yard at Pershing and Xcel Energy owning the rest of the substation. | WI | WI | BaseRel |  |  | 14500000 | 2018-06-01 | 2018-06-01 | 345 | 115 | Bottom-up
B in MTEP16 | B | West | GRE | 8920 | 2016-08-11 |  | Elisha 115/34.5 | Build 11.4 miles 115 kV from Hubbard to Elisha. Build 4.9 miles 115 kV from Elisha to Potato Lake tap. | MN | MN | Other |  | Distribution | 15817000 | 2022-09-01 | 2022-09-01 | 115 | 34.5 | Bottom-up
B in MTEP16 | B | West | GRE | 9200 | 2016-08-11 | 203613 | Two Inlets Pumping Station (X1A) | Tap the IM-PT line near Potato Lake substation and build ~7.5 miles of 115kV transmission line to connect the future Two Inlets substation. The substation will supply power to the Enbridge Two Inlets pump station. | MN | MN | Other |  | Reliability | 7344393.37 | 2018-10-19 | 2018-10-19 | 115 |  | Bottom-up
B in MTEP16 | B | West | GRE | 9201 | 2016-08-11 | 203610 | Backus Pumping Station (X2A) | Build 115 kV line from a new interconnection to the MP?s 115 kV #142 line (Badoura ? Pine River) to the Bull Moose substation - Backus Pump Station | MN | MN | Other |  | Reliability | 2105606.54 | 2018-10-31 | 2018-10-31 | 115 |  | Bottom-up
B in MTEP16 | B | West | GRE | 9202 | 2016-08-11 | 203611 | Palisade Pumping Station (X3A) | Build 115 kV line from MP's 115 kV #13 line to the Enbridge Palisade Pumping Station. | MN | MN | Other |  | Reliability | 13058755.19 | 2018-10-31 | 2018-10-31 | 115 |  | Bottom-up
B in MTEP16 | B | West | GRE | 9203 | 2016-08-11 | 203612 | Cromwell Pumping Station (X4A) | Build 115 kV line from line to the Cromwell Pumping Station. | MN | MN | Other |  | Reliability | 920000 | 2018-10-11 | 2018-10-11 | 115 |  | Bottom-up
B in MTEP16 | B | West | GRE | 10102 | 2016-04-13 |  | Owatonna Area Project | Construct a 33 mile 161 kV line from Freeborn/Hayward to West Owatonna. | [8 empty] | #N/A | #N/A | Bottom-up
B in MTEP16 | B | West | ITCM | 9100 | 2015-05-28 | Burlington Area 69kV | Burlington Terminal & 4th St-Agency 69kV | Upgrade the Burlington 69kV terminal so the Burlington-South Burlington line is conductor limited. Rebuild the Burlington 4th Street-Agency 69kV line to T2-477 (140MVA). | IA | IA |  |  |  |  | 2019-12-19 | 2019-12-31 | 69 |  | Bottom-up
B in MTEP16 | B | West | MDU | 9122 | 2015-06-10 |  | East Bismarck-Expressway 115 Upgrade | Replace switches and line jumpers at East Bismarck Jct. on the 115 kV line to Expressway Sub. | ND | ND |  |  |  | 125000 | 2020-06-01 | 2020-06-01 | 115 |  | Bottom-up
B in MTEP16 | B | West | MDU | 9140 | 2015-06-12 |  | Coyote-NACO Sub 115 Upgrade | Reconductor Coyote Jct-NACO sub 115 kV line with 477 ACSS | ND | ND |  |  |  | 1270000 | 2020-09-01 | 2020-09-01 | 115 |  | Bottom-up
B in MTEP16 | B | West | MDU | 9180 | 2015-06-16 |  | Green River Capacitors | Increase Green River Jct. 15 Mvar capacitors to 20 Mvar | ND | ND |  |  |  | 400000 | 2020-10-01 | 2020-10-01 | 115 |  | Bottom-up
B in MTEP16 | B | West | MEC | 2937 | 2016-07-22 | G0103 | Sub 39: Second 345-161 kV Xfmr | Add a second 345-161 kV xfmr. Expand 345 kV and 161 kV buses. | IL | IL | BaseRel |  |  | 10900000 | 2022-06-01 | 2022-06-01 | 345 | 161 | Bottom-up
B in MTEP16 | B | West | MEC | 2938 | 2016-07-22 | G0104 | Uprate Sub 39 - Cordova 345 kV Line | Change out structures to increase rating. | IL | IL | BaseRel |  |  | 1300000 | 2021-12-01 | 2021-12-01 | 345 |  | Bottom-up
B in MTEP16 | B | West | MP | 9642 | 2015-09-08 | 20 Line Bus Relocation | 20 Line Bus Relocation | Move 20 Line (Blackberry - 20L Tap) from Blackberry Bus 2 to Blackberry Bus 1 | MN | MN |  |  |  | 1500000 | 2019-12-31 | 2019-12-31 | 115 |  | Bottom-up
B in MTEP16 | B | West | MP | 9643 | 2015-09-11 | Little Falls Tie Breaker | Little Falls 115 kV Tie Breaker Addition | Add a tie breaker in the Little Falls 115 kV bus. Bus 1 to consist of 163 Line (Little Falls - CWP Little Falls), 46 Line (Little Falls - Mud Lake), and 1TR (115/34 kV). Bus 2 to consist of 868 Line (Little Falls - West St Cloud), 49 Line (Little Falls - Blanchard), 10K Cap Bank, and 2TR (115/34 kV). Line-connected transformer 2TR will need to be reconfigured to connect to Bus 2. | MN | MN |  |  |  | 1000000 | 2017-06-01 | 2017-06-01 | 115 |  | Bottom-up
B in MTEP16 | B | West | MP | 9644 | 2015-09-11 | North Shore Cap Banks | North Shore Cap Banks | Add three cap banks in the North Shore Loop. Establish a shunt cap bank station (2x20 MVAr) on the site of the future North Shore Switching Station near Silver Bay, MN, interconnected to existing Tac Harbor - Silver Bay 115 kV Line. Add a second 138 kV cap bank (1x15 MVAr) at the Hoyt Lakes Substation. | MN | MN | BaseRel |  |  | 2500000 | 2017-12-31 | 2017-12-31 | 115 |  | Bottom-up
B in MTEP16 | B | West | MP | 9646 | 2015-09-08 | Nashwauk 14 Line Upgrade | Nashwauk 14 Line Upgrade | Increase capacity of Nashwauk - 14 Line Tap 115 kV line | MN | MN |  |  |  | 500000 | 2020-05-01 | 2020-05-01 | 115 |  | Bottom-up
B in MTEP16 | B | West | MP | 9647 | 2015-09-08 | 53 Line Upgrade | 53 Line Upgrade | Increase capacity of existing Nashwauk - National 115 kV Line (53 Line) | MN | MN |  |  |  | 500000 | 2020-05-01 | 2020-05-01 | 115 |  | Bottom-up
B in MTEP16 | B | West | MP | 10285 | 2015-10-30 | Forbes Tie Breaker Failure Relay | Forbes 38-44MW Breaker Failure Relay | Install breaker failure relay on Forbes 38-44MW 115 kV bus tie breaker | MN | MN |  |  |  |  | 2020-05-01 | 2020-05-01 | 115 |  | Bottom-up
B in MTEP16 | B | West | MPC, OTP | 4813 | 2016-05-25 | OTP | Clearbrook West 115 kV-Bagley West 230 kV | Clearbrook West to Bagley West 230 kV - new 115 kV transmission line (16 miles) 795 ACSR conductor. Bagley West 230/115 kV new substation. Add 230/115 kV Breakers 140 MVA Transformer & new line termination. Bagley West 230 kV tap. Project taps proposed Clearbrook to Clearbrook West 115 kV radial line. Bagley North 115 kV Switching substation, Add 115 kV 3 Breaker Ring Bus | MN | MN | BaseRel |  |  | 12300000 | 2020-12-31 | 2020-12-31 | 230 | 115 | Bottom-up
B in MTEP16 | B | West | OTP | 9997 | 2016-09-01 |  | Rolette 230/69/41.6 kV Substation | Tap Xcel's 230 kV line between Rugby and Glenboro and install 230/69/41.6 kV Transformer - Install three 230 kV Breakers, one 69 kV Breaker, one 41.6 kV Breaker and install one 230/69/41.6 kV Transformer (60 MVA). Construct 12 miles of 41.6 kV line and 6 miles of 69 kV line. | ND | ND | Other |  | Reliability | 9000000 | 2018-12-01 | 2018-12-01 | 230 | 41.6 | Bottom-up
B in MTEP16 | B | West | OTP | 10001 | 2016-09-01 |  | Voltaire 115/41.6 kV Substation | Build a new 115/41.6 kV substation in the Voltaire area by tapping MISO facilities and re-terminating existing OTP - owned 41.6 kV circuits from CPEC - owned Voltaire substation to new OTP - owned 115/41.6 kV delivery. Install one 40 MVA Transformer 115/41.6 kV. Install four 41.6 kV Breakers. | ND | ND | Other |  | Reliability | 5000000 | 2018-10-01 | 2018-10-01 | 115 | 41.6 | Bottom-up
B in MTEP16 | B | West | OTP | 10043 | 2015-09-17 |  | Jamestown 345 Breaker Addition | Install an additional 345 kV breaker to meet TPL-001-4 Compliance Standard. | ND | ND |  |  |  | 2000000 | 2020-12-31 | 2020-12-31 | 345 |  | Bottom-up
B in MTEP16 | B | West | OTP | 10903 | 2016-09-26 |  | Rugby 115 kV Breaker/Line Addition | Rugby 115 kV Breaker/Line Addition - Install a new 115 kV Breaker and 2 miles of line to Rugby-Harvey line. | ND | ND | Other |  | Reliability | 1500000 | 2017-12-01 | 2017-12-01 | 115 |  | Bottom-up
A in MTEP03 | A | Central | SIPC | 81 | 2011-04-22 |  | Carrier Mills 161kV | A new 25-mile 161kV transmission line from Southern Illinois Power Cooperative's power plant to a new 161/69kV substation located north of Carrier Mills, IL. | IL | IL | Other |  |  | 10200000 | 2016-10-01 | 2016-10-01 | 161 | 69 | Bottom-up
A in MTEP06 | A | Central | AmerenIL | 739 | 2006-03-17 |  | Franklin County Power Plant Connection | Franklin County Power Plant Connection - Tap 345 kV Line 4561 Tap, and Install new 345 kV ring bus | IL | IL | Other |  |  | 6410900 | 2020-11-01 | 2020-11-01 | 345 |  | Bottom-up
A in MTEP08 | A | Central | DEI | 1899 | 2011-09-27 | 604B5493 | Macy to Rochester Metals Jct 69kV reconductor | Reconductor Macy to Rochester Metals Jct section of 6957 circuit with 477ACSR - approx 9.1 miles | IN | IN | Other |  | Reliability | 4707000 | 2016-12-31 | 2016-12-31 | 69 |  | Bottom-up
A in MTEP08 | A | Central | HE | 1929 | 2008-01-10 | None Yet | Georgetown Primary Ring Bus | 138kV Ring Bus addition / Modification to Georgetown Primary | IN | IN | Other |  | Reliability | 1250000 | 2012-09-01 | 2012-09-01 | 138 |  | Bottom-up
A in MTEP08 | A | Central | Vectren | 1782 | 2014-09-30 |  | NorthEast Sub Bus re-config | Rebuild existing straight bus with more reliable breaker and half scheme | IN | IN | Other |  | Reliability | 8000000 | 2024-12-31 | 2024-12-31 | 138 |  | Bottom-up
A in MTEP08 | A | Central | Vectren | 1784 | 2014-09-30 |  | Jasper#3 Sub Exp-Victory Line | Extend existing Victory line to new term at existing sub | IN | IN | Other |  |  | 3625000 | 2019-12-31 | 2019-12-31 | 69 |  | Bottom-up
A in MTEP08 | A | Central | Vectren | 1788 | 2014-09-30 |  | Y34 - St. Wendel to Mohr Rd | New 69kV line from St. Wendel Sub to Mohr Rd Sub | IN | IN | Other |  | Reliability | 2750000 | 2016-12-31 | 2016-12-31 | 69 |  | Bottom-up
A in MTEP08 | A | Central | Vectren | 1789 | 2014-09-30 |  | Y56 - City of Boonville Loop | New 69kV line from Boonville Sub to Boonville Pioneer Sub | IN | IN | Other |  | Reliability | 1400000 | 2018-12-31 | 2018-12-31 | 69 |  | Bottom-up
A in MTEP08 | A | East | METC | 1448 | 2006-10-25 | 196 | Simpson | Project to connect a distribution transformer at Simpson | MI | MI | Other |  |  | 2200000 | 2019-12-31 | 2019-12-31 | 138 | 12.5 | Bottom-up
A in MTEP08 | A | West | ITCM | 1744 | 2009-09-25 | GM-MAQ | Maquoketa-Grand Mound 161kV Reconductor | Reconductor 161kV from Maquoketa to Grand Mound (old East Calamus-Maquoketa 161kV line) | IA | IA | BaseRel |  |  | 10150000 | 2019-12-31 | 2019-12-31 | 161 |  | Bottom-up
A in MTEP08 | A | West | NWEC | 2011 | 2009-11-16 | 2009-03 | Frederic-Lewis 34.5KV Rebuild | Rebuild the 34.5Kv system between Frederic and Lewis sub at 69KV with 477ASCR and horizontal post construction. | WI | WI | Other |  |  | 350000 | 2011-06-01 | 2011-06-01 | 69 |  | Bottom-up
A in MTEP08 | A | West | NWEC | 2012 | 2009-11-16 | 2010-01 | Falun-Penta 34.5KV Rebuild | Rebuild the 34.5Kv system between Falun and Penta sub at 69KV with 477ASCR and horizontal post construction. | WI | WI | Other |  |  | 538000 | 2011-09-01 | 2011-09-01 | 69 |  | Bottom-up
A in MTEP08 | A | West | NWEC | 2013 | 2009-11-16 | 2010-02 | Penta-Siren Tap 34.5KV Rebuild | Rebuild the 34.5Kv system between Penta sub and Siren Tap at 69KV with 477ASCR and horizontal post construction. | WI | WI | Other |  |  | 175000 | 2011-06-01 | 2011-06-01 | 69 |  | Bottom-up
A in MTEP08 | A | West | NWEC | 2016 | 2009-11-16 | 2011-02 | Frederic-Coffee Cup 69KV reconductor | Reconductor 69KV line with 477ACSR | WI | WI | Other |  |  | 100000 | 2013-01-01 | 2013-01-01 | 69 |  | Bottom-up
A in MTEP08 | A | West | NWEC | 2018 | 2009-11-16 | 2012-01 | Balsam Lake-Centuria 69KV line | Build new 69KV line to Centuria and build Distribution Sub | WI | WI | Other |  |  | 1200000 | 2011-06-01 | 2011-06-01 | 69 | 12.47 | Bottom-up
A in MTEP08 | A | West | XEL | 675 | 2008-06-30 |  | Rebuild Westgate to Scott County 69 kV to 115 kV | Upgrade 20.1 miles Westgate-Deephaven-Excelsior-Scott County 69kV to 115 kV using 795 ACSS conductor, Upgrade 2 miles Westgate-Eden Prairie 115kV #1 and #2 to 400MVA (PrjID 606), Substation work at Deephaven, Excelsior and Scott County. | MN | MN | Other |  |  | 14000000 | 2017-06-15 | 2017-06-15 | 115 |  | Bottom-up
A in MTEP09 | A | Central | AmerenIL | 2273 | 2010-04-05 |  | Supply to LaFarge Customer Substation | Provide 161 kV supply to customer substation | IL | IL | Other |  | Distribution | 570000 | 2020-06-01 | 2020-06-01 | 161 |  | Bottom-up
A in MTEP09 | A | Central | DEI | 2154 | 2011-09-27 | AMIN0360 | Carmel Rohrer Rd 69/12kv New Sub | Carmel Rohrer Rd 69/12-22.4MVA sub to looped through the 6989 ckt. at or near the existing Carmel Shell Oil tap | IN | IN | Other |  | Distribution | 591143 | 2019-06-01 | 2019-06-01 | 69 | 12 | Bottom-up
A in MTEP09 | A | Central | Vectren | 2466 | 2014-09-30 | SIGE7 | Roesner Rd 138/12kV Substation | New 138/12kV Substation for load growth | IN | IN | Other |  | Distribution | 3000000 | 2019-06-01 | 2019-06-01 | 138 | 12.47 | Bottom-up
A in MTEP09 | A | East | METC | 662 | 2016-08-15 | METC_10_007 | Weeds Lake | Loop the 345kV Argenta - Robinson Park 345kV circuit into a new 345/138kV EHV substation called Weeds Lake. Build 4 new (approximately 6 miles) 138kV circuits to loop the two Argenta-Milham 138kV lines into the substation. | MI | MI | BaseRel |  |  | 49248128 | 2016-12-15 | 2016-12-15 | 345 | 138 | Bottom-up
A in MTEP09 | A | East | METC | 2478 | 2015-11-24 |  | Capital Ave | New distribution interconnection served from Battle Creek - Verona #2 138kV (Line connection change to Battle Creek to Island Road) | MI | MI | Other |  | Distribution | 178188 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
A in MTEP09 | A | East | METC | 2481 | 2016-06-08 |  | Forrest Grove | New distribution interconnection served from Campbell-Ransom 138kV circuit. | MI | MI | Other |  | Distribution | 170000 | 2018-05-31 | 2018-05-31 | 138 |  | Bottom-up
A in MTEP09 | A | East | METC | 2482 | 2014-01-31 |  | Hawthorne | New distribution interconnection served from Four Mile - Blendon 138kV circuit. | MI | MI | Other |  | Distribution | 170000 | 2020-05-31 | 2020-05-31 | 138 |  | Bottom-up
A in MTEP09 | A | East | METC | 2483 | 2016-02-29 |  | Maines Road | New distribution interconnection served from Marshall - Blackstone 138kV circuit | MI | MI | Other |  | Distribution | 176386 | 2016-12-01 | 2016-12-01 | 138 |  | Bottom-up
A in MTEP09 | A | East | METC | 2485 | 2016-06-08 |  | Ironwood | New distribution interconnection served from CE's 138kV spur on the Ransom-Buck Creek 138kV. | MI | MI | Other |  | Distribution | 12000 | 2019-06-01 | 2019-06-01 | 138 |  | Bottom-up
A in MTEP09 | A | East | METC | 2486 | 2016-08-15 |  | Haakwood | New distribution interconnection served from Riggsville-Livingston 138kV (on the Rondo-Vanderbilt section) | MI | MI | Other |  | Distribution | 170000 | 2018-06-01 | 2018-06-01 | 138 |  | Bottom-up
A in MTEP09 | A | East | METC | 2501 | 2015-02-26 |  | Northern Reactive | Install 3 capacitors in the northern part of Michigan | MI | MI | BaseRel |  |  | 2700001 | 2030-06-01 | 2030-06-01 | 0 |  | Bottom-up
A in MTEP09 | A | East | WPSC | 2736 | 2010-01-06 | EB-SB | East Bay-South Boardman Line Rebuild | East Bay - South Boardman Dist - South Boardman 69 kV line rebuild (16 miles) to 143 MVA | MI | MI | Other |  | Reliability | 7500000 | 2010-03-31 | 2016-12-31 | 69 |  | Bottom-up
A in MTEP09 | A | East | WPSC | 2770 | 2009-02-03 |  | Gilmore | New distribution interconnection served from Hersey to Vestaburg circuit. | MI | MI | Other |  | Distribution | 500000 | 2017-06-01 | 2017-12-31 | 69 |  | Bottom-up
A in MTEP09 | A | West | ITCM | 2367 | 2009-04-01 | ITCM-08-033 | Anita Area 34kV to 69kV Rebuilds | Rebuild 5 miles from the Anita-Exira REC to 69kV. Also rebuild 4.7 miles of the Anita to th e Anita-Wiota Joint sub. Rebuild 21.9 miles from Thompson- Redfield. These lines will continue to opeate at 34kV. | IA | IA | Other |  | Condition | 2425000 | 2014-08-27 | 2016-12-31 | 34 |  | Bottom-up
A in MTEP09 | A | West | ITCM | 2371 | 2009-09-25 | ITCM-08-041 | New Marengo 69kV Switching Station | Construct a new 3-terminal 69kV switching station at the existing Marengo 34kV sub. | IA | IA | Other |  | Condition | 1900000 | 2016-12-31 | 2016-12-31 | 69 |  | Bottom-up
A in MTEP09 | A | West | MP | 2759 | 2009-11-13 | Laskin | Laskin | Move Virginia 115/46 kV Transformer to Laskin | MN | MN | Other |  | Distribution | 1500000 | 2017-12-31 | 2017-12-31 | 115 | 46 | Bottom-up
A in MTEP10 | A | Central | DEI | 1520 | 2009-09-17 | 502G6713 | Durbin 230/69 | Construct a new Durbin 230/69kv 150mva substation with 2 69kv line terminals. | IN | IN | Other |  | Reliability | 9167825.75 | 2017-06-01 | 2017-06-01 | 230 | 69 | Bottom-up
A in MTEP10 | A | Central | DEI | 2143 | 2011-09-27 | 602J3066 | Frances Creek 345/69kV Bank 2 | Add Frances Creek 345/69kV Bank 2 - 200MVA with LTC | IN | IN | Other |  | Reliability | 6887000 | 2020-06-01 | 2020-06-01 | 345 | 69 | Bottom-up
A in MTEP10 | A | East | ITCT | 2929 | 2016-04-22 |  | Ariel Substation (formerly Holland) | Distribution Interconnection to add two new 120/13.2kV transformers at Holland. Connects to the Wheeler to Troy 120kV circuit. | MI | MI | Other |  | Distribution | 2800000 | 2016-11-30 | 2016-11-30 | 120 |  | Bottom-up
A in MTEP10 | A | West | GRE | 2564 | 2016-09-08 | 20225 | St. Wendel 3.0 mile, 115 kV line | St. Wendel 3.0 mile, 115 kV line | MN | MN | Other |  | Distribution | 1500000 | 2017-11-08 | 2017-11-08 | 115 |  | Bottom-up
A in MTEP10 | A | West | GRE | 2577 | 2016-02-10 | 20312 | Columbus (CE) 69 kV Substation | Columbus (previously Elmcrest) (CE) 69 kV Substation | MN | MN | Other |  | Distribution | 140000 | 2021-05-18 | 2021-05-18 | 69 |  | Bottom-up
A in MTEP10 | A | West | GRE | 2579 | 2010-09-15 | 20273 | Foster Lake (WH) 69 kV Substation | Foster Lake (WH) 69 kV Substation | MN | MN | Other |  | Distribution | 140000 | 2020-10-30 | 2020-10-30 | 69 |  | Bottom-up
A in MTEP10 | A | West | GRE | 2589 | 2009-11-19 | 20328 | Barnes Grove (DEA) 2.0 mile, 69 kV line | Barnes Grove (DEA) 2.0 mile, 69 kV line | MN | MN | Other |  | Distribution | 115001 | 2023-07-20 | 2023-07-20 | 69 |  | Bottom-up
A in MTEP10 | A | West | GRE | 2670 | 2012-12-04 | 20446 | Schuster Lake 115/41.6 Source | Schuster Lake115/41.6 Source | MN | MN | Other |  | Reliability | 4480714.28 | 2020-04-14 | 2020-04-14 | 115 | 41.6 | Bottom-up
A in MTEP10 | A | West | ITCM | 3048 | 2009-09-14 | Jeff-Perlee | Jefferson Co-Perlee 69kV Rebuild | Rebuild the Jefferson Co-Perlee 69kV line section. | IA | IA | Other |  | Condition | 2700000 | 2022-12-31 | 2022-12-31 | 69 | 69 | Bottom-up
A in MTEP10 | A | West | ITCM | 3053 | 2010-06-28 | Keokuk-Carbide | Keokuk Hydro-Carbide 69kV Dbl Ckt | Build a new 69kV circuit from Keokuk Hydro-Carbide. | IA | IA | Other |  | Reliability | 3240000 | 2016-12-31 | 2016-12-31 | 69 | 69 | Bottom-up
A in MTEP10 | A | West | ITCM | 3055 | 2009-09-14 | CR 34kV Plan | Cedar Rapids 34kV Conversion Plan | ITCM, working with IP & L, has formed a plan to better serve Cedar Rapids load with new larger, 2-transformer substations that will allow retirement of the 4kV system along with several other small distribution substations. Most of these new substations will be served from a new 69 kV and 161 kV Cedar Rapids transmission system that will use the existing 34.5 kV system right-of-way. This will allow retirement of several existing 34.5kV lines while shifting distribution load to a higher voltage to allow better normal and contingency performance. | IA | IA | Other |  | Reliability | 9310000 | 2011-04-29 | 2019-12-31 | 161 | 69 | Bottom-up
A in MTEP10 | A | West | ITCM | 3057 | 2010-06-28 | WB 34kV Shift | West Branch 34kV Load Shift Projects | Construct 69kV taps for the Moscow & New Liberty dist. Subs | IA | IA | Other |  | Distribution | 2505000 | 2018-12-31 | 2019-12-31 | 69 | 34 | Bottom-up
A in MTEP10 | A | West | ITCM | 3058 | 2009-09-14 | Vinton 34kV Plan | Vinton-Hazleton 34kV Conversion Plan | The plan includes rebuilding a line between Dundee and Vinton substations and converting this line to 69 kV operation. In order to operate this line at 69 kV a 161/69 kV transformer will need to be installed at Vinton. Also, an approximatley 6 mile line will be built to connect the Hazleton source to the Dundee - Vinton line. This plan also includes rebuilding a line between Coggon and Hiawatha substations and converting this line to 69 kV operation. A 161/69 kV transformer will need to be installed at Coggon. | IA | IA | Other |  | Distribution | 5160000 | 2011-12-31 | 2016-12-31 | 161 | 69 | Bottom-up
A in MTEP10 | A | West | MP | 2547 | 2009-12-08 | Essar | Essar | Essar project adds a 95 MW new mine and taconite plant load in fall 2011 with 50 MW DRI facility fall of 2012 total demand to 145 MW. Future load additions could increase total demand to 300 MW | MN | MN | Other |  | Distribution | 14000000 | 2013-03-08 | 2027-04-01 | 230 | 14 | Bottom-up
A in MTEP10 | A | West | MP | 2761 | 2009-11-13 | Dunka Rd | Polymet | add new 138/14 kV substaion off MP 138 KV Line #1 | MN | MN | Other |  | Distribution | 3242847 | 2017-01-31 | 2017-01-31 | 138 | 14 | Bottom-up
A in MTEP10 | A | West | MPW | 2934 | 2016-09-15 | MPW-SS | South Sub add transformer in parallel with existing 75 MVA transformer | Add a 134 MVA transformer at South Sub (633301-633501) in parallel with existing 75 MVA transformer. | IA | IA | Other |  | Reliability | 5400000 | 2016-12-01 | 2016-12-01 | 161 | 69 | Bottom-up
A in MTEP10 | A | West | NWEC | 3092 | 2009-11-16 | 2012-02 | Webb Lake 69KV line | Rebuild 34.5KV line to Webb Lake at 69KV with horizontal post construction and #4/0 ACSR | WI | WI | Other |  | Condition | 425000 | 2012-06-01 | 2012-06-01 | 69 |  | Bottom-up
A in MTEP11 | A | Central | AmerenIL | 2239 | 2011-11-03 | 17 Prop. MVP Port.1 (64) FG9 | Proposed MVP Portfolio 1 - Sidney to Rising 345 kV line | Sidney to Rising 345 kV line | IL | IL | MVP |  |  | 8703420 | 2016-06-01 | 2016-09-01 | 345 |  | Top-Down
A in MTEP11 | A | Central | AmerenIL | 3017 | 2016-01-27 | 09 Prop. MVP Port.1 | Proposed MVP Portfolio 1 - Maywood-Herleman-Meredosia-Ipava & Meredosia-Austin 345 kV Line | Maywood-Herleman-Meredosia-Ipava & Meredosia-Austin 345 kV lines | IL | IL | MVP |  |  | 705400612 | 2016-01-10 | 2017-11-15 | 345 | 138 | Top-Down
A in MTEP11 | A | Central | AmerenIL | 3169 | 2011-11-03 | 10 Prop. MVP Port.1 | Proposed MVP Portfolio 1 - Pawnee to Pana - 345 kV Line | Pawnee to Pana 345 kV line including additional transformer at Pana | IL | IL | MVP |  |  | 135496358 | 2016-11-15 | 2018-11-15 | 345 | 138 | Top-Down
A in MTEP11 | A | Central | AmerenIL, DEI | 2237 | 2011-11-03 | 11 Prop. MVP Port.1 (62) | Proposed MVP Portfolio 1 - Pana - Mt. Zion - Kansas - Sugar Creek 345 kV line | Pana to Mt. Zion to Kansas to Sugar Creek 345 kV line. Install transformers at Mt. Zion and Kansas | IN | IL | MVP |  |  | 399992176 | 2015-02-26 | 2018-11-15 | 345 | 138 | Top-Down
A in MTEP11 | A | Central | AmerenIL, MEC | 3022 | 2015-04-02 | 16 Prop. MVP Port.1 | Proposed MVP Portfolio 1 - Fargo-Sandburg-Oak Grove 345 kV Line | Fargo-Sandburg-Oak Grove 345 kV Line - New 70 mile, 3000 A summer emergency capability line. 345 kV PCBs: 3-Fargo, 1-Oak Grove. 3-Sandburg. 560 MVA xfmr at Sandburg | IL | IA | MVP |  |  | 219254491.11 | 2016-11-15 | 2018-11-15 | 345 | 138 | Top-Down
A in MTEP11 | A | Central | AmerenMO | 3170 | 2015-04-01 | 08 Prop. MVP Port.1 | Proposed MVP Portfolio 1 - Zachary-Maywood 345 kV Line | Zachary - Maywood 345 kV, 58 miles, 3000A. Establish a new 345 kV substation at Maywood | MO | MO | MVP |  |  | 153369959 | 2016-01-10 | 2018-11-15 | 345 |  | Top-Down
A in MTEP11 | A | Central | AmerenMO, ITCM, MEC | 2248 | 2015-03-24 | 07 Prop. MVP Port.1 | Proposed MVP Portfolio 1 - Zachary - Ottumwa 345 | Zachary Substation - New 560 MVA, 345/161 kV Transformer. New 71 mile 345 kV line from Zachary to Ottumwa with 3000 A summer emergency capability | MO | IA | MVP |  |  | 191850586.95 | 2017-06-01 | 2018-11-15 | 345 | 161 | Top-Down
A in MTEP11 | A | Central | DEI | 3379 | 2012-03-23 | AMIN0138 | Shelbyville McKay Rd. 69kV Dist Sub | Shelbyville McKay Rd. - add new 69/12kV distribution sub in the 6976 ckt. Loop through with 954acsr and a set of 1200A line switches. | IN | IN | Other |  | Reliability | 553710 | 2017-06-01 | 2017-06-01 | 69 | 12 | Bottom-up
A in MTEP11 | A | Central | DEI | 3386 | 2010-09-15 | AMIN0379 | Carmel Springmill Rd. to Hortonville 69kV Line and Brkrs | Carmel Springmill Rd. Sub - Add 3-69kV breakers in straight bus config and build new .23 mile 69kV 954ACSS@200C line from Springmill Sub to old Springmill Jct. to complete circuit to Hortonville. Change operating mode at Homeplace to close loop from 146th to Springmill. | IN | IN | Other |  | Reliability | 1866000 | 2019-06-01 | 2019-06-01 | 69 |  | Bottom-up
A in MTEP11 | A | Central | DEI, NIPS | 2202 | 2015-11-02 | 14 Prop. MVP Port.1 | Proposed MVP Portfolio 1 - Reynolds to Greentown 765 kV line | Reynolds to Greentown 765 kV line | IN | IN | MVP |  |  | 387493373 | 2013-08-29 | 2018-06-01 | 765 | 345 | Top-Down
A in MTEP11 | A | Central | IPL | 3273 | 2015-12-01 |  | Southwest - Stout CT Line Rating Upgrade | Increase line rating from 322 to 345MVA | IN | IN | Other |  | Reliability | 300000 | 2018-06-30 | 2018-06-30 | 138 |  | Bottom-up
A in MTEP11 | A | East | ITCT | 3281 | 2016-02-22 | 7 | Chelsea (formerly Lima) Substation | Distribution Interconnection Request | MI | MI | Other |  | Distribution | 6500000 | 2016-12-31 | 2016-12-31 | 120 |  | Bottom-up
A in MTEP11 | A | East | ITCT | 3285 | 2016-07-14 | ITCT_12_007 | Shoal 120kV Capacitor | 33.3 Mvar Capacitor at Shoal 120kV | MI | MI | BaseRel |  |  | 4330000 | 2016-11-30 | 2016-11-30 | 120 |  | Bottom-up
A in MTEP11 | A | East | NIPS | 3203 | 2011-11-03 | 12 Prop. MVP Port.1 | Proposed MVP Portfolio 1 - Reynolds to Burr Oak to Hiple 345 kV | Reynolds to Burr Oak to Hiple 345 kV line and tie in second AEP 345 kV circuits at Reynolds and Hiple | IN | IN | MVP |  |  | 388000000 | 2019-12-31 | 2019-12-31 | 345 |  | Top-Down
A in MTEP11 | A | East | WPSC | 3331 | 2010-09-15 | RW-HT | Redwood to Hart | Rebuild the Redwood to Hart line section with a larger conductor | MI | MI | Other |  | Reliability | 1000000 | 2016-12-31 | 2016-12-31 | 69 |  | Bottom-up
A in MTEP11 | A | East | WPSC | 3335 | 2010-09-15 | Burnips Xmsn | Burnip Transmission Station Upgrade | Upgrade to replace outdated equipment. Bus, breakers, relays, and other equipment as necessary. | MI | MI | Other |  | Condition | 800000 | 2022-12-31 | 2022-12-31 | 69 |  | Bottom-up
A in MTEP11 | A | West | ATC | 3206 | 2013-07-05 | PR04117 F2676 WO068196 | G833-4_J022-3 Long Term Solution | 1) Construct a new Barnhart 345 & 138 kV substation 2) Install a new 345/138 kV transformer at Barnhart 3) Loop Edgewater-South Fond du Lac, Edgewater-Cedarsauk, Sheboygan Energy Center-Granville 345 kV lines into Barnhart 4) Loop the South Sheboygan Falls-Mullet River 138 kV line into Barnhart 138 kV 5) Construct a new 138 kV line from Barnhart to Plymouth #4 6) Construct a new 138 kV line from Plymouth #4 to Howards Grove 7) Construct a new 138 kV line from Howards Grove to Erdman 8) Convert the existing Forest Junction-Howards Grove-Plymouth #4 138 kV line and the northern portion of the existing Plymouth #4-Holland 138 kV line to 345 kV 9) Terminate the not-converted Holland 138 kV line at Barnhart 138 kV 10) Terminate the southern end of the converted 345 kV line at Barnhart 11) Construct a new Branch River 345 kV substation 12) Loop the converted 345 kV line into Branch River 345 kV substation 13) Loop the Point Beach-Forest Juction, Point Beach-Sheboygan Energy Center 345 kV lines into Branch River 14) Uprate Barnhart-Cedarsauk 345 kV line to 960 MVA for SN/SE | WI | WI | GIP |  |  | 46647000 | 2018-12-31 | 2018-12-31 | 345 |  | Externally-Driven
A in MTEP11 | A | West | ATC, DPC, ITCM, XEL | 3127 | 2014-09-22 | PR04030 F3398 WO68924, WO68924 | Proposed MVP Portfolio 1: N LaCrosse-N Madison-Cardinal-Eden-Hickory Creek 345 kV | Construct N LaCrosse-N Madison-Cardinal 345 kV & Hickory Creek-Eden-Cardinal 345 kV line. Install Eden transformer. | WI,IA | IA | MVP |  |  | 1045495000 | 2013-06-05 | 2023-12-31 | 345 | 138 | Top-Down
A in MTEP11 | A | West | GRE | 2679 | 2010-09-15 | 200331 | Ramsey-Grand Forks (81.02 mi.) 230 kV Rebuild | Ramsey-Grand Forks (81.02 mi.) 230 kV Rebuild | MN | MN | Other |  | Condition | 41496024.63 | 2021-05-31 | 2021-05-31 | 230 |  | Bottom-up
A in MTEP11 | A | West | GRE | 3454 | 2014-09-12 | 201035 | Pomerleau Lake Line Termination | Terminate the Parkers Lake - Elm Creek 115 kV line to the Pomerleau Lake breaker station that Xcel Energy plans to establish in the 2013 timeframe | MN | MN | Other |  | Reliability | 2126607.36 | 2017-06-13 | 2017-10-27 | 115 |  | Bottom-up
A in MTEP11 | A | West | GRE, MP | 2634 | 2012-12-04 | 20388 | Savanna-Cromwell | Savanna-Cromwell | MN | MN | BaseRel |  |  | 5647421 | 2013-09-30 | 2016-03-31 | 115 |  | Bottom-up
A in MTEP11 | A | West | ITCM | 3412 | 2012-01-07 | FTMadison | Fort Madison Interconnection | Install tap capable of double circuit 69kV to Fort Madison substation and install associated relay equipment. | IA | IA | Other |  | Distribution | 1740000 | 2016-10-07 | 2016-10-07 | 69 |  | Bottom-up
A in MTEP11 | A | West | ITCM | 3413 | 2012-01-07 | Gladbrook | Gladbrook 161kV tap | Install a 161kV tap pole in the Marshalltown to Traer line with two line switches. Construct a 161kV tap line to the new Gladbrook substation. | IA | IA | Other |  | Distribution | 300000 | 2015-12-31 | 2015-12-31 | 161 | 161 | Bottom-up
A in MTEP11 | A | West | ITCM | 3418 | 2012-01-07 | Mt Vernon 6420 | Mount Vernon Circuit 6420 Rebild to 69kV | This project rebuilds the sections (approximately 17 miles) of Mount Vernon circuit 6420 that will be utilized in the overall 34.5kV to 69kV conversion plan but have not yet been constructed for 69kV operation. | IA | IA | Other |  | Distribution | 7150000 | 2015-12-31 | 2015-12-31 | 34 | 34 | Bottom-up
A in MTEP11 | A | West | ITCM | 3422 | 2012-01-07 | S Brdwy TEQ | South Broadway TEQ | Upgrades terminal equipment. Change out existing relays, add new control building, add 69kV bus. | IA | IA | Other |  | Distribution | 852000 | 2015-06-30 | 2015-06-30 | 69 |  | Bottom-up
A in MTEP11 | A | West | ITCM, MEC | 3205 | 2014-03-31 | 03 Prop. MVP Port.1 | Proposed MVP Portfolio 1: Lakefield Jct. - Winnebago - Winco - Kossuth County & Obrien County - Kossuth County - Webster 345 kV line | New 345 kV line from Lakefield Junction to Kossuth County via Winnebago and Winco and a new 345 kV line from Obrien County to Webster via Kossuth County. Includes 161 kV rebuild as underbuild along portions of the route. | MN,IA | IA | MVP |  |  | 516336690.32 | 2015-12-22 | 2018-06-01 | 345 | 161 | Top-Down
A in MTEP11 | A | West | ITCM, MEC | 3213 | 2014-03-31 | 04 Prop. MVP Port.1 | Proposed MVP Portfolio 1 - Winco to Hazleton 345 kV line | Winco to Lime Creek to Killdeer to Blackhawk to Hazleton 345 kV line and Lime Creek, Killdeer and Black Hawk transformers | IA | IA | MVP |  |  | 377229516 | 2015-08-14 | 2018-12-31 | 345 | 161 | Top-Down
A in MTEP11 | A | West | MDU, OTP | 2220 | 2015-09-29 | 06 Prop. MVP Port.1 | MVP Portfolio 1 - Ellendale to Big Stone South | Big Stone to Ellendale 345 kV line | SD,ND | ND | MVP |  |  | 395670000 | 2019-09-30 | 2019-09-30 | 345 | 230 | Top-Down
A in MTEP11 | A | West | MDU, OTP, XEL | 2221 | 2014-03-24 | 01 Prop. MVP Port.1 (46) | MVP Portfolio 1 - Big Stone South to Brookings | Brookings to Big Stone 345 kV line (double ckt capable) | SD | SD | MVP |  |  | 226720000 | 2017-09-30 | 2017-09-30 | 345 | 230 | Top-Down
A in MTEP11 | A | West | OTP, XEL | 3481 | 2015-10-26 | OTP | Buffalo - Casselton 115 kV Line | Construct 16 mile 115 kV line from Buffalo - Casselton (ND); Replace Buffalo 345/115 kV Transformer; Rebuild portion of Sheyenne - Mapleton 115 kV Line | ND | ND | BaseRel |  |  | 5600000 | 2013-11-01 | 2017-06-30 | 345 | 115 | Bottom-up
A in MTEP12 | A | Central | AmerenMO | 3366 | 2015-09-11 |  | Wallen Creek Substation High-Side Transfer | Install 2-2000 A,138 kV PCBs | MO | MO | Other |  | Reliability | 2635000 | 2018-12-01 | 2018-12-01 | 138 |  | Bottom-up
A in MTEP12 | A | Central | BREC | 3792 | 2012-04-20 | Matanzas | Wilson-Matanzas 161 kV Interconnection | Create a new 161 kV BREC-LG&E/KU interconnection by looping the Wilson-Paradise portion of the three terminal interconnection through a new Matanzas substation (LG&E\KU) The loop will require 600 feet of new 954 MCM ACSS construction and will be located 10.5 miles from Wilson. The new LG&E\KUMatanzas station will include 2 161/138 kV transformers, (2) 161 kV line terminals, (2) 138 kV line terminals, (6) 138 kV breakers, and (6) 161 kV breakers. | KY | KY | Other |  | Reliability |  | 2013-09-01 | 2016-01-01 | 161 |  | Bottom-up
A in MTEP12 | A | Central | DEI | 3542 | 2015-09-15 | AMIN0447 | New Castle Ingersoll 1 Bank 2 Repl | New Castle Ingersoll 1 Bank 2 Repl ? Replace 34/12kV bank w/22MVA 69/12kV Bank. Add 69kV tap line. | IN | IN | Other |  | Distribution | 579657 | 2017-06-01 | 2017-06-01 | 69 | 12 | Bottom-up
A in MTEP12 | A | East | ITCT | 3591 | 2016-03-22 | ITC_13_028 | St. Clair 345 kV Station Equipment Upgrades | Replace 345kV station equipment in the B, C and D rows at St. Clair. | MI | MI | BaseRel |  |  | 924000 | 2016-05-31 | 2016-05-31 | 345 |  | Bottom-up
A in MTEP12 | A | East | ITCT | 3624 | 2016-03-23 |  | ITCT Customer Interconnections - Year 2016 | Customer interconnection requests and retirements | MI | MI | Other |  | Distribution | 2000000 | 2016-12-31 | 2016-12-31 | 120 |  | Bottom-up
A in MTEP12 | A | East | METC | 3590 | 2015-02-26 |  | SVC at Tippy | Install Static Var Compensator (SVC) at Tippy | MI | MI | BaseRel |  |  | 28500000 | 2030-06-01 | 2030-06-01 | 138 |  | Bottom-up
A in MTEP12 | A | East | METC | 3599 | 2014-03-31 |  | Palisades 345 kV Station Equipment Upgrades | Upgrade the station equipment at Palisades in rows 25, 27, and 29. | MI | MI | BaseRel |  |  | 4000000 | 2018-12-31 | 2018-12-31 | 345 |  | Bottom-up
A in MTEP12 | A | East | METC | 3625 | 2016-03-23 |  | METC Customer Interconnections - Year 2016 | Customer interconnection requests and retirements | MI | MI | Other |  | Distribution | 2500000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP12 | A | West | ATC | 1270 | 2015-09-15 | PR04508, F4199,WO68710 | Rebuild Arcadian-Waukesha 138 kV lines | Rebuild the two Arcadian-Waukesha 138 kV lines | WI | WI | BaseRel |  |  | 23406000 | 2025-06-01 | 2025-06-01 | 138 |  | Bottom-up
A in MTEP12 | A | West | ATC | 3679 | 2014-06-13 | NP-Package2_3 F3501 WO069260 | Green Bay to Morgan 345 kV project and Menominee Co to Delta Co 138 kV line | New Green Bay sub to Morgan 345 kV line and new 138 kV line from Holmes to 18th road | WI | MI | BaseRel |  |  | 356848000 | 2016-08-13 | 2018-10-25 | 345 | 69 | Bottom-up
A in MTEP12 | A | West | ATC | 3952 | 2014-06-13 | NP_GB-M 138, PR05016 F3501 WO069260 | Green Bay - Morgan 138 kV line | Green Bay - Morgan 138 kV line | WI | WI | Other |  | Reliability | 76711000 | 2018-05-13 | 2018-10-28 | 345 | 138 | Bottom-up
A in MTEP12 | A | West | GRE | 3470 | 2011-01-11 |  | MISO G667 |  | MN | MN | GIP |  |  | 722000 | 2014-12-31 | 2014-12-31 | 0 |  | Externally-Driven
A in MTEP12 | A | West | GRE | 11543 | 2016-07-25 | 200497 | G549 - Glacial Ridge | Install new 69kV 3-way switch structure in the GRE AG-WL line. | MN | MN | GIP |  |  | 150000 | 2018-11-01 | 2018-11-01 | 69 |  | Externally-Driven
A in MTEP12 | A | West | GRE | 11563 | 2016-07-25 | 202038 | G830 - McHenry Substation Upgrade | Install 115 kV ring bus at McHenry substation | ND | ND | GIP |  |  | 4952173 | 2017-11-01 | 2017-11-01 | 115 |  | Externally-Driven
A in MTEP12 | A | West | ITCM | 3627 | 2011-12-13 | Chariton-Corydon | Chariton-Corydon 69 kV Rebuild | Rebuild the 69 kV line from Chariton to Corydon. | IA | IA | Other |  | Condition | 8351986 | 2016-12-30 | 2016-12-30 | 69 |  | Bottom-up
A in MTEP12 | A | West | ITCM | 3628 | 2011-12-13 | Lehigh SS | Relocate Lehigh Switch Station | Construct a new Lehigh Switch Station and retire the existing site. This will require a new 69 kV line from the General Food sub to the Northwest sub. | IA | IA | Other |  | Relocation | 6755200 | 2017-08-25 | 2017-08-25 | 69 |  | Bottom-up
A in MTEP12 | A | West | ITCM | 3629 | 2013-06-27 | 3rd DBQ CKT | 8th Street-Salem 161 kV line | Build a new 8th Street-Salem 161 kV line. This will require ~3.5 miles of new 161 kV line to tie to an existing 69 kV line out of 8th Street that is constructed to 161 kV standards. A new 161 kV terminal will be required at Salem and 8th Street. | IA | IA | BaseRel |  |  | 7222073 | 2016-12-31 | 2016-12-31 | 161 | 69 | Bottom-up
A in MTEP12 | A | West | ITCM | 3630 | 2011-12-13 | Adams-Stewartville | Adams to Stewartville 69 kV Rebuild | Rebuild the ~35 mile line section due to age & condition. | IA | IA | Other |  | Reliability | 12200000 | 2018-12-31 | 2018-12-31 | 69 |  | Bottom-up
A in MTEP12 | A | West | ITCM | 3631 | 2011-12-13 | RockCrk-MillCrk | Rock Creek to Mill Creek 69 kV Rebuild | Rebuild the ~5 mile line section to T2-477 ACSR | IA | IA | Other |  | Reliability | 2500000 | 2017-12-31 | 2017-12-31 | 69 |  | Bottom-up
A in MTEP12 | A | West | ITCM | 3632 | 2011-12-13 | Arnold 161 | Arnold 161kV Bus Upgrades | Move the Arnold-Hiawatha 161 kV line terminal to a new terminal position next to the Arnold-6th Street 161 kV line by adding 2 new 161 kV breakers. | IA | IA | BaseRel |  |  | 2400000 | 2017-12-31 | 2017-12-31 | 161 |  | Bottom-up
A in MTEP12 | A | West | ITCM | 3638 | 2011-12-13 | Corydon Sub Rbld | Corydon 69 kV Sub Rebuild | Complete rebuild of the substation with all new equipment. | IA | IA | Other |  | Condition | 5129204 | 2017-12-31 | 2017-12-31 | 69 |  | Bottom-up
A in MTEP12 | A | West | ITCM | 3639 | 2011-12-13 | Chariton Sub Rbld | Chariton 69 kV Sub Rebuild | Complete rebuild of the substation with all new equipment. | IA | IA | Other |  | Condition | 7683367 | 2016-09-02 | 2016-09-02 | 69 |  | Bottom-up
A in MTEP12 | A | West | ITCM | 3640 | 2011-12-13 | Belmond-Meservey | Belmond-Meservey | Rebuild the 4.65 mile section old line to new T2-4/0 ACSR. | IA | IA | Other |  | Condition | 1627500 | 2018-12-31 | 2018-12-31 | 69 |  | Bottom-up
A in MTEP12 | A | West | ITCM | 3643 | 2011-12-13 | Osceola-Woodburn | Osceola Rec. to Woodburn Jct. 69 kV Rebuild | Rebuild the 5.5 mile section old line to new T2-4/0 ACSR. | IA | IA | Other |  | Condition | 1950000 | 2022-12-31 | 2022-12-31 | 69 |  | Bottom-up
A in MTEP12 | A | West | ITCM | 3644 | 2011-12-13 | Knoxville-Lucas | Knoxville to Lucas County 69 kV Rebuild | Rebuild 10.6 miles of old line to new T2-4/0 ASCR. | IA | IA | Other |  | Condition | 3750000 | 2021-12-31 | 2021-12-31 | 69 |  | Bottom-up
A in MTEP12 | A | West | ITCM | 3645 | 2011-12-13 | Tirboji-Orleans Tap | Triboji 6750 (Oleans Tap) 69 kV Rebuild | Rebuild ~9.5 miles of old line to new T2-4/0 ASCR. | IA | IA | Other |  | Condition | 3350000 | 2017-12-31 | 2017-12-31 | 69 |  | Bottom-up
A in MTEP12 | A | West | ITCM | 3647 | 2011-12-13 | East IA Rebuilds | Eastern Iowa Project Rebuilds | Rebuild the 34.5 kV line sections to 69 kV construction and operate at 34.5 kV until conversion. | IA | IA | Other |  | Condition | 18900000 | 2013-06-10 | 2021-12-31 | 34 |  | Bottom-up
A in MTEP12 | A | West | ITCM | 3648 | 2011-12-13 | Marshalltown-Grand Jct | Marshalltown-Grand Junction Area Conversion | Rebuild the 34.5 kV line sections to 69 kV construction and operate at 34.5 kV until conversion. | IA | IA | Other |  | Condition | 10300000 | 2013-07-19 | 2019-12-31 | 34 |  | Bottom-up
A in MTEP12 | A | West | ITCM | 3649 | 2011-12-13 | Plaza LI | Plaza Interconnection | The Marshalltown ? Timber Creek 161 kV line will be tapped in & out of the new Plaza substation, with line terminals including breakers and a bus tie breaker. | IA | IA | Other |  | Distribution | 1750000 | 2020-12-31 | 2020-12-31 | 161 |  | Bottom-up
A in MTEP12 | A | West | MEC | 3710 | 2014-03-31 | T3094 | Norwalk 161-33 kV transformer | Add 33 MVA 161-13 kV transformer at existing substation | IA | IA | Other |  | Distribution | 886413 | 2021-07-01 | 2021-07-01 | 161 | 13.2 | Bottom-up
A in MTEP12 | A | West | XEL | 3769 | 2011-12-13 | Mankato - Twin Cities through flow mitigation | Mankato - Twin Cities through flow mitigation | Re-build 13 miles of 69 kV line from Carver County substation to Arlington to 477 ACSR conductor and Install 5.4 MVAR capacitor at Crystal Foods substation along with Auto transfer switch. | MN | MN | Other |  | Reliability | 4155551 | 2019-03-01 | 2019-03-01 | 69 |  | Bottom-up
A in MTEP12 | A | West | XEL | 3775 | 2011-12-13 | Couderay - Osprey 161 kV line | Couderay - Osprey 161 kV line | This project will continue the 161 kV connection from Stone Lake - Couderay (Radisson) on to Osprey. This is needed to supply power to the eastern 115 kV line running between Bayfront - Ironwood - Chippewa falls during low hydro conditions. There will be a new 161/115 kV connection at Osprey | WI | WI | BaseRel |  |  | 7000000 | 2015-06-03 | 2017-01-27 | 161 | 115 | Bottom-up
A in MTEP12 | A | West | XEL | 3797 | 2012-01-07 | Maple River - Red River 2nd 115 kV circuit | Maple River - Red River 2nd 115 kV line | build 5 miles of new 115 kV circuit between Maple River and Red River substations | ND | ND | Other |  | Reliability | 15619485 | 2017-10-31 | 2017-12-22 | 115 |  | Bottom-up
A in MTEP13 | A | Central | AmerenIL | 2302 | 2013-02-25 |  | Madison Industrial-Madison State Street 138 kV | Reconductor 2.35 miles of 795 kcmil SAC conductor to 1200 A summer emergency capability | IL | IL | BaseRel |  |  | 1637000 | 2016-12-01 | 2016-12-01 | 138 |  | Bottom-up
A in MTEP13 | A | Central | AmerenIL | 4272 | 2012-11-09 |  | Grand Tower-Makanda 138 kV Line Rebuild | Rebuild 16.91 miles of existing 556 kcmil ACSR conductor with conductor capable of carrying 1200 A under summer emergency conditions. | IL | IL | Other |  | Condition |  | 2016-12-01 | 2016-12-01 | 138 |  | Bottom-up
A in MTEP13 | A | Central | CWLP | 4270 | 2012-11-19 | NAuburn-CthmMain 138 | N Auburn-Chatham Main 138 kV Reconductor | Reconductor N Auburn- Chatham Main 138 kV Line to 795 ACSS | IL | IL | BaseRel |  |  | 130000 | 2014-06-01 | 2014-06-01 | 138 | 138 | Bottom-up
A in MTEP13 | A | Central | DEI | 4029 | 2012-09-12 | AMIN0705 | Sylvania to Yedo 6935 Rebuild | Rebuild radial tap in the 6935 ckt from Sylvania to Kingman to Yedo with 477acsr @ 100C and upgrade Kingman line switches (2) to 1200A. | IN | IN | Other |  | Reliability | 2770000 | 2016-12-31 | 2016-12-31 | 69 |  | Bottom-up
A in MTEP13 | A | Central | DEI | 4030 | 2012-09-12 | AMIN0706 | Cayuga 69 to Gessie Jct 6936 Rebuild | Rebuild 6936 ckt from Cayuga 69 sub towards Gessie Jct. (str. 804-2501) with 477acsr @ 100C | IN | IN | Other |  | Reliability | 3100000 | 2016-12-31 | 2016-12-31 | 69 |  | Bottom-up
A in MTEP13 | A | Central | DEI | 4032 | 2012-09-12 | AMIN0744 | Five Points 230kV Station Upgrade Phase I | Five Points Station Upgrade Phase I ? Install new prefabricated control building. Replace 230kV breakers and relays. Replace 230kV circuit switchers with 230kV breakers. Replace 230-138kV bank protection. Replace 230kV bus protection. | IN | IN | Other |  | Reliability | 5406000 | 2017-12-31 | 2017-12-31 | 230 | 138 | Bottom-up
A in MTEP13 | A | Central | DEI | 4033 | 2016-01-14 | AMIN0758 | Camp Atterbury to Edinburg 6950 Rebuild | Camp Atterbury to Edinburg 6950 Reconductor 2/0 Cu (4.0 miles) to 477ACSR and uprate existing 477ACSR 80C to 477ACSR 100C (4.5 miles). | IN | IN | Other |  | Reliability | 1650765 | 2017-12-31 | 2017-12-31 | 69 |  | Bottom-up
A in MTEP13 | A | Central | DEI | 4037 | 2012-09-12 | AMIN0841 | Lafayette 230kV Ring Bus - Ph. 2 | Lafayette 230kV Sub Ring Bus - Phase 2, install two 230kV 40KIA breakers, support structures, bus and 954KCM jumpers to complete five-breaker - 230kV ring bus. Install three transformer protection schemes. | IN | IN | BaseRel |  |  | 1618000 | 2019-12-31 | 2019-12-31 | 230 |  | Bottom-up
A in MTEP13 | A | Central | IPL | 4724 | 2015-04-03 |  | Eagle Valley 138kV Substation - DPP J238 | J238 - 138kV - Generator interconnection substation - install four bay breaker and a half design substation for 725MW CCGT in Morgan County Indiana at the existing Pritchard Plant site. | IN | IN | GIP |  |  |  | 2016-04-16 | 2016-04-16 | 138 |  | Externally-Driven
A in MTEP13 | A | East | ITCT | 1550 | 2016-03-23 | ITC_12_012 | Sunset to Hager Underground 120 kV Rebuild | Replace the 0.08 miles of underground 1500 KCM CU XLPE SSC 120 kV conductor from the Hager to Sunset 120 kV circuit with 5000 KCM CU XLPE 120 kV conductor. Also address clearance issues causing the sag limit on the 954 ACSR overhead conductor portion of this circuit | MI | MI | BaseRel |  |  | 2200000 | 2016-12-31 | 2016-12-31 | 120 |  | Bottom-up
A in MTEP13 | A | East | ITCT | 3938 | 2016-04-22 | ITCT_12_008 | Greenwood 120 kV Capacitors | Install two 120kV, 26 Mvar capacitors capacitor banks at the Greenwood substation with 2 synchronous breakers and a 120 kV line breaker. | MI | MI | BaseRel |  |  | 2020000 | 2017-07-15 | 2017-07-15 | 120 |  | Bottom-up
A in MTEP13 | A | East | ITCT | 4145 | 2016-03-23 | ITC_12_009 | Quaker to Southfield (CTL18-2) 120 kV Underground Rebuild | Reconductor the 0.36 mile Quaker to Southfield Underground cable section using 5000 KCM CU XLPE cable. | MI | MI | BaseRel |  |  | 3960000 | 2016-12-31 | 2016-12-31 | 120 |  | Bottom-up
A in MTEP13 | A | East | ITCT | 4153 | 2015-06-29 | ITC_13_021 | Toll Road + SVC | Relocate all ITCTransmission circuits at the Fermi 120 kV switchyard to a new station nearby (Toll Road station). This station would be configured as a breaker-and-a-half scheme. Create three feeds from Toll Road to the Fermi 120 kV switchyard. Install a 100 MVAR Static VAR Compensator at Toll Road. | MI | MI | BaseRel |  |  | 40000000 | 2017-12-31 | 2018-12-31 | 120 |  | Bottom-up
A in MTEP13 | A | East | ITCT | 4159 | 2014-01-31 | ITC-008 | ITCT Annual Wood Pole Replacement Program 2016 | Replace aging wood poles with concrete poles or steel towers. | MI | MI | Other |  | Condition | 8500000 | 2016-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | East | ITCT | 4163 | 2014-01-31 | ITC-010 | ITCT Annual Surge Arrestor Replacement Program 2016 | Replace old Silicon Carbide and Gap-type surge arresters with the new MOV gapless type ones in substations. | MI | MI | BaseRel |  |  | 360000 | 2016-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | East | ITCT | 4171 | 2014-01-31 | ITC-014 | ITCT Annual Misc Line Equipment Replacement Program 2016 | Replace cross arms that need to be replaced to maintain lines in serviceable conditions. Replace defective and damaged insulators for system reliability. Replace defective pole guying for system reliability or to meet code issues. | MI | MI | Other |  | Condition | 5000000 | 2016-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | East | ITCT | 4175 | 2016-08-30 | ITC-015 | ITCT Pole Top Switch Additions/Replacement Program 2014 | Installing, or replacing as appropriate, pole-top switches at tap points of circuits will provide the operational flexibility to sectionalize parts of the line to isolate faults or perform maintenance work on it without having to shut down the entire circuit. | MI | MI | Other |  | Reliability | 2400000 | 2014-10-15 | 2016-12-31 | 120 |  | Bottom-up
A in MTEP13 | A | East | ITCT | 4176 | 2016-08-30 | ITC-016 | ITCT Pole Top Switch Additions/Replacement Program 2015 | Installing, or replacing as appropriate, pole-top switches at tap points of circuits will provide the operational flexibility to sectionalize parts of the line to isolate faults or perform maintenance work on it without having to shut down the entire circuit. | MI | MI | Other |  | Reliability | 2400000 | 2015-12-31 | 2016-12-31 | 120 |  | Bottom-up
A in MTEP13 | A | East | ITCT | 4177 | 2016-08-30 | ITC-017 | ITCT Pole Top Switch Additions/Replacement Program 2016 | Installing, or replacing as appropriate, pole-top switches at tap points of circuits will provide the operational flexibility to sectionalize parts of the line to isolate faults or perform maintenance work on it without having to shut down the entire circuit. | MI | MI | Other |  | Reliability | 2400000 | 2016-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | East | ITCT | 4181 | 2014-01-31 | ITC-019 | ITCT Instrument Transformer Replacement 2016 | Replace the aging potential devices including potential transformers and coupling-capacitor type potential devices. | MI | MI | Other |  | Condition | 360000 | 2016-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | East | ITCT | 4187 | 2014-01-31 | ITC-022 | ITCT Annual NERC Protection Compliance Program 2016 | Upgrade relay throughout system. | MI | MI | Other |  | Condition | 2400000 | 2016-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | East | ITCT | 4191 | 2014-01-31 | ITC-024 | ITCT Annual Breaker Replacement Program 2016 | Replace defective breakers throughout system | MI | MI | Other |  | Condition | 6250000 | 2016-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | East | ITCT | 4195 | 2014-01-31 | ITC-026 | ITCT Annual Battery Replacement Program 2016 | Replace battery chargers with the new ones. | MI | MI | Other |  | Condition | 200000 | 2016-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | East | ITCT | 4199 | 2014-01-31 | ITC-31 | ITCT Disconnect Switch Replacement Program 2016 | Replace problematic Pennsylvania Type A6A-2, EEE, RI&E, WESTINGHOUSE, HK-PORTER, AND DELTA-STAR disconnect switches (or any disconnect switches with problematic auxiliary latch assemblies) | MI | MI | Other |  | Condition | 400000 | 2016-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | East | ITCT | 4204 | 2014-01-31 | ITC-028 | ITCT Annual Relay Betterment Program 2016 | Annual relay betterment program | MI | MI | Other |  | Condition | 10400000 | 2016-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | East | ITCT | 4286 | 2015-04-03 | ITC_12_015 | Henry Ford Substation | Loop in the Frisbie ? Waterman 120 kV underground cable to feed the Henry Ford substation. Splices and terminals will be installed and underground cable run from the existing line to the new substation. The substation is located approximated 150 feet fro | MI | MI | Other |  | Distribution | 5000000 | 2018-05-31 | 2018-05-31 | 120 |  | Bottom-up
A in MTEP13 | A | East | ITCT | 4287 | 2016-08-15 | ITC_12_034 | Hilton Road (formerly Ferndale) Substation | Loop either the Lincoln - Northeast 120 kV or the Lincoln ? Northeast ? Northwest 120 kV circuit to feed the new Hilton substation. The substation is located adjacent to the circuit. At the new station, 3-120 kV breakers and the associated 120 kV stat | MI | MI | Other |  | Reliability | 3800000 | 2017-03-31 | 2017-03-31 | 120 |  | Bottom-up
A in MTEP13 | A | East | METC | 4143 | 2016-03-22 | METC_12_017 | Verona - Marshall 138kV (Verona pos 388) Station Equipment Upgrade | Terminal Equipment upgrade at Verona 138 kV | MI | MI | Other |  | Reliability | 80000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP13 | A | East | METC | 4146 | 2016-07-14 | METC_12_023 | Marshall - Blackstone 138kV Rebuild | Rebuild 34.5 miles of the Marshall-Blackstone 138kV circuit utilizing single circuit 138kV structures and 954 ACSR conductor. | MI | MI | Other |  | Condition | 46300000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP13 | A | East | METC | 4147 | 2016-02-22 | METC_12_024 | Battle Creek - Island Road 138kV Rebuild | Rebuild 23.9 miles of the Battle Creek ? Island Road 138kV circuit utilizing single circuit 138kV structures and 954 ACSR conductor. | MI | MI | Other |  | Condition | 24300000 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
A in MTEP13 | A | East | METC | 4149 | 2015-12-28 | METC_12_026 | Argenta - Tallmadge 345kV Sag Remediation | Remediate sag on the Argenta ? Tallmadge 345kV line to bring its thermal rating up to 2422 Amp (1447 MVA) | MI | MI | BaseRel |  |  | 1500000 | 2016-06-30 | 2016-06-30 | 345 |  | Bottom-up
A in MTEP13 | A | East | METC | 4150 | 2016-03-22 | METC_12_014 | Verona-Argenta 138kV (Verona pos 277) Terminal Equipment Upgrade | Upgrade station equipment at Verona. | MI | MI | BaseRel |  |  | 140000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP13 | A | East | METC | 4157 | 2013-09-13 | METC-009 | METC Annual Wood Pole Replacement Program 2016 | Replace defective and aging wood poles with concrete poles or steel poles. | MI | MI | Other |  | Condition | 9000000 | 2016-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | East | METC | 4161 | 2012-09-14 | METC-011 | METC Annual Surge Arrestor Replacement Program 2016 | Replace old Silicon Carbide and Gap-type surge arresters with the new MOV gapless type ones in substations. | MI | MI | Other |  | Condition | 360000 | 2016-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | East | METC | 4167 | 2013-09-13 | METC-015 | METC Annual Misc Line Equipment Replacement Program 2016 | Replace cross arms that need to be replaced to maintain lines in serviceable conditions. Replace defective and damaged insulators for system reliability. Replace defective pole guying for system reliability or to meet code issues. | MI | MI | Other |  | Condition | 6000000 | 2016-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | East | METC | 4174 | 2016-08-30 | METC-018 | METC Pole Top Switch Additions/Replacement Program 2016 | Installing, or replacing as appropriate, pole-top switches at tap points of circuits will provide the operational flexibility to sectionalize parts of the line to isolate faults or perform maintenance work on it without having to shut down the entire circuit. | MI | MI | Other |  | Reliability | 3600000 | 2016-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | East | METC | 4179 | 2013-09-13 | METC-020 | METC Instrument Transformer Replacement - Year 2016 | Replace the aging instrument transformers including potential transformers and coupling-capacitor type instrument transformers. | MI | MI | Other |  | Condition | 360000 | 2016-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | East | METC | 4184 | 2012-09-14 | METC-023 | METC Annual NERC Protection Compliance Program 2016 | Upgrade relay throughout system. | MI | MI | Other |  | Condition | 2400000 | 2016-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | East | METC | 4189 | 2012-09-14 | METC-025 | METC Annual Breaker Replacement Program 2016 | Replace defective breakers throughout system | MI | MI | Other |  | Condition | 9000000 | 2016-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | East | METC | 4193 | 2013-09-13 | METC-027 | METC Annual Battery Replacement Program 2016 | Replace battery chargers with new ones. | MI | MI | Other |  | Condition | 120000 | 2016-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | East | METC | 4203 | 2013-06-13 | METC-033 | METC Disconnect Switch Replacement Program 2016 | Replace problematic Pennsylvania Type A6A-2, EEE, RI&E, WESTINGHOUSE, HK-PORTER, AND DELTA-STAR disconnect switches (or any disconnect switches with problematic auxiliary latch assemblies) | MI | MI | Other |  | Condition | 900000 | 2016-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | East | METC | 4205 | 2012-09-14 | METC-029 | METC Annual Relay Betterment Program 2016 | Annual relay betterment program | MI | MI | Other |  | Condition | 7000000 | 2016-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | East | METC | 4207 | 2016-08-30 | METC-031 | METC Annual Power Plant Control Relocation Program 2016 | Replace controls for METC substations that currently exist in power plant buildings. Locate new controls in dedicated METC control houses. | MI | MI | Other |  | Relocation | 2400000 | 2016-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | East | METC | 4218 | 2015-12-28 | METC_12_027 | Bass Creek - Black River 138kV Sag Remediation | Remediate the sag limit on the Bass Creek - Black river 138kV line up its conductor rating of 208 MVA (871 A) | MI | MI | BaseRel |  |  | 180000 | 2016-06-30 | 2016-06-30 | 138 |  | Bottom-up
A in MTEP13 | A | East | WPSC | 4084 | 2015-04-03 | NS-VB | North Shade to Vestaburg | North Shade to Vestaburg Rebuild | MI | MI | Other |  | Condition | 10000000 | 2018-12-31 | 2018-12-31 | 69 |  | Bottom-up
A in MTEP13 | A | East | WPSC | 4085 | 2015-04-03 | LC-FNX | Lake County to Fountain Junction | Lake County to Fountain Junction Rebuild | MI | MI | Other |  | Reliability | 3100000 | 2016-12-31 | 2016-12-31 | 69 |  | Bottom-up
A in MTEP13 | A | West | ATC | 3813 | 2014-01-31 | PR04982,F3654 | Rebuild Dam Heights-Portage 69 kV | Reconductor the entire Dam Heights-Portage 69 kV line with T2-4/0 ACSR conductor | WI | WI | Other |  | Condition | 33700000 | 2017-12-31 | 2017-12-31 | 69 |  | Bottom-up
A in MTEP13 | A | West | ATC | 3817 | 2016-01-11 | PR04856 | Install Shoto 138 kV breaker | Shoto 138/69 kV transformer highside breaker additions | WI | WI | Other |  | Relaying | 4325000 | 2017-12-01 | 2017-12-01 | 138 |  | Bottom-up
A in MTEP13 | A | West | ATC | 3841 | 2014-01-31 | PR05179,F3680,F3681 | Convert Pulliam-Glory Rd 69 kV | Convert Pulliam-Glory Road 69 kV Line to 138 kV | WI | WI | Other |  | Reliability | 22675655 | 2016-03-01 | 2016-12-01 | 138 | 69 | Bottom-up
A in MTEP13 | A | West | ATC | 3892 | 2013-02-18 | PR05233 | Rebuild Stagecoach-Wick Drive 69 kV | Reconductor Stagecoach-Black Rock 69 kV; transfer the existing conductor to rebuild Black Earth-Wick Drive 69 kV. | WI | WI | Other |  | Reliability | 3500000 | 2017-01-01 | 2017-01-01 | 69 |  | Bottom-up
A in MTEP13 | A | West | ATC | 3895 | 2014-01-31 | PR04860,F4003,WO069303 | Reconductor Oak Creek-Kansas 138 kV | Reconductor Oak Creek-Ramsey-Kansas 138 kV line | WI | WI | Other |  | Reliability | 830000 | 2016-06-01 | 2016-06-01 | 138 |  | Bottom-up
A in MTEP13 | A | West | GRE | 4008 | 2014-09-15 | 201610 | New Market & Cleary Lake Area Projects | The New Market & Cleary Lake Area project, a joint project between NSP and GRE, consists of rebuilding existing transmission lines and constructing new 69 kV transmission lines. The 69 kV line rebuilds and new constructions are to 115 kV standard for future 115 kV operation. | MN | MN | BaseRel |  |  | 200000 | 2015-12-15 | 2016-08-31 | 69 |  | Bottom-up
A in MTEP13 | A | West | GRE | 4009 | 2012-09-11 | 20462 | St. Boni Second 115/69 kV Substation Improvements | Install second 115/69 kV transformer at St. Boni including modifictions on the 115 and 69 kV buses for additional breakers | MN | MN | Other |  | Reliability | 10185577.27 | 2017-02-06 | 2017-02-06 | 115 | 69 | Bottom-up
A in MTEP13 | A | West | GRE, MP | 3531 | 2015-08-10 | Deer River | Zemple (formerly Deer River) Substation | New 230/115 kV Substation | MN | MN | BaseRel |  |  | 17404002 | 2015-03-31 | 2016-11-08 | 230 | 23 | Bottom-up
A in MTEP13 | A | West | ITCM | 4099 | 2012-09-14 | AleaW-SBroadway | Albert Lea Westside-South Broadway 69kV Rebuild | Rebuild approximately 2 miles of the Albert Lea Westside-South Broadway 69kV line to T2-4/0 capacity. | MN | MN | Other |  | Condition | 840000 | 2021-12-31 | 2021-12-31 | 69 | 69 | Bottom-up
A in MTEP13 | A | West | ITCM | 4101 | 2012-09-14 | Montgomery-Waseca | Montgomery-Waseca Jct 69kV Rebuild | Rebuild the ~29.5 mile Montgomery-French Lake Tap-Waseca Jct 69kV line to T2-4/0. | MN | MN | Other |  | Condition | 26137683 | 2016-12-31 | 2020-12-31 | 69 | 69 | Bottom-up
A in MTEP13 | A | West | ITCM | 4102 | 2012-09-14 | Columbus Jct-Newport | Columbus Jct-Newport 69kV Rebuild | Rebuild the ~19 mile Columbus Jct-IBP Tap-Winfield Tap-Cairo REC-Newport 69kV line to T2-4/0. | IA | IA | Other |  | Condition | 13798885 | 2021-12-31 | 2021-12-31 | 69 | 69 | Bottom-up
A in MTEP13 | A | West | ITCM | 4103 | 2012-09-14 | NBurl-Mediapolis | North Burlington-Mediapolis 69kV Rebuild | Rebuild the ~6.4 mile North Burlington-North Burlington Tap 69kV line to T2-4/0. | IA | IA | Other |  | Reliability | 5760000 | 2016-09-01 | 2016-09-01 | 69 | 69 | Bottom-up
A in MTEP13 | A | West | ITCM | 4104 | 2012-09-14 | Lansing-Monona | Lansing-Monona 69kV Rebuild | Rebuild the ~25 mile Lansing-Harper's Ferry Tap-Waterville Tap-Monona 69kV line to T2-4/0. | IA | IA | Other |  | Condition | 20975036 | 2020-12-31 | 2020-12-31 | 69 | 69 | Bottom-up
A in MTEP13 | A | West | ITCM | 4105 | 2012-09-14 | Decorah-Waukon | Decorah-Waukon 69kV Rebuild | Rebuild the ~23 mile Decorah-Ludlow Tap-Waukon 69kV line to T2-4/0. | IA | IA | Other |  | Condition | 9660000 | 2022-12-31 | 2022-12-31 | 69 | 69 | Bottom-up
A in MTEP13 | A | West | ITCM | 4106 | 2012-09-14 | Windsor-Richfield | Windsor-Richfield 69kV Rebuild | Rebuild the ~11.2 mile Windsor-Hawk Tap-Richfield 69kV line to T2-4/0. | IA | IA | Other |  | Condition | 4750000 | 2020-12-31 | 2020-12-31 | 69 | 69 | Bottom-up
A in MTEP13 | A | West | ITCM | 4107 | 2012-09-14 | Emery-Lehigh | Emery-Lehigh Tap 69kV Rebuild | Rebuild the ~4.5 mile Emery-Lehigh 69kV line to T2-4/0. | IA | IA | Other |  | Condition | 2295600 | 2017-08-04 | 2017-08-04 | 69 | 69 | Bottom-up
A in MTEP13 | A | West | ITCM | 4108 | 2012-09-14 | Ellendale-WOwatonna | Ellendale-West Owatonna 69kV Rebuild | Rebuild the ~13 mile Ellendale-West Owatonna 69kV line to T2-4/0. | MN | MN | Other |  | Condition | 7281277 | 2022-12-31 | 2022-12-31 | 69 | 69 | Bottom-up
A in MTEP13 | A | West | ITCM | 4113 | 2012-09-14 | Hayward TEQ | Hayward Breaker 665 Terminal Uprate | Upgrade 69kV terminal equipment on the Hayward breaker 665. | MN | MN | Other |  | Reliability | 15000 | 2015-04-30 | 2015-04-30 | 161 | 69 | Bottom-up
A in MTEP13 | A | West | ITCM | 4114 | 2012-09-14 | Triboji TEQ | Triboji Breaker 6730 Terminal Uprate | Upgrade 69kV terminal equipment on the Triboji breaker 6730 and change the CT ratio at Flying Cloud. | IA | IA | Other |  | Reliability | 20000 | 2015-04-30 | 2015-04-30 | 161 | 69 | Bottom-up
A in MTEP13 | A | West | ITCM | 4115 | 2012-09-14 | Fletcher Sub | New Fletcher 161/69kV Sub & Line Taps | Construct a new Fletcher 161/69kV sub next ot the Marsahalltown. Fletcher will be served from the new Marshalltown 161kV ring position. | IA | IA | Other |  | Condition | 7173600 | 2019-12-31 | 2019-12-31 | 161 | 69 | Bottom-up
A in MTEP13 | A | West | ITCM | 4116 | 2012-09-14 | East IA phase 2 | Eastern Iowa Phase 2 Rebuilds | Eastern Iowa Study Rebuild and Conversion Projects (Phase 2) ? Rebuild 34kV single CKT to DBL CKT 69kV for Marion ? Anamosa & Hiawatha ? Coggon ? Mt. Vernon ? Linn TWP REC New Line ? Linn TWP REC ? Cornell New Line ? Springville ? Amber 34kV Rebuild to 69kV ? Lovell REC Tap ? Monticello Industrial 34kV Rebuild to 69kV ? Hiawatha ? Echo Hill REC 69 kV Conversion | IA | IA | Other |  | Condition | 13150000 | 2014-03-14 | 2017-12-31 | 69 | 69 | Bottom-up
A in MTEP13 | A | West | ITCM | 4118 | 2012-09-14 | Grand Jct-Jeff WCC | Grand Junction-Jefferson WCC Rebuild | Rebuild ~7 miles of 34kV lines to 69kV consturction (operate at 34kV). | IA | IA | Other |  | Condition | 6117600 | 2017-12-25 | 2017-12-25 | 34 | 34 | Bottom-up
A in MTEP13 | A | West | ITCM | 4121 | 2012-09-14 | Cust Interconnet Blanket | Customer Interconnections with short lead time | These projects are being done at the request of an interconnection customer in order to facilitate new load, re-distribute existing load, improve the performance of the sub-transmission and distribution systems, or to accommodate a new Transmission-to-Transmission connection request. | IA,MN | IA,MN | Other |  | Distribution | 2000000 | 2013-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | West | ITCM | 4122 | 2012-09-14 | Misc Line Blanket | Annual Misc Line Equipment Replacement | Replace defective cross arms, damaged or defective line insulators, failed line arrestors, and damaged, defective or non-code compliant pole guys. | IA,MN | IA,MN | Other |  | Reliability | 4000000 | 2013-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | West | ITCM | 4123 | 2012-09-14 | Breaker Blanket | Breaker Replacement Program | Replace the breakers with new breakers. Prioritized replacement of breakers identified as high-maintenance or over-duty with modern technology circuit breakers should continue in order to improve the reliability of the transmission system. Adoption of this alternative is consistent with industry wide trend towards the use of low/no-maintenance SF6 gas puffer-style dead tank circuit breakers with built in bushing current transformers and very low SF6 gas emissions. | IA,MN | IA,MN | Other |  | Reliability | 5000000 | 2013-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | West | ITCM | 4124 | 2012-09-14 | Fiber Optic Blanket | Fiber Optic Static Wire Additions Project | Project includes the Engineering, Procurement, Construction and Commissioning of Fiber Optic Static Wire Additions for use with ITCM?s SCADA system and protective relaying. | IA,MN | IA,MN | Other |  | Metering | 720000 | 2014-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | West | ITCM | 4125 | 2012-09-14 | PCB Blanket | PCM Equipment Replacement Program | Replace the PCB equipment as other project work allows for outages. | IA,MN | IA,MN | Other |  | Reliability | 3600000 | 2013-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | West | ITCM | 4126 | 2012-09-14 | Pole Top Switch Blanket | Pole Top Switch Replacement Program | Annual program to replace pole top switches that are inoperable, unreliable, or that cannot be adequately adjusted. | IA,MN | IA,MN | Other |  | Reliability | 960000 | 2013-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | West | ITCM | 4127 | 2012-09-14 | Relay Blanket | Relay Betterment Program | Improve some of the existing relay protection systems and replace end-of-life relays with new microprocessor based replays. Add fiber optics to improve communication between stations where the previously installed pilot scheme is defective or is malfunctioning. | IA,MN | IA,MN | Other |  | Reliability | 2500000 | 2013-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | West | ITCM | 4128 | 2012-09-14 | SMART GRID Blanket | SMART GRID Project | Replace, upgrade, or install TELECOM, RTUs, Relay, etc. | IA,MN | IA,MN | Other |  | Metering | 4800000 | 2013-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | West | ITCM | 4129 | 2012-09-14 | Wood Pole Blanket | Wood Pole Replacement Program | Replace aging wood poles, cross arms, and pole guys with like-for-like poles and equipment. | IA,MN | IA,MN | Other |  | Condition | 3500000 | 2013-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP13 | A | West | ITCM, MEC | 3249 | 2014-03-31 | G5566, 32337 | NE 54th Ave.-Bondurant 161 kV line | New 161 kV line from NE 54th Ave. Substation to Bondurant Substation and associated substation equipment additions. | IA | IA | Other |  | Distribution | 11221895 | 2018-12-01 | 2018-12-01 | 161 |  | Bottom-up
A in MTEP13 | A | West | MEC | 2952 | 2016-09-16 | T3316 | NE 54th Ave. 161-13 kV Substation | Construct the NE 54th Ave. 161-13 kV Substation | IA | IA | Other |  | Distribution | 1300000 | 2018-06-01 | 2018-06-01 | 161 | 13 | Bottom-up
A in MTEP13 | A | West | MEC | 3248 | 2015-09-15 | G2705, 32335 | Rising Sun - NE 54th Ave. 161 kV Line | New 161 kV line from new Rising Sun Substation on DPS-Reasnor line to NE 54th Ave. and associated substation equipment additions. | IA | IA | Other |  | Distribution | 14036000 | 2018-05-01 | 2018-06-01 | 161 |  | Bottom-up
A in MTEP13 | A | West | MEC | 4256 | 2015-10-01 | G4251 | NW 70th Avenue Substation | New 161 kV line from Highways 141 and 44 Substation to NW 70 Avenue Sub to 100th and 54th Avenue Sub and new 161-13 kV 70th Avenue Substation | IA | IA | Other |  | Distribution | 9070000 | 2016-12-01 | 2016-12-01 | 161 | 13 | Bottom-up
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | NERC Facility Ratings Alert: Low Priority | Derates & physical mitigation on NERC "Low" priority lines | MN | MN | Other |  | Reliability | 44959385.29 | 2013-12-16 | 2016-12-31 | 161 |  | Bottom-up
A in MTEP13 | A | West | OTP | 3667 | 2012-09-28 | OTP | Nunda to Rutland 41.6 kV Line Rebuild | Rebuild 8 miles of 41.6 kV line | SD | SD | Other |  | Condition | 466000 | 2015-11-30 | 2015-11-30 | 41.6 | 41.6 | Bottom-up
A in MTEP13 | A | West | OTP | 4233 | 2016-09-21 | OTP | Parshall 41.6 kV Transformer | Replace 69/41.6 kV transformer at Parshall with a 10 MVA, 41.6/24 kV transformer | ND | ND | Other |  | Reliability | 500000 | 2017-05-01 | 2017-05-01 | 41.6 | 24 | Bottom-up
A in MTEP13 | A | West | XEL | 4224 | 2012-09-14 |  | Ironwood Switch Replacement | Replace aging in-line disconnect switches with new three-way GOAB switches outside Ironwood substation. Re-conductor .5 miles of Line W3607, .5 miles of W3628, .5 miles of W3631 | WI | WI | Other |  | Condition | 1150000 | 2015-12-15 | 2020-12-01 | 34.5 |  | Bottom-up
A in MTEP13 | A | West | XEL | 4305 | 2013-01-10 |  | SW MN High Voltage Mitigation | Install 1x25 MVAr switched reactor at Fenton and 1x25 MVAr switched reactor at Yankee | MN | MN | BaseRel |  |  | 8100000 | 2017-03-01 | 2019-06-01 | 115 |  | Bottom-up
A in MTEP13 | A | West | XEL | 4308 | 2013-01-10 |  | W3404 Cedar Falls - Menomonie 69 kV rebuild | Rebuilding 5 miles of 4/0 and 336 ACSR conductor between Cedar Falls-Menomonie 69 kV to 795 ACSR. Also, replacing bus work at Cedar Falls from 4/0 to 1590 AAC to increase the rating | WI | WI | Other |  | Reliability | 4087810 | 2016-12-31 | 2016-12-31 | 69 |  | Bottom-up
A in MTEP13 | A | West | XEL | 4314 | 2013-01-10 |  | Ashland - Ironwood 88 kV rebuild | Rebuild the 88 kV line between Bay Front - Saxon Pump - Norrie due to age and condition | WI,MI | WI | Other |  | Condition | 35977500 | 2021-12-01 | 2021-12-01 | 88 |  | Bottom-up
A in MTEP14 | A | Central | AmerenIL | 4076 | 2014-12-17 | AMRN32 | ADM-Peoria (Hiram) Project | ADM - Peoria - (Hiram Substation) - Build new 2.2 miles of 138 kV line wih 2000 A summer emergency capability. Reconnect deenergized 4.6 mile 138 kV line between Edwards Plant and Bartonville Substation. Add two new 138 kV, 2000 A PCBs at Edwards Plant. Relocate 138 kV lines outside Edwards Plant to make room for connecting the deenergized 138 kV line into Edwards Plant. Relocate 69 kV lines on one tower at Bartonville. | IL | IL | Other |  | Distribution | 6320000 | 2015-06-10 | 2017-06-01 | 138 |  | Bottom-up
A in MTEP14 | A | Central | AmerenIL | 4345 | 2015-01-09 |  | Gifford Substation 138 kV Ring Bus | Establish a new 138 kV, 3-breaker ring bus at the existing Rantoul Junction in the Paxton, East-Sidney-1 138 kV Line | IL | IL | Other |  | Reliability | 4775000 | 2019-05-22 | 2019-05-22 | 138 |  | Bottom-up
A in MTEP14 | A | Central | AmerenIL | 4471 | 2015-01-09 |  | Cahokia-Dupo Ferry-1 138 kV Line | Replace 6.98 miles of 2-300 kcmil Copper conductor with largest size conductor existing structures will carry. | IL | IL | Other |  | Condition | 10403000 | 2017-12-01 | 2017-12-01 | 138 |  | Bottom-up
A in MTEP14 | A | Central | AmerenIL | 4474 | 2015-01-09 | AMRN40 | LaSalle Tap (Hickok) 138 kV Breaker Station | Install new 3-position breaker station in the Hennepin-Oglesby-1556 138 kV line at the tap to LaSalle Air Products and North LaSalle Substations. 3-2000A PCBs needed. Upgrade terminal equipment to match line capability. | IL | IL | Other |  | Reliability | 4400032 | 2019-09-01 | 2019-09-01 | 138 |  | Bottom-up
A in MTEP14 | A | Central | AmerenIL | 4477 | 2015-01-09 | AMRN42 | Clayton Junction (Monument) 138 kV Breaker Station | Install 138 kV breaker station at Clayton Junction. Needed: 3-2000 A PCBs. | IL | IL | Other |  | Reliability | 4950000 | 2019-09-01 | 2019-09-01 | 138 |  | Bottom-up
A in MTEP14 | A | Central | AmerenIL | 4479 | 2015-01-09 |  | Ramsey, East 345 kV Ring Bus | Install 345 kV ring bus. Needed: 3-3000 A PCBs. | IL | IL | Other |  | Reliability | 6000000 | 2019-09-01 | 2019-09-01 | 345 |  | Bottom-up
A in MTEP14 | A | Central | AmerenIL | 4480 | 2015-01-09 |  | Oglesby 138 kV Substation - Rebuild | Rebuild Oglesby Substation. Utilize a breaker-and-a-half arrangement. | IL | IL | Other |  | Reliability | 14660550 | 2020-11-01 | 2020-11-01 | 138 |  | Bottom-up
A in MTEP14 | A | Central | AmerenIL | 4495 | 2015-01-09 | AMRN44 | Rivermines-Maries-1, Clark-Osage-2, Maries-Osage-1 138 kV Lline Rebuild | Rivermines-Maries-1, Clark-Osage-2, and Maries-Osage-1 138 kV Lines - Rebuild/reconductor 95 miles of 250 kcmil Copper in the Clark-Osage-2 138 kV line, 60 miles of 250 kcmil Copper in the Rivermines-Maries-1 138 kV line, and 34.3 miles of 250 kcmil Copper in the Maries-Osage-1 138 kV line with 556 kcmil ACSS conductor or equivalent. Note that this is a 95 mile double-circuit tower line. | MO | MO | Other |  | Reliability | 46500000 | 2016-12-01 | 2016-12-01 | 138 |  | Bottom-up
A in MTEP14 | A | Central | AmerenMO | 2993 | 2015-01-09 |  | Dupo Ferry-Buck Knob Reconductoring | Dupo Ferry-Buck Knob 138 kV Line - Replace 22 mi. of 2-300 ACSR with maximum size conductor existing towers will support. | MO | MO | Other |  | Condition | 31367940 | 2018-12-01 | 2018-12-01 | 138 |  | Bottom-up
A in MTEP14 | A | Central | AmerenMO | 4723 | 2015-01-09 |  | Kelso-Lutesville-1 345 kV Replace Structures | Replace 50% of structures (17.6 miles) to maintain at least a 100 degree C conductor temperature capability on this line. | MO | MO | Other |  | Condition | 8441336 | 2017-12-01 | 2017-12-01 | 345 |  | Bottom-up
A in MTEP14 | A | Central | DEI | 3545 | 2014-12-17 | AMIN0465 | Wabash Riv 138KV Gen Sta Phase II | Wabash Riv 138KV Gen Sta. Phase II (Bus #2 & Transfer Bus): Perform Line associated relay work. Repl. breakers: 138230-9, 13847 and DS Switches. Replace Bus Insulators. | IN | IN | Other |  | Condition | 1434000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP14 | A | Central | DEI | 3550 | 2016-08-03 | AMIN0499 | Martinsville 69kv Normally Open Loop | Construct approximately 1.5 mi of 69kv line to complete a normally open loop between Martinsville SE and Martinsville East distribution subs. | IN | IN | Other |  | Reliability | 1434000 | 2017-12-31 | 2017-12-31 | 69 |  | Bottom-up
A in MTEP14 | A | Central | DEI | 3556 | 2014-12-17 | AMIN0573 | Greenwood South 69kV Dist. Sub. | Build a new 69-12kV 22.4MVA sub in the 69102 line adjacent +/- to the existing HE Gilmore 69kv sub | IN | IN | Other |  | Distribution | 481000 | 2016-12-31 | 2016-12-31 | 69 | 12 | Bottom-up
A in MTEP14 | A | Central | DEI | 4368 | 2015-01-09 | AMIN0950 | Dresser - Wabash Riv. New 138kV Line | Build a new 138kV line from Dresser to Wabash River Gen. Station with 2000A terminal equipment and 954ACSS - 200C conductor; approx. 10 miles | IN | IN | BaseRel |  |  | 14500000 | 2017-03-31 | 2017-03-31 | 138 |  | Bottom-up
A in MTEP14 | A | Central | DEI | 4402 | 2015-01-09 | AMIN0133 | Huntington Riverfork to State St 69143 Reconductor | Huntington Riverfork to State St 69143 ckt: Reconductor 2.85 miles of 69kV transmission 2/0 Cu to 477 ACSR conductor. Begin about half mile east of Hunt Riv Fk sub at pole 823-6512 and continue to Hunt State St Sub 69kv bus. Also reconductor 4/0 ACSR river span. | IN | IN | Other |  | Reliability | 2520282 | 2016-12-31 | 2016-12-31 | 69 |  | Bottom-up
A in MTEP14 | A | Central | DEI | 4408 | 2015-01-09 | AMIN0837 | Huntington 138 to State St 69143 Reconductor | Reconductor 2.5 miles of the 69143 ckt from Huntington 138 sub to State St with 477ACSR @ 100C | IN | IN | Other |  | Reliability | 2600000 | 2016-12-30 | 2016-12-30 | 69 |  | Bottom-up
A in MTEP14 | A | Central | DEI | 4411 | 2015-01-09 | AMIN0863&4&5 | Bloomington 6991 Reconductor | Reconductor 13.7 miles of the 6991 ckt from Bloomington Dunn St sub to Bloomington 230 sub with 954ACSR @ 100C | IN | IN | Other |  | Reliability | 1843000 | 2014-07-16 | 2016-12-31 | 69 |  | Bottom-up
A in MTEP14 | A | Central | DEI | 4414 | 2015-01-09 | AMIN0885 | Wabash Chippewa 69 Alt Feed | New N.O. alternate 69kv feed from 69132 ckt over to Wabash Chippewa 69kv sub | IN | IN | Other |  | Reliability | 2244000 | 2016-12-31 | 2016-12-31 | 69 |  | Bottom-up
A in MTEP14 | A | Central | DEI | 4415 | 2015-01-09 | AMIN0890 | Veedersburg West 230-69kv Bk 2 addition | Veedersburg West: Add 75MVA 230/69 Bk 2 with LTC at Veedersburg West sub; add breaker to 69kV ring bus and tie in new bank; convert 230kV bus into 4-breaker ring | IN | IN | Other |  | Reliability | 3509000 | 2020-06-01 | 2020-06-01 | 230 | 69 | Bottom-up
A in MTEP14 | A | Central | DEI | 4417 | 2015-01-09 | AMIN0988 | Pumpkin Center 69KV Brk Repl | Pumpkin Center: Replace OCB 6952, OCB 69123, OCB 69230, (1) Ground Switch, (2) 230KV ABS and Motor Mechs, Lighting Arrestors, Line & Bus Pots, (7) 69KV Disconnect Switches and Station Service Transformer. Replace 230/69 Circuit Switcher with a 230KV Gas Circuit Breaker. | IN | IN | Other |  | Reliability | 2424000 | 2017-12-31 | 2017-12-31 | 69 |  | Bottom-up
A in MTEP14 | A | Central | DEI | 4418 | 2015-01-09 | AMIN1067&AMIN1316 | Hillsdale North 230-69 Sub | Construct new Hillsdale North 230-69kV substation to be inserted in the 23003 ckt with high and low side ring buses, 1-200MVA bank, 2-69kv line terminals. Loop the existing 6906 ckt through. Change Normal Operational status to Open between Hillsdale Sw. Sta. 69kV (250579) and Montezuma 69kV (250695). | IN | IN | Other |  | Reliability | 12300000 | 2017-06-01 | 2017-06-01 | 230 | 69 | Bottom-up
A in MTEP14 | A | Central | HE | 4714 | 2015-01-09 | 1052 Ratts 138/161 kV Transformer Upgrade | Ratts 138/161 kV Transformer Upgrade | New Transformer | IN | IN | Other |  | Reliability | 3500000 | 2014-05-15 | 2014-05-15 | 161 | 138 | Bottom-up
A in MTEP14 | A | Central | HE | 4715 | 2015-01-09 | 1052 Ratts 138 kV Transmission Upgrade | Ratts 138 kV Transmission line Upgrade | Upgrade Transmission line | IN | IN | Other |  | Reliability | 200000 | 2014-05-15 | 2014-05-15 | 138 |  | Bottom-up
A in MTEP14 | A | Central | PPI | 4434 | 2016-06-21 | 5 | Alsey 2nd 138 kV Tap to Ameren | Add 0.33 mile double circuit 138 kV line from Alsey-Ameren to sectionalize the Ameren 59 mile Jerseyville-Alsey-Meredosia line into a 35 mile Jerseyville-Alsey segment and a 24 mile Alsey-Meredosia segment. Add Alsey 138 kV breaker.. | IL | IL | Other |  | Reliability | 1039100 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP14 | A | East | ITCT | 4499 | 2016-08-15 | ITCT_14_010 | Tuscola 120 kV Capacitor | Install a 33.3 MVAR capacitor at the Tuscola 120 kV station | MI | MI | BaseRel |  |  | 1350000 | 2017-03-31 | 2017-03-31 | 120 |  | Bottom-up
A in MTEP14 | A | East | ITCT | 4500 | 2015-03-26 | ITCT_13_043 | Carrigan 120 kV Switching Station | Reconfigure the Lee - Menlo and Wabash - Yuma 120 kV circuits into a switching station named Carrigan. | MI | MI | BaseRel |  |  | 7380000 | 2017-12-31 | 2017-12-31 | 120 |  | Bottom-up
A in MTEP14 | A | East | ITCT | 4518 | 2015-04-08 | ITC_15_004 | Monroe 345/120 kV Transformer 304 Replacement | Replace the 345/120 kV Transformer 304 at Monroe. | MI | MI | Other |  | Reliability | 3800000 | 2017-04-01 | 2017-04-01 | 345 | 120 | Bottom-up
A in MTEP14 | A | East | ITCT | 4519 | 2015-11-13 | ITCT_13_018 | Custer - Monroe #2 120 kV & Monroe - Whiting 120 kV Circuits | Reconfigure the Custer ? Whiting 120 kV line into Monroe to create the Custer ? Monroe 2 120 kV and Monroe ? Whiting 120 kV lines. | MI | MI | Other |  | Reliability | 12300000 | 2040-04-01 | 2040-04-01 | 120 |  | Bottom-up
A in MTEP14 | A | East | ITCT | 4529 | 2015-03-26 | ITC_13_37 | Brownstown to Elm 230 kV Sag Remediation | Remediate the sag limit on the Brownstown to Elm 230kV line up to its conductor rating | MI | MI | Other |  | Reliability | 485000 | 2016-12-31 | 2016-12-31 | 230 |  | Bottom-up
A in MTEP14 | A | East | ITCT | 4530 | 2015-03-26 | ITC_13_38 | Brownstown to Navarre 230 kV Sag Remediation | Remediate the sag limit on the Brownstown to Navarre 230kV line up to a higher sag limit | MI | MI | Other |  | Reliability | 290000 | 2016-12-31 | 2016-12-31 | 230 |  | Bottom-up
A in MTEP14 | A | East | ITCT | 4531 | 2015-03-26 | ITC_13_39 | Dorset to Milan 120 kV Sag Remediation | Remediate the sag limit on the Dorset to Milan 120kV line up to its conductor rating | MI | MI | Other |  | Reliability | 225000 | 2016-12-31 | 2016-12-31 | 120 |  | Bottom-up
A in MTEP14 | A | East | ITCT | 4532 | 2015-03-26 | ITC_13_40 | Wayne to Hines 230 kV Sag Remediation | Remediate the sag limit on the Wayne to Hines 230kV line up to its conductor rating | MI | MI | Other |  | Reliability | 155000 | 2016-12-31 | 2016-12-31 | 230 |  | Bottom-up
A in MTEP14 | A | East | ITCT | 4566 | 2016-03-23 |  | ITCT Customer Interconnections - Year 2017 | Customer interconnection requests and retirements | MI | MI | Other |  | Distribution | 2000000 | 2017-12-31 | 2017-12-31 | 120 |  | Bottom-up
A in MTEP14 | A | East | ITCT | 4567 | 2016-03-23 |  | ITCT Customer Interconnections - Year 2018 | Customer interconnection requests and retirements | MI | MI | Other |  | Distribution | 2000000 | 2018-12-31 | 2018-12-31 | 120 |  | Bottom-up
A in MTEP14 | A | East | ITCT | 4573 | 2014-12-17 |  | ITCT Transformer Refurbishment Program 2016 | Replace leaking oil pumps and valves, transformer oil, surge arresters, and bushings. | MI | MI | Other |  | Condition | 600000 | 2016-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP14 | A | East | ITCT | 4584 | 2015-03-26 | ITC_13_029 | Trenton Channel 120 kV Bus 14 Second Independent Bus Protection | Install a second independent bus protection scheme on Trenton Channel 120 kV bus 14 so that three (3) phase to ground fault on the bus will be cleared within 5 cycles when the existing single bus protection scheme is shutdown. | MI | MI | Other |  | Reliability | 108000 | 2016-12-31 | 2016-12-31 | 120 |  | Bottom-up
A in MTEP14 | A | East | ITCT | 4585 | 2015-03-26 | ITC_13_030 | Trenton Channel 120 kV Bus 17 Second Independent Bus Protection | Install a second independent bus protection scheme on Trenton Channel 120 kV bus 17 so that a three (3) phase to ground fault on the bus will be cleared within 5 cycles when the existing single bus protection scheme is shutdown. | MI | MI | Other |  | Reliability | 360000 | 2016-12-31 | 2016-12-31 | 120 |  | Bottom-up
A in MTEP14 | A | East | ITCT | 4701 | 2014-12-17 |  | NERC Alert Facility Ratings for 2016 | Verify and remediate facilities as required due to the industry-wide NERC alert | MI | MI | Other |  | Reliability | 3600000 | 2016-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP14 | A | East | ITCT | 4737 | 2016-07-14 | ITC_13_026 & ITC_13_036 | Micah & Klam (Genesee County Pumping) 120kV Stations | Customer interconnection request to provide 120 kV service to two new substations serving Genesee County Pumping. Build 7.6 miles of new 954 ACSR on double circuit towers to feed the new substations. | MI | MI | Other |  | Distribution | 14090000 | 2015-12-11 | 2016-08-31 | 120 |  | Bottom-up
A in MTEP14 | A | East | METC | 1803 | 2016-02-22 | METC_13_041 | Plum-Stover 138 kV Rebuild | Rebuild the 8.8 mile 138 kV line to 954 ACSR and OPGW (Pre-build to 230 kV construction). | MI | MI | Other |  | Reliability | 10500000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP14 | A | East | METC | 4504 | 2015-03-27 | METC_13_047 | Vergennes - Marquette 138 kV Sag Remediation | Remediate the sag limit on the 795 ACSR from the Vergennes - Marquette 138 kV circuit up to the conductor limit. | MI | MI | Other |  | Reliability | 345000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP14 | A | East | METC | 4505 | 2014-12-17 | METC_13_048 | Bass Creek - Sternberg 138 kV Sag Remediation | Remediate the sag limits on the 336.4 and 266.8 ACSR portions of the Bass Creek - Sternberg 138 kV circuit. | MI | MI | Other |  | Reliability | 1200000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP14 | A | East | METC | 4521 | 2015-04-09 | METC_13_040 | Riggsville - Rondo 138 kV Sag Remediation | Remediate sag on the Riggsville - Rondo 138 kV section to bring its rating up to the conductor limit (174 MVA). | MI | MI | Other |  | Reliability | 324000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP14 | A | East | METC | 4522 | 2014-12-17 | METC_13_042 | Lawndale - Murphy 138 kV Rebuild | Rebuild the 3/0 Cu & 2/0 Cu 6-wire (1.188 mile) and 336 ACSR (1.713 mile) sections on the Lawndale ? Murphy 138 kV line to 954 ACSR. The 3/0 Cu & 2/0 Cu 6-wire section will be rebuilt on single-circuit steel poles while the 336 ACSR section will be rebui | MI | MI | Other |  | Reliability | 2800000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP14 | A | East | METC | 4537 | 2016-03-23 | METC-997 | METC Customer Interconnections - Year 2017 | Customer interconnection requests and retirements | MI | MI | Other |  | Distribution | 2500000 | 2017-12-31 | 2017-12-31 | 138 |  | Bottom-up
A in MTEP14 | A | East | METC | 4538 | 2016-03-23 | METC-996 | METC Customer Interconnections - Year 2018 | Customer interconnection requests and retirements | MI | MI | Other |  | Distribution | 2500000 | 2018-12-31 | 2018-12-31 | 138 |  | Bottom-up
A in MTEP14 | A | East | METC | 4539 | 2014-12-17 | METC-995 | METC Hemphill Control Relocation Project - Years 2015, 2016, 2017 | Replace METC relaying and controls at Hemphill Substation. Locate the new relaying and controls in a new dedicated METC control center. Install dedicated METC AC and DC systems. | MI | MI | Other |  | Relocation | 3640000 | 2017-12-31 | 2017-12-31 | 0 |  | Bottom-up
A in MTEP14 | A | East | METC | 4542 | 2014-12-17 | METC-990 | METC Morrow Control Relocation Project - Years 2015, 2016, 2017 | Replace METC relaying and controls at Morrow Substation. Locate the new relaying and controls in a new dedicated METC control center. Install dedicated METC AC and DC systems. | MI | MI | Other |  | Relocation | 3110000 | 2017-12-31 | 2017-12-31 | 0 |  | Bottom-up
A in MTEP14 | A | East | METC | 4546 | 2014-12-17 | METC-986 | METC Power Transformer Refurbishment Program - Year 2016 | Replace leaking oil pumps and valves, transformer oil, surge arresters, and bushings | MI | MI | Other |  | Condition | 600000 | 2016-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP14 | A | East | METC | 4555 | 2015-03-26 | METC_13_018 | Tippy to Stronach 138 kV Circuit Dual Pilot Relay Protection Installation | Install a dual pilot relay protection system on the Tippy to Stronach 138 kV circuit so that three (3) phase to ground faults will be cleared within 5 cycles. The Tippy 138 kV BK 177 bypassing will also be removed. | MI | MI | Other |  | Reliability | 575000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP14 | A | East | METC | 4556 | 2016-06-07 | METC_13_032 | Blackstone 138 kV Second Bus Protection and Independent Relay Component | Install a second bus relay scheme on Blackstone blue and white busses and install second independent relay components on Blackstone end of the Blackstone-Marshall 138 kV circuit, Blackstone-Tompkins 138 kV ckts #1 and #2 and Blackstone-Leoni 138 kV ckts # | MI | MI | Other |  | Reliability | 845000 | 2017-03-31 | 2017-03-31 | 138 |  | Bottom-up
A in MTEP14 | A | East | METC | 4557 | 2015-03-26 | METC_13_017 | Croton to Four Mile 138 kV Circuit Dual Pilot Relay Protection Installation | Add a dual pilot relay protection system on Croton to Four Mile 138 kV circuit so that 3 phase to ground faults on the circuit will be cleared within 5 cycles. | MI | MI | Other |  | Reliability | 483000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP14 | A | East | METC | 4558 | 2015-12-28 | METC_13_030 | Karn to Manning 138 kV Circuits - Dual Pilot Relay Protection Scheme | Install a dual pilot relay protection scheme on the Karn to Manning 138 kV circuit | MI | MI | Other |  | Reliability | 460000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP14 | A | East | METC | 4559 | 2015-12-28 | METC_13_031 | Karn to Saginaw River 138 kV Circuits - Dual Pilot Relay Protection Scheme | Install a dual pilot relay protection scheme on the Karn to Saginaw River 138 kV circuit | MI | MI | Other |  | Reliability | 575000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP14 | A | East | METC | 4699 | 2014-12-17 |  | METC NERC Alert Facility Ratings for 2016 | Verify and remediate facilities as required due to the industry-wide NERC alert | MI | MI | Other |  | Reliability | 11200000 | 2016-12-31 | 2016-12-31 | 0 |  | Bottom-up
A in MTEP14 | A | East | METC | 4814 | 2015-03-26 | METC_14_010 | Battle Creek to Morrow #1 138 kV Sag Remediation | Remediate the sag limit on the Battle Creek to Morrow #1 138 kV line up to the most limiting conductor. | MI | MI | Other |  | Reliability | 366000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP14 | A | East | METC | 4815 | 2015-04-03 | METC_14_011 | Verona to Foundry 138 kV Sag Remediation | Remediate the sag limit on the Verona - Foundry 138 kV line up to the most limiting conductor. | MI | MI | Other |  | Reliability | 815000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP14 | A | South | Entergy-AR | 4751 | 2014-12-17 | 14-EAI-020-8 | EAI Underrated Breaker Project: Jacksonville North 115 kV B3621-CBO | Upgrade breaker to increase short circuit interrupting capability | AR | AR | Other |  | Reliability | 279164 | 2016-12-01 | 2016-12-01 | 115 |  | Bottom-up
A in MTEP14 | A | South | Entergy-AR | 4755 | 2015-09-10 | 14-EAI-022-2 | EAI SPOF Projects: Modify relaying at ISES 500/161 kV | EAI SPOF Projects: Modify relaying at ISES 500/161 kV | AR | AR | Other |  | Reliability | 16215941 | 2017-06-01 | 2017-06-01 | 500 |  | Bottom-up
A in MTEP14 | A | South | Entergy-AR | 4756 | 2015-09-10 | 14-EAI-022-3 | EAI SPOF Projects: Modify relaying at Mabelvale 500 kV | EAI SPOF Projects: Modify relaying at Mabelvale 500 kV | AR | AR | Other |  | Relaying | 8013145 | 2016-12-30 | 2016-12-30 | 500 |  | Bottom-up
A in MTEP14 | A | South | Entergy-AR | 4757 | 2015-09-10 | 14-EAI-022-4 | EAI SPOF Projects: Modify relaying at El Dorado 500 kV | EAI SPOF Projects: Modify relaying at El Dorado 500 kV | AR | AR | Other |  | Relaying | 1000000 | 2018-06-01 | 2018-06-01 | 500 |  | Bottom-up
A in MTEP14 | A | South | Entergy-AR | 7761 | 2016-02-16 | 14-EAI-27 | Datto: Add 161 kV 24 MVAR Capacitor Bank | Install a new 24 MVAR 161 kV mobile temporary capacitor bank at the Datto station. Also the tap position of the 161/115 kV autotransformer at Datto will be changed from 156.975 kV to 161 kV for better reactive support to the the 115 kV network. | AR | AR | BaseRel |  |  | 1522059 | 2016-12-31 | 2016-12-31 | 161 |  | Bottom-up
A in MTEP14 | A | South | Entergy-AR | 8040 | 2015-09-10 | 14-EAI-028 | ANO - Mabelvale 500kV: Replace Substation Equipment | ANO - Mabelvale 500kV: Replace Substation Equipment | AR | AR | Other |  | Economic | 1809881 | 2018-06-01 | 2018-06-01 | 500 |  | Bottom-up
A in MTEP14 | A | South | Entergy-AR | 8041 | 2015-09-10 | 14-EAI-029 | ANO - Pleasant Hill 500kV: Replace Substation Equipment | ANO - Pleasant Hill 500kV: Replace Substation Equipment | AR | AR | Other |  | Economic | 1431807 | 2017-12-01 | 2017-12-01 | 500 |  | Bottom-up
A in MTEP14 | A | South | Entergy-LA | 4605 | 2015-07-30 | 14-EGL-017 | Crown Zellerbach Area: Construct new 230-138 kV substation on the Fancy Point to Waterloo 230 kV line | Construct a new 230-138 kV station along the existing Crown Zellerbach to Starhill Tap Point 138 kV line approximately 0.86 miles from Crown Zellerbach going toward Starhill Tap Point. Tap the Waterloo to Fancy Point 230 kV line approximately 2.0 miles from Fancy Point going toward Waterloo and extend the Waterloo to Fancy Point line with conductor rated at a minimum of 1956 A, 779 MVA from the tap point approximately 1.8 miles in-and-out of the 230 kV side of the new station. Install 300 MVA, 230-138 kV autotransformer. | LA | LA | BaseRel |  |  | 17190728 | 2017-09-01 | 2017-09-01 | 230 | 138 | Bottom-up
A in MTEP14 | A | South | Entergy-LA | 4761 | 2014-12-17 | 14-EGL-022-1 | EGSL SPOF Projects: Modify relaying at Willow Glen 500 kV | EGSL SPOF Projects: Modify relaying at Willow Glen 500 kV | LA | LA | Other |  | Relaying | 6003861 | 2018-04-25 | 2018-04-25 | 500 |  | Bottom-up
A in MTEP14 | A | South | Entergy-LA | 4762 | 2014-12-17 | 14-EGL-022-2 | EGSL SPOF Projects: Modify relaying at Fancy Point 500kV | EGSL SPOF Projects: Modify relaying at Fancy Point 500kV | LA | LA | Other |  | Relaying | 440111 | 2018-06-01 | 2018-06-01 | 500 |  | Bottom-up
A in MTEP14 | A | South | Entergy-LA | 4763 | 2014-12-17 | 14-EGL-024-1 | EGSL Underrated Breaker Project: Jaguar 69 kV 20940-CO | Upgrade breaker to increase short circuit interrupting capability | LA | LA | Other |  | Reliability | 970497 | 2016-12-31 | 2016-12-31 | 69 |  | Bottom-up
A in MTEP14 | A | South | Entergy-LA | 4764 | 2014-12-17 | 14-EGL-024-2 | EGSL Underrated Breaker Project: Jaguar 69 kV 20905-CO | Upgrade breaker to increase short circuit interrupting capability | LA | LA | Other |  | Reliability |  | 2016-12-31 | 2016-12-31 | 69 |  | Bottom-up
A in MTEP14 | A | South | Entergy-LA | 4765 | 2014-12-17 | 14-EGL-024-3 | EGSL Underrated Breaker Project: Blount 69 kV 14105-TC | Upgrade breaker to increase short circuit interrupting capability | LA | LA | Other |  | Reliability |  | 2016-12-31 | 2016-12-31 | 69 |  | Bottom-up
A in MTEP14 | A | South | Entergy-LA | 4769 | 2014-12-17 | 12-ELL-004 | Schriever: Construct new 230 kV substation | Construct new Schriever 230 kV Substation | LA | LA | Other |  | Distribution | 13443939 | 2017-03-31 | 2017-03-31 | 230 |  | Bottom-up
A in MTEP14 | A | South | Entergy-LA | 4770 | 2014-12-17 | 14-ELL-008-1 | ELL Underrated Breaker Project: Waterford 230 kV S7145-CO | Upgrade breaker to increase short circuit interrupting capability | LA | LA | Other |  | Reliability | 1082400 | 2016-12-31 | 2016-12-31 | 230 |  | Bottom-up
A in MTEP14 | A | South | Entergy-LA | 4771 | 2014-12-17 | 14-ELL-008-2 | ELL Underrated Breaker Project: Waterford 230 kV S7154-CO | Upgrade breaker to increase short circuit interrupting capability | LA | LA | Other |  | Reliability |  | 2016-12-31 | 2016-12-31 | 230 |  | Bottom-up
A in MTEP14 | A | South | Entergy-LA | 4773 | 2014-12-17 | 14-ELL-009-1 | ELL SPOF Projects: Modify relaying at Ninemile 230 kV | ELL SPOF Projects: Modify relaying at Ninemile 230 kV | LA | LA | Other |  | Relaying | 4036969 | 2017-03-01 | 2017-03-01 | 230 |  | Bottom-up
A in MTEP14 | A | South | Entergy-LA | 4774 | 2014-12-17 | 14-ELL-009-2 | ELL SPOF Projects: Modify relaying at Southport 230 kV | ELL SPOF Projects: Modify relaying at Southport 230 kV | LA | LA | Other |  | Relaying |  | 2017-04-01 | 2017-04-01 | 230 |  | Bottom-up
A in MTEP14 | A | South | Entergy-LA | 4775 | 2014-12-17 | 14-ELL-009-3 | ELL SPOF Projects: Modify relaying at Labarre 230 kV | ELL SPOF Projects: Modify relaying at Labarre 230 kV | LA | LA | Other |  | Relaying |  | 2017-06-01 | 2017-06-01 | 230 |  | Bottom-up
A in MTEP14 | A | South | Entergy-LA | 4776 | 2014-12-17 | 14-ELL-009-4 | ELL SPOF Projects: Modify relaying at Harrahan 230 kV | ELL SPOF Projects: Modify relaying at Harrahan 230 kV | LA | LA | Other |  | Relaying |  | 2017-02-01 | 2017-02-01 | 230 |  | Bottom-up
A in MTEP14 | A | South | Entergy-LA | 4778 | 2014-12-17 | 14-ENO-003-1 | ENOI SPOF Projects: Modify relaying at Market Street 230 kV | ENOI SPOF Projects: Modify relaying at Market Street 230 kV | LA | LA | Other |  | Relaying |  | 2016-11-01 | 2016-11-01 | 230 |  | Bottom-up
A in MTEP14 | A | South | Entergy-LA | 8284 | 2014-12-17 |  | Richardson to Iberville 230 kV line; Add second Coly 500/230 kV autotransformer; Bagatelle - Sorrento cut-in to Panama; Upgrade Wilton - Romeville 230 kV line | From MCPS study - Project substantially similar to PC-W: Tap the Bagatelle - Sorrento line into Panama substation; Upgrade line bay bus at Romeville substation; Construct line using 1780 ACSR ~ 11.0 mi. Add second 1200 MVA, 500-230 kV autotransformer at Coly | LA | LA | Other |  | Economic | 60196515 | 2016-07-16 | 2018-12-31 | 500 | 230 | Bottom-up
A in MTEP14 | A | South | Entergy-MS | 4614 | 2015-09-10 | 12-EMI-001 | Franklin - McComb build new 115 kV line (constructed to 230 kV) | Construct a new line from Franklin-McComb with a rating of at least 398MVA (double-bundled 954ACSR for reduced impedance). Construction of the line should meet 230kV specifications, but will be initially operated at 115kV | MS | MS | BaseRel |  |  | 33412348 | 2017-11-15 | 2017-11-15 | 115 | 115 | Bottom-up
A in MTEP14 | A | South | Entergy-MS | 4788 | 2014-12-17 | 14-EMI-008-3 | EMI Underrated Breaker Project: Rex Brown 115 kV J9732-CO | Upgrade breaker to increase short circuit interrupting capability | MS | MS | Other |  | Reliability |  | 2016-12-31 | 2016-12-31 | 115 |  | Bottom-up
A in MTEP14 | A | South | Entergy-MS | 4789 | 2014-12-17 | 14-EMI-008-4 | EMI Underrated Breaker Project: Rex Brown 115 kV J9742-CO | Upgrade breaker to increase short circuit interrupting capability | MS | MS | Other |  | Reliability |  | 2016-12-31 | 2016-12-31 | 115 |  | Bottom-up
A in MTEP14 | A | South | Entergy-MS | 4790 | 2014-12-17 | 14-EMI-008-5 | EMI Underrated Breaker Project: Rex Brown 115 kV J9743-CO | Upgrade breaker to increase short circuit interrupting capability | MS | MS | Other |  | Reliability |  | 2016-12-31 | 2016-12-31 | 115 |  | Bottom-up
A in MTEP14 | A | South | Entergy-MS | 4793 | 2014-12-17 | 14-EMI-008-8 | EMI Underrated Breaker Project: Greenville 115 kV J9940-CO | Upgrade breaker to increase short circuit interrupting capability | MS | MS | Other |  | Reliability |  | 2016-12-31 | 2016-12-31 | 115 |  | Bottom-up
A in MTEP14 | A | West | ATC | 1624 | 2014-12-17 | PR05259, F4004 | Uprate Portage-Trienda 138 kV | Increase clearance and uprate SS equipment | WI | WI | Other |  | Reliability | 2000000 | 2022-06-01 | 2022-06-01 | 138 |  | Bottom-up
A in MTEP14 | A | West | ATC | 1708 | 2014-12-17 | F2105, PRF5915 | Construct Fairwater-Mackford Prairie 69 kV line and upgrade area 69 kV | Construct Fairwater-Mackford Prairie 69 kV line, Reconfigure the North Randolph-Ripon 69 kV line to form a second Ripon-Metomen 69 kV line and retire the circuit between Metomen and the Mackford Prairie tap | WI | WI | Other |  | Reliability | 20400000 | 2017-01-01 | 2017-09-26 | 69 |  | Bottom-up
A in MTEP14 | A | West | ATC | 2031 | 2014-12-17 | PR03903, F1670 | Rebuild Colley Rd-Brick Church 69 kV | Rebuild Colley Rd-Brick Church 69 kV (Y-32) | WI | WI | Other |  | Reliability | 36968500 | 2018-06-01 | 2018-06-01 | 69 |  | Bottom-up
A in MTEP14 | A | West | ATC | 2056 | 2014-12-17 | PR03226, F4000 | Uprate Oak Creek-Pennsylvania 138 kV | Uprate Oak Creek-Pennsylvania 138 kV | WI | WI | Other |  | Reliability | 4000000 | 2017-01-31 | 2017-01-31 | 138 |  | Bottom-up
A in MTEP14 | A | West | ATC | 3096 | 2014-12-17 | PR04463, F3735 | Uprate Munising-Blaney Park 69 kV | Increase ground clearance for the Inland line Munising-Blaney Park 69 kV to 167 deg F (37 MVA) clearance | MI | MI | Other |  | Reliability | 13000000 | 2020-12-31 | 2020-12-31 | 69 |  | Bottom-up
A in MTEP14 | A | West | ATC | 3510 | 2016-09-15 | PR04651, F3421 | Rebuild Mukwonago-St Martins 138 kV | Rebuild Mukwonago-Edgewood-St. Martins 138 kV Line, includes replacing jumpers at Edgewood and Mukwonago | WI | WI | Other |  | Reliability | 23121000 | 2019-06-15 | 2019-06-15 | 138 |  | Bottom-up
A in MTEP14 | A | West | ATC | 3808 | 2014-12-17 | PR04505, F2570 | Construct Bain-Spring Valley-North Lake Geneva 138 kV | Reconductor Bain-Spring Valley 138; construct a 138/69 kV Geneva substation; construct a new Spring Valley-Geneva 138 kV line; construct a new Geneva-North Lake Geneva 138 kV line; construct Twin Lakes-Geneva 138 kV line; reconductor Katzenberg-Richm | WI | WI | Other |  | Reliability | 70546000 | 2019-06-01 | 2019-06-01 | 138 | 69 | Bottom-up
A in MTEP14 | A | West | ATC | 3890 | 2014-12-17 | PR05235, F4000 | Reconductor Port Washington-Saukville 138 kV 4 | Reconductor Port Washington-Saukville 138 kV line | WI | WI | Other |  | Reliability | 2284000 | 2021-12-31 | 2021-12-31 | 138 |  | Bottom-up
A in MTEP14 | A | West | ATC | 3891 | 2014-12-17 | PR05236, F4000 | Reconductor Port Washington-Saukville 138 kV 6 | Reconductor Port Washington-Saukville 138 kV line | WI | WI | Other |  | Reliability | 2843000 | 2021-12-31 | 2021-12-31 | 138 |  | Bottom-up
A in MTEP14 | A | West | ATC | 3900 | 2014-12-17 | PR05587, F4003 | Reconductor Bain-Albers 138 kV | Reconductor Bain-Albers 138 kV line | WI | WI | Other |  | Reliability | 1300000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP14 | A | West | ATC | 3904 | 2014-12-17 | PR05672, F4001 | Reconductor McCue-Lamar 69 kV | Reconductor McCue-Lamar 69 kV line | WI | WI | Other |  | Reliability | 3500000 | 2016-06-10 | 2016-06-10 | 69 |  | Bottom-up
A in MTEP14 | A | West | ATC | 4711 | 2014-12-17 | PR04967, F3654 | Rebuild Wautoma - Montello Tap (Y-17) 69kV line | Rebuild the 13.1 mile portion of Y-19 (WAU-A11 69 kV) with T2 4/0 Penguin. Rebuild the 6.1 mile portion of line Y-19 (A11-MOO 69 kV) with T2 4/0 Penguin. All structures used will allow operation to 200 deg F normal and 300 deg F emergency | WI | WI | Other |  | Condition | 13600000 | 2016-10-17 | 2016-10-17 | 69 |  | Bottom-up
A in MTEP14 | A | West | ATC | 4728 | 2014-12-17 | PR05988 | Reconfigure University 138 kV area | Reconfigure the University area lines of Whitewater - University (4453) 138kV line, Bluff Creek - University (6552) 138kV line and Mukwonago - Whitewater (77353) 138kV line into new lines of Whitewater - University (4453A) 138kV line, Mukwonago - Universi | WI | WI | Other |  | Reliability | 5075000 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
A in MTEP14 | A | West | ATC | 4731 | 2014-12-17 | PR06093 | Rebuild Horicon 69 kV Bus | Replace the 4/0 Copper Main Strin Bus, Jumpers and lugs. In addition to the 336 ACSR Jumpers, 69 kV station Post insulators and bus support clamps. This will increase the bus & bus jumper ratings that are currently limiters and raise the limit to that of | WI | WI | Other |  | Condition | 210000 | 2016-07-01 | 2016-07-01 | 69 |  | Bottom-up
A in MTEP14 | A | West | ATC | 4734 | 2014-12-17 | PR06137 | Construct Cedar Creek T-D Interconnection 115 kV | Construct a new 115kV substation tapping 115kV line T-20 between Weston and Dewey | WI | WI | Other |  | Distribution | 2000000 | 2015-04-29 | 2015-06-01 | 115 |  | Bottom-up
A in MTEP14 | A | West | CFU | 4588 | 2014-12-17 | Univ. | University Ave. Substation | New Substation with 161/69 kV transformer and 69kV line to serve the network 69kV system | IA | IA | Other |  | Reliability | 6934500 | 2017-04-01 | 2017-04-01 | 161 | 69 | Bottom-up
A in MTEP14 | A | West | CFU-PMEU | 4386 | 2015-11-03 | RRHP | RRHP - Pella W interconnection | Reconfiguration of Pella West 69 kV Substation to improve load serving reliability for City of Pella. Substation will be reconfigured from a line breaker to a ringbus scheme. | IA | IA | Other |  | Reliability | 2360335 | 2017-04-01 | 2017-04-01 | 69 |  | Bottom-up
A in MTEP14 | A | West | GRE | 2600 | 2014-12-17 | 20339 | Big Sandy (LCP) 4.0 mile, 69 kV line | Big Sandy (LCP) 4.0 mile, 69 kV line | MN | MN | Other |  | Distribution | 4239175 | 2016-09-23 | 2016-09-23 | 69 |  | Bottom-up
A in MTEP14 | A | West | GRE, XEL | 4379 | 2016-05-10 | 20451 | Quarry-West St. Cloud 115 kV line and West St. Cloud Breaker station | Build a 115 kV line from Quarry to the West St. Cloud substation and fully breaker the West St. Cloud substation | MN | MN | Other |  | Reliability | 9250000 | 2017-04-13 | 2017-04-13 | 115 |  | Bottom-up
A in MTEP14 | A | West | GRE-WMU | 4380 | 2015-01-09 | 202647 | Priam Substation | Move Willmar 115/69 kV transformer to new Priam substation location | MN | MN | Other |  | Reliability | 4000000 | 2019-05-01 | 2019-05-01 | 115 | 69 | Bottom-up
A in MTEP14 | A | West | ITCM | 4455 | 2014-12-17 | DAEC Tap Rebuild | DAEC Tap 3.32 miles Rebuild | Rebuild the 34kV operated line to 69kV standards. Continue to operate at 34kV. | IA | IA | Other |  | Condition | 2674264 | 2016-12-31 | 2016-12-31 | 34 |  | Bottom-up
A in MTEP14 | A | West | ITCM | 4456 | 2014-12-17 | East Nevada St | East Nevada Street Expansion | Install 69 kV bus and three breaker positions in the East Nevada St substation. Initially one breaker will be installed with the Timber Creek to East Nevada St line rebuild, and the remaining breakers will be installed closer to the 69 kV conversion | IA | IA | Other |  | Condition | 400000 | 2016-05-27 | 2020-12-31 | 34 |  | Bottom-up
A in MTEP14 | A | West | ITCM | 4459 | 2014-12-17 | East IA phase 3 | Eastern Iowa Rebuild & Conversion Plan Phase 3 | ITCM has worked with the stakeholders in the Eastern Iowa Study area to find a solution that is acceptable to everyone. A conversion plan was chosen that maximizes the number of miles of 34.5 kV lines that can be retired and gives the most substations lo | IA | IA | Other |  | Condition | 4440000 | 2015-08-31 | 2018-12-31 | 69 |  | Bottom-up
A in MTEP14 | A | West | ITCM | 4461 | 2014-12-17 | Emrld Isle Conv | Hiawatha-Emerald Isle-Marion 69kV Conversion | This project converts the line from Hiawatha to Marion to 69 kV operation. Alliant Energy will also be installing a new substation by the name of Emerald Isle on the Hiawatha to Marion 69 kV line. ITC will then be installing three breakers at the Emeral | IA | IA | Other |  | Condition | 1841957 | 2016-06-16 | 2016-09-03 | 69 |  | Bottom-up
A in MTEP14 | A | West | ITCM | 4462 | 2014-12-17 | Keswick-Victor Conv | Keswick-Victor 69kV Conversion | Convert the Keswick - Victor to 69kV. Build Victor 69kV Switching Station substation and install a 69/34.5kV XFMR to provide back up for the 34.5kV system in the Victor and Brooklyn area until that area is converted to 69kV in 2020. | IA | IA | Other |  | Condition | 3000000 | 2021-12-30 | 2021-12-30 | 69 | 34 | Bottom-up
A in MTEP14 | A | West | ITCM | 4463 | 2014-12-17 | OtterCk-Fletcher | Otter Creek-Fletcher 69kV Conversion | Convert the 34kV lines between Otter Creek and Fletcher to 69kV operation. The 34kV terminal at Marshalltown will be retired and a new 69kV source from the new Fletcher sub will feed the new line. | IA | IA | Other |  | Condition | 240000 | 2019-12-31 | 2019-12-31 | 69 |  | Bottom-up
A in MTEP14 | A | West | ITCM | 4465 | 2014-12-17 | Mtwn-StnyPt 161 Conv | Marshalltown-Stoney Point 161kV Conversion | Covert Marshalltown - Stoney Point to 161kV operation. Add additional 161kV terminal at Marshalltown. Install at 161/36kV transformer at Marshalltown. Add additional 161kV terminal at Marshalltown for a total of two additional 161kV terminals at Marshallt | IA | IA | Other |  | Reliability | 1100000 | 2016-12-31 | 2016-12-31 | 161 |  | Bottom-up
A in MTEP14 | A | West | ITCM | 4467 | 2014-12-17 | Fairbank-Oelwein | Fairbank-Oelwein 5.5 mile 69kV Rebuild | Rebuild 5.5 miles of the Oelwein-Fairbank 69kV line. | IA | IA | Other |  | Condition | 2805000 | 2019-12-31 | 2019-12-31 | 69 |  | Bottom-up
A in MTEP14 | A | West | ITCM | 4704 | 2014-12-17 | Mtown-Parnell-CR | Marshalltown-Parnell-Cedar Rapids 34kV Rebuild Plan | The project wll rebuild several 34kV lines to 69kV standards to prepare for the future conversion to 69kV. | IA | IA | Other |  | Condition | 46190500 | 2015-08-17 | 2021-12-31 | 34 |  | Bottom-up
A in MTEP14 | A | West | MDU | 3083 | 2015-03-31 | Dickinson Loop | Dickinson 115 kV Loop | Complete 115 kV loop & new 115/41.6 subsation in Dickinson area | ND | ND | Other |  | Reliability | 2250000 | 2014-05-07 | 2018-07-01 | 115 | 41.6 | Bottom-up
A in MTEP14 | A | West | MDU | 4133 | 2015-01-09 | Collins | Collins distribution substation | A new 115/12.47 kV distribution substation on the Heskett-NW Bismarck 115 kV line | ND | ND | Other |  | Distribution | 1500000 | 2015-12-01 | 2017-03-01 | 115 | 12.47 | Bottom-up
A in MTEP14 | A | West | MDU | 4134 | 2015-01-09 | South 9th | South 9th distribution substations | A new 115/12.47 kV distribution substation on the East Bismarck-Sweet Ave 115 kV line | ND | ND | Other |  | Distribution | 4200000 | 2017-06-01 | 2017-06-01 | 115 | 12.47 | Bottom-up
A in MTEP14 | A | West | MDU | 4141 | 2015-01-09 | Wishek Reactor | Wishek Jct Reactor | A new tertiary reactor on Wishek 230/115/13.8 kV transformer | ND | ND | Other |  | Reliability | 500000 | 2016-09-30 | 2016-09-30 | 13.8 |  | Bottom-up
A in MTEP14 | A | West | MEC | 4255 | 2015-09-16 | G2676 | Sioux City Airport Sub | Construct the Sioux City Airport 161-13 kV Substation | IA | IA | Other |  | Distribution | 2500000 | 2017-05-01 | 2017-05-01 | 161 | 13 | Bottom-up
A in MTEP14 | A | West | MEC | 4594 | 2015-09-16 | G2675 | Sioux City Airport Substation Line Taps | 161 kV Line taps into Sioux City Airport Substation | IA | IA | Other |  | Distribution | 140000 | 2017-05-01 | 2017-05-01 | 161 |  | Bottom-up
A in MTEP14 | A | West | MH, MP | 3831 | 2014-12-17 | GNTL | Great Northern Transmission Line | U.S. portion of new Dorsey - Iron Range 500 kV transmission line, including 500 kV line from border crossing to Iron Range, midpoint series compensation station, new Iron Range 500/230 kV yard adjacent to existing Blackberry 230/115 kV Substation, and interconnection to 230 kV system at Blackberry. | MN | MB | TDSP |  |  | 676242932 | 2020-06-01 | 2020-06-01 | 500 | 230 | Externally-Driven
A in MTEP14 | A | West | MP | 4044 | 2014-12-17 | Canosia Road Substation | Canosia Road Substation | New 115/14 kV substation in Arrowhead - Cloquet 115 kV line | MN | MN | Other |  | Distribution | 4868663 | 2016-06-30 | 2016-06-30 | 115 | 14 | Bottom-up
A in MTEP14 | A | West | MP | 4045 | 2014-12-17 | Embarrass Transformer | Embarrass Transformer | New 115/23 kV transformer at Embarrass Switching Station | MN | MN | Other |  | Distribution | 1850000 | 2016-10-01 | 2016-10-01 | 115 | 23 | Bottom-up
A in MTEP14 | A | West | MP | 4426 | 2015-01-09 | Hoyt Lakes Substation Modernization | Hoyt Lakes Substation Modernization | Rebuild and reconfigure existing Hoyt Lakes Substation | MN | MN | Other |  | Reliability | 3000000 | 2017-01-31 | 2017-01-31 | 138 |  | Bottom-up
A in MTEP14 | A | West | MRES | 4470 | 2016-09-26 | Woodpecker Mitigation | Woodpecker Damage Mitigation | Addressign woodpecker damage on MRES facilities | MN | MN | Other |  | Condition | 150000 | 2014-06-30 | 2016-12-31 | 230 |  | Bottom-up
A in MTEP14 | A | West | OTP | 4444 | 2015-09-25 | OTP | NERC Alert Facility Ratings for Low Priority | Verify and remediate facilities as required due to the industry-wide NERC alert | MN,ND,SD | MN,ND,SD | Other |  | Reliability | 7701028 | 2016-12-31 | 2016-12-31 | 115 |  | Bottom-up
A in MTEP14 | A | West | XEL | 4693 | 2014-12-17 |  | Rebuild Douglas County-West Union 69 kV | Rebuild the Douglas County - West Union 69 kV line to 477 ACSR and transfer Osakis substation load to Douglass County | MN | MN | Other |  | Reliability | 3011966 | 2016-12-23 | 2016-12-23 | 69 |  | Bottom-up
A in MTEP14 | A | West | XEL | 4694 | 2014-12-17 |  | Install Gravel Island 161 kV Capacitor Banks | Install two steps of 30 Mvar capacitor banks at Gravel Island substation on the 161 kV bus | WI | WI | BaseRel |  |  | 3500000 | 2017-08-01 | 2017-08-01 | 161 |  | Bottom-up
A in MTEP14 | A | West | XEL | 4697 | 2014-12-17 |  | Reconductor Split Rock-Lakefield Jct 345 kV | Replace approximately 35 miles of 964 ACSS with 477 T2 between the Split Rock and Lakefield Jct substations | MN | MN | Other |  | Reliability | 5547376 | 2015-12-15 | 2018-11-30 | 345 |  | Bottom-up
A in MTEP15 | A | Central | AmerenIL | 3689 | 2015-12-28 |  | Keystone 138/34 kV Substation - Replace 138 kV breaker | Keystone 138-13.8 kV Substation - Replace 138 kV circuit breaker 1396 in the Wallace-Keystone line with a minimum 2000 A continuous 40 kA interrupting circuit breaker | IL | IL | Other |  | Reliability | 500000 | 2016-11-15 | 2016-11-15 | 138 |  | Bottom-up
A in MTEP15 | A | Central | AmerenIL | 4078 | 2015-12-28 | AMRN33 | Sandburg-Monmouth 138 kV Line Upgrade | Rebuild approx. 4 miles of 477 kcmil ACSR conductor to meet or exceed the 1521 A summer emergency capability of the 1272 kcmil ACSR conductor which makes up the rest of this line. Replace wavetrap at Galesburg Monmouth Substation with equipment capable of carrying 2000 A continuously. | IL | IL | BaseRel |  |  | 4200000 | 2016-11-15 | 2016-11-15 | 138 |  | Bottom-up
A in MTEP15 | A | Central | AmerenIL | 4079 | 2015-12-28 |  | Huff 138-69 kV Substation Connection | Establish new bulk substation connecting to the Havana-Danvers 138 kV Line 1352 between Powerton Jct. and Lilly Substation. | IL | IL | Other |  | Reliability | 3000000 | 2017-06-01 | 2017-06-01 | 138 | 69 | Bottom-up
A in MTEP15 | A | Central | AmerenIL | 4494 | 2015-12-28 |  | East Galesburg 161/138 kV XFMR Replacement | Replace existing parallel 161/138 kV Transformers at East Galesburg with a single 161/138 kV Transformer at Sandburg 345/138 kV Substation. | IL | IL | BaseRel |  |  | 3681580 | 2016-12-01 | 2016-12-01 | 161 | 138 | Bottom-up
A in MTEP15 | A | Central | AmerenIL | 7825 | 2015-12-28 |  | Mascoutah Municipal (Hilgard) 138 kV Breaker Station | Install a 4-breaker 138 kV ring bus (2000 A, 40 kA) at or near the tap to Mascoutah Municipal on the existing Turkey Hill-Ashley 138 kV Line 1482. | IL | IL | Other |  | Reliability | 5900000 | 2019-12-01 | 2019-12-01 | 138 |  | Bottom-up
A in MTEP15 | A | Central | AmerenIL | 8050 | 2015-12-28 |  | Baldwin 345/138kV Transformer Replacement | Baldwin Plant 345/138 kv Transformer - Replace existing 448MVA with a 560 MVA unit | IL | IL | Other |  | MP funded | 5650000 | 2015-06-01 | 2015-06-01 | 345 | 138 | Bottom-up
A in MTEP15 | A | Central | AmerenIL | 8054 | 2015-12-28 |  | Tilden Jct to Sparta 138kv | Tilden Jct to Sparta 138kv - Reconductor approx. 5.7 of 4.77 KCM ACSR | IL | IL | Other |  | MP funded | 2710721 | 2016-12-01 | 2016-12-01 | 138 |  | Bottom-up
A in MTEP15 | A | Central | AmerenIL | 8055 | 2015-12-28 |  | Sparta Tap - Steelville - 138kv | Sparta Tap to Steelville 138kv - Reconductor approx. 7.4 of 4.77 KCM ACSR | IL | IL | Other |  | MP funded | 2318247 | 2016-06-01 | 2016-06-01 | 138 |  | Bottom-up
A in MTEP15 | A | Central | AmerenIL | 8060 | 2015-12-28 |  | Fayetteville South Tap - Tilden 138kv | Fayetteville South Tap to Tilden 138kv - Reconductor approx. 1.5 of 1113 KCM ACSR | IL | IL | Other |  | MP funded | 1500000 | 2016-12-01 | 2016-12-01 | 138 |  | Bottom-up
A in MTEP15 | A | Central | AmerenIL | 8134 | 2015-12-28 |  | Tilden Jct to Tilden 138kv | Tilden Jct to Tilden 138kv - Reconductor one span of 1113 KCM ACSR | IL | IL | Other |  | MP funded | 175920 | 2015-12-01 | 2015-12-01 | 138 |  | Bottom-up
A in MTEP15 | A | Central | AmerenIL | 8137 | 2015-12-28 |  | Turkey Hill to Mascoutah 138kv | Turkey Hill to Mascoutah 138kv - Reconductor approx. 8.5 of 4.77 KCM ACSR | IL | IL | Other |  | MP funded | 4250000 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
A in MTEP15 | A | Central | AmerenIL | 8581 | 2015-12-28 |  | California Ridge Wind Farm Expansion | Increase of plant output capacity to 250 MW | IL | IL | Other |  | Reliability | 48000 | 2017-03-02 | 2017-03-02 | 138 |  | Bottom-up
A in MTEP15 | A | Central | AmerenMO | 7871 | 2015-12-28 |  | Keokuk Plant 69 kV Breaker Addition | Install new 1200 A, 69 kV line position and circuit breaker to accommodate new 69 kV line to be constructed by ITC Midwest. | IA | IA | Other |  | Reliability | 460000 | 2016-12-31 | 2016-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | Central | AmerenMO | 8840 | 2015-12-28 |  | Hitt Substation | Install 161 kV breaker and extend 161 kV line 0.2 miles to supply Hitt 161-34.5 kV Substation from Heritage Substation. Relocate 40 Mvar, 161 kV capacitor bank from Wedekind to Heritage Substation. Install 2-161 kV bus-tie breakers at Heritage, 3-161 kV breakers at Wedekind, and 1-161 kV breaker at Cape. | MO | MO | Other |  | Reliability | 120000 | 2016-05-25 | 2016-11-14 | 161 | 161 | Bottom-up
A in MTEP15 | A | Central | BREC | 3435 | 2015-12-28 | LRP1 | Rome Junction to West Owensboro 69 kV reconductor. | Reconductor 5.8 miles of 3/0 and 267 MCM ACSR with 336 MCM ACSS | KY | KY | Other |  | Reliability | 440000 | 2017-12-31 | 2017-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | Central | BREC | 3436 | 2015-12-28 | LRP2 | Wilson to Sacremento 69 kV line addition | New 11 mile line and line terminal at Wilson | KY | KY | Other |  | Reliability | 2100000 | 2018-12-31 | 2018-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | Central | BREC | 3437 | 2015-12-28 | LRP3 | Thruston Junction to East Owensboro reconductor. | Reconductor .4 miles of 3/0 ACSR with 336 MCM ACSR | KY | KY | Other |  | Reliability | 40000 | 2018-12-31 | 2018-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | Central | BREC | 3438 | 2015-12-28 | LRP4 | Daviess County to Philpot Tap reconductor. | Reconductor 7.7 miles of 267 MCM ACSR with 336 MCM ACSS | KY | KY | Other |  | Reliability | 580000 | 2018-12-31 | 2018-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | Central | BREC | 3441 | 2015-12-28 | LRP7 | Olivet Church Road to Olivet Church Road Tap 69 kV reconductor. | Reconductor 1.4 miles of 4/0 ACSR with 336 MCM ACSS | KY | KY | Other |  | Reliability | 150000 | 2015-12-31 | 2015-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | Central | BREC | 3444 | 2015-12-28 | LRP10 | Meade County 161/69 transformer addition | Add a third 56 MVA transformer to the existing Meade County substation. Modified to replace both 56 MVA transformers with two 100 MVA transfomers. | KY | KY | BaseRel |  |  | 4000000 | 2015-12-31 | 2015-12-31 | 161 | 69 | Bottom-up
A in MTEP15 | A | Central | BREC | 9420 | 2015-12-28 |  | Aleris Expansion | The proposed service plan for the Aleris load includes construction of a new-terrain 1.7 mile 161 kV radial circuit from Coleman EHV to serve the 28 MW load at the existing 161/13.8 kV delivery point. In addition, the plan includes a new-terrain 2 mile 161 kV circuit to provide service to a new 161/13.8 kV delivery point necessary to serve the expanded load (44 MW at 90% PF maximum contract demand). | KY | KY | Other |  | Reliability | 9550000 | 2017-03-31 | 2017-03-31 | 161 |  | Bottom-up
A in MTEP15 | A | Central | BREC, PJM, Vectren | 10142 | 2015-12-28 |  | Duff-Rockport-Coleman 345 kV | New 28.5 miles of single circuit, single conductor 345 kV transmission from Duff to Coleman, including sub upgrades (MISO); 14 miles of new double circuit 345 kV to Rockport, including two Rockport 765/345 kV transformers (PJM) | KY | IN | MEP |  |  | 67443248 | 2021-01-01 | 2021-01-01 | 345 |  | Top-Down
A in MTEP15 | A | Central | CWLD | 8300 | 2016-07-11 |  | Mill Creek 161 kV Substation | Regulatory Approval issues has caused a delay in this project. Construct new Mill Creek 161 kV substation | MO | MO | Other |  | Reliability | 32000000 | 2030-06-01 | 2030-06-01 | 161 | 13.8 | Bottom-up
A in MTEP15 | A | Central | DEI | 2144 | 2015-12-28 | 604J3062 | Franklin 230 to Earlywood 69kv Reconductor | Franklin 230kV sub to Earlywood sub reconductor 1.06 mile - 69kV - 69165 line with 954ACSR@100C | IN | IN | Other |  | Reliability | 1170000 | 2017-06-30 | 2017-06-30 | 69 |  | Bottom-up
A in MTEP15 | A | Central | DEI | 7882 | 2015-12-28 | AMIN1047 | Bloomington Rogers St - Dunn St New 69kV Line | Construct new 69kV line from Bloomington Rogers St. to Bloomington Dunn St. (also includes Dunn St. bus work - AMIN1046) 954ACSR@100C | IN | IN | Other |  | Reliability | 4820000 | 2017-06-01 | 2017-06-01 | 69 |  | Bottom-up
A in MTEP15 | A | Central | DEI | 7883 | 2015-12-28 | AMIN1093 | Bloomington Downtown 69/12kV Sub | Construct new 22.4MVA - 69/12kV sub near downtown Bloomington in the new line established by project AMIN1047 / 7882. | IN | IN | Other |  | Reliability | 602000 | 2017-06-02 | 2017-06-02 | 69 | 12 | Bottom-up
A in MTEP15 | A | Central | DEI | 7885 | 2015-12-28 | AMIN1052 | Frankfort Burlington St - Middlefork 69kV Reconductor | Frankfort Burlington St to Middlefork 69kV - 69133 ckt: Reconductor 12.4 miles with 954ACSR@100C | IN | IN | Other |  | Reliability | 6636000 | 2017-03-31 | 2017-03-31 | 69 |  | Bottom-up
A in MTEP15 | A | Central | DEI | 7903 | 2015-12-28 | AMIN0701 | Martinsville SE - HE Park Ave 69kV Reconductor | Martinsville SE - HE Park Ave 69kV - 6903 ckt: Reconductor 3.4 miles with 954ACSR@100C | IN | IN | Other |  | Reliability | 2102000 | 2025-06-01 | 2025-06-01 | 69 |  | Bottom-up
A in MTEP15 | A | Central | DEI | 7911 | 2015-12-28 | AMIN1146 | Frankfort 230kV and 69kV Ring Buses | Frankfort 230kV: complete 4-brkr ring bus; 69kV: complete 6-brkr ring bus and retire Jefferson Jct with new line terminal for 69kV line to Frankfort Muni. | IN | IN | Other |  | Reliability | 5109020 | 2018-12-31 | 2018-12-31 | 230 | 69 | Bottom-up
A in MTEP15 | A | Central | DEI | 7946 | 2015-12-28 | AMIN1070 | Speed - Jeffersonville New 138kV Line | Loop existing 138kV line from Speed to Clark Maritime to Jeffersonville. Add 2.52 mile 138kV line section from Speed to Memphis Jct and tie into existing 13890 circuit. Add .01 mile 138kV line section from Jeffersonville Jct. to Jeffersonville sub. Install 138kV line terminals at Speed and Jeffersonville. | IN | IN | Other |  | Reliability | 5472000 | 2017-12-31 | 2017-12-31 | 138 |  | Bottom-up
A in MTEP15 | A | Central | DEI | 7953 | 2015-12-28 | AMIN0393T | Mohawk Industrial 69kV Sub Loop | New 1.2 mile 69kV line to complete 69130 ckt. loop through Mohawk Industrial 69/12kV sub. | IN | IN | Other |  | Reliability | 1309000 | 2016-12-31 | 2016-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | Central | DEI | 7957 | 2015-12-28 | AMIN1440/AMIN1289 | Kokomo S. Main St. Sub Relocate | Relocate Kokomo S. Main St. 69/12kV distribution sub to higher ground (new sub name will be Kokomo Apperson) | IN | IN | Other |  | Reliability | 1261000 | 2017-06-01 | 2017-06-01 | 69 | 12 | Bottom-up
A in MTEP15 | A | Central | DEI | 7961 | 2016-06-14 | AMIN1290 | Fairview 138kV Breaker Replacements | Fairview 138kV Breaker Replacements: replace OCB 13858, 13854, and relays at line terminals 13854, 13855, 13858 | IN | IN | Other |  | Condition | 4211000 | 2017-12-31 | 2017-12-31 | 138 |  | Bottom-up
A in MTEP15 | A | Central | DEI | 7963 | 2015-12-28 | AMIN1291 | New Castle 138kV Breaker Replacements | New Castle 138kV Breaker Replacements: replace OCB 13805, 13835, 13842, 13873, 13869-1, 13869-2, and relays at line terminals 13805, 13835, 13842, 13873, 13843 | IN | IN | Other |  | Condition | 2516322 | 2018-12-31 | 2018-12-31 | 138 |  | Bottom-up
A in MTEP15 | A | Central | DEI | 7964 | 2015-12-28 | AMIN1292 | Kokomo Highland Park 69kV Breaker Replacements | Kokomo Highland Park Equipment: Replace OCB 69230-4, -5, -6, -7, OCB BK 7 CAP, 69kV primary UG cables, relays at terminals 6910, 6911, 6913, 6928, 6992, 13879, 13887, 138kV TRANSFER | IN | IN | Other |  | Condition | 3351124 | 2018-12-31 | 2018-12-31 | 138 | 69 | Bottom-up
A in MTEP15 | A | Central | DEI | 7969 | 2015-12-28 | AMIN1324 | Edwardsport - Amo 345kV Intermediate Structure Replacements | Edwardsport - Amo 345kV - 34528 ckt. replace intermediate tansient structures with deadend structures - every 2.5 miles (22 structures). | IN | IN | Other |  | Reliability | 16052359 | 2017-12-31 | 2017-12-31 | 345 |  | Bottom-up
A in MTEP15 | A | Central | DEI | 7974 | 2015-12-28 | AMIN1322 | Lafayette 230 - Attica 230kV Reconductor | Lafayette 230 - Attica 230kV - 23027 ckt: Reconductor 5.4 miles at Lafayette 230 end with 900ACSR-OVAL@100C; also reconductor portions of double-circuited 13877 and 13878 circuits with 954ACSR-OVAL@100C - total of 9.9 miles. | IN | IN | Other |  | Reliability | 3684530 | 2018-12-31 | 2018-12-31 | 230 | 138 | Bottom-up
A in MTEP15 | A | Central | DEI | 7982 | 2015-12-28 | AMIN1314 | Advance - Dover 69kV Rebuild | Advance - Dover 69kV - 69134 ckt: Rebuild 7.9 mile line with 477ACSR@100C - replacing all structures with steel poles. | IN | IN | Other |  | Condition | 4903384 | 2017-12-31 | 2017-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | Central | DEI | 7984 | 2015-12-28 | AMIN1283 | Medora - Brownstown 69kV Rebuild | Medora - Brownstown 69kV - 6952 ckt: Rebuild 4.85 mile line transferring existing 477ACSR conductor - replacing all structures with steel poles. | IN | IN | Other |  | Condition | 2590705 | 2018-12-31 | 2018-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | Central | DEI | 7987 | 2015-12-28 | AMIN1278 | New Pekin Jct - Salem 69kV Rebuild | New Pekin Jct - Salem 69kV - 69153 ckt: Rebuild 9.4 mile line with 477ACSR@100C - replacing all structures with steel poles. | IN | IN | Other |  | Condition | 4028000 | 2018-12-31 | 2018-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | Central | DEI | 7989 | 2015-12-28 | AMIN1279 | Edwardsport - HE Rogers Jct 69kV Rebuild | Edwardsport - HE Rogers Jct 69kV - 6951 ckt: Rebuild 9.8 mile line with 477ACSR@100C - replacing all structures with steel poles. (HE Rogers Jct is located between Edwpt and Odon Jct) | IN | IN | Other |  | Condition | 7391505 | 2016-12-31 | 2016-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | Central | DEI | 7991 | 2015-12-28 | AMIN1277 | Rushville - HE Milroy 69kV Rebuild | Rushville - HE Milroy 69kV - 6920 ckt: Rebuild 7.2 mile line with 477ACSR@100C - replacing all structures with steel poles. | IN | IN | Other |  | Condition | 6699202 | 2016-12-31 | 2016-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | Central | DEI | 7992 | 2015-12-28 | AMIN1281 | Hillenbrand Jct - Andersonville Jct 69kV Rebuild | Hillenbrand Jct - Batesville North - Andersonville Jct 69kV - 6919 ckt: Rebuild 7.93 mile line with 477ACSR@100C - replacing all structures with steel poles. | IN | IN | Other |  | Condition | 6472095 | 2018-12-31 | 2018-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | Central | DEI | 9246 | 2015-12-28 | TIN1607 | Lafayette SE to Laf S Jct2 new 138kV line | Lafayette SE to new Lafayette S Jct 2 (in existing 13808 ckt.) - build new 138kV - 1.75 mile - 954acsr@100c - 13899 ckt.; add new breaker in Laf SE ring; add (2) line switches at new jct and operate Laf S Jct to Laf S Jct 2 N.O. | IN | IN | BaseRel |  |  | 3976181 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
A in MTEP15 | A | Central | DEI | 9247 | 2015-12-28 | TIN1674-AMIN1151 | Lafayette 230 sub - 138Kv bus tie brkr and relays | Lafayette 230 sub - insert a redundant 138kV bus tie breaker in series with existing breaker; add redundant bus differential relays to both 138kV bus 1 and 2. Scope also includes (5) 138Kv antiquated breaker and relay replacements, disconnect switches and misc buswork. | IN | IN | BaseRel |  |  | 4500000 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
A in MTEP15 | A | Central | DEI, HE | 7940 | 2015-12-28 | AMIN1184 | Bedford - HE Worthington 138kV Reconductor | Bedford - HE Worthington 138kV - 13840 ckt: Reconductor 33 miles with 954ACSR and replace all structures. Also reconductor 2 miles of 13823 where it is double circuited with 954ACSR starting at the Bedford end | IN | IN | BaseRel |  |  | 36169000 | 2018-07-31 | 2018-07-31 | 138 |  | Bottom-up
A in MTEP15 | A | Central | HE | 10343 | 2015-12-28 |  | Hubbell Primary 138 kV Ring Bus and Transformer Addition | Construct a 138kV ring bus and add a second 138/69kV transformer | IN | IN | Other |  | Distribution | 10047000 | 2016-06-01 | 2016-06-01 | 138 |  | Bottom-up
A in MTEP15 | A | Central | IPL | 4262 | 2015-12-28 |  | Pritchard - Centerton - Honey Creek - Southport 138 kV line rating upgrade | Increase line rating from 242 to 302 MVA | IN | IN | GIP |  |  |  | 2016-12-31 | 2016-12-31 | 138 |  | Externally-Driven
A in MTEP15 | A | Central | IPL | 4263 | 2015-12-28 |  | Pritchard - Heartland Crossing - Mooresville 138 kV line rating upgrade | Increase line rating from 191 to 242 MVA | IN | IN | GIP |  |  |  | 2016-12-31 | 2016-12-31 | 138 |  | Externally-Driven
A in MTEP15 | A | Central | IPL | 4264 | 2015-12-28 |  | Pritchard - Franklin Township | New 138 kV transmission line rated 322 MVA | IN | IN | GIP |  |  |  | 2016-12-31 | 2016-12-31 | 138 |  | Externally-Driven
A in MTEP15 | A | Central | IPL | 7701 | 2015-12-28 |  | Thompson Substation Upgrade | New 345 kV breaker, relocated Hanna E 275 MVA autotransformer and new 2-138 kV breakers | IN | IN | Other |  | Reliability |  | 2015-11-23 | 2016-06-01 | 345 | 138 | Bottom-up
A in MTEP15 | A | Central | IPL | 7704 | 2015-12-28 |  | Rockville Substation Breaker Additions | New 2-345 kV breakers and 138 kV bus tie breaker | IN | IN | Other |  | Reliability |  |  |  | 345 |  | Bottom-up
A in MTEP15 | A | Central | IPL | 9402 | 2015-12-28 |  | Guion - Westlane Line Upgrade | Upgrade conductor rating to 298 MVA via line clearance. | IN | IN | BaseRel |  |  |  | 2017-07-15 | 2017-07-15 | 138 |  | Bottom-up
A in MTEP15 | A | Central | PPI | 7881 | 2015-12-28 | 2015-12 | Fishhook-Pittsfield 138 kV | Construct new 14.5 mile 138 kV line from the new Ameren Fishhook 138 kV switching station on the Meredosia-East Quincy South 138 kV line to the PPI Pittsfield 138/69 kV substation. | IL | IL | Other |  | Reliability | 7637747 | 2017-12-01 | 2018-12-31 | 138 | 69 | Bottom-up
A in MTEP15 | A | Central | PPI | 7889 | 2015-12-28 | 2015-14,35,37 | Fishhook-Liberty 138 kV, Liberty 138/69 kV, and St. Anthony 138/69 kV | Construct Fishhook-Liberty 138 kV line, Liberty 138/69 kV substation, and replace St. Anthony 138/69 kV transformer. | IL | IL | Other |  | Reliability | 11724709 | 2019-12-31 | 2019-12-31 | 138 | 69 | Bottom-up
A in MTEP15 | A | Central | Vectren | 4391 | 2016-05-19 | 2013SIGE5 | Pigeon Creek Cap Bank Addition | Add a 15.6 MVAR cap bank at the Pigeon Creek Sub | IN | IN | Other |  | Reliability | 600000 | 2019-12-31 | 2019-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | East | ITCT | 7891 | 2016-07-14 | ITC_14_020 | Stone Pool Substation | New 3 transformer 120 kV distribution substation | MI | MI | Other |  | Distribution | 16525000 | 2017-05-01 | 2017-05-01 | 120 |  | Bottom-up
A in MTEP15 | A | East | ITCT | 7892 | 2016-03-22 | ITC_14_028 | Bartlett Substation | Interconnection Request for a new 120 kV, 2 transformer distribution substation | MI | MI | Other |  | Distribution | 7920000 | 2019-06-13 | 2019-06-13 | 120 |  | Bottom-up
A in MTEP15 | A | East | ITCT | 8083 | 2015-12-28 | ITC_14_013 | Cortland Relay Replacement | The proposed solution is to upgrade the limiting relaying on the Cortland - Warren 120 kV line to increase its summer emergency rating. | MI | MI | Other |  | Reliability | 300000 | 2017-06-01 | 2017-06-01 | 120 |  | Bottom-up
A in MTEP15 | A | East | ITCT | 8087 | 2016-08-03 | ITC_14_022 | Stratford 33.3 MVAR Capacitor Bank | Install a 33.3 MVAR capacitor bank on the 120 kV bus 101 at Stratford along with the necessary station equipment. | MI | MI | BaseRel |  |  | 820000 | 2018-06-01 | 2018-06-01 | 120 |  | Bottom-up
A in MTEP15 | A | East | ITCT | 8094 | 2015-12-28 | ITC_14_018 | Fitz 345/120 kV Transformer and 120 kV Station | Install a 345/120 kV transformer and construct a 120 kV, 3 breaker yard (ring bus configuration with space to expand to a breaker and a half configuration) at the existing Fitz substation. The Adams-Bunce Creek 120 kV line, which runs adjacent to the Fitz property, would be looped into the new 120 kV side of the substation. To facilitate looping the line, less than 0.1 miles of new double circuit structures would be constructed with 1431 ACSR being installed on both sides of the new structures. Sag limits on the Bunce-Wabash#2 120 kV line and the Fitz-Bunce Creek 120 kV line will also need to be remediated to accommodate this project | MI | MI | BaseRel |  |  | 13200000 | 2018-06-01 | 2018-06-01 | 345 | 120 | Bottom-up
A in MTEP15 | A | East | ITCT | 9245 | 2016-07-05 | ITC_14_023 | J327 Generator Interconnection | ITCT will add 2-120 kV breakers (Positions LM and LF) with associated disconnects at Rapson 120 kV substation to accomodate the interconnection of a 150 MW wind farm. | MI | MI | GIP |  |  | 1330000 | 2016-09-02 | 2016-09-02 | 120 |  | Externally-Driven
A in MTEP15 | A | East | ITCT | 9360 | 2016-07-05 | ITC_15_001 | Scio Substation | This is a load interconnection request from DTE Energy to construct a 120/13.2 kV substation in Scio Township, MI. ITCT will construct a 120 kV straight bus with 2-120 kV line breakers and a 120 kV section breaker, as well as, associated disconnect switches, control house, and all other required connection equipment at Scio substation. Scio will be fed by looping in the existing Lark - Spruce 120 kV circuit. | MI | MI | Other |  | Reliability | 10350000 | 2018-12-31 | 2018-12-31 | 120 | 13.2 | Bottom-up
A in MTEP15 | A | East | ITCT | 9362 | 2015-12-28 | ITC_15_005 & ITC_15_006 | State (formerly “Maize”) and Blue Substations | DTE has submitted a load interconnection request for 2 new 120/41.6 kV substations proposing to serve load in the City of Ann Arbor and the University of Michigan Campus. ITCT would Install 2-120 kV line breakers and 1-120 kV section breaker w/ associated disconnects in a straight bus configuration at State (formerly "Maize") and Blue substations respectively. At, Pioneer substation, ITCT would add 2-120 kV line breaker and create 2 new positions to terminate 2 new lines between Pioneer and State (formerly "Maize"). ITCT would construct approx. 2.6 miles of double circuit 120 kV structures between Pioneer and State (formerly "Maize") , and string 954 ACSR to create the 120 kV State (formerly "Maize")-Pioneer 1 and 2 circuits. At, Phoenix substation, ITCT would add 2-120 kV line breaker, 1-120 kV section breaker, relocate the Phoenix end of the Phoenix-Lark line, and create 2 new positions to terminate 2 new lines between Phoenix and Blue. ITCT would construct 2, approx. 2.7 mile underground lines between Phoenix and Blue using 2500 CU XLPE cable to create the 120 kV Blue-Phoenix 1 and 2 circuits. | MI | MI | Other |  | Reliability | 97873000 | 2018-12-31 | 2019-05-01 | 120 | 41.6 | Bottom-up
A in MTEP15 | A | East | ITCT | 9440 | 2015-12-28 | ITC_14_027 | Waterman 120kV Cable Relocation for GICB | Portions of the following ITCT circuits will need to be relocated to accomodate the construction of the Gordie Howe International Bridge (GICB) and the related US customs area: Waterman-Cato 120kV (underground), Waterman-St. Antoine 120kV (underground), Waterman-Frisbie 120kV (underground), Waterman-Zug 120kV (Overhead), and Waterman-DIG-Navarre 230kV (overhead). | MI | MI | Other |  | Reliability | 25000000 | 2017-12-31 | 2017-12-31 | 230 |  | Bottom-up
A in MTEP15 | A | East | METC | 2810 | 2015-12-28 | METC_13_038 | Delhi - Canal Jct 138kV Rebuild | Rebuild 7.2 miles of 4/0 ACSR and 336.4 ACSR utilizing 954 ACSR on new 138 kV structures. Also replace terminal equipment at the Delhi 138 kV station. | MI | MI | Other |  | Reliability | 7500000 | 2018-12-31 | 2018-12-31 | 138 |  | Bottom-up
A in MTEP15 | A | East | METC | 3926 | 2015-12-28 | METC_14_016 | Dort to Pasadena (Goss) station equipment replacement | Replace/reset relay equipment and replace trainers in the Dort station | MI | MI | Other |  | Reliability | 225000 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
A in MTEP15 | A | East | METC | 4506 | 2015-12-28 | METC_14_018 | Four Mile - Wealthy Street 138 kV Rebuild | Rebuild 0.59 miles of 6-wired 266.8 ACSR + 3/0 Cu conductor from the Four Mile - Mullins Jct. section using 954 ACSR and rebuild 0.37 miles of 266.8 ACSR + 3/0 Cu, 6.75 miles of 2-3/0 Cu, and 0.49 miles of 795 ACSR from the Wealthy Street - Mullins Jct 138 kV segment utilizing 954 ACSR on new 138 kV structures. Install OPGW along the entire length of the circuit. Also upgrade terminal equipment at the Four Mile and Wealthy Street 138 kV stations. | MI | MI | BaseRel |  |  | 8600000 | 2018-12-31 | 2018-12-31 | 138 |  | Bottom-up
A in MTEP15 | A | East | METC | 4508 | 2015-12-28 | METC_14_038 | Broadmoor to Plaster Creek 138 kV Sag Remediation | Remediate the sag on the 795 ACSR from the Broadmoor - Plaster Creek 138 kV circuit to the conductor limit. | MI | MI | Other |  | Reliability | 190000 | 2018-06-01 | 2018-06-01 | 138 |  | Bottom-up
A in MTEP15 | A | East | METC | 4509 | 2015-12-28 | METC_13_043 | Argenta - Battle Creek 345kV Sag Remediation and Station Equipment | Remediate Sag Limit to SEMER 2350 Amps. Upgrade station equipment at Battle Creek 345kV. | MI | MI | Other |  | Reliability | 2568000 | 2017-12-31 | 2017-12-31 | 345 |  | Bottom-up
A in MTEP15 | A | East | METC | 4524 | 2016-01-04 | METC_14_031 | Emmet - Livingston 138 kV Sag Remediation | Remediate sag on the Emmet - Livingston 138 kV line to bring its rating up to the conductor limit (208 MVA). | MI | MI | Other |  | Reliability | 182000 | 2017-12-31 | 2017-12-31 | 138 |  | Bottom-up
A in MTEP15 | A | East | METC | 8066 | 2015-12-28 | METC_14_022 | Amber - Donaldson Creek 138 kV Rebuild | Rebuild approx. 19.8 miles of the Amber to Donaldson Creek 138 kV circuit using 954 ACSR and OPGW on 138 kV future double circuit structures. | MI | MI | BaseRel |  |  | 23000000 | 2018-06-01 | 2018-06-01 | 138 |  | Bottom-up
A in MTEP15 | A | East | METC | 8067 | 2015-12-28 | METC_14_019 | Beals Road 138 kV Station Equipment Replacement | Replace 138 kV terminal equipment within the Beals Road Substation | MI | MI | Other |  | Reliability | 400000 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
A in MTEP15 | A | East | METC | 8070 | 2015-12-28 | METC_14_017 | North Belding 138 kV Station Equipment Replacement | Replace thermal limiting equipment at the North Belding station. | MI | MI | Other |  | Reliability | 120000 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
A in MTEP15 | A | East | METC | 8072 | 2015-12-28 | METC_14_047 | Riggsville to Port Calcite to Rockport 138 kV Rebuild | Rebuild 69 miles of existing 138 kV wood poles to double circuit capable 138 kV construction steel monopoles and string one side with T2 477 ACSR (or another similar capacity anti-galloping conductor configuration). | MI | MI | Other |  | Condition | 96505000 | 2019-12-31 | 2019-12-31 | 138 |  | Bottom-up
A in MTEP15 | A | East | METC | 8077 | 2016-04-07 | METC_14_039 | Vestaburg to Alma 138 kV Rebuild | Rebuild the Vestaburg - Alma 138 kV circuit utilizing 138 kV single circuit steel poles and 954 ACSR conductor. Install OPGW along the entire length of the circuit. | MI | MI | Other |  | Condition | 18200000 | 2018-12-31 | 2018-12-31 | 138 |  | Bottom-up
A in MTEP15 | A | East | METC | 8078 | 2015-12-28 | METC_14_025 | Donaldson Creek 33.3 MVAR Capacitor | Install a 33.3 MVAR capacitor at Donaldson Creek. | MI | MI | BaseRel |  |  | 1200000 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
A in MTEP15 | A | East | METC | 8080 | 2015-12-28 | METC_14_027 | Coldwater 3 x 18 MVAR 138 kV Capacitor | Install a 3 x 18 MVAR capacitor and necessary substation equipment at the 138 kV Coldwater Substation. | MI | MI | BaseRel |  |  | 3900000 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
A in MTEP15 | A | East | METC | 8090 | 2015-12-28 | METC_14_035 | Cornell - Blue Water Jct. 138 kV Sag Remediation | Remediate the sag limit on the Cornell to Blue Water Jct. section of the Cornell - Bingham 138 kV circuit to increase its summer emergency rating to at least 760 A. | MI | MI | Other |  | Reliability | 320000 | 2018-06-01 | 2018-06-01 | 138 |  | Bottom-up
A in MTEP15 | A | East | METC | 8091 | 2016-03-22 | METC_14_030 | Donaldson Creek - White Lake 138 kV Sag Remediation | Remediate the sag limit on the Donaldson Creek - White Lake 138 kV line to 160 MVA (670 Amp). | MI | MI | Other |  | Reliability | 360000 | 2018-06-01 | 2018-06-01 | 138 |  | Bottom-up
A in MTEP15 | A | East | METC | 8096 | 2015-12-28 | METC_14_036 | Roosevelt to Gaines 345 kV Sag Remediation | Remediate the sag limit on the Roosevelt - Gaines 345 kV circuit. This will bring the rating up to the 2156 ACSR summer emergency limit of 2,830 A. | MI | MI | Other |  | Reliability | 380000 | 2017-12-31 | 2017-12-31 | 345 |  | Bottom-up
A in MTEP15 | A | East | METC | 8109 | 2015-12-28 | METC_14_032 | Gaylord - Livingston 138kV Sag Remediation | Remediate the sag limit on the Gaylord to Livingston 138 kV line up to its conductor rating of 174 MVA (730 Amp). | MI | MI | Other |  | Reliability | 75000 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
A in MTEP15 | A | East | METC | 8118 | 2015-12-28 | METC_14_040 | Beecher - Samaria 138 kV Rebuild | Rebuild the 636 ACSR portion of the Beecher to Samaria 138 kV circuit utilizing 954 ACSR on 138 kV double circuit steel poles. Relocate the Beecher-Whiting 138 kV line to the open side of the new structures. Replace overloaded terminal equipment at Beecher and upgrade relaying at Morocco. | MI | MI | Other |  | Condition | 25600000 | 2018-12-31 | 2018-12-31 | 138 |  | Bottom-up
A in MTEP15 | A | East | METC | 8119 | 2016-08-30 |  | METC Pole Top Switches Additions-Replacement Program - 2017 | Install or replace an existing a new 138 kV, 2-way, full-load-break pole top switch at various tap points across the METC system | MI | MI | Other |  | Reliability | 3600000 | 2017-12-31 | 2017-12-31 | 138 |  | Bottom-up
A in MTEP15 | A | East | METC | 8121 | 2015-12-28 | METC_14_037 | Hackett Jct. - Laundra Jct. 138 kV Sag Remediation | Remediate the sag limit on the Hackett Jct. - Laundra Jct. section of the Bullock - Saginaw River 138 kV circuit to increase its summer emergency rating to at least 840 A. | MI | MI | Other |  | Reliability | 90000 | 2018-12-31 | 2018-12-31 | 138 |  | Bottom-up
A in MTEP15 | A | East | METC | 8122 | 2016-08-30 |  | METC Pole Top Switches Additions-Replacement Program - 2018 | Install or replace an existing a new 138 kV, 2-way, full-load-break pole top switch at various tap points . | MI | MI | Other |  | Reliability | 3600000 | 2018-12-31 | 2018-12-31 | 138 |  | Bottom-up
A in MTEP15 | A | East | METC | 8124 | 2015-12-28 | METC_14_046 | Argenta - Morrow 138 kV Rebuild | Rebuild approximately 10 miles of existing 138 kV steel lattice towers with wood cross arms to double circuit capable 230 kV construction steel monopoles and string one side with 954 ACSR. | MI | MI | Other |  | Condition | 13900000 | 2018-12-31 | 2018-12-31 | 138 |  | Bottom-up
A in MTEP15 | A | East | METC | 8126 | 2016-07-14 | METC_15_003 | Kenowa Reactor 28R Replacement | Replace the reactor with a new standard 345kV, 100 MVAR and upgrade relaying. | MI | MI | Other |  | Condition | 3500000 | 2016-08-15 | 2016-08-15 | 345 |  | Bottom-up
A in MTEP15 | A | East | METC | 8127 | 2016-08-30 | METC_14_024 | Six Ludington 345 kV Circuit Breaker Replacements | Replace the 22H9, 24H9, 25H9, 22F7, 24F7, and 25F7 Ludington 345 kV circuit breakers with the circuit breakers containing 400 ohm pre-insertion resistors. | MI | MI | Other |  | Reliability | 8640000 | 2017-12-31 | 2017-12-31 | 345 |  | Bottom-up
A in MTEP15 | A | East | METC | 8144 | 2016-03-22 | METC_14_029 | Meyer (formerly “Hayes Street”) 345/138 kV Station | Construct a new EHV “Meyer” (formerly “Hayes Street”) substation approximately four miles north of the Tallmadge station, loop the existing Ludington - Tallmadge #2, Kenowa - Argenta 345 kV and Cobb - Tallmadge #1 138 kV circuits into the new station and install a new 345/138 kV transformer at Meyer. The solution will also require replacing the limiting terminal equipment at the Tallmadge 345 kV station (pos. 27HR) and remediating the sag limits on the Argenta - Meyer 345 kV circuit (formerly Argenta - Kenowa 345 kV line) to at least 1,524 MVA (2,550 A) and on the Tallmadge - Meyer #1 345 kV circuit (formerly Ludington - Tallmadge #2 345 kV) to 2,007 MVA (3,358 A). | MI | MI | BaseRel |  |  | 31700000 | 2018-05-31 | 2018-05-31 | 345 | 138 | Bottom-up
A in MTEP15 | A | East | METC | 8170 | 2015-12-28 | METC_13_033 | Leoni to Page Ave 138kV - Install 2nd relay component at Leoni | Install the second relay component on the Leoni to Page Ave. 138 kV circuit at Leoni end so that, for faults on the Page Ave. end, the Leoni breaker will trip and clear the fault with one relay component failure. | MI | MI | Other |  | Reliability | 75000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
A in MTEP15 | A | East | METC | 8171 | 2016-08-16 | METC_13_016 | Croton to Felch Road 138 kV Circuit Dual Pilot Relay Protection Installation and Sparing Removal | 1. Install dual pilot relay protection system on Croton to Felch Road 138 kV circuit so that 3 phase to ground faults on the circuit will be cleared within 7 cycles. 2. Remove the sparing scheme of using Croton 138 kV breaker 500 to spare breaker 388 for Croton to Felch Road 138 kV circuit. 3. Remove Felch Road 138 kV BK 188 Bypassing | MI | MI | Other |  | Reliability | 540000 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
A in MTEP15 | A | East | METC | 8460 | 2015-12-28 | METC_14_045 | Hemphill - Sabine 138 kV Sag Remediation | Remediate the sag limit on the Sabine - Hemphill 138 kV line to increase its summer emergency rating to the 336 ACSR conductor rating of 208 MVA (871 Amps). | MI | MI | Other |  | Reliability | 140000 | 2017-12-31 | 2017-12-31 | 138 |  | Bottom-up
A in MTEP15 | A | East | METC | 8461 | 2015-12-28 | METC-14-043 | Cobb - Sternberg 138 kV Sag Remediation | Remediate the sag limit on the Cobb-Sternberg 138 kV line to bring its rating up to 174 MVA (730 Amp). | MI | MI | Other |  | Reliability | 480000 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
A in MTEP15 | A | East | METC | 8540 | 2015-12-28 | METC_14_044 | Claremont - Layton 138 kV Sag Remediation | Remediate the sag limit on the Claremont-Layton section of the Claremont - Cornell #1 138 kV line to bring its rating up to 209 MVA (874 Amps). | MI | MI | Other |  | Reliability | 520000 | 2017-12-31 | 2017-12-31 | 138 |  | Bottom-up
A in MTEP15 | A | East | METC | 9361 | 2016-03-23 | METC_15_002 | Green 138 kV Substation | A load interconnection request from Consumers Energy (CE) to serve the new Facility for Rare Isotope Beams (FRIB) on the Michigan State University campus. METC will install 4-138 kV breakers and associated disconnects, laid out in a ring bus configuration (future breaker and a half), as well as the control house, and all other 138 kV equipment required at the new Green substation. METC will loop the existing Delhi - College 138 kV line into Green and CE will construct two new 138 kV underground circuits between the Spartan and Green substations. METC will install approx. 7.2 miles of OPGW on the existing structures between College and Tihart, and add an anti-islanding scheme at College to avoid islanding the generation at Spartan with the load fed out of College sub. | MI | MI | Other |  | Reliability | 5307000 | 2016-10-01 | 2016-10-01 | 138 |  | Bottom-up
A in MTEP15 | A | East | NIPS | 8500 | 2015-12-28 |  | Lagrange 138kV Ring Bus | Create 138kV Ring Bus at lagrange Substation | IN | IN | BaseRel |  |  | 2715000 | 2018-12-31 | 2018-12-31 | 138 | 138 | Bottom-up
A in MTEP15 | A | East | NIPS | 9405 | 2015-12-28 |  | Kosciusko 13881 Switch | Replace Line Switch and substation Conductor at Kosciusko. | IN | IN | BaseRel |  |  | 147845 | 2018-05-01 | 2018-05-01 | 138 |  | Bottom-up
A in MTEP15 | A | East | NIPS | 9406 | 2015-12-28 |  | Reynolds 138kV (138109) Switches | Replace (2) 138kV Switches at Reynolds | IN | IN | BaseRel |  |  | 112665 | 2018-05-01 | 2018-05-01 | 138 |  | Bottom-up
A in MTEP15 | A | East | NIPS | 9461 | 2016-01-05 |  | Hiple 138kV Relay | Add Redundant 138kV Bus Differential Relay at Hiple | IN | IN | BaseRel |  |  | 50000 | 2018-12-31 | 2018-12-31 | 138 |  | Bottom-up
A in MTEP15 | A | East | WPSC | 3567 | 2015-12-28 | HY-WN | Hersey to Weidman | Hersey to Weidman line rebuild | MI | MI | Other |  | Reliability | 11500000 | 2017-12-31 | 2017-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | East | WPSC | 4086 | 2015-12-28 | FNX-SV | Fountain Junction to Scottville | Fountain Junction to Scottville Rebuild | MI | MI | Other |  | Reliability | 4650000 | 2016-12-31 | 2016-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | East | WPSC | 4384 | 2015-12-28 | Airport Xmsn | Airport Station Modification | The current configuration of the Airport station is not desirable from a planning or protection standpoint. The transformer protection clears the entire 138kV bus, there is primarily electromechanical relaying in the station and both the 138kV and 69kV the stations have oil circuit breakers. This project will upgrade both busses to ring bus configurations, put the current 138kV and 69kV stations in a common fence, replace oil breakers with SF6 and bring the design up to current Wolverine standards. | MI | MI | Other |  | Reconfig | 4190000 | 2017-01-01 | 2018-12-31 | 138 | 69 | Bottom-up
A in MTEP15 | A | East | WPSC | 7660 | 2015-12-28 | Advance Transmission | Advance Station Upgrade | Complete relocation and rebuild of the current Advance switching station to a ring bus design with a new protection and control system. | MI | MI | Other |  | Relocation | 2250000 | 2016-12-31 | 2016-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | East | WPSC | 7661 | 2015-12-28 | Vestaburg Transmission | Vestaburg Transmission | Convert transfer bus to straight bus, replace old station swiches and upgrade relaying to add a sparing scheme. | MI | MI | Other |  | Reconfig | 170000 | 2017-12-31 | 2017-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | East | WPSC | 7662 | 2015-12-28 | Atlanta Transmission | Atlanta Transmission | Replace outdated and unreliable switches on the bus and replace transformer bushings. | MI | MI | Other |  | Condition | 250000 | 2017-12-31 | 2017-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | East | WPSC | 7663 | 2015-12-28 | Gaylord OCB | Gaylord OCB | Replace oil breaker and upgrade battery bank and relaying for 125VDC operation | MI | MI | Other |  | Condition | 300000 | 2017-12-31 | 2017-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | East | WPSC | 8220 | 2016-08-30 | CV-WC Line Raise | Casnovia to White Cloud Line Raise | 1.93 miles of line has been requested by GLE to be raised to accommodate distribution underbuild. This project will rebuild a total of 2.5 miles to gradually tie the new taller poles into the existing line. The existing conductor is planned to be used for this project. | MI | MI | Other |  | Relocation | 800000 | 2016-05-31 | 2016-05-31 | 69 |  | Bottom-up
A in MTEP15 | A | East | WPSC | 8221 | 2015-12-28 | Airport Line Mods | Airport Station Line Modifications | This project will construct the line modifications required to route lines into the new Airport station. | MI | MI | Other |  | Relocation | 1000000 | 2017-12-31 | 2017-12-31 | 138 | 69 | Bottom-up
A in MTEP15 | A | East | WPSC | 8380 | 2015-12-28 | Advance Line Mods | Advance Line Modifications | Line modifications to support the new Advance Transmission station project. | MI | MI | Other |  | Relocation | 1250000 | 2016-12-31 | 2016-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | South | AECC | 8320 | 2015-12-28 |  | Tap EAI El Dorado - Monticello East 115 kV line: Construct 115 kV line, Hermitage 115/13.2 kV substation | Tap Entergy El Dorado 115 kV line: Construct 1.6 miles 115 kV line and Hermitage 115/13.2 kV substation. | AR | AR | Other |  | Distribution | 2060000 | 2017-10-01 | 2017-10-01 | 115 | 13.2 | Bottom-up
A in MTEP15 | A | South | AECC | 8341 | 2015-12-28 |  | Corning North 115kV Expansion | Expanding the Corning North 115kV Substation to add a second transformer. This expansion is necessary to serve a new 2.5MW load of the feed mill and poultry houses associated with the poultry processing plant coming online in the area. | AR | AR | Other |  | Distribution | 1500000 | 2015-08-01 | 2015-08-01 | 115 |  | Bottom-up
A in MTEP15 | A | South | AECC | 8342 | 2015-12-28 |  | Pocahontas East 161kV Load Addition | 3.5 mile radial tap from the coop owned Pocahontas East substation to a new distribution substation to accomodate new load in the area associated with the PECO Poultry Processing Plant. | AR | AR | Other |  | Distribution | 4750000 | 2015-08-01 | 2015-08-01 | 161 |  | Bottom-up
A in MTEP15 | A | South | AECC | 8400 | 2015-12-28 |  | Tap EAI El Dorado to Monticello East 115kV line, Construct 115kV line, 115/69kV substation | Tap EAI El Dorado to Monticello East 115kV line, build 13 miles 115kV line, build 115/69kV substation | AR | AR | Other |  | Distribution | 6400000 | 2017-04-01 | 2017-04-01 | 115 | 69 | Bottom-up
A in MTEP15 | A | South | AECC | 8402 | 2016-09-20 |  | Camden South to Camden West 115kV transmission line, 115/13.2kV substation | Construct 7 mile 115kV transmission line from the existing Camden South delivery point to the proposed Camden West substation, construct Camden West 115/13.2kV substation. | AR | AR | Other |  | Distribution | 3950000 | 2019-12-01 | 2019-12-01 | 115 | 13.2 | Bottom-up
A in MTEP15 | A | South | AECC | 8420 | 2016-02-22 |  | Ingram 161/25kV Substation | New 161/25kV substation with inital load of 12,000kW. | AR | AR | Other |  | Distribution | 5861500 | 2017-12-01 | 2017-12-01 | 161 | 24.9 | Bottom-up
A in MTEP15 | A | South | AECC | 8480 | 2015-12-28 |  | Gainesville 161/13.2kV Substation | New 161/13.2kV substation with initial load of 9,500 KW. | AR | AR | Other |  | Distribution | 7000000 | 2017-01-01 | 2017-01-01 | 161 | 13.2 | Bottom-up
A in MTEP15 | A | South | CLECO | 8980 | 2015-12-28 |  | West Fork 230kV Ring Bus | Add a 230 kV Ring Bus at Westfork Substation. | LA | LA | Other |  | Reliability | 2308708 | 2015-10-30 | 2015-10-30 | 230 |  | Bottom-up
A in MTEP15 | A | South | CLECO | 9042 | 2015-12-28 |  | Coughlin Breaker Replacements | Replace Breakers 8000, 8128, 8006, 8115, 8009 at Coughlin. | LA | LA | Other |  | Reliability | 725008 | 2015-10-01 | 2015-10-01 | 138 |  | Bottom-up
A in MTEP15 | A | South | CLECO | 9340 | 2015-12-28 |  | 9340 - Longville Line Tap | Tap the Existing Deridder to Nelson 138 kV line and build a new substation Longville to serve new customer load. | LA | LA | Other |  | Reliability | 4400000 | 2016-12-01 | 2016-12-01 | 138 |  | Bottom-up
A in MTEP15 | A | South | CLECO | 9421 | 2015-12-28 |  | TXEastern Opelousas Tap | Tap the Existing Plaisance to Veazie 138 kV line with a new substation Texas Eastern to serve current customer plant expansion. | LA | LA | Other |  | Distribution | 5400000 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
A in MTEP15 | A | South | CLECO, Entergy-LA | 7988 | 2015-12-28 | 15-ELL-001 | Schriever to Bayou Vista 230 kV line(Entergy and CLECO Joint Project) | Construct approximately 30.44 miles of 230 kV line from Terrebonne 230 kV substation(Entergy owned) to Bayou Vista 230 kV substation (CLECO owned).This is a CLECO and Entergy joint project, Cleco's portion includes 12.1 miles of 230 kV line and expanding Bayou Vista substation to 230 kV and installing 230-138 kV auto transformer at Bayou Vista substation. Entergy's portion includes approx. 18.33 miles of 230 line from Schriever 230 kV substation. | LA | LA | BaseRel |  |  | 75900000 | 2018-06-01 | 2018-06-01 | 230 | 138 | Bottom-up
A in MTEP15 | A | South | Entergy-AR | 4666 | 2015-12-28 | 12-EAI-014 | Mabelvale-Bryant: Reconductor 115kV line | Identified in MCPS study to relieve congestion on the Mabelvale - Bryant - Bryant South 115 kV line. EAI has agreed to fund the upgrade to reduce congestion for the area. | AR | AR | Other |  | Economic | 6371120 | 2019-12-01 | 2019-12-01 | 115 |  | Bottom-up
A in MTEP15 | A | South | Entergy-AR | 4669 | 2016-02-16 | 11-EAI-015 | Jim Hill Area Upgrades - Rebuild Jim Hill - Datto line and convert to 161kV | Rebuild the Jim Hill - Datto 115kV line and convert it from 115kV to 161kV operation. Install breakers at Datto. After the completion of the project, remove the mobile temporary capacitor bank at Datto. | AR | AR | BaseRel |  |  | 43729766 | 2019-05-01 | 2019-05-01 | 161 |  | Bottom-up
A in MTEP15 | A | South | Entergy-AR | 7925 | 2015-12-28 | 14-EAI-026 | Black Rock to Imboden: Construct new 69kV transmission line | Add 69kV breaker in AECC's Black Rock station and build a new 0.4 mile 69 kV line from Black Rock to Imboden. | AR | AR | Other |  | Distribution | 3133719 | 2016-10-15 | 2016-10-15 | 69 |  | Bottom-up
A in MTEP15 | A | South | Entergy-AR | 7928 | 2015-12-28 | 15-EAI-002 | Jonesboro EHV: Tap ISES - Dell 500kV line and build 500/161 kV station near Hergett station | Tap ISES - Dell 500kV line, build a 500/161kV station with a 800MVA auto, and tie in the Jonesboro - Hergett and Hergett - Trumann W. 161kV lines into the new station. | AR | AR | BaseRel |  |  | 74965393 | 2017-11-15 | 2017-11-15 | 500 | 161 | Bottom-up
A in MTEP15 | A | South | Entergy-AR | 8680 | 2015-12-28 | 15-EAI-008 | Conway Middle Road 161 kV substation: Construct new substation | Construct a new 161 kV substation at Conway Middle Road. The new substation will be cut into the Conway Industrial - Hamlet SS 161 kV line approximately 0.7 miles east of Conway Industrial. | AR | AR | Other |  | Distribution | 786000 | 2016-09-20 | 2016-09-20 | 161 |  | Bottom-up
A in MTEP15 | A | South | Entergy-AR | 8681 | 2015-12-28 | 15-EAI-009 | Jefferson Industrial 115 kV substation: Construct new substation | Construct NEW 115 kV substation named Jefferson Industrial to serve new industrial block load request. New substation will be cut into Woodward - Pine Bluff Arsenal D 115 kV line. | AR | AR | Other |  | Distribution | 5257000 | 2016-11-01 | 2016-11-01 | 115 |  | Bottom-up
A in MTEP15 | A | South | Entergy-AR | 8860 | 2015-12-28 | 14-EAI-020-9 | EAI Underrated Breaker Project: Paragould 115 kV B7315-TCO | Replace breaker B7315-TCO at Paragould due to insufficient fault interrupting capability. | AR | AR | Other |  | Reliability | 256005 | 2016-12-01 | 2016-12-01 | 115 |  | Bottom-up
A in MTEP15 | A | South | Entergy-LA | 4604 | 2015-12-28 | 14-EGL-016 | Port Hudson to Zachary REA 69 kV Line Reconductor | Upgrade the Port Hudson to Zachary 69 kV line conductor, risers, and line jumpers (approximately 5.76 miles, existing rating of 93 MVA) to a rating of at least 211 MVA. Upgrade the remaining entire electrical circuit path including but not be limited to the line switches, traps, or any and all other appurtenant facilities along the line segment between and including Port Hudson and Zachary REA stations to a minimum of 1200 A, 143 MVA. The resulting line rating will be limited then by the 1200 A, 143 MVA station equipment | LA | LA | BaseRel |  |  | 11202000 | 2017-02-24 | 2017-02-24 | 69 |  | Bottom-up
A in MTEP15 | A | South | Entergy-LA | 4606 | 2015-12-28 | 14-EGL-004 | Fancy Point: Add 2nd 500-230 kV, 1200 MVA transformer | Add a second 500-230 kV, 1200MVA bank (composed of single phase units) at the Fancy Point substation. | LA | LA | BaseRel |  |  | 92000000 | 2019-03-01 | 2019-03-01 | 500 | 230 | Bottom-up
A in MTEP15 | A | South | Entergy-LA | 4630 | 2015-12-28 | 11-EGL-018 | Francis to Marydale: Upgrade 69 kV line | Reconductor the Francis to Marydale 69 kV line to a minimum of 105 MVA | LA | LA | BaseRel |  |  | 13283208 | 2017-06-01 | 2017-06-01 | 69 |  | Bottom-up
A in MTEP15 | A | South | Entergy-LA | 7919 | 2015-12-28 | 15-EGL-002 | Vincent 230 kV Substation: Add 61 MVAR capacitor bank | Install 230 kV 61 MVAR cap bank at Vincent 230 kV substation | LA | LA | BaseRel |  |  | 1324421 | 2016-12-01 | 2016-12-01 | 230 |  | Bottom-up
A in MTEP15 | A | South | Entergy-LA | 7923 | 2015-12-28 | 15-EGL-005 | Lake Charles Bulk to Chlomal 69 kV Line: Reconductor line | Re-conductor Lake Charles Bulk to Chlomal 69 kV line and station equipment at Lake Charles bulk. | LA | LA | BaseRel |  |  | 2905700 | 2017-06-01 | 2017-06-01 | 69 |  | Bottom-up
A in MTEP15 | A | South | Entergy-LA | 7948 | 2015-12-28 | 15-EGL-009 | Scott to Carencro 69 kV line: Reconductor Line | Upgrade relay/relay settings at Carencro and Re-conductor Scott to Carencro 69 kV line | LA | LA | BaseRel |  |  | 6822535 | 2017-06-01 | 2017-06-01 | 69 |  | Bottom-up
A in MTEP15 | A | South | Entergy-LA | 8585 | 2015-12-28 | 15-EGL-016 | LCTP: Construct new Rhodes 500 kV switching station | Construct a new 500 kV, 3000 A, three breaker ring bus switching station west of Nelson on the Nelson to Hartburg 500 kV line. | LA | LA | BaseRel |  |  | 28070000 | 2018-03-18 | 2018-03-18 | 500 |  | Bottom-up
A in MTEP15 | A | South | Entergy-LA | 8586 | 2015-12-28 | 15-EGL-017-01 | LCTP: Construct new 500-230 kV Bulk Substation west of Carlyss. Install new 500-230 kV, 1200 MVA autotransformer composed of three single phase units | Construct a new 500-230 kV substation west of the existing Carlyss 230 kV substation. This includes the installation of a new 500-230 kV, 1200 MVA autotransformer bank at the new 500-230 kV bulk station comprised of (3) single phase units. | LA | LA | BaseRel |  |  | 31530000 | 2018-03-18 | 2018-03-18 | 500 | 230 | Bottom-up
A in MTEP15 | A | South | Entergy-LA | 8587 | 2015-12-28 | 15-EGL-017-02 | LCTP: Construct new 500 kV transmission line from Rhodes to new 500/230 kV Bulk Substation west of Carlyss | Construct approximately 11.5 miles of new 500 kV transmission line from the new Rhodes 500 kV switching station to a new 500-230 kV bulk station west of the existing Carlyss 230 kV substation. | LA | LA | BaseRel |  |  | 43000000 | 2018-03-18 | 2018-03-18 | 500 |  | Bottom-up
A in MTEP15 | A | South | Entergy-LA | 8588 | 2015-12-28 | 15-EGL-017-03 | LCTP: Construct new 230 kV line from new Bulk Substation to Carlyss 230 kV substation | Construct approximately 1.5 miles of new 230 kV transmission line from the new 500-230 kV bulk substation west of Carlyss to the existing Carlyss 230 kV substation. | LA | LA | BaseRel |  |  | 8690000 | 2018-03-18 | 2018-03-18 | 230 |  | Bottom-up
A in MTEP15 | A | South | Entergy-LA | 8589 | 2015-12-28 | 15-EGL-018 | LCTP: Reconfigure Carlyss 230 kV substation into a breaker and a half configuration | Expand the existing Carlyss 230 kV substation into a breaker and a half operating scheme. Replace the underrated 230 kV breakers with ones having sufficient short circuit interrupting due to the increase in fault currents. The breakers to be replaced are: 8775-IC 13145-CO 13150-CO 13155-CO 13480-CO 13500-CO 13580-CO | LA | LA | BaseRel |  |  | 14050000 | 2018-03-18 | 2018-03-18 | 230 |  | Bottom-up
A in MTEP15 | A | South | Entergy-LA | 8590 | 2015-12-28 | 15-EGL-019 | LCTP: Construct new 12 mile 230 kV line from Carlyss to new 230 kV substation adjacent to Graywood | Construct approximately 12 miles of new 230 kV transmission line from Carlyss to the Solac 230 kV substation. The line will be designed and routed to accommodate a future cut-in into the Calcasieu substation. Add a 230 kV line bay terminal at Carlyss and the Graywood 230 kV substation to facilitate the termination of the new line. | LA | LA | BaseRel |  |  | 33160000 | 2018-03-18 | 2018-03-18 | 230 |  | Bottom-up
A in MTEP15 | A | South | Entergy-LA | 9284 | 2015-12-28 | 15-ELL-006 | Bayou Verret 230 kV: Add Cap Bank | Install two 40.7 MVAR 230 kV cap banks at Bayou Verret substation. | LA | LA | BaseRel |  |  | 1684477 | 2017-08-31 | 2017-08-31 | 230 |  | Bottom-up
A in MTEP15 | A | South | Entergy-LA | 9285 | 2015-12-28 | 15-ELL-005 | Waterford - Vacherie 230 kV: Reconductor Line | Reconductor the Waterford to Vacherie 230 kV line. | LA | LA | BaseRel |  |  | 19732950 | 2019-06-01 | 2019-06-01 | 230 |  | Bottom-up
A in MTEP15 | A | South | Entergy-MS | 7898 | 2015-12-28 | 15-EMI-001 | Greenville to Greenville East 115 kV: Upgrade switches | Upgrade LAB, TAB, and BAB switches in E Greenville line bay at Greenville 115 kV to greater than 810A rating. | MS | MS | BaseRel |  |  | 463871 | 2016-12-31 | 2016-12-31 | 115 |  | Bottom-up
A in MTEP15 | A | South | Entergy-MS | 7901 | 2015-12-28 | 15-EMI-002 | Natchez to Natchez SES (both lines) 115 kV: Upgrade relaying | Upgrade 600A relaying and CTs at Natchez SES and Natchez on both 115 kV lines (line 168 and 169) to minimum 810A (minimum conductor on 3 inbetween line sections). | MS | MS | BaseRel |  |  | 796791 | 2016-12-01 | 2016-12-01 | 115 |  | Bottom-up
A in MTEP15 | A | South | Entergy-TX | 4617 | 2015-12-28 | 13-ETI-013 | Egypt to Panorama 138 kV Line: Reconductor line | Reconductor approximately 1.16 miles of 138 kV line to a minimum of 468 MVA (1272 ACSS). Line Bay bus and risers (currently 649.5 ACAR rated at 860 amps) and 1033 AAC rated at 1017 amps) will also need to be replaced at Panorama to meet or exceed the conductor rating of 468 MVA (1957 amps). | TX | TX | BaseRel |  |  | 3347942 | 2017-05-01 | 2017-05-01 | 138 |  | Bottom-up
A in MTEP15 | A | South | Entergy-TX | 4653 | 2015-12-28 | 11-ETI-038 | Reconductor Sabine to Port Neches Bulk (via Linde Line 516) | Install reactor at Port Neches Bulk on the Sabine bay. | TX | TX | BaseRel |  |  | 4358791 | 2017-12-01 | 2017-12-01 | 138 |  | Bottom-up
A in MTEP15 | A | South | Entergy-TX | 7947 | 2015-12-28 | 11-ETI-002 | Reconductor Sabine to Port Neches Bulk (Line 515): Add Reactor at Sabine 138 kV | Sabine to Port Neches 138 kv line install reactors at Sabine 138 kV. | TX | TX | BaseRel |  |  | 4363775 | 2017-12-01 | 2017-12-01 | 138 |  | Bottom-up
A in MTEP15 | A | South | Entergy-TX | 8582 | 2015-12-28 | 15-ETI-007-01 | Alden 138 kV Substation: Add 200 MVAR SVC | Add a +200/-100 MVar SVC at the existing Alden 138 kV substation. | TX | TX | BaseRel |  |  | 31593000 | 2016-10-03 | 2016-10-03 | 138 |  | Bottom-up
A in MTEP15 | A | South | Entergy-TX | 8583 | 2015-12-28 | 15-ETI-007-02 | Oakridge 138 kV Substation: Add Capacitor Bank | Add a 138 kV, 25.1 MVAR capacitor bank to the 138 kV bus. | TX | TX | BaseRel |  |  | 912000 | 2016-10-03 | 2016-10-03 | 138 |  | Bottom-up
A in MTEP15 | A | South | Entergy-TX | 9241 | 2015-12-28 | 15-ETI-019 | Deer Lake 138 kV substation: Construct New Substation | Construct a new 138 kV substation to serve load in the Montgomery County, TX area. The new substation will be placed on the existing Ponderosa to Navasota line number 96 between the Fish Creek and Spring Branch substations near the line crossing of Deer Lake Lodge Road. | TX | TX | Other |  | Reliability | 675157 | 2016-12-01 | 2016-12-01 | 138 |  | Bottom-up
A in MTEP15 | A | South | Entergy-TX | 9242 | 2015-12-28 | 15-ETI-020 | Wildcat 69 kV substation: Construct New Substation | Entergy is proposing to construct a new 69 kV substation (Wildcat 69 kV Substation) which will serve a new block load addition in East Texas, near Beaumont, TX. The new block load addition will be placed on 69 kV line 98 which is between the South Beaumont and Nitro 69 kV substations. New transmission facilities including approximately 0.1 miles of new 69 kV double circuited transmission line will also need to be constructed in order to connect the new substation. The new substation will be where 69 kV line 98 intersects with Sulphur Plant Road. The interconnection will cut the existing 69 kV line 98 between South Beaumont and Nitro, at approximately 1.5 miles north of Nitro. The line will then be routed in and out through the new Wildcat 69 kV substation which is located adjacent to the transmission line. | TX | TX | Other |  | Reliability | 5159000 | 2016-11-01 | 2016-11-01 | 69 |  | Bottom-up
A in MTEP15 | A | South | Entergy-TX | 9280 | 2015-12-28 | 15-ETI-016 | Cypress 500/138 kV: New 2nd Auto | Install second 500/138 kV auto at Cypress. | TX | TX | BaseRel |  |  | 14392680 | 2020-06-01 | 2020-06-01 | 500 | 138 | Bottom-up
A in MTEP15 | A | South | Entergy-TX | 9281 | 2015-12-28 | 15-ETI-014 | Cleveland - Tarkington 138 kV: Reconductor Line | Reconductor 9.3 miles and upgrade all related equipment | TX | TX | BaseRel |  |  | 9451175 | 2018-08-31 | 2018-08-31 | 138 |  | Bottom-up
A in MTEP15 | A | South | Entergy-TX | 9282 | 2015-12-28 | 15-ETI-015-1 | South Beaumont - Carroll St Ckt1 138 kV: Reconductor Line | Reconductor 3.3 miles and upgrade all related equipment. | TX | TX | BaseRel |  |  | 1636587 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
A in MTEP15 | A | South | Entergy-TX | 9283 | 2015-12-28 | 15-ETI-015-2 | South Beaumont - Carroll St Ckt2 138 kV: Reconductor Line | Reconductor 3.3 miles and upgrade all related equipment | TX | TX | BaseRel |  |  | 1767746 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
A in MTEP15 | A | South | Entergy-TX | 9460 | 2015-12-28 | 15-ETI-001 | South Beaumont 138 kV: Replace Existing 138/69 Autos & Reconfigure Bus Work | Replace the 2 Existing 138/69 kV Autos with 200 MVA autos and reconfigure the Bus Work. | TX | TX | BaseRel |  |  | 16559809 | 2017-11-01 | 2017-11-01 | 138 | 69 | Bottom-up
A in MTEP15 | A | South | Entergy-TX | 9482 | 2015-12-28 | 15-ETI-023 | China to Stowell 230 kV: Construct New Line | Construct a new 230 kV line from China to Stowell with a minimum rating of 1950 Amps. Install a 230/138 kV 400 MVA autotransformer at Stowell. | TX | TX | BaseRel |  |  | 57300000 | 2019-06-01 | 2019-06-01 | 230 | 138 | Bottom-up
A in MTEP15 | A | South | Entergy-TX | 10487 | 2016-01-06 | 15-ETI-024; 15-ETI-025 | Western Region Economic Project(WREP): New Grimes to Lewis Creek 230 kV Line, New Grimes 345/230 kV Auto, & Newton Bulk to Leach 138 kV reconductor | Build a new 230 kV line from Grimes to Lewis Creek and install a second 345/230 kV auto at the Grimes station. Rebuild the ~25 mile long Newton Bulk – Leach 138 kV line. | TX | TX | Other |  | Economic | 155820000 | 2019-06-01 | 2020-06-01 | 345 | 230 | Bottom-up
A in MTEP15 | A | South | ETEC | 8208 | 2015-12-28 | PRJ 07 | Luce Bayou 138kV | Cut into Tarkington-Long John 138 kV and install new Luce Bayou 138 kV substation. | TX | TX | Other |  | Distribution | 16300000 | 2017-12-31 | 2017-12-31 | 138 |  | Bottom-up
A in MTEP15 | A | South | LAFA | 8820 | 2015-12-28 |  | Northeast Station | New 230-69 autotransformer to feed new 69kv line to feed new 69kv station to alleviate distribution loading. | LA | LA | Other |  | Distribution | 10500000 | 2018-12-31 | 2018-12-31 | 230 | 69 | Bottom-up
A in MTEP15 | A | South | SMEPA | 8120 | 2016-09-26 |  | Rebuild L18 and L18A (Ellisville to Glade GOAB to Cleo) 69kV Lines | Rebuild the existing Ellisville - Glade GOAB - Cleo 69kV lines using 795 ACSR conductor. | MS | MS | Other |  | Reliability | 2860000 | 2016-10-31 | 2017-04-30 | 69 |  | Bottom-up
A in MTEP15 | A | South | SMEPA | 8560 | 2016-02-03 |  | SMEPA/SOCO IC (Jasper County) | Tap the Missionary - Waynesboro 161kV line (SMEPA L232) at the intersection with Mississippi Power Company (MPCo?s) Laurel East - Enterprise 230kV line. Add a new 230/161kV autotransformer at the Missionary substation and convert the entire Missionary - Waynesboro line to 230kV operation. Construct a new 161kV line from Homewood - Missionary utilizing existing double circuit lines as well as rebuilding existing 69kV lines to double circuit specifications that currently span from Homewood - Missionary. *Note: L232 was constructed using 230kV insulation, but is currently operated at 161kV | MS | MS | Other |  | Reliability | 18960000 | 2017-12-31 | 2020-09-01 | 230 | 161 | Bottom-up
A in MTEP15 | A | South | SMEPA | 9000 | 2015-12-28 |  | Rebuild L71A (Benndale to Benndale GT) 69kV Line | Rebuild the existing Benndale - Benndale GT 69kV line using 795 ACSR conductor and 48-fiber OPGW. | MS | MS | Other |  | Reliability | 370000 | 2016-07-15 | 2016-07-15 | 69 |  | Bottom-up
A in MTEP15 | A | South | SMEPA | 9020 | 2016-09-26 |  | Rebuild L37A&B (Big Level to Wiggins GOAB) 69kV Line | Rebuild the existing Big Level - Wiggins GOAB 69kV line using 795 ACSR conductor and 48-fiber OPGW. | MS | MS | Other |  | Reliability | 1875000 | 2017-12-31 | 2017-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | West | ATC | 3159 | 2015-12-28 | PR03817 | Uprate West Middleton-Stage Coach 69 kV | West Middleton-Timberlane-Stage Coach 69 kV line uprate | WI | WI | Other |  | Reliability | 2000000 | 2017-12-31 | 2018-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | West | ATC | 4353 | 2015-12-28 | PR05933 | Construct Creekview 138 kV T-D | Add new load at Creekview 138 kV substation and associated network upgrades | WI | WI | Other |  | Distribution | 16000000 | 2017-12-01 | 2017-12-01 | 138 |  | Bottom-up
A in MTEP15 | A | West | ATC | 4419 | 2015-12-28 | PR05948 | Uprate Sunset Point jumpers | Uprate the jumpers of 138kV lines Sunset Point - Mears Corners (MCRG21) and Sunset Point - Ellinwood (STPG311) | WI | WI | BaseRel |  |  | 109000 | 2016-05-17 | 2016-06-01 | 138 |  | Bottom-up
A in MTEP15 | A | West | ATC | 4421 | 2015-12-28 | PR06011 | Construct Williams Bay 138 kV Substation | Loop Elkhorn - Brick Church (X-44) 138kV line in and out of Williams Bay, add two 138kV line breakers and addition of a new distribution transformer | WI | WI | Other |  | Distribution | 4450000 | 2017-07-01 | 2017-07-01 | 138 |  | Bottom-up
A in MTEP15 | A | West | ATC | 4422 | 2015-12-28 | PR05969 | Construct Brillion Iron Works 138/69 kV substation and extend M-65 69 kV line | Loop Shoto - Glenview (L-90) 138kV line into new 138/69/12.47kV Brillion Iron Works (BIW) substation, add a 138/69kV transformer at BIW and extend Glenview - Brillion Iron (M-65) 69kV line to new 69kV bus | WI | WI | Other |  | Distribution | 12500000 | 2016-08-19 | 2016-08-19 | 138 | 69 | Bottom-up
A in MTEP15 | A | West | ATC | 4732 | 2015-12-28 | PR06105 | Construct Ogden Street 69 kV T-D | Construct a new 69kV line from Ogden St. - Bayshore, rebuild Bayshore - 2nd St. - Fiber switching structure (N-14) 69kV and install two line breakers at Odgen St. | WI | WI | Other |  | Distribution | 10400000 | 2018-12-01 | 2018-12-01 | 69 |  | Bottom-up
A in MTEP15 | A | West | ATC | 7601 | 2015-12-28 | PR06199 | Montello 69 kV breaker additions | Add line breakers to Y-17 at Montello 69 kV. Add 8 Mvar capacitor at Montello 69 kV and remove mobile capacitor at Lakehead Portage. | WI | WI | Other |  | Reliability | 3400000 | 2016-06-21 | 2016-07-01 | 69 |  | Bottom-up
A in MTEP15 | A | West | ATC | 7602 | 2015-12-28 | PR05440 | Rerate Bunker Hill - Kelly 115 kV | Rerate Bunker Hill - Kelly 115 kV based on SBRM. This project is a part of PR05440. | WI | WI | BaseRel |  |  | 4800000 | 2019-10-31 | 2019-10-31 | 115 |  | Bottom-up
A in MTEP15 | A | West | ATC | 7603 | 2015-12-28 | PR05440 | Rebuild Bunker Hill - Blackbrook 115 kV | Rebuild Blackbrook - Bunker Hill portion of M-13. Retire Blackbrook and Bunker Hill stations and build new Roehring Rd ring bus. | WI | WI | BaseRel |  |  | 25200000 | 2019-11-01 | 2019-11-01 | 115 |  | Bottom-up
A in MTEP15 | A | West | ATC | 7741 | 2015-12-28 | PR06198 WO:600800 F4314 | Dellwood Line Breaker 69 kV | Install capacitor bank at Dellwood 69 kV and remove mobile capacitor bank at McKenna. | WI | WI | Other |  | Reliability | 3100000 | 2016-12-15 | 2016-12-15 | 69 |  | Bottom-up
A in MTEP15 | A | West | ATC | 7780 | 2015-12-28 | PR6489 | T-D Esker View | Build new 138/24.9 kV distribution substation. | WI | WI | Other |  | Distribution | 4500000 | 2017-03-01 | 2017-03-01 | 138 | 24.9 | Bottom-up
A in MTEP15 | A | West | ATC | 7981 | 2015-12-28 | PR05258 | Rebuild Beardsley St 69 kV Substation | Breaker additions at Beardsley St to sectionalize J-10 circuit | WI | WI | Other |  | Reliability | 2500000 | 2016-12-31 | 2016-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | West | ATC | 8065 | 2015-12-28 | PR07164, WO601615, F4693 | Construct Southeast Wisconsin - Northeast Illinois 345 kV transmission reinforcement | Reconfigure the Pleasant Prairie - Arcadian 345kV (PLPL81) and Zion - Libertyville 345 kV (2224) transmission lines to loop into a new 4 position (breaker and half) 345 kV Switching Station. | WI | IL | BaseRel |  |  | 52000000 | 2020-12-31 | 2020-12-31 | 345 |  | Bottom-up
A in MTEP15 | A | West | ATC | 8071 | 2015-12-28 |  | Plains - National 138 kV line | New Plains - National 138 kV line | MI | MI | BaseRel |  |  | 124602000 | 2023-12-31 | 2023-12-31 | 138 |  | Bottom-up
A in MTEP15 | A | West | ATC | 8660 | 2015-12-28 | PR07030 | Construct Somers 138 kV T-D | Reconfigure Somers substation to add second 138/24.9 kV distribution transformer. | WI | WI | Other |  | Distribution | 2800000 | 2020-09-01 | 2020-09-01 | 138 | 24.9 | Bottom-up
A in MTEP15 | A | West | ATC | 9080 | 2015-12-28 |  | Install W. Marinette 138-69 kV transformer high-side protection | Install high and low side breakers on existing 138/69 kV transformer. . | WI | WI | Other |  | Reliability | 4500000 | 2018-12-31 | 2018-12-31 | 138 |  | Bottom-up
A in MTEP15 | A | West | ATC | 9081 | 2015-12-28 |  | Reconductor De Pere - Glory Road 138 kV | Reconductor R122 De Pere - Glory Road 138 kV line | WI | WI | BaseRel |  |  | 736000 | 2018-03-01 | 2018-03-01 | 138 |  | Bottom-up
A in MTEP15 | A | West | DPC | 7664 | 2015-12-28 |  | Rebuild Briggs Road-La Crosse Tap 161 kV | Dairyland Power Cooperative plans to rebuild the Briggs Road-La Crosse Tap 161 kV line on the existing right-of-way. The rebuild will include replacing the poles and installing 795 ACSS conductor for 8.8 miles between the Briggs Road substation and the La Crosse Tap 3-way switch. | WI | WI | Other |  | Condition | 12000000 | 2017-04-21 | 2017-04-21 | 161 |  | Bottom-up
A in MTEP15 | A | West | GRE | 3782 | 2015-12-28 | 20425 | Mantrap 115 kV Conversion | Convert Mantrap and Potato Lake Dist. Substation from 34.5 kV to 115 kV operation | MN | MN | Other |  | Distribution | 4463269.15 | 2016-10-27 | 2016-10-27 | 115 |  | Bottom-up
A in MTEP15 | A | West | GRE | 4377 | 2015-12-28 | 202497 | Yankee Doodle Bus Tie Breaker | Install bus tie breaker between Yankee Doodle North and South | MN | MN | BaseRel |  |  | 891673.78 | 2016-11-03 | 2016-11-03 | 115 |  | Bottom-up
A in MTEP15 | A | West | GRE | 7894 | 2015-12-28 | 202989 | Stockade Pumping Station | GRE proposes to tap the GRE-owned Wakefield - Big Swan 115 kV line and build a new, ~6 mile, 115 kV transmission to the proposed pumping station. | MN | MN | Other |  | Reliability | 3812779 | 2017-10-02 | 2017-10-02 | 115 | 115 | Bottom-up
A in MTEP15 | A | West | GRE | 7899 | 2015-12-28 | 202988 | Cedar Lake Pumping Station | Install a transmission line to connect to MVEC's Cedar Lake pump station sub. Line to be built to 115kV specs but initially energized at 69kV. Line length is undetermined at this point. 6 miles are assumed. | MN | MN | Other |  | Reliability | 4989151.97 | 2017-10-19 | 2017-10-19 | 115 | 115 | Bottom-up
A in MTEP15 | A | West | GRE | 7912 | 2015-12-28 | 202919 | Lawndale to Bass Lake 2.0 mile 115 kV Rebuild | Construct two miles of 115 kV line with 795 ACSS conductor from Lawndale Tap, which is between Bass Lake and Cedar Island, to the high side structure of new Wright Hennepin Electric Cooperative's Lawndale #2 distribution substation. | MN | MN | Other |  | Distribution | 2000000 | 2021-05-01 | 2021-05-01 | 115 | 115 | Bottom-up
A in MTEP15 | A | West | ITCM | 8042 | 2015-12-28 | Burl Sourth Sub | ITCM Burlington South Sub Modifications | Alliant Energy will install high side protection at the Burlington South substation. ITC protection equipment will be removed and switches will be replaced. | IA | IA | Other |  | Relaying | 60000 | 2016-12-31 | 2016-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | West | ITCM | 8043 | 2015-12-28 | Cust Interconnet Blanket | ITCM Customer Interconnections with short lead time | These projects are being done at the request of an interconnection customer in order to facilitate new load, re-distribute existing load, improve the performance of the sub-transmission and distribution systems, or to accommodate a new Transmission-to-Transmission connection request. | IA,MN,IL | IA,MN,IL | Other |  | Distribution | 4800000 | 2017-12-31 | 2018-12-31 | 345 | 69 | Bottom-up
A in MTEP15 | A | West | ITCM | 8048 | 2015-12-28 | Cntrl Enclosure Blanket | ITCM Control Enclosure Blanket | Replace the older control enclosures that are too deteriorated to be refurbished. | IA,MN,IL | IA,MN,IL | Other |  | Condition | 1860000 | 2015-12-31 | 2016-12-31 | 345 | 69 | Bottom-up
A in MTEP15 | A | West | ITCM | 8049 | 2015-12-28 | NERC Com Mitigation | ITCM NERC Compliance Mitigation | Install a redundant DC Battery system and add a redundant differential relay scheme to the 345/161kV transformer. 1.Meeting NERC Compliance guidelines 2.Addressing issues related to the DAEC INPO audit also identifying the need for having redundant tripping from redundant battery sets 3.Redundant batteries at a nuclear facility. | IA,MN,IL | IA,MN,IL | Other |  | Reliability | 180000 | 2015-12-31 | 2016-12-31 | 345 | 69 | Bottom-up
A in MTEP15 | A | West | ITCM | 8051 | 2015-12-28 | NRUC/ERUC | ITCM NRUC/ERUC Replacement Program | The need for replacing miscellaneous aged, broken, or failed equipment in the field ? primarily in substations. Equipment replacements identified from maintenance inspections, such as batteries, field capacitors, control building HVAC units, transformer t | IA,MN,IL | IA,MN,IL | Other |  | Condition | 9000000 | 2015-12-31 | 2016-12-31 | 345 | 69 | Bottom-up
A in MTEP15 | A | West | ITCM | 8053 | 2015-12-28 | Poor Performing Ckts | ITCM Poor Performing Circuits Blanket | Rebuild poor performing circuits that have been identified as a system reliability issue | IA,MN,IL | IA,MN,IL | Other |  | Reliability | 4800000 | 2015-12-31 | 2016-12-31 | 69 | 34 | Bottom-up
A in MTEP15 | A | West | ITCM | 8057 | 2015-12-28 | SCADA Blanket | ITCM SCADA Program | 1. Project includes the Engineering, Procurement, Construction and Commissioning of ITCM?s SCADA system 2. Upgrade and/or install TELECOM, Remote Terminal Unit (RTU)s, Annunciator and Relay communication network 3. Re-direction of alarm signals and station data communications | IA,MN,IL | IA,MN,IL | Other |  | SCADA | 360000 | 2015-12-31 | 2016-12-31 | 345 | 69 | Bottom-up
A in MTEP15 | A | West | ITCM | 8058 | 2015-12-28 | Signage Blanket | ITCM Tower/Pole Signage Program | Add pole signage to transmission towers and poles that are not currently numbered to aid field personnel in troubleshooting activities and performing scheduled inspections and maintenance. | IA,MN,IL | IA,MN,IL | Other |  | Condition | 1200000 | 2015-12-31 | 2016-12-31 | 345 | 69 | Bottom-up
A in MTEP15 | A | West | ITCM | 8074 | 2015-12-28 | Fairfax Cap | ITCM Fairfax 42MVAR 161kV Cap | Adding a 42 MVAR 161 kV capacitor bank at Fairfax is part of the plan to add a total of 170 MVAR in the Cedar Rapids area. | IA | IA | BaseRel |  |  | 1687896 | 2017-06-30 | 2017-06-30 | 161 |  | Bottom-up
A in MTEP15 | A | West | ITCM | 8086 | 2015-12-28 | Radio 69kV Cap | ITCM Radio 13.2MVAR 69kV Cap | Adding a 13.2 MVAR 69 kV capacitor bank at NE Marion (Radio) is part of the plan to add a total of 170 MVAR in the Cedar Rapids area. | IA | IA | Other |  | Reliability | 524804 | 2016-02-29 | 2016-02-29 | 69 |  | Bottom-up
A in MTEP15 | A | West | ITCM | 8088 | 2015-12-28 | Hiawatha Cap | ITCM Hiawatha 42MVAR 161kV Cap | Adding a 42 MVAR 161 kV capacitor bank at Hiawatha is part of the plan to add a total of 170 MVAR in the Cedar Rapids area. | IA | IA | BaseRel |  |  | 193795.2 | 2018-12-31 | 2018-12-31 | 161 |  | Bottom-up
A in MTEP15 | A | West | ITCM | 8093 | 2015-12-28 | PCI 161/69kV TRF | ITCM PCI 161/69kV Transformer | A 200 MVA unit will be purchased and installed as an in-service spare at Prairie Creek Industrial (PCI). | IA | IA | Other |  | Reliability | 3617594 | 2016-12-31 | 2016-12-31 | 161 | 69 | Bottom-up
A in MTEP15 | A | West | ITCM | 8106 | 2015-12-28 | Hrn Lk Sub & Cap | ITCM Heron Lake Sub Rebuild and 161kV Cap | Install two 21 MVAR banks and rebuild the Heron Lake 161kV sub to a ring bus(designed for future bkr and 1/2). | MN | MN | BaseRel |  |  | 16929252 | 2019-12-31 | 2019-12-31 | 161 | 69 | Bottom-up
A in MTEP15 | A | West | ITCM | 8125 | 2015-12-28 | Anita-Grand Jct Rblds ph1 | ITCM Anita-Grand Junciton Area Rebuilds Phase 1 | Rebuild the Anita-Anita Muni-Adair-Thompson Junction (17.6 miles) to 69kV construction, continue to operate at 34kV | IA | IA | Other |  | Condition | 11159322 | 2017-12-31 | 2017-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | West | ITCM | 8128 | 2015-12-28 | Anita-Grand Jct Rblds ph2 | ITCM Anita-Grand Junction Area Rebuilds phase 2 | Add a new Redfield-Panora 69kV line (10 miles) and rebuild Bagley Jct-Bagley REC Tap-Bagley Town-Herndon-Dawson-Perry (19.25 miles) to 69kV construction, continue to operate at 34kV | IA | IA | Other |  | Condition | 20693758.8 | 2017-12-31 | 2019-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | West | ITCM | 8129 | 2015-12-28 | Anita-Grand Jct Rblds ph3 | ITCM Anita-Grand Junction Area Rebuilds phase 3 | Rebuild the Jefferson WCC- Scranton line to 69kV(14.5 miles) and rebuild Perry-Madrid North (12.4 miles) to 69kV (continue to operate at 34kV). | IA | IA | Other |  | Condition | 11837228.4 | 2018-12-31 | 2018-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | West | ITCM | 8132 | 2015-12-28 | Anita-Grand Jct Rblds ph4 | ITCM Anita-Grand Junction Area Rebuilds phase 4 | Rebuild the Bagley Junction-Scranton (16 miles) distribution substation to 69kV (continue to operate at 34kV) | IA | IA | Other |  | Condition | 8104200 | 2019-12-31 | 2019-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | West | ITCM | 8150 | 2015-12-28 | Belle Plaine Conv | ITCM Belle Plaine Area Conversion | The conversion will need a new 161/69kV 100MVA transformer at Belle Plaine. Four 69kV breakers are needed at Belle Plaine. A three position breaker station will be needed south of Belle Plaine. A three position breaker station is needed west of Chelsea. | IA | IA | Other |  | Condition | 11578827.6 | 2025-12-31 | 2025-12-31 | 161 | 69 | Bottom-up
A in MTEP15 | A | West | ITCM | 8151 | 2015-12-28 | B Plaine-Vinton-Traer | ITCM Belle Plaine-Vinton-Traer Conversion | Two additional 69kV breakers are needed at the Vinton substation. One additional 69kV breaker is needed at the Traer substation. | IA | IA | Other |  | Condition | 1932610.8 | 2025-12-31 | 2025-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | West | ITCM | 8152 | 2015-12-28 | Conroy-Parnell Conv | ITCM Conroy-Parnell Conversion | A new 161/69kV 100MVA transformer and three 69kV breakers are needed at the Parnell Substation. | IA | IA | Other |  | Condition | 3812623.2 | 2025-12-31 | 2025-12-31 | 161 | 69 | Bottom-up
A in MTEP15 | A | West | ITCM | 8153 | 2015-12-28 | Parnell-Keswick Conv | ITCM Parnell-Keswick Conversion | Add a new Keswick three (3) terminal 69kV switch station | IA | IA | Other |  | Condition | 2931082.8 | 2025-12-31 | 2025-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | West | ITCM | 8154 | 2015-12-28 | Fairfax-Marengo Conv | ITCM Fairfax-Marengo Conversion | Convert the Fairfax-Marengo Area to 69kV. Two 69kV breakers are needed at the Fairfax Substation. Four 69kV breakers are needed at the Marengo Substation. | IA | IA | Other |  | Condition | 6632210.8 | 2025-12-31 | 2025-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | West | ITCM | 8155 | 2015-12-28 | Mtown-Tama-Laurel Conv | ITCM Marshalltown-Tama-Laurel Conversion | Convert the Marshalltown-Tama-Laurel to 69kV. One breaker is needed at the Fletcher 69kV Substation. Four 69kV breakers are needed at the Tama Breaker Substation. Three 69kV breakers are needed at the Laurel breaker substation. | IA | IA | Other |  | Condition | 6601909.2 | 2025-12-31 | 2025-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | West | ITCM | 8157 | 2015-12-28 | J233 Mtown Upgrades | ITCM J233 Marshalltown Network Upgrades | Three new terminals are needed at the Marshalltown substation to accommodate interconnection to the generating facilities 3 GSUs. | IA | IA | GIP |  |  | 3850000 | 2015-12-31 | 2015-12-31 | 161 |  | Externally-Driven
A in MTEP15 | A | West | ITCM | 8158 | 2015-12-28 | DAEC Switch Station | ITCM DAEC 69kV Switch Station | ITC will need to construct a new three (3) terminal, three (3) break 69 kV switch station northwest of the city of Palo, Iowa. The existing Vinton ? DAEC ? Hiawatha 69 kV transmission lines will need to be tapped and re-routed into the new substation. | IA | IA | Other |  | Reliability | 3062831 | 2017-03-31 | 2017-03-31 | 69 |  | Bottom-up
A in MTEP15 | A | West | ITCM | 8160 | 2015-12-28 | Morgan Valley-Beverly 345 | ITCM Morgan Valley-Beverly 345kV | The project builds a new 345 kV switching station in the DAEC-Tiffin 345 kV line (Morgan Valley Switch Station), adds a new 6.5 mile 345 kV line from the new Morgan Valley Switchstation to a new 345/161 kV substation adjacent to the existing Beverly 161/69/34.5 kV substation. The new 345 kV portion of the substation connects to the existing Beverly substation via a new 345/161 kV autotransformer. | IA | IA | BaseRel |  |  | 38156592 | 2021-05-01 | 2021-05-01 | 345 | 161 | Bottom-up
A in MTEP15 | A | West | ITCM | 8161 | 2015-12-28 | Amers-Doud ph1 | ITCM Ames-Doud (South Ckt) Phase 1 | The first phase will include converting Ames Mine to 69 kV operation from Ames NADC, and the second phase will include converting from Ames Mine to a new Ames 69 kV breaker station. | IA | IA | Other |  | Condition | 2004000 | 2016-12-31 | 2016-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | West | ITCM | 8162 | 2015-12-28 | Ames-Doud ph2 | ITCM Ames-Doud (South Ckt) Phase 2 | The line from a new Ames 69 kV breaker station to Ames Mine to Ames NADC will be converted to 69 kV operation. The remainder of this line back to Doud is already operated at 69 kV. This will be completed in two phases at the request of IPL. The first phase will include converting Ames Mine to 69 kV operation from Ames NADC, and the second phase will include converting from Ames Mine to a new Ames 69 kV breaker station. | IA | IA | Other |  | Condition |  | 2017-12-31 | 2017-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | West | ITCM | 8164 | 2015-12-28 | Ames-Barilla Conv | ITCM Ames-Barilla Conversion | Construct a new 4 termianl Ames switch station and convert the line for this sub to Barilla to 69kV operation. | IA | IA | Other |  | Condition | 7092831.6 | 2017-12-31 | 2017-12-31 | 69 |  | Bottom-up
A in MTEP15 | A | West | ITCM | 8166 | 2015-12-28 | Vinton-Hiawath Conv | ITCM Vinton-Hiawatha Conversion Terminals | A new 69kV Hiawatha terminal will be added and CIPCO will construct a short section of line from the new terminal down to the temporary connection point where the temporary connection will be removed and the Toddville REC line will then be connected to the new CIPCO segment fed from the new Hiawatha 69kV terminal. At the Vinton end, a new 69kV terminal will be added to allow the entire line from Hiawatha to Vinton to be network operated at 69kV. | IA | IA | Other |  | Condition | 1108800 | 2016-08-05 | 2016-08-05 | 69 |  | Bottom-up
A in MTEP15 | A | West | ITCM | 8167 | 2015-12-28 | Doud-Ames Conv ph1 | ITCM Doud-Ames Transmission Conversion Phase 1 | The line between Doud and Ames Transmission will be converted to 69 kV operation. The taps at the distributions substations may be modified to re-connect the new 69 kV high side distribution substations, and the existing 69 kV terminals at Boone Jct will be re-terminated to breaker positions at Doud. A 161/69 kV transformer will be installed at Doud, and the existing 161/69 kV transformer at Boone Jct. will be removed. This conversion will take place in two phases. Phase one will include the Doud substation work and converting from Doud to Clear Lake REC to Gilbert REC to Squaw Valley REC, and phase two will include converting from Squaw Valley REC to Gilbert (IPL) to Ames Transmission. | IA | IA | Other |  | Condition | 6129000 | 2016-07-19 | 2016-07-19 | 161 | 69 | Bottom-up
A in MTEP15 | A | West | ITCM | 8168 | 2015-12-28 | Doud-Ames Conv ph2 | ITCM Doud-Ames Transmission Conversion Phase 2 | The line between Doud and Ames Transmission will be converted to 69 kV operation. The taps at the distributions substations may be modified to re-connect the new 69 kV high side distribution substations, and the existing 69 kV terminals at Boone Jct will be re-terminated to breaker positions at Doud. A 161/69 kV transformer will be installed at Doud, and the existing 161/69 kV transformer at Boone Jct. will be removed. This conversion will take place in two phases. Phase one will include the Doud substation work and converting from Doud to Clear Lake REC to Gilbert REC to Squaw Valley REC, and phase two will include converting from Squaw Valley REC to Gilbert (IPL) to Ames Transmission. | IA | IA | Other |  | Condition | 1380600 | 2017-03-31 | 2017-03-31 | 69 |  | Bottom-up
A in MTEP15 | A | West | MEC | 8020 | 2015-12-28 |  | Pleasant Corner-Beacon 161 kV Line & Terminal | Construct the new Pleasant Corner-Beacon 161 kV line & install a new 161 kV line terminal at Beacon | IA | IA | BaseRel |  |  | 15265000 | 2019-12-01 | 2019-12-01 | 161 |  | Bottom-up
A in MTEP15 | A | West | MEC | 8028 | 2016-06-30 |  | Hastings Replace 161-69 kV Transformer | Replace the Hastings 89.6 MVA 161-69 kV transformer with a 125 MVA transformer. | IA | IA | Other |  | Reliability | 2000000 | 2023-06-01 | 2023-06-01 | 161 | 69 | Bottom-up
A in MTEP15 | A | West | MEC | 8030 | 2015-12-28 |  | Clarksville-Waverly West 69 kV Line | Construct three miles of new 69 kV line between Clarksville and Waverly West Substations. | IA | IA | Other |  | Reliability | 2600000 | 2017-06-01 | 2017-06-01 | 69 |  | Bottom-up
A in MTEP15 | A | West | MEC | 8035 | 2015-12-28 |  | Sub 78 Uprate Terminal to Q56 | At Sub 78, upgrade the 161 kV terminal to Q56 to a minimum of 1412A, consistent with the line conductor top rating; including replacing 1192 AAC line drops and 1200A line backer. | IA | IA | BaseRel |  |  | 207000 | 2017-04-01 | 2017-04-01 | 161 |  | Bottom-up
A in MTEP15 | A | West | MEC | 8036 | 2015-12-28 |  | Sub 56 Uprate Terminal to Q78 | At Sub 56, upgrade the 161 kV terminal to Q78 to a minimum of 1412A, consistent with the line conductor max rating; including replacing 1192 AAC line drops. | IA | IA | BaseRel |  |  | 91000 | 2017-04-01 | 2017-04-01 | 161 |  | Bottom-up
A in MTEP15 | A | West | MEC | 8037 | 2015-12-28 | 02307 & 02309 | Sub 93 Replace 345 kV Breakers 964 & 954 | Replace the Louisa Sub 93, 345 kV circuit breakers 93-964 and 93-954 with new 3000 Amp circuit breakers. Replace related equipment with 3000 Amp equipment (jumpers, etc.). | IA | IA | Other |  | Condition | 853000 | 2017-11-15 | 2017-11-15 | 345 |  | Bottom-up
A in MTEP15 | A | West | MEC | 8038 | 2015-12-28 | G7141 | GRS Replace 69 kV Line Switches 4647, 4648 | Near Sub 41 Tap, replace 600A 69 kV line disconnect switches 4647 and 4648 with new 1200A line switches. | IL | IL | Other |  | Reliability | 153000 | 2017-06-01 | 2017-06-01 | 69 |  | Bottom-up
A in MTEP15 | A | West | MEC | 8039 | 2016-09-16 | G7154 | Sub R - GRS Tap 69 kV Rebuild | Rebuild the 69 kV line from Sub R to the three-way GRS tap in Rock Island. Replace underground cable and upgrade overhead section as needed to match cable rating. | IL | IL | Other |  | Reliability | 3325000 | 2020-11-01 | 2020-11-01 | 69 |  | Bottom-up
A in MTEP15 | A | West | MEC | 8059 | 2015-12-28 |  | DPS 69 kV Breaker & Switch Replacement | Replace eight 69 kV circuit breakers and sixteen 69 kV switches at the DPS Substation. | IA | IA | Other |  | Reliability | 850000 | 2017-12-01 | 2017-12-01 | 69 |  | Bottom-up
A in MTEP15 | A | West | MEC | 8340 | 2015-12-28 |  | Ashawa-Army Post-Willow Creek-Greenfield Plaza 161 kV line rebuild | Rebuild and reconductor the Ashawa-Army Post-Willow Creek-Greenfield Plaza 161 kV line with T-2 556.5 MC ACSR conductor. | IA | IA | BaseRel |  |  | 4217833 | 2014-06-15 | 2017-06-15 | 161 |  | Bottom-up
A in MTEP15 | A | West | MEC | 8740 | 2015-12-28 |  | Brooks-Adams County 161 kV Line | Construct a new 10-mile 161 kV line from Brooks Substation to the new Adams county Substation and add two 161 kV line circuit breakers at Brooks Substation. Remove eight miles of existing 161 kV line from Idaho Avenue Substation to Adams County Substation. | IA | IA | BaseRel |  |  | 9250000 | 2016-12-01 | 2016-12-01 | 161 |  | Bottom-up
A in MTEP15 | A | West | MEC | 8880 | 2015-12-28 |  | Sycamore: Maintenance project to replace failed 161-69 kV transformer AG8T1 | Replace failed Sycamore Substation 161-69 kV transformer AG8T1 with a new 167 MVA 161-69 kV transformer - failed asset replacement maintenance project | IA | IA | Other |  | Condition | 1645000 | 2015-05-01 | 2015-05-01 | 161 | 69 | Bottom-up
A in MTEP15 | A | West | MEC | 9160 | 2015-12-28 |  | Hastings 69 kV Capacitor Reduction | Reduce the reactive capability of the 69 kV capacitor at Hastings Substation from 33.6 MVAR to 21.6 MVAR. | IA | IA | Other |  | Reliability | 51657 | 2015-04-19 | 2015-04-19 | 69 |  | Bottom-up
A in MTEP15 | A | West | MP | 7995 | 2015-12-28 | Maturi 115/23 kV Transformer | Maturi 115/23 kV Transformer | Add 115/23 kV transformer at existing Maturi Substation | MN | MN | Other |  | Distribution | 1426000 | 2015-12-31 | 2015-12-31 | 115 | 23 | Bottom-up
A in MTEP15 | A | West | MP | 7998 | 2015-12-28 | Dog Lake Expansion | Dog Lake Substation Expansion | Add breakers and extend a short 115 kV line to the existing Dog Lake Substation to sectionalize the Verndale - Dog Lake - Scearcyville three terminal line | MN | MN | Other |  | Reliability | 3090000 | 2017-12-31 | 2017-12-31 | 115 |  | Bottom-up
A in MTEP15 | A | West | MP | 7999 | 2015-12-28 | Straight River Substation | Straight River Substation | Tap new Hubbard - Menahga/Blueberry 115 kV Line and build a dedicated 115/34.5 kV substation in order to re-establish service to an existing MP pipeline customer in anticipation of the eventual removal of both 115/34.5 kV transformers from Hubbard effected by the GRE development of 115 kV lines from Hubbard - Menahga and Hubbard - Potato Lake | MN | MN | Other |  | Distribution | 2810000 | 2016-10-01 | 2016-10-01 | 115 | 34.5 | Bottom-up
A in MTEP15 | A | West | MP | 8000 | 2015-12-28 | 16 Line Relocation | 16 Line Relocation | Relocate a segment of the existing Arrowhead - 16L Tap 115 kV Line around proposed United Taconite basin expansion | MN | MN | Other |  | Reliability | 4740000 | 2018-05-01 | 2018-05-01 | 115 |  | Bottom-up
A in MTEP15 | A | West | MP | 8001 | 2015-12-28 | Enbridge East | Enbridge East Extension | Extension from Gary - Stinson 115 kV to serve a new Enbridge distribution station at the Superior Terminal | WI | WI | Other |  | Reliability | 802541 | 2015-10-01 | 2015-10-01 | 115 |  | Bottom-up
A in MTEP15 | A | West | MP | 8002 | 2015-12-28 | Enbridge South Sub | South Sub Extension | Extension from existing Nemadji Tap to serve a new Enbridge distribution station at the Superior Terminal | WI | WI | Other |  | Reliability | 1229500 | 2015-07-15 | 2015-07-15 | 115 |  | Bottom-up
A in MTEP15 | A | West | MP | 8003 | 2015-12-28 | Hawthorne II | Hawthorne II Extension | Reconfiguration of existing Hawthorne Tap to accommodate line switches and a second Enbridge pumping station (and potential future extensions) | WI | WI | Other |  | Reliability | 530000 | 2015-12-31 | 2015-12-31 | 161 |  | Bottom-up
A in MTEP15 | A | West | MP | 9060 | 2015-12-28 | Forbes Transformer | Forbes 230/115 kV Transformer Addition | Addition of a second 230/115 kV Transformer at the Forbes Substation. | MN | MN | BaseRel |  |  | 4000000 | 2016-10-01 | 2016-10-01 | 230 | 115 | Bottom-up
A in MTEP15 | A | West | MP | 9061 | 2015-12-28 |  | Minntac 230 kV Bus Expansion | Addition of circuit breakers and aossicated equipment to convert the current substation to a ring bus configuration. | MN | MN | BaseRel |  |  | 4000000 | 2016-10-01 | 2016-10-01 | 230 |  | Bottom-up
A in MTEP15 | A | West | MP | 9062 | 2015-12-28 | Maturi Transformer Replacement | Maturi 115/34.5 kV Transformer Replacement | Replace existing Maturi 10 MVA transformer with a larger-capacity 18.6 MVA transformer of the same basic size. Move Maturi 10 MVA transformer to new Straight River Substation (MTEP Project #7999) | MN | MN | Other |  | Distribution | 400000 | 2016-05-01 | 2016-05-01 | 115 | 34.5 | Bottom-up
A in MTEP15 | A | West | MP | 9063 | 2015-12-28 | Hat Trick | Hat Trick 115 kV Project | New 115/23 kV substation in Laskin - 37 Line Tap 115 kV Line | MN | MN | Other |  | Distribution | 5834850 | 2016-12-31 | 2016-12-31 | 115 | 23 | Bottom-up
A in MTEP15 | A | West | OTP | 8240 | 2015-12-28 |  | Jamestown Network Upgrades 345/115 kV | To accommodate the interconnection of MISO queue projects J262 and J263 as originally identified in the MISO February 2013 DPP Studies, OTP will make Network Upgrades to the 345/115/41.6 kV system. Three Facilities: 1. Replace existing 345/115/41.6 kV transformers #1 and #2 at Jamestown with a larger 336 MVA transformers 2. Install 345 kV Breaker and bus work as a tie between transformers. 3. Install 115 kV Breaker in ring bus for J262-263 injection. ISD - 10/31/2016 | ND | ND | GIP |  |  | 9550000 | 2016-10-31 | 2016-10-31 | 345 | 115 | Externally-Driven
A in MTEP15 | A | West | OTP | 8281 | 2016-09-14 |  | Donaldson 115 kV Breaker | Add a new 115 kV breaker at Donaldson to the Donaldson to Drayton 115 kV line to improve reliability of area loads. This breaker will reduce fault exposure to Donaldson loads by 17 miles and improve operations, maintenance, and relaying flexibility at Donaldson. | MN | MN | Other |  | Reliability | 370000 | 2018-07-31 | 2018-07-31 | 115 |  | Bottom-up
A in MTEP15 | A | West | XEL | 8075 | 2015-12-28 |  | Lake Bavaria Substation | Build a new 115/34.5 kV distribution substation southwest of the Twin Cities. This will tap the existing radial GRE line going to the GRE-Victoria substation. Additionally, also install a 40 MVAR capacitor bank for voltage support. | MN | MN | Other |  | Distribution | 1153304 | 2016-12-30 | 2016-12-30 | 115 |  | Bottom-up
A in MTEP15 | A | West | XEL | 8079 | 2015-12-28 |  | Line 0714 Rebuild | Rebuild 3.6 miles of 69 kV line from Madelia Switching Station to Village of Madelia to 336 ACSR | MN | MN | Other |  | Reliability | 1594000 | 2019-06-01 | 2019-06-01 | 69 |  | Bottom-up
A in MTEP15 | A | West | XEL | 8097 | 2015-12-28 |  | Poplar Lake Reactor | Install a 20 MVAR 161 kV reactor at DPC's Poplar Lake substation | WI | WI | Other |  | Reliability | 2339744 | 2016-10-07 | 2016-10-07 | 161 |  | Bottom-up
A in MTEP15 | A | West | XEL | 8107 | 2016-09-01 |  | Yankee Cut over | Install a 3rd 115/34.5 kV transformer at Yankee, cut over the Buffalo Ridge feeder 321 and serve from Yankee | MN | MN | Other |  | Distribution | 4000000 | 2019-01-01 | 2019-01-01 | 115 | 34.5 | Bottom-up
A in MTEP15 | A | West | XEL | 8113 | 2015-12-28 |  | Ward County 230 kV | Construct new 230/115 kV substation near Minot, ND construct new 230 kV line from new substation to GRE McHenry substation Joint project with BEPC | ND | ND | BaseRel |  |  | 38961100 | 2018-12-01 | 2018-12-01 | 230 | 115 | Bottom-up
A in MTEP15 | A | West | XEL | 8117 | 2015-12-28 |  | Ward County - Souris 115 kV Line Rebuild | Rebuild 115 kV lines from Ward County to Souris substation | ND | ND | BaseRel |  |  | 14400000 | 2023-09-30 | 2023-09-30 | 115 |  | Bottom-up
A in MTEP15 | A | West | XEL | 8142 | 2015-12-28 |  | Stone Lake TR2 Upgrade | Upgrade Stone Lake TR2 to 112 MVA | WI | WI | Other |  | Reliability | 2227000 | 2017-12-01 | 2017-12-01 | 161 | 69 | Bottom-up
A in MTEP15 | A | West | XEL | 8149 | 2015-12-28 |  | Bayfield Loop 69 kV | This project builds new 69 kV line 20 miles from the existing Stinson - Bayfront 115 kV line to a new substation near Bayfield, WI. New substation at the 115 kV tap location and a new 69/34.5 kV sub near Bayfield. Also included in the project is a rebuild of the existing Iron River - Herbster 34.5 kV line to 69 kV standards. All of the lines in the Bayfield loop will be operated at 34.5 kV for the initial planning horizon and converted when necessary. | WI | WI | Other |  | Reliability | 40000000 | 2018-12-01 | 2018-12-01 | 115 | 34.5 | Bottom-up
A in MTEP15 | A | West | XEL | 8780 | 2015-12-28 |  | Bailey Road Substation | Add a new Bailey 345/115 kV substation located east of the Red Rock substation located on the existing Red Rock-AS King 345 kV line. Install two 345/115 kV, 448 MVA transformers. Reterminate four existing 115 kV lines from Red Rock to Bailey Road. Add 115/34.5 kV, 70 MVA distribution to the substation. | MN | MN | BaseRel |  |  | 34500000 | 2018-06-01 | 2018-06-01 | 345 | 115 | Bottom-up
B | B | East | ITCT | 1850 | 2014-01-31 |  | Hancock 230/120kV Transformer | Cut the Wixom-Quaker 230kV circuit into Hancock Station, install a 230/120kV transformer. | MI | MI | BaseRel |  |  | 9000000 | 2020-12-31 | 2020-12-31 | 230 | 120 | Bottom-up
B | B | West | ATC | 1946 | 2013-02-18 |  | Install 2nd Spring Green 138/69 kV Transformer | Install a 2nd Spring Green 138/69 kV Transformer with a 100 MVA summer normal rating | WI | WI | Other |  | Reliability | 5578636 | 2024-06-01 | 2024-06-01 | 138 | 69 | Bottom-up
B | B | West | GRE, ITCM | 1741 | 2011-12-13 |  | G517: Dotson - Storden - Heron Lake 161 kV | Network upgrades for G517. Build a new Heron Lake - Cottonwood Co 161 kV line and a new Cottonwood Co 161 kV switch station. Build Cottonwood Co to Dotson 161 kV line. | MN | MN | GIP |  |  | 36719820 | 2013-12-31 | 2013-12-31 | 161 |  | Bottom-up
B in MTEP10 | B | East | ITCT | 1856 | 2014-01-31 |  | Belle River - Greenwood - Pontiac 345kV cut into Jewell | Cut the Pontiac section of the Belle River-Greenwood-Pontiac 345kV circuit into and out of Jewell station. Utilize an existing unused side of 345kV tower for one of the circuits into Jewell, and relocate the Jewell-Spokane 230kV circuit | MI | MI | BaseRel |  |  | 5200000 | 2030-12-31 | 2030-12-31 | 345 |  | Bottom-up
B in MTEP10 | B | East | ITCT | 2932 | 2015-03-25 |  | St Antoine-Essex #2 120 kV | Construct 2nd underground cable from St Antoine to Essex (5.1 miles). | MI | MI | BaseRel |  |  | 54800000 | 2020-06-01 | 2020-06-01 | 120 |  | Bottom-up
B in MTEP10 | B | East | METC | 3210 | 2014-01-31 |  | Vanderbilt - Riggsville 138 kV Rebuild | Rebuild 30.3 miles of 138 kV 266 ACSR to 954 ACSR FDC 230 kV construction. | MI | MI |  |  |  | 33254000 | 2016-06-01 | 2016-06-01 | 138 |  | Bottom-up
B in MTEP10 | B | West | ITCM | 1746 | 2011-12-13 |  | Lakefield-Adams 161 kV Rebuild | Rebuild Lakefield-Fox Lake-Rutland-Winnebago-Hayward-Adams 161 kV line to double circuit 345 & 161 kV. Allow for a 345 kV line position for future use. | MN | MN | BaseRel |  |  | 97580000 | 2014-12-31 | 2018-12-31 | 161 |  | Bottom-up
B in MTEP11 | B | Central | AmerenMO | 2973 | 2014-11-17 |  | Howard Bend Substation Connection | Howard Bend 138-12 kV Substation - Provide 138 kV ring bus connection from Mason-Carrollton-8 138 kV line to new Howard Bend Substation. Install 1-138 kV, 2000 A PCB at Carrollton Substation as a bus-tie. | MO | MO | Other |  | Distribution | 1371000 | 2022-12-01 | 2022-12-01 | 138 |  | Bottom-up
B in MTEP11 | B | East | METC | 1815 | 2014-01-31 |  | Chase - Mecosta 138kV Rebuild | Rebuild 7.2 miles of 138kV 110 and 115 CU to 954 ACSR. Prebuild to 230kV construction. | MI | MI | BaseRel |  |  | 8900000 | 2020-06-01 | 2020-06-01 | 138 |  | Bottom-up
B in MTEP11 | B | West | MEC | 3215 | 2016-09-14 | T6242 | Sub 49 161 kV Capacitor | Add 50 MVAr 161 kV capacitor | IL | IL | BaseRel |  |  | 840000 | 2030-06-01 | 2030-06-01 | 161 |  | Bottom-up
B in MTEP11 | B | West | MEC | 3266 | 2013-09-15 | T6164 | Sub 56-89 161 Line Uprate | Increase 161 kV line rating. | IA | IA | BaseRel |  |  | 680000 | 2024-06-01 | 2024-06-01 | 161 |  | Bottom-up
B in MTEP12 | B | Central | AmerenIL | 2290 | 2015-09-11 |  | Joppa 345 kV Switching Station 2nd. Xfmr | Add 2nd. 345/161 kV, 560 MVA Transformer | IL | IL | Other |  | Reliability |  | 2023-06-01 | 2023-06-01 | 345 | 161 | Bottom-up
B in MTEP12 | B | Central | AmerenIL | 3336 | 2012-03-06 |  | Gilman-Watseka Reconductoring | Reconductor to 1600 A summer emergency capability | IL | IL | BaseRel |  |  | 4763000 | 2020-06-01 | 2020-06-01 | 138 |  | Bottom-up
B in MTEP12 | B | Central | AmerenIL | 3342 | 2014-11-17 |  | Diamond Star-McClean County Sw. Station - Increase Ground Clearance | Increase ground clearance on 2.4 miles of 477 kcmil ACSR conductor | IL | IL | BaseRel |  |  | 240000 | 2025-06-01 | 2025-06-01 | 138 |  | Bottom-up
B in MTEP12 | B | Central | AmerenIL | 3687 | 2016-07-11 |  | North Decatur 138-34 kV Substation - Replace 138 kV Breakers | North Decatur 138-34 kV Substation - Replace 138 kV circuit breaker 1313 in the North Decatur-Clinton Route 54 line with a minimum 2000 A continuous 40 kA interrupting circuit breaker. Upgrade other limiting terminal equipment to a minimum of 2000 A. | IL | IL | Other |  | Reliability | 500000 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
B in MTEP12 | B | Central | AmerenIL | 3703 | 2016-08-15 |  | New Berlin 138-69 kV Sub | New Berlin 138-69 kV Substation - Install new 112 MVA, 138-69 kV Substation. Connect to Auburn, North-Jacksonville Industrial 138 kV Line 1306. | IL | IL | Other |  | Distribution |  | 2022-12-01 | 2022-12-01 | 138 | 69 | Bottom-up
B in MTEP12 | B | Central | AmerenMO | 3701 | 2012-03-06 | AMRN25 | Cotter Creek 138-34.5 kV Substation Supplies | Cotter Creek 138-34.5 kV Substation - Provide 138 kV supplies to new Cotter Creek Substation. This will consist of installing a 2000 A, 138 kV PCB at Joachim Substation, and extending new 138 kV line from Joachim to Cotter Creek Substation. Also, for the second 138 kV supply to Cotter Creek, a new 3-2000 A breaker 138 kV switching station (Olympian Village) will be established in the Joachim-St. Francois-2 138 kV line, with a 138 kV line extended from Olympian Village Switching Station to Cotter Creek Substation. | MO | MO | Other |  | Distribution | 31230640 | 2023-06-01 | 2023-06-01 | 138 |  | Bottom-up
B in MTEP12 | B | Central | AmerenMO | 3708 | 2012-03-06 |  | Fountain Lake 2nd. Transformer | Install 2nd. 138-12.5 kV Transformer | MO | MO | Other |  | Distribution |  | 2018-06-01 | 2018-06-01 | 138 | 12.5 | Bottom-up
B in MTEP12 | B | East | ITCT | 1295 | 2014-01-31 |  | Quaker to Southfield #2 120 kV | Rebuild the existing Quaker to Drexel to Southfield circuit utilizing 1431 ACSR conductor on double circuit 230 kV towers and add a second Quaker to Southfield circuit on this new tower line | MI | MI | BaseRel |  |  | 51050000 | 2018-06-01 | 2018-06-01 | 120 |  | Bottom-up
B in MTEP12 | B | East | ITCT | 2933 | 2014-01-31 |  | Superior - Wayne 120 kV Reconductor | Re-conductor approximately 10.5 miles of 477 ACSR conductor of the Superior ? Wayne 120 kV circuit to 795 ACSR. | MI | MI | BaseRel |  |  |  | 2020-12-31 | 2020-12-31 | 120 |  | Bottom-up
B in MTEP12 | B | East | ITCT | 3589 | 2014-01-31 |  | Lee - Menlo 120 kV Rebuild | Rebuild approximately 5.4 miles of 267 ACSR conductor to 954 ACSR between Lee and the Lake Huron Pumping Tap and approximately 6.4 miles of 267 ACSR conductor to 954 ACSR between Menlo and the Lake Huron Pumping Tap and replace station equipment Lee and M | MI | MI | BaseRel |  |  | 11200000 | 2018-06-01 | 2018-06-01 | 120 |  | Bottom-up
B in MTEP12 | B | East | METC | 3137 | 2014-01-31 |  | Warren - Bard Road 138 kV Rebuild | Rebuild approximately 19.6 miles of the Warren to Bard Road 138 kV circuit to 230 kV double circuit construction using 954 ACSR. One side would be energized at 138kV, with the other side left vacant for future use. Also replace terminal equipment at Bard Road. | MI | MI | BaseRel |  |  | 27800000 | 2017-12-31 | 2017-12-31 | 138 |  | Bottom-up
B in MTEP12 | B | East | METC | 3582 | 2014-01-31 |  | Bullock - Summerton 138 kV Rebuild | Rebuild the entire circuit between Bullock and Summerton to 954 ACSR on single-circuit, 138 kV steel pole structures and replace the terminal equipment at Bullock | MI | MI | BaseRel |  |  | 20000000 | 2017-06-01 | 2017-06-01 | 138 |  | Bottom-up
B in MTEP12 | B | East | METC | 3594 | 2014-11-04 |  | Tittabawassee 345 kV Station Equipment Upgrades | Replace 345kV station equipment in rows 34 and 36 at Tittabawassee. | MI | MI | BaseRel |  |  | 3500000 | 2018-12-31 | 2018-12-31 | 345 |  | Bottom-up
B in MTEP12 | B | West | OTP | 3659 | 2016-06-28 | OTP | Roberts County 115/69/41.6 kV Substation | New 115/69/41.6 kV Substation ( joint with WAPA and East River Electric Cooperative ) | SD | SD | Other |  | Reliability | 2000000 | 2018-11-01 | 2018-11-01 | 115 | 41.6 | Bottom-up
B in MTEP12 | B | West | OTP | 3661 | 2016-06-28 | OTP | Grenville 69/41.6 kV Substation | Build a new 69/41.6 kV Substation between Otter Tail Power and East River Electric Systems | SD | SD | Other |  | Reliability | 700000 | 2017-12-31 | 2017-12-31 | 69 | 41.6 | Bottom-up
B in MTEP12 | B | West | OTP | 3664 | 2016-06-28 | OTP | Mooreton - Roberts Jct (Abercrombie) 41.6 kV Line | Build 16 miles of new 41.6 kV line | ND | ND | Other |  | Reliability | 3800000 | 2018-12-31 | 2018-12-31 | 41.6 |  | Bottom-up
B in MTEP13 | B | Central | AmerenIL | 4069 | 2012-09-15 |  | Stalllints Substation Bus-Tie Breaker Addition | Install 2-138 kV, 2000 A bus-tie breakers | IL | IL | BaseRel |  |  | 897220 | 2020-06-01 | 2020-06-01 | 138 |  | Bottom-up
B in MTEP13 | B | Central | AmerenIL | 4071 | 2014-11-17 | AMRN31 | Wood River-Stallings 138 kV Line Upgrade | Wood River-Stallings 138 kV Line 1456 - Increase clearances to ground on 5.63 miles of 477 kcmil ACSR between Cottage Hills and Wanda to permit operation at 120 degrees C. Reconductor 6.01 miles of 477 kcmil ACSR in the Stallings-Wanda section with conductor capable of carrying 1600 A under summer emergency conditions. Replace or reconnect 600 A CTs and replace an 800 A PCB at Cottage Hills with equipment capable of carrying 1200 A continuously. | IL | IL | BaseRel |  |  | 11004000 | 2025-06-01 | 2025-06-01 | 138 |  | Bottom-up
B in MTEP13 | B | Central | AmerenMO | 4067 | 2015-09-11 |  | Meramec-Watson-2 138 kV Line Reconductoring | Reconductor 3.7 miles to 1600 A summer emergency capability. | MO | MO |  |  |  | 2107484 | 2018-06-01 | 2018-06-01 | 138 |  | Bottom-up
B in MTEP13 | B | Central | AmerenMO | 4075 | 2014-11-17 |  | Sioux-Huster-3 138 kV Reconductoring | Reconductor 5.9 miles of 954 kcmil ACSR with conductor capable of carrying 1600 A under summer emergency conditions. Replace 1200 A terminal equpment (dixconnect switches, CT's, bus conductor) at Huster with equipment capable of carrying 1600 A or better. | MO | MO |  |  |  | 5900000 | 2024-06-01 | 2024-06-01 | 138 |  | Bottom-up
B in MTEP13 | B | East | METC | 4346 | 2015-11-13 |  | Karn-Garfield 138kV Rebuild | Rebuild the 33.5 mile copper portion of the Karn to Garfield circuit using single circuit 138kV structures and 954 ACSR conductor. Mitigate several additional points of interest on the remaining portions (795 and 1431 ACSR). Replace station equipment at | MI | MI |  |  |  | 39500000 | 2018-12-31 | 2018-12-31 | 138 |  | Bottom-up
B in MTEP13 | B | West | GRE | 4012 | 2016-06-30 | 20326 | Hardy Lake Substation (CWP) 115 kV | GRE will build new Crow Wing Power 115 KV Hardy Lake Substation | MN | MN | Other |  | Distribution | 207500 | 2020-12-31 | 2020-12-31 | 115 |  | Bottom-up
B in MTEP13 | B | West | GRE | 4013 | 2012-09-11 | 20334 | Air Lake (DEA) 115 kV Substation | GRE will build new Dakota Electric 115 kv South Air Lake substation. | MN | MN | Other |  | Distribution | 864000 | 2026-05-02 | 2026-05-02 | 115 |  | Bottom-up
B in MTEP13 | B | West | GRE | 4015 | 2014-12-19 | 20414 | Le Homme Dieu 115 kV | GRE will convert Runestone's LeHommeDieu 69 kV distribution sub to 115 kV | MN | MN | Other |  | Distribution | 365000 | 2027-12-31 | 2027-12-31 | 115 |  | Bottom-up
B in MTEP13 | B | West | GRE | 4016 | 2016-06-30 | 20507 | Cashel 115 kV conversion | GRE will convert Agralite Cashel 41.6 kV distribution sub to 115 kV | MN | MN | Other |  | Distribution | 625000 | 2022-05-31 | 2022-05-31 | 115 |  | Bottom-up
B in MTEP13 | B | West | MEC | 4252 | 2012-09-15 | G4083 | Neal North:161 kV Breaker Replacements | Replace 161 kV oil circuit breaker 9680 at the Neal North Substation | IA | IA | BaseRel |  |  | 325000 | 2015-06-30 | 2015-06-30 | 161 |  | Bottom-up
B in MTEP13 | B | West | MP | 3756 | 2015-05-07 | Wrenshall | Wrenshall | Add Transformer and breakers at Wrenshall | MN | MN |  |  |  | 3000000 | 2020-12-31 | 2020-12-31 | 115 | 69 | Bottom-up
B in MTEP13 | B | West | MP | 4295 | 2015-06-10 | HVDC Valve Hall Replacement | HVDC Valve Hall Replacement | Modernization of HVDC terminals at Arrowhead & Square Butte | ND | MN | Other |  | Condition | 75000000 | 2020-12-31 | 2020-12-31 | 250 |  | Bottom-up
B in MTEP14 | B | Central | AmerenIL | 4489 | 2014-12-17 |  | Fargo-Pioneer 138 kV Line 1347 Rebuild | Rebuild line between Fargo and Radnor. Tentative 1600 A summer emergency target rating. | IL | IL |  |  |  | 3000000 | 2018-11-15 | 2018-11-15 | 138 |  | Bottom-up
B in MTEP14 | B | Central | AmerenMO | 4498 | 2014-12-17 | AMRN45 | Berntie-Jim Hill 161 kV Line | Construct approximately 20 miles of 161 kV line between Jim Hill Plant and Berntie Substation in southeast, Missouri. The new line should have a 2000 A summer emergency rating. Construct 161 kV ring bus at Berntie Substation. Install 161 kV breaker at Jim Hill. | MO | MO |  |  |  | 30500000 | 2020-06-01 | 2020-06-01 | 161 |  | Bottom-up
B in MTEP14 | B | East | METC | 1795 | 2014-12-17 | METC_13_037 | David Jct. - Bingham 138kV | Rebuild approximately 19 miles of 336.4 ACSR utilizing 954 ACSR on new 138 kV future double circuit structures. | MI | MI | BaseRel |  |  | 19000000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
B in MTEP14 | B | East | METC | 3922 | 2014-12-17 | METC_13_039 | Alpine J - Rogue River J - Cannon J 138kV Rebuild | Rebuild 8.4 miles of 336 ACSR utilizing 954 ACSR on new 138 kV structures. | MI | MI | BaseRel |  |  | 8200000 | 2016-12-31 | 2016-12-31 | 138 |  | Bottom-up
B in MTEP14 | B | East | METC | 4510 | 2014-12-17 | METC_13_044 | Morrow - Battle Creek 138kV #1 Rebuild | Rebuild approximately 22 miles of Morrow to Battle Creek 138kV #1 to 954 ACSR. Upgrade station equipment at Morrow. | MI | MI | BaseRel |  |  | 24640000 | 2017-12-31 | 2017-12-31 | 138 |  | Bottom-up
B in MTEP14 | B | East | METC | 4511 | 2016-07-05 | METC_13_046 | Verona-Foundry 138 kV Rebuild | Rebuild approximately 21 miles of Verona to Foundry 138kV to 1431 ACSR. Upgrade station equipment at Verona. | MI | MI | BaseRel |  |  | 16021000 | 2019-12-31 | 2019-12-31 | 138 |  | Bottom-up
B in MTEP14 | B | East | WPSC | 4383 | 2016-03-30 | Bradley Xmsn | Bradley New Station | This project alleviates an identified thermal violation on the Bradley to Gaines line which is limited by equipment in the Bradley station. In addition, the current configuration of the Bradley and Wayland stations are not desirable from a planning or protection standpoint. The transformer protection clears the entire 138kV bus, there is primarily electromechanical relaying in the Bradley station and there are oil breakers in the Bradley station. This project will upgrade both the Wayland and Bradley busses to ring bus configurations, put the current 138kV and 69kV stations in a common fence, replace oil breakers with SF6 and bring the design up to current Wolverine standards. | MI | MI | Other |  | Reconfig | 4650000 | 2017-01-01 | 2022-12-31 | 138 | 69 | Bottom-up
B in MTEP14 | B | South | SMEPA | 4439 | 2015-04-03 | LRTPS11-RP2102 | Plant Morrow to Purvis Bulk 161kV Line | Tap existing Purvis to Lumberton 161kV line. Construct a 161kV switching station with 3 breakers at Tap Point (new). Construct a 3 mile 161kV line from the Tap point to Morrow (new). Uprate existing line section from Purvis to Tap Point to Lumberton to 296 MVA. Add 161kV breaker at Morrow (new) | MS | MS | Other |  | Reliability | 3498200 | 2021-06-01 | 2021-06-01 | 161 |  | Bottom-up
B in MTEP14 | B | South | SMEPA | 4440 | 2015-04-03 | LRTPS11-RP2106 | Lumberton-Wiggins-Benndale 161kV Conversion | Rebuild line 35A, 37A, 37B and 37C @ 161kV insulation (new). Add 161kV breaker at Lumberton and Benndale 161kV stations (new). Construct a new Stillmore and Big Level switching station with 3 breakers (new). Construct a 8 mile line to Stillmore (new). Convert Stillmore and Big Level distribution stations to 161kV | MS | MS | BaseRel |  |  | 15755800 | 2021-06-01 | 2021-06-01 | 161 |  | Bottom-up
B in MTEP14 | B | South | SMEPA | 4441 | 2015-04-03 | LRTPS11-RP2607 | State Line 161kV Source Project | Tap existing Waynesboro to Hintonville 161kV line. Construct a 161kV switching station with 3 breakers at Tap Point (new). Construct a 161kV switch yard at State Line with breakers (new). Construct a 19 mile 161kV line from Tap point to State Line 161kV station (new). Add a 161/69kV 100MVA transformer at State Line (new). Add 69kV bay and breaker at State Line 69kV station (new). | MS | MS | BaseRel |  |  | 14250000 | 2026-06-01 | 2026-06-01 | 161 | 69 | Bottom-up
B in MTEP14 | B | West | ATC, MP | 3832 | 2015-05-07 | Iron Range - Arrowhead 345 kV | Iron Range - Arrowhead 345 kV Line | Blackberry-Arrowhead 345kV double circuit | MN | MN |  |  |  | 220481656.22 | 2025-12-31 | 2025-12-31 | 500 | 345 | Bottom-up
B in MTEP14 | B | West | GRE | 4376 | 2016-06-30 | 202496 | Parkwood-Crooked Lake 115 kV Reconductor | Reconductor the existing conductor to 795 ACSS | MN | MN |  |  |  | 500000 | 2020-04-29 | 2020-04-29 | 115 |  | Bottom-up
B in MTEP14 | B | West | MDU | 3082 | 2014-12-17 | NW Bism | NW Bismarck Ring Bus | Install 115kV ring bus at the NW Bismarck substation | ND | ND |  |  |  | 3050000 | 2017-06-01 | 2017-06-01 | 115 |  | Bottom-up
B in MTEP14 | B | West | MP | 2548 | 2014-12-17 | Duluth 230 kV Project | Duluth 230 kV Project | Add a second 230/115 kV transformer and upgrade an existing line to 230 kV | MN | MN |  |  |  | 6000000 | 2026-12-31 | 2026-12-31 | 230 | 115 | Bottom-up
B in MTEP14 | B | West | MP | 3856 | 2015-06-10 | HVDC 750 MW | HVDC 750 MW Upgrade | Upgrade existing HVDC line & terminal from Square Butte-Arrowhead to 750MW | ND,MN | MN |  |  |  | 200000000 | 2020-12-31 | 2020-12-31 | 250 | 230 | Bottom-up
B in MTEP14 | B | West | MPC, OTP | 4232 | 2014-09-18 | OTP, MPC | Winger-Thief River Falls 230 kV Line | Winger Sub Expansion, Thief River Sub Expansion, New 47 mile 230kV Transmission Line Between Winger & Thief River, Thief River 230/115 Transformer | MN | MN | BaseRel |  |  | 28000000 | 2024-11-15 | 2024-11-15 | 230 | 115 | Bottom-up
B in MTEP15 | B | Central | AmerenIL | 3010 | 2015-03-19 | AMRN13 | Baldwin-Grand Tower-N.W. Cape (Heritage) 345 kV Line | New 69 mile, single-circuit line (possible double circuit), 3000 A SE capability (Baldwin-Grand Tower - 45 miles; Grand Tower-N.W. Cape - 24 miles). Grand Tower 345/138 kV Substation - 1-560 MVA transformer, 345 kV Ring bus | IL | IL | Other |  | Reliability | 5000000 | 2030-06-01 | 2030-06-01 | 345 | 138 | Bottom-up
B in MTEP15 | B | Central | AmerenIL | 7802 | 2015-11-24 |  | West Frankfort, East-West-Frankfort-1 138 kV Reconductoring | Reconductor 5.25 miles of 1272 kcmil ACSR conductor with conductor capable of carrying 1600 A under summer emergency conditions. Replace bus conductor at West Frankfort, East with conductor having capability equal to or greater than the new line conductor. | IL | IL | BaseRel |  |  |  | 2026-06-01 | 2026-06-01 | 138 |  | Bottom-up
B in MTEP15 | B | Central | AmerenIL | 7821 | 2016-06-02 |  | Kickapoo Capacitor Bank Addition | Install --2-7.2 Mvar, 34.5 kV capacitor banks and PCBs. | IL | IL | BaseRel |  |  |  | 2020-06-01 | 2020-06-01 | 34.5 |  | Bottom-up
B in MTEP15 | B | Central | AmerenIL | 7826 | 2015-03-19 |  | Turkey Hill 138 kV Bus-Tie Breaker | Install 138 kV bus tie breaker. Needed: 1-138 kV, 2000 A (minimum), 40 kA PCB. | IL | IL | Other |  | Reliability |  | 2019-12-01 | 2019-12-01 | 138 |  | Bottom-up
B in MTEP15 | B | Central | AmerenIL | 7861 | 2015-03-19 |  | Effingham Northwest Breaker Additions | Install 2-138 kV, 2000 A, 40 kA PCBs, one on each 138 kV line position. Upgrade bus conductor to 2000 A continuous capability. | IL | IL | Other |  | Reliability |  | 2019-06-01 | 2019-06-01 | 138 |  | Bottom-up
B in MTEP15 | B | Central | AmerenIL | 7863 | 2015-03-19 |  | Tilden Substation 138 kV Ring Bus | Establish a 5 position 138 kV ring bus for 4-138 kV lines and 1-138/34.5 kV transformer. | IL | IL | Other |  | Reliability |  | 2020-12-01 | 2020-12-01 | 138 |  | Bottom-up
B in MTEP15 | B | Central | AmerenMO | 7862 | 2014-12-05 |  | Buick Smelter Substation Relocation | Relocate substation. Remove existing substation, install 2 motor-operated 161 kV switches and 2 customer owned and installed 161 kV circuit switchers. Make provisions for the addition of a third 161-4 kV transformer. | MO | MO | Other |  | Condition |  | 2020-12-01 | 2020-12-01 | 161 | 4 | Bottom-up
B in MTEP15 | B | Central | BREC | 3440 | 2014-09-16 | LRP6 | Reid EHV 161/69 kV transformer | Add a 56 MVA transformer to the existing Reid EHV substation. | KY | KY | BaseRel |  |  | 5000000 | 2024-12-31 | 2024-12-31 | 161 | 69 | Bottom-up
B in MTEP15 | B | Central | PPI | 7888 | 2015-04-28 | 2015-19,20,41 | Tyson 161/69 kV substation and 69 kV lines | Project Modified from original submittal and moved to Appendix B. Tyson substation is no longer part of this project. 69 kV terminal addition at MidAmerican Sub 39. Construct new 11 mile 69 kV line from MidAmerican Sub 39 to PPI/Jo-Carroll Energy Ladwig Substation. Construct 0.2 mile 69 kV line from the City of Geneseo plant to Jo-Carroll Energy Geneseo Substation. | IL | IL | Other |  | Reliability | 289300 | 2016-12-31 | 2016-12-31 | 69 | 69 | Bottom-up
B in MTEP15 | B | Central | Vectren | 4395 | 2014-10-06 | 2013SIGE9 | NE cap bank tertiary conversion | Remove existing cap banks from the tertiary winding of the 138/69 kV transformer at Northeast sub, and install equivalent cap banks on the 69 kV bus with breakers | IN | IN |  |  |  | 450000 | 2019-12-31 | 2019-12-31 | 69 |  | Bottom-up
B in MTEP15 | B | Central | Vectren | 4396 | 2016-05-18 | 2013SIGE10 | Z71 Scott - Toyota | Install new approx. 13 mile 138 kV line designate Z71 (not Z75). | IN | IN |  |  |  | 13000000 | 2020-12-31 | 2020-12-31 | 138 |  | Bottom-up
B in MTEP15 | B | Central | Vectren | 4397 | 2014-10-06 | 2013SIGE11 | Y31 Leonard Rd. - Z93 Rebuild | Rebuild approx. 6.8 miles of 69 kV | IN | IN |  |  |  | 5100000 | 2020-12-31 | 2020-12-31 | 69 |  | Bottom-up
B in MTEP15 | B | Central | Vectren | 4398 | 2014-10-06 | 2013SIGE12 | Y52-1 NE - Sunbeam Rebuild | Rebuild and reconductor approx. 3 miles of 69 kV | IN | IN |  |  |  | 2250000 | 2021-12-31 | 2021-12-31 | 69 |  | Bottom-up
B in MTEP15 | B | Central | Vectren | 4399 | 2016-05-19 | 2013SIGE13 | Newtonville 161 kV ring bus conversion | Convert existing 161 kV bus to a ring bus configuration | IN | IN |  |  |  | 1000000 | 2023-12-31 | 2023-12-31 | 161 |  | Bottom-up
B in MTEP15 | B | East | ITCT | 3943 | 2014-12-02 |  | Navarre 230/120 kV Transformer #201 | Increase the CT ratio on the low-side breaker of the Navarre 230/120 kV Transformer #201. | MI | MI |  |  |  |  | 2018-12-31 | 2018-12-31 | 230 | 120 | Bottom-up
B in MTEP15 | B | East | ITCT | 4520 | 2015-04-22 | ITC_14_001 | Mortar Creek (formerly Hull Road) Station | Build Mortar Creek 345 kV station and reconfigure the Bayshore to Monroe 345 kV, Lemoyne to Majestic 345 kV, and Morocco to Milan to Monroe 345 kV lines into it in a breaker-and-a-half scheme configuration. | MI | MI | Other |  | Reliability | 23950000 | 2018-06-01 | 2018-06-01 | 345 |  | Bottom-up
B in MTEP15 | B | East | ITCT | 8068 | 2015-04-22 | ITC_13_061 | Brownstown - Monroe #2 345 kV Sag Remediation | Remediate the sag limit on the Brownstown to Monroe #2 345 kV line | MI | MI | Other |  | Reliability | 1200000 | 2017-12-31 | 2017-12-31 | 345 |  | Bottom-up
B in MTEP15 | B | East | ITCT | 8069 | 2015-04-22 | ITC_13_056 | Lemoyne - Majestic 345 kV Sag Remediation | Remediate the sag limit on the Lemoyne - Majestic 345 kV line to increase its summer emergency rating to a minimum rating of 1822 MVA / 3049 Amps. | MI | MI | Other |  | Reliability | 2500000 | 2018-12-31 | 2018-12-31 | 345 |  | Bottom-up
B in MTEP15 | B | East | ITCT | 8099 | 2015-04-22 | ITC_14_014 | Lincoln to Northeast/Northwest 120 kV Rebuild | Rebuild about 2.95 miles of 477 ACSR on the Lincoln section of the Lincoln/Northeast/Northwest circuit to 1431 ACSR on new 120 kV double circuit towers. The other side of these towers supports a portion of the Lincoln to Northeast 120 kV circuit which will also be upgraded to 1431 ACSR. Upgrades or replacement of any limiting equipment at Lincoln, Hilton Road (formerly Ferndale), and Northeast substations will also be necessary. | MI | MI | Other |  | Reliability | 4200000 | 2018-12-31 | 2018-12-31 | 120 |  | Bottom-up
B in MTEP15 | B | East | METC | 1804 | 2014-12-02 |  | Marquette - Easton Jct. 138kV | Replace limiting equipment at the Marquette 138 kV station | MI | MI |  |  |  |  | 2018-12-31 | 2018-12-31 | 138 |  | Bottom-up
B in MTEP15 | B | East | METC | 3927 | 2015-07-22 | METC_14_026 | Saginaw River 138 kV Station Equipment Replacement | Replace limiting equipment from the Saginaw River 138 kV station. | MI | MI | Other |  | Reliability | 2800000 | 2017-12-31 | 2017-12-31 | 138 |  | Bottom-up
B in MTEP15 | B | East | METC | 4525 | 2015-04-22 | METC_14_015 | Goss 345/138 kV Transformer #2 | Install a second 345/138 kV transformer and install/upgrade station equipment at Goss. | MI | MI | Other |  | Reliability | 9300000 | 2018-12-31 | 2018-12-31 | 345 | 138 | Bottom-up
B in MTEP15 | B | East | METC | 8123 | 2015-04-22 | METC_14_028 | Weeds Lake Transformer #2 and Looping in Argenta to Twin Branch 345 kV | Install a second 345/138 kV transformer at the Weeds Lake Substation and loop in the Argenta to Twin Branch 345 kV line. This creates a Weeds Lake - Twin Branch 345 kV line and a 2nd Argenta - Weeds Lake 345 kV circuit | MI | MI | Other |  | Reliability | 17500000 | 2018-12-31 | 2018-12-31 | 345 | 138 | Bottom-up
B in MTEP15 | B | East | METC | 8130 | 2015-04-22 | METC_13_049 | Pere Marquette to Keystone 230 kV | Construct a new 75 mile, 230 kV circuit between Keystone and Pere Marquette Substation. Approx. 20 miles of the new line will be on new double circuit steel pole structures, 30 miles from rebuiding existing 138 kV structures to 230 kV double circuit steel poles, and 25 miles on existing DCTs with a vacant side of the structures. Install a 345/230 kV transformer and associated terminal equipment at Pere Marquette substation. Add a 230/138 kV transformer and associated terminal equipment at Keystone substation. Project will also swap the line positions of the Keystone-Wexford 138 kV and the 138 kV side of the Keystone 345/138 kV transformer at Keystone substation. | MI | MI | BaseRel |  |  | 90198000 | 2018-12-31 | 2018-12-31 | 345 | 138 | Bottom-up
B in MTEP15 | B | East | NIPS | 8026 | 2014-12-01 |  | Dekalb Transformer | Upgrade Dekalb 138/69kV Transformer. This will also increase ratings of the Dekalb to Auburn 138kV Line | IN | IN |  |  |  | 2700000 | 2017-12-31 | 2017-12-31 | 138 | 69 | Bottom-up
B in MTEP15 | B | East | WPSC | 8222 | 2016-03-30 | Bradley line mods | Bradley Station Line Modifications | This project will construct the line modifications required to route lines into the new Bradley station. | MI | MI | Other |  | Relocation | 1000000 | 2022-12-31 | 2022-12-31 | 138 | 69 | Bottom-up
B in MTEP15 | B | East | WPSC | 8360 | 2015-03-30 | Alba New Station | Alba New Station | The Alba transmission tie station represents the oldest tie on the Wolverine system. It is located on a small parcel of leased property with limited expansion capability. The existing station shall be replaced with a new in/out transmission line design, three (3) breaker substation, modern control house, metering, protection relaying and a 50 or 90MVA, 138/69kV tie transformer, dependent upon load requirements. | MI | MI | Other |  | Condition | 4000000 | 2022-12-31 | 2022-12-31 | 138 | 69 | Bottom-up
B in MTEP15 | B | East | WPSC | 8361 | 2015-03-30 | Alba Line Mods | Alba Line Mods | This project will address 138kV transmission line and structure reconfiguration costs associated with construction of the new Alba transmission substation, so that the 138kV ITC/METC looped transmission line segments can successfully enter and leave the substation | MI | MI | Other |  | Reconfig | 1000000 | 2022-12-31 | 2022-12-31 | 138 | 69 | Bottom-up
B in MTEP15 | B | South | CLECO | 7993 | 2015-04-01 |  | Rodemacher to East Leesville(reconductor) | Reconductor Rodemacher to East Leesville 230 kv line. | LA | LA | BaseRel |  |  | 10000000 | 2024-05-01 | 2024-05-01 | 230 |  | Bottom-up
B in MTEP15 | B | South | Entergy-TX | 4799 | 2015-09-11 | 13-ETI-021 | Dishman: Construct new substation | Construct new 230kV substation on the Amelia to Helbig 230kV line | TX | TX | Other |  | Distribution | 10500000 | 2021-06-01 | 2021-06-01 | 230 |  | Bottom-up
B in MTEP15 | B | South | SMEPA | 8141 | 2015-04-03 |  | Rebuild L16 (Hoy - Sharon GOAB) 69kV Line | Rebuild the existing Hoy - Sharon GOAB 69kV line using 161kV double circuit specifications and 795 ACSR conductor. | MS | MS | BaseRel |  |  | 1273600 | 2026-06-01 | 2026-06-01 | 69 |  | Bottom-up
B in MTEP15 | B | South | SMEPA | 8143 | 2015-04-03 |  | Rebuild L45A (Foxworth - Pickwick GOAB) 69kV Line | Rebuild the existing Foxworth - Pickwick GOAB 69kV line using 161kV specifications and 795 ACSR conductor. | MS | MS | BaseRel |  |  | 2050300 | 2026-06-01 | 2026-06-01 | 69 |  | Bottom-up
B in MTEP15 | B | West | ATC | 1718 | 2016-09-15 | F2081 | Install Custer 138/69 kV transformer | Install a 138/69 kV transformer at Custer substation | WI | WI | Other |  | Reliability | 4904268 | 2026-06-01 | 2026-06-01 | 138 | 69 | Bottom-up
B in MTEP15 | B | West | ATC | 1719 | 2016-09-15 | F2081 | Construct Shoto-Custer 138 kV line | Construct a Shoto-Custer 138 kV line | WI | WI | BaseRel |  |  | 22938000 | 2026-12-31 | 2026-12-31 | 138 |  | Bottom-up
B in MTEP15 | B | West | ATC | 3678 | 2014-09-10 | NP-Package1 | Construct Marquette-Mackinac 138 kV | Rebuilds Forsyth to Nine Mile as 138 kV line and rebuilds from Nine Mile to Straits area as 138 kV. This includes a new 138 kV connection between Seney and Roberts. | MI | MI | Other |  | Reliability | 262850000 | 2050-12-31 | 2050-12-31 | 138 | 69 | Bottom-up
B in MTEP15 | B | West | ATC | 3838 | 2014-09-10 | NP Project | Construct Plains-National 345 kV | New 345 kV line from Plains to National, including new National substation and transformers | WI | MI |  |  |  | 180800000 | 2019-06-01 | 2050-12-31 | 345 | 138 | Bottom-up
B in MTEP15 | B | West | ATC | 7580 | 2014-09-10 | PR06427 | Install 138 kV Werner West Inductor | Install a 138 kV 25 Mvar inductor at Werner West | WI | WI |  |  |  | 1524446 | 2018-06-01 | 2018-06-01 | 138 |  | Bottom-up
B in MTEP15 | B | West | ATC | 7581 | 2014-09-10 | PR06425 | Install 138 kV Forest Jct Inductor | Install a 138 kV 25 Mvar inductor at Forest Jct | WI | WI |  |  |  | 1762635 | 2018-06-01 | 2018-06-01 | 138 |  | Bottom-up
B in MTEP15 | B | West | ATC | 7584 | 2015-01-14 | PR04986 | Rebuild New Holstein - St Nazianz - Custer 69 kV | Rebuild P-68 New Holstien - St Nazianz- Custer 69 kV circuit with T2-4/0 ACSR | WI | WI |  |  |  | 15941421 | 2022-12-31 | 2022-12-31 | 69 |  | Bottom-up
B in MTEP15 | B | West | ATC | 7585 | 2014-09-18 | PR06370 | Install 2nd Colley Rd 138/69 kV transformer | Add 2nd 138/69 kV transformer at Colley Rd | WI | WI |  |  |  | 9944381 | 2023-06-01 | 2023-06-01 | 138 | 69 | Bottom-up
B in MTEP15 | B | West | ATC | 7586 | 2014-09-18 | PR05856 | Atlantic 138/69 kV bus reconfiguation and transformer addition | Reconfigure the Atlantic substations 138 kV and 69 kV bus work. Denergize the existing Atlantic 138/69 kV transformer and install a new 138/69 kV transformer. | WI | WI |  |  |  | 9043283 | 2019-06-01 | 2019-06-01 | 138 | 69 | Bottom-up
B in MTEP15 | B | West | ATC | 7762 | 2014-09-18 | PR06460 | Rebuild Y-19 Wautoma - Harrison 69 kV | Rebuild Y-19 from Wautoma to Harrison 69 kV with T2 4/0 Penguin conductor. | WI | WI |  |  |  |  | 2023-12-31 | 2023-12-31 | 69 |  | Bottom-up
B in MTEP15 | B | West | ATC | 7763 | 2014-09-18 | PR06467 | Rebuild Y-47 Mckenna - Castle Rock 69 kV | Rebuild Y-145 from McKenna - Castle Rock 69 kV with T2 4/0 | WI | WI |  |  |  |  | 2023-12-31 | 2023-12-31 | 69 |  | Bottom-up
B in MTEP15 | B | West | ATC | 7764 | 2016-08-11 | PR06465 | Rebuild Y-49 Wautoma - Chaffee Creek 69 kV | Rebuild Y-49 from Wautoma - Chaffee Creek 69 kV with T2 4/0 | WI | WI |  |  |  |  | 2023-12-31 | 2023-12-31 | 69 |  | Bottom-up
B in MTEP15 | B | West | ATC | 7765 | 2014-09-18 | PR06467 | Rebuild Y-145 Lincoln - McKenna 69 kV | Rebuild Y-145 from Lincoln Pumping Station - McKenna 69 kV with T2 4/0 Penguin conductor. | WI | WI |  |  |  |  | 2023-12-31 | 2023-12-31 | 69 |  | Bottom-up
B in MTEP15 | B | West | ATC | 8073 | 2014-09-15 |  | Plains - Marquette Area Reinforcement Project | Uprate Plains - Arnold 138 kV line and upgrade existing Plains 345/138 kV transformer and install a 2nd Plains 345/138 kV transformer | MI | MI |  |  |  | 43720000 | 2023-12-01 | 2023-12-01 | 345 | 138 | Bottom-up
B in MTEP15 | B | West | ATC | 8076 | 2015-11-23 |  | Morgan - Plains Area Reinforcement Project | New Thunder Substation, Loop Morgan - Plains 345 into new Thunder Substation, New Morgan - Thunder 138 kV line, Convert Thunder - Crivitz 69 kV to 138 kV. | WI | WI |  |  |  | 105000000 | 2023-12-01 | 2023-12-01 | 345 | 69 | Bottom-up
B in MTEP15 | B | West | ATC | 8082 | 2015-10-01 |  | Green Bay Area Reinforcement Project | Highway V - Preble 138 kV line reconductor | WI | WI |  |  |  | 6000000 | 2020-12-01 | 2020-12-01 | 138 |  | Bottom-up
B in MTEP15 | B | West | ATC | 8084 | 2014-09-15 |  | Rhinelander Area Reinforcement Project | Uprate Highway 8 - Clear Lake 115 kV line | WI | WI |  |  |  | 24000000 | 2020-12-01 | 2020-12-01 | 115 |  | Bottom-up
B in MTEP15 | B | West | ATC | 8089 | 2015-01-14 |  | Lakota-Winona 69 kV to 138 kV Conversion and Mass Substation Expansion | Convert the existing 69-kV lines from Conover-Mass and Mass-Winona from 69 kV to 138 kV; Modify the existing Mass Substation to accommodate 138-kV buswork and a new 138/69-kV transformer | WI,MI | MI |  |  |  | 100000000 | 2021-12-01 | 2021-12-01 | 138 | 69 | Bottom-up
B in MTEP15 | B | West | ATC | 8263 | 2014-11-04 | PR06463 FP:4485 WO:601142 | Rebuild Y-45 W. Wisconsin Rapids - Sigel 69 kV | Rebuild Y-45 on existing right of way. No terminal equipment is being replaced. | WI | WI |  |  |  | 18667906 | 2021-12-31 | 2021-12-31 | 69 |  | Bottom-up
B in MTEP15 | B | West | ATC | 8440 | 2014-11-11 | PR04970 | Rebuild Oak Creek- Hayes 138 kV | Asset maintenance, reconductor line 811 Oak Creek - Hayes | WI | WI |  |  |  | 13743440 | 2019-12-31 | 2019-12-31 | 138 |  | Bottom-up
B in MTEP15 | B | West | ATC | 8441 | 2014-11-11 | PR04202 | Escanaba Load Addition T-D | Build new Escanaba 69 kV substation with distribution loads | MI | MI |  |  |  | 5616000 | 2016-12-31 | 2016-12-31 | 69 | 12.47 | Bottom-up
B in MTEP15 | B | West | ATC | 8444 | 2015-01-14 |  | Replace First Ave-Sawyer 69 kV (UG) | Asset maintenance, Replace UG Cable from 1st Ave-Sawyer 69 kV line | WI | WI |  |  |  |  | 2020-12-31 | 2020-12-31 | 69 |  | Bottom-up
B in MTEP15 | B | West | ATC | 8620 | 2015-01-07 |  | Construct Howards Grove - Erdman 138 kV | Construct a new 138 kV line from Howards Grove to Erdman | WI | WI |  |  |  |  | 2018-12-12 | 2018-12-12 | 138 |  | Bottom-up
B in MTEP15 | B | West | ATC | 8641 | 2015-01-08 | PR7009 | Install Boscobel Capacitor | Project consists of adding a 2nd 8.16 MVAR step | WI | WI |  |  |  | 1394539 | 2023-06-01 | 2023-06-01 | 69 |  | Bottom-up
B in MTEP15 | B | West | GRE | 2632 | 2014-12-19 | 20385 | Onigum 115 kV Conversion | Onigum 115 kV Conversion | MN | MN | Other |  | Distribution | 5300000 | 2022-11-30 | 2022-11-30 | 115 |  | Bottom-up
B in MTEP15 | B | West | ITCM | 8111 | 2015-05-29 | CR-N Liberty Upgrades | ITCM Cedar Rapids-North Liberty Area Upgrades | 161 and 69 kV upgrades in the Cear Rapids to North Liberty, IA area including a new North Liberty 161/69kV sub and new Rose Hollow to North Liberty to Fairfax 161kV line. | IA | IA | BaseRel |  |  | 74482581.6 | 2019-12-31 | 2024-12-31 | 161 | 69 | Bottom-up
B in MTEP15 | B | West | ITCM | 8842 | 2015-03-19 | Quad-Rock Ck 345 | Quad Cities-Rock Creek 345kV Dbl Ckt | Rebuild the Quad Cities to Rock Creek 345kV line to double circuit and add 345kV terminals at both substations. | IA,IL | IA,IL | BaseRel |  |  |  | 2024-12-31 | 2024-12-31 | 345 |  | Bottom-up
B in MTEP15 | B | West | ITCM | 8843 | 2015-03-19 | Rock Creek 2nd 345/161kV | Rock Creek 2nd 345/161kV Transformer | Add a 2nd 345/161kV 450MVA transformer at the Rock Creek substation. | IA | IA | BaseRel |  |  |  | 2024-12-31 | 2024-12-31 | 345 | 161 | Bottom-up
B in MTEP15 | B | West | ITCM | 8844 | 2015-03-19 | Albany-Galena 161kV Rebuild | Albany-Galena 161kV Rebuild | Rebuild the Albany-York-Savanna-Galena 161kV line. | IL | IL | BaseRel |  |  |  | 2024-12-31 | 2024-12-31 | 161 |  | Bottom-up
B in MTEP15 | B | West | MEC | 8023 | 2015-04-09 |  | Hills - Sub E 161 kV Reconductor | Reconductor the Hills - Sub E 161 kV line in Iowa City to increase the line rating. | IA | IA | BaseRel |  |  | 4000000 |  |  | 161 |  | Bottom-up
B in MTEP15 | B | West | MEC | 8114 | 2015-04-09 |  | Sub A - Sub 84 69 kV Line Uprate | Replace structures to allow a higher conductor operating temperature. | IA | IA | Other |  | Reliability | 225000 | 2018-06-01 | 2018-06-01 | 69 |  | Bottom-up
B in MTEP15 | B | West | MP | 7913 | 2015-05-07 |  | 868 Line Upgrade | Increase capacity of Little Falls - West St. Cloud 115 kV Line | MN | MN | BaseRel |  |  | 6800000 | 2019-11-01 | 2019-11-01 | 115 |  | Bottom-up
B in MTEP15 | B | West | MPC, OTP | 4237 | 2014-09-12 | OTP, MPC | Hensel-Drayton 115 kV #2 | Hensel Sub Expansion, Drayton Sub Expansion, Hensel-Drayton 115 kV Transmission Line | ND | ND | BaseRel |  |  | 6500000 | 2021-11-15 | 2021-11-15 | 115 |  | Bottom-up
B in MTEP15 | B | West | OTP | 4236 | 2015-03-20 | OTP | Ortonville 115/41.6 kV Transformer | Replace Transformer - 40 MVA | MN | MN | Other |  | Reliability | 1000000 | 2020-11-15 | 2020-11-15 | 115 | 41.6 | Bottom-up
B in MTEP15 | B | West | OTP | 8085 | 2016-09-14 |  | Kerkhoven Town Conversion to 115 kV Service - 115/12.5 kV | Build a new, approximately, one mile 115 kV line from the GRE Kerkhoven 115/41.6 kV sub to the new OTP Kerkhoven Town substation. Also convert the Kerkhoven town delivery substation from 41.6 kV to 115 kV through the installation of a new 10 MVA 115/12.5 kV transformer. This project will consist of two facilities: 1. New 115/12.5 kV Substation at Kerkhoven Town with a new (1) 115 kV breaker and a new 10 MVA 115/12.5 kV transformer. 2. Approxmetely 1 mile of115 kV transmission line from the GRE Kerkhoven 115 kV Substation to the New Kerkhoven Town 115/12.5 kV substation. The total estimated cost of this project is $ 1.7 million. The expected in service date for this project is November 15, 2020. | MN | MN | Other |  | Reliability | 1700000 | 2020-11-15 | 2020-11-15 | 115 | 12.5 | Bottom-up
Note on O3: Projects may be partially in service. For previous cycles, only the active investment is reported

## Fac Legend
MTEP16 MISO Transmission Expansion Plan 2016 |  | Appendices A, B
Facility Table Field Legend
Project table has blue highlighted header. A project may have multiple facilties.
Facility table has beige highlighted header. A project's facilities may have different in service dates.
Facilty Table Field Legend
Field | Description
Target Appendix | Target appendix for the MTEP16 planning cycle. "A in MTEP16" projects were reviewed and approved in MTEP16. This column also indicates what projects were approved in prior MTEPs that are not yet in service.
App AB | Appendix the project is in. B>A for projects moving during this planning cycle.
Region | MISO Planning Region: Central, East, West or South
Geographic Location by TO Member System | Project geographic location by Transmission Owner member systems
PrjID | Indicates the Facility's Project. Projects may have multiple facilities.
Facility ID | Facility ID: MISO facility identifier
Expected ISD | Expected In Service Date for this facility
From Sub | From substation for transmission line or location of transformer or other equipment
To Sub | To substation for transmission line or transformer designation
Ckt | Circuit identifier
Max kV | Maximum voltage of this facility
Min kV | Minumum voltage of this facility (transformer low-side voltage)
Facility Rating | Rating of the facility in applicable units. Typically Summer rate
Facility Description | Brief description of transmission facility
State | State the facility is located in
Miles Upg. | Transmission line miles on existing rights of way (ROW)
Miles New | Transmission line miles on new rights of way (ROW)
Plan Status | Indicates status of project in planning or implementation. Conceptual, Proposed, Planned, Last Milestone Achieved, Under Construction and In Service
Estimated Cost | Total estimated facility cost
Cost Shared | Y if facility is cost shared per Attachment FF
Postage Stamp | Y if facility has postage stamp cost allocation per Attachment FF
MISO Facility | Y for facilities under MISO functional control. NT for non-transferred facilities under Agency Agreements

## MTEP16_AppAB_Facility
MTEP16 MISO Transmission Expansion Plan 2016 | [27 empty] | Appendices A, B
Appendices A, B: Project Facility Table 10/03/2016
Target Appendix | App AB | Planning Region | Geographic Location by TO Member System | PrjID | Prj Rec Date | Owner PrjID | Facility ID | Record Date | Facility Type | Expected ISD | From Sub | To Sub | Ckt | Max kV | Min kV | Facility Rating | Facility Description | State | Miles Upg. | Miles New | Plan Status | Estimated Cost | Est Type | Gen Int Upgrade Type | TSR Cond Upg | Cost Shared | Postage Stamp | MISO Facility
A in MTEP16 | B>A | Central | AmerenIL | 3005 | 2016-04-28 | AMRN38 | 8614 | 2015-04-29 | LN | 2017-06-01 | Baldwin | Baldwin Tap | 1526 | 138 |  | 399 | Build a 138 kV double-circuit line between Baldwin Substation and the tap to the South Belleville-Tilden 1526 138 kV line by rebuilding 2 miles of existing single-circuit 138 kV line to double-circuit capability, both circuits to have 2000 A summer emergency capability. | IL |  | 2 | Planned | 2400000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | Central | AmerenIL | 3005 | 2016-04-28 | AMRN38 | 8615 | 2015-04-29 | CB | 2017-06-01 | Baldwin | Install 138 kV Breakers |  | 138 |  |  | Construct a 5 position 138 kV ring bus at Baldwin Substation (5 - 3000 A, 40 kA PCBs) | IL |  |  | Planned | 1000000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | Central | AmerenIL | 7820 | 2015-12-14 |  | 20090 | 2016-05-11 | LNrc | 2017-06-01 | Hennepin | Kewanee | 6101 | 138 |  | 214 | Upgrade terminal equipment at Hennepin terminal. | IL |  |  | Planned | 300000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | Central | AmerenIL | 7860 | 2015-09-11 |  | 20100 | 2016-09-09 | LNrb | 2016-06-01 | Effingham 138 | Effingham NW | 1 | 138 |  | 240 | Elevate 2.72 miles of 954 kcmil ACSR conductor to permit operation at 120 degrees C. Verify line hardware, splices, etc. will permit operations at 120 degrees C. Upgrade terminal equipment at Effingham 138 Substation. | IL | 2.72 |  | M5_In Service | 2000000 |  |  | N | N | N | Y
A in MTEP16 | B>A | Central | AmerenIL | 7869 | 2016-05-23 |  | 20107 | 2016-05-23 | SUB | 2016-05-01 | Alsey Tap |  |  | 138 |  |  | Install 138 kV breaker station near tap to the PPI Alsey Plant on the Jersesyville, Northwest-Meredosia-1 138 kV line. May be an ultimate 6-breaker ring bus. | IL |  |  | M5_In Service | 6626495 |  |  | N | N | N | Y
A in MTEP16 | B>A | Central | AmerenIL | 9261 | 2016-05-23 |  | 20851 | 2016-05-23 | SUB | 2017-12-01 | Searitt |  |  | 138 |  | 287 | Build a 3-breaker 138 kV ring bus adjacent to the North Decatur-Latham-1566 138 kV line near the planned Enbridge Pumping Station. Re-route the North Decatur-Latham-1566 138 kV line into and out of the new breaker station. | IL |  |  | Planned | 4119500 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | Central | AmerenIL | 9261 | 2016-05-23 |  | 20852 | 2016-05-23 | LN | 2016-06-01 | Searitt | Enbridge | 1 | 138 |  | 143 | Construct radial 138 kV line from Searitt Breaker Station to Enbridge Pumping Station to supply customer load. Line conductor to have a minimum summer normal rating of at least 600 A. | IL |  | 0.5 | Planned | 444167 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | Central | AmerenIL | 9722 | 2016-08-09 |  | 21106 | 2016-05-23 | TX | 2016-10-03 | Frederick, North |  |  | 138 | 69 | 112 | Replace exsisting 138-69 kV transformer bank with 112 MVA unit. | IL |  |  | Planned |  |  |  | N | N | N | NT
A in MTEP16 | B>A | Central | AmerenIL | 9726 | 2016-02-02 |  | 21110 | 2016-05-16 | SUB | 2018-06-01 | Fogarty |  |  | 138 | 34.5 | 112 | Provide 138 kV connection to supply 138-34.5 kV transformer. | IL |  |  | Planned | 1726448 |  |  | N | N | N | NT
A in MTEP16 | B>A | Central | AmerenIL | 9727 | 2016-05-23 |  | 21111 | 2016-05-23 | SUB | 2019-06-01 | Wakefield |  |  | 138 | 34.5 | 112 | Establish 138 kV ring bus; connect ot South Bloomington-Clinton-1372 line. | IL |  |  | Planned | 7430056 |  |  | N | N | N | NT
A in MTEP16 | B>A | Central | AmerenIL | 9736 | 2016-01-13 |  | 21123 | 2016-05-16 | LNrc | 2016-05-01 | East Quincy | Hamilton | 4 | 138 | 138 | 159 | Replace existing conductor. | IL | 30.61 |  | M5_In Service | 8315916 |  |  | N | N | N | Y
A in MTEP16 | B>A | Central | AmerenIL | 9741 | 2016-03-11 |  | 21128 | 2016-06-01 | TEQ | 2016-05-24 | Porter Road | East Collinsville | 1 | 138 | 138 | 160 | Upgrade terminal equipment at Porter Road. | IL |  |  | M5_In Service | 50000 |  |  | N | N | N | Y
A in MTEP16 | B>A | Central | AmerenIL | 9845 | 2015-09-14 |  | 21222 | 2015-09-14 | SUB | 2017-05-01 | Gallatin |  |  | 138 | 69 | 159 | Construct 138 kV ring bus in Kansas-Hutsonville 138 kV line | IL |  |  | Planned | 5621250 | Engineering |  | N | N | N | NT
A in MTEP16 | B>A | Central | AmerenIL | 9853 | 2016-08-09 |  | 21230 | 2015-09-14 | TEQ | 2017-06-01 | Prairie State | Mt. Vernon, West | 1 | 345 | 345 | 1401 | Upgrade terminal equipment at Mt. Vernon, West | IL |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | Central | AmerenIL | 9869 | 2016-08-09 |  | 21251 | 2015-09-14 | TEQ | 2017-06-01 | Havana | Elkhart | 1 | 138 | 138 | 160 | Upgrade terminal equipment | IL |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | Central | AmerenIL | 9873 | 2016-08-09 |  | 21256 | 2015-09-14 | TX | 2016-12-01 | Edwards Plant |  |  | 138 | 69 | 150 | Install 138-69 kV transformer | IL |  |  | Planned |  |  |  | N | N | N | NT
A in MTEP16 | B>A | Central | AmerenIL | 10884 | 2016-03-11 |  | 21681 | 2016-06-01 | TX | 2016-05-23 | Roxford |  |  | 345 | 138 | 700 | Replace 345/138 kV, 560 MVA transformer with a 700 MVA unit. | IL |  |  | M5_In Service | 3611589 |  |  | N | N | N | Y
A in MTEP16 | B>A | Central | AmerenIL | 10884 | 2016-03-11 |  | 21682 | 2016-06-01 | TEQ | 2016-05-23 | Roxford |  |  | 345 |  | 1793 | Install a 3000 A, 50 kA PCB to place the Roxford 345/138 kV transformer on its own position at Roxford Substation. | IL |  |  | M5_In Service |  |  |  | N | N | N | Y
A in MTEP16 | B>A | Central | AmerenIL | 10904 | 2016-03-18 |  | 21688 | 2016-03-18 | LNrb | 2016-12-01 | Brokaw | Gibson City South | 1 | 138 |  | 255 | Rebuild to 1200 A summer emergency capability. | IL | 28.5 |  | Planned | 10218299 | Planning Preliminary |  | N | N | N | Y
A in MTEP16 | B>A | Central | AmerenIL | 10904 | 2016-03-18 |  | 21689 | 2016-03-18 | TEQ | 2016-12-01 | Gibson City South |  |  | 138 |  | 478 | Upgrade terminal equipment | IL |  |  | Planned | 100000 | Planning Preliminary |  | N | N | N | Y
A in MTEP16 | B>A | Central | AmerenIL | 11063 | 2016-04-19 |  | 21713 | 2016-04-19 | TEQ | 2016-12-01 | Rising | North Champaign | 1592 | 138 |  | 399 | Upgrade terminal equipment at Rising Substation terminal | IL |  |  | Planned | 1747553 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | Central | AmerenMO | 10483 | 2015-12-16 |  | 21586 | 2015-12-16 | LNup | 2016-12-01 | Cape | Kelso | 2 | 161 | 161 | 280 | Increase ground clearance, upgrade terminal equipment at Cape and Kelso. | MO | 5.99 |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | Central | AmerenMO | 10483 | 2015-12-16 |  | 21587 | 2016-05-16 | LNup | 2016-12-01 | Kelso | Miner | 2 | 161 | 161 | 280 | Increase ground clearance, upgrade terminal equipment at Kelso and Miner. | MO | 19.85 |  | Planned | 5586082 |  |  | N | N | N | Y
A in MTEP16 | B>A | Central | AmerenMO | 10604 | 2016-08-09 |  | 21624 | 2016-01-13 | LNrc | 2016-12-01 | Page | Sioux | 1 | 138 |  | 241 | Replace conductor to match capability of the rest of the line | MO | 14.28 |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | Central | CWLD | 10162 | 2016-06-16 |  | 21625 | 2016-09-14 | TEQ | 2016-03-01 | McBaine | McBaine Tap | 1 | 161 |  | 249 | New wave trap and new switch on McBaine-McBaine Tap 161 kV line. | MO |  |  | M5_In Service | 50000 | Budgetary | Generator | N | N | N | Y
A in MTEP16 | B>A | Central | DEI | 2873 | 2015-10-06 | DIN0216 | 5026 | 2015-10-06 | Dist | 2018-06-01 | Danville East | new dist sub | 1 | 69 | 12 |  | Construct new Danville East substation near HRH hospital - single 22.4MVA transformer - 6945 ckt to be looped through | IN |  | 0.5 | Planned | 990000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | Central | DEI | 9834 | 2015-10-30 | AMIN1055 | 21211 | 2015-10-30 | LNrb | 2018-12-31 | Noblesville Gen Station | Tipton West | 1 | 230 |  | 501 | Noblesville to Tipton West 23008 ckt: Replace all single/H-frame pole structures with steel poles, reconductor with 954ACSR45X7 OVAL / OPGW and build Switching Station with 3-2000A line switches near existing Carmel 146th St. junction. | IN | 12 |  | Planned | 12079985 | Engineering w/AFUDC |  | N | N | N | Y
A in MTEP16 | B>A | Central | DEI | 9850 | 2016-08-03 | AMIN1129 | 21227 | 2016-08-03 | SwSta | 2017-12-31 | Lebanon Prairie Crk. SS |  |  | 69 |  | 100 | New Lebanon Prairie Crk. 69kV Switching Station to be inserted in the 6983 ckt. | IN |  | 1.1 | Planned | 3518244 | Engineering w/AFUDC |  | N | N | N | NT
A in MTEP16 | B>A | Central | DEI | 9854 | 2015-09-17 | AMIN1407 | 21231 | 2015-09-17 | CB | 2017-12-31 | Speed |  |  | 138 |  |  | Speed 138kV - Replace OCB 13850, 13857, 13869, 13881, 138138 TIE and obsolete relays on CIR 13850, 13857, 13881. | IN |  |  | Planned | 2264125 | Engineering w/AFUDC |  | N | N | N | Y
A in MTEP16 | B>A | Central | DEI | 9855 | 2015-11-30 | TIN1422 | 21232 | 2015-11-30 | CB | 2020-12-31 | Columbus North |  |  | 230 | 69 |  | Columbus North: Replace OCB 6975, 6929, 69230-1, 6950 and obsolete relays on CIR 6929, 6950, 6975, 6982. Also replace relays on CIR 23019. | IN |  |  | Planned | 2711016 | Engineering w/AFUDC |  | N | N | N | NT
A in MTEP16 | B>A | Central | DEI | 9856 | 2015-09-14 | TIN1406 | 21233 | 2015-09-14 | CB | 2017-12-31 | Walton |  |  | 230 | 69 |  | Walton: Replace OCB 69 KV CAP BK, 69230-1, 69110, 69 KV TRANSFER, 6927, 6987, 23020-21. | IN |  |  | Planned | 3303866 | Engineering w/AFUDC |  | N | N | N | NT
A in MTEP16 | B>A | Central | DEI | 9858 | 2016-01-25 | TIN1469 | 21238 | 2016-01-25 | TX | 2018-12-31 | Bedford 345kV |  |  | 345 | 138 | 400 | Bedford 345: Replace 345/138kV Bank 7 | IN |  |  | Planned | 4151661 | Engineering w/AFUDC |  | N | N | N | Y
A in MTEP16 | B>A | Central | DEI | 9858 | 2016-01-25 | TIN1469 | 21239 | 2016-01-25 | CB | 2018-12-31 | Bedford 345kV |  |  | 345 | 69 |  | Bedford 345: Replace relays on CIR 6995, 13829, 13837, 34506, 34521. Replace all 69kV and 138kV Oil Circuit Breakers. | IN |  |  | Planned | 7927152 | Engineering w/AFUDC |  | N | N | N | NT
A in MTEP16 | B>A | Central | DEI | 9888 | 2015-09-14 | TIN1528 | 21275 | 2015-09-14 | LNrb | 2017-12-31 | Middlefork | Deer Crk. Jct. | 1 | 69 |  | 100 | Rebuild 6988 ckt. from MiddleFork sub to deadend 879/1041-01 and from Deer Cr Jct to 879/1046. 477acsr@120C w/ OPGW - 187 wood poles to be replaced with light duty steel. | IN | 7.1 |  | Planned | 4860632 | Engineering w/AFUDC |  | N | N | N | NT
A in MTEP16 | B>A | Central | DEI | 9889 | 2015-09-14 | TIN1530 | 21277 | 2015-09-14 | LNrb | 2017-12-31 | Sharpsville | Kokomo Southeast |  | 69 |  | 100 | Rebuild 69174 ckt. from Sharpsville sub to Kokomo SE. 477acsr@120C w/ OPGW - 174 wood poles to be replaced with light duty steel. | IN | 7.3 |  | Planned | 4287945 | Engineering w/AFUDC |  | N | N | N | NT
A in MTEP16 | B>A | Central | DEI | 9890 | 2015-09-14 | TIN1536 | 21278 | 2015-09-14 | LNup | 2017-12-31 | Gibson Gen. Sta. | HE Merom Gen. Sta. |  | 345 |  |  | Gibson to Merom: Install (10) double deadend structures in the 34511 ckt. | IN |  |  | Planned | 4433734 | Engineering w/AFUDC |  | N | N | N | Y
A in MTEP16 | B>A | Central | DEI | 9891 | 2015-09-14 | TIN1534 | 21279 | 2015-09-14 | LNup | 2016-12-31 | Flat Rock | Hope Jct. |  | 69 |  |  | Flat Rock to Hope Jct. 6975 ckt. pole replacements (45), replace line switches at both ends. Transfer existing conductor to new poles. | IN | 3.3 |  | Planned | 1087274 | Engineering w/AFUDC |  | N | N | N | NT
A in MTEP16 | B>A | Central | DEI | 9892 | 2016-07-22 | TIN1533 | 21280 | 2016-07-22 | LNup | 2018-12-31 | Lewis Crk. | Flat Rock |  | 69 |  |  | Lewis Crk. to Flat Rock 6975 ckt. pole replacements (100), replace line switches at Lewis Crk with 1200A. Transfer existing conductor to new poles. | IN | 5.7 |  | Planned | 1875342 | Engineering w/AFUDC |  | N | N | N | NT
A in MTEP16 | B>A | Central | DEI | 9893 | 2015-09-14 | TIN1581 | 21281 | 2015-09-14 | CB | 2017-06-01 | Shelbyville Northeast |  |  | 138 | 69 |  | Shelbyville Northeast - Replace CIR 6946, 6976, 69183, 13803, 13865 relays, replace OCBs 6946, 6976, 69183, 69138-1, 13803, replace Bank 1 ground switch with circuit switcher, and station battery. | IN |  |  | Planned | 3511433 | Engineering w/AFUDC |  | N | N | N | NT
A in MTEP16 | B>A | Central | DEI | 9897 | 2015-09-15 | DIN1393 | 21295 | 2015-09-15 | Dist | 2018-06-01 | River Ridge Gateway |  |  | 138 | 12 |  | River Ridge Gateway 138-12kV Sub. to be inserted in the 13857 ckt. between Clark Maritime and HE Northport | IN |  |  | Planned | 1000000 | Planning Preliminary |  | N | N | N | NT
A in MTEP16 | B>A | Central | DEI | 9905 | 2015-11-30 | TIN1529 | 21313 | 2015-11-30 | LNrb | 2017-12-31 | Sharpsville | Windfall Jct. |  | 69 |  | 100 | Rebuild 69174 from Sharpsville sub to Windfall Jct - 477acsr@120C w/ OPGW - 81 wood poles to be replaced with light duty steel. Replace (3) Windfall Jct switches with 1200A. Install new motor mechs on 69-1 and 69-3 at Windfall Junction. | IN | 3.5 |  | Planned | 2179983 | Engineering w/AFUDC |  | N | N | N | NT
A in MTEP16 | B>A | Central | DEI | 9914 | 2015-10-26 | TIN1609 | 21327 | 2015-10-26 | LNrb | 2017-06-01 | Mohawk | Lee Hanna Jct |  | 69 |  | 153 | Rebuild 5.84 mile 69kV - 69130 ckt. from Mohawk to Mohawk Ind. Jct to Lee Hanna Jct with 954ACSR@120C - replace (2) Lee Hanna Jct line switches with 1200A | IN | 5.84 |  | Planned | 3741298 | Engineering w/AFUDC |  | N | N | N | NT
A in MTEP16 | B>A | Central | DEI | 9926 | 2016-07-22 | DIN1620 | 21338 | 2016-07-22 | Dist | 2018-12-31 | Spelterville |  |  | 138 | 34 |  | Spelterville: expand sub footprint, Install 138/34kV 60MVA Bank | IN |  |  | Planned | 1000000 | Planning Preliminary |  | N | N | N | NT
A in MTEP16 | B>A | Central | DEI | 10144 | 2015-09-30 | TIN1640 | 21480 | 2015-09-30 | CB | 2017-12-31 | Cayuga Gen. Sta. |  |  | 230 |  |  | Cayuga Gen. Sta.: Replace existing 230kV OCBs 23011-03, 23013-11,230B9-13 and associated disconnect switches. New brkrs will be 3000 amp, 63KIA with 3000A disc. switches | IN |  |  | Planned | 1536000 | Engineering w/AFUDC |  | N | N | N | Y
A in MTEP16 | B>A | Central | DEI | 11343 | 2016-08-10 | TIN1923 | 21762 | 2016-06-07 | LNrc | 2018-06-01 | Lafayette SE | General Foods Jct | 1 | 138 |  | 301 | Lafayette SE to General Foods Jct 13808 Reconductor: reconductor 0.64 mile of 138kV line with 954acsr@120C | IN | 0.64 |  | Planned | 1060000 | Planning Preliminary |  | N | N | N | Y
A in MTEP16 | B>A | Central | IPL | 9220 | 2015-06-23 |  | 20836 | 2015-06-23 | CB | 2018-12-31 | Parker |  |  | 138 |  |  | Replacement of 138 kV line breaker on 132-07 line due to results of annual short circuit analysis; NERC TPL-001-4 requirements R2.3 and R2.8. | IN |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | Central | IPL | 9220 | 2015-06-23 |  | 20843 | 2015-06-23 | CB | 2018-12-31 | Parker |  |  | 138 |  |  | Replacement of 138 kV bus-tie breaker due to results of annual short circuit analysis; NERC TPL-001-4 requirements R2.3 and R2.8. | IN |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | Central | IPL | 9220 | 2015-06-23 |  | 20842 | 2015-06-23 | CB | 2018-12-31 | Parker |  |  | 138 |  |  | Replacement of 138 kV line breaker on 132-17 line due to results of annual short circuit analysis; NERC TPL-001-4 requirements R2.3 and R2.8. | IN |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | Central | IPL | 9221 | 2015-06-23 |  | 20837 | 2015-06-23 | CB | 2016-12-31 | Southport |  |  | 138 |  |  | Replacement of 138 kV line breaker on 132-29 line due to results of annual short circuit analysis; NERC TPL-001-4 requirements R2.3 and R2.8. | IN |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | Central | IPL | 9222 | 2015-06-23 |  | 20838 | 2015-06-23 | CB | 2016-12-31 | Thompson |  |  | 138 |  |  | Replacement of 138 kV line breaker on 132-77 line due to results of annual short circuit analysis; NERC TPL-001-4 requirements R2.3 and R2.8. | IN |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | Central | IPL | 9222 | 2015-06-23 |  | 20841 | 2015-06-23 | CB | 2016-12-31 | Thompson |  |  | 138 |  |  | Replacement of 138 kV bus-tie breaker due to results of annual short circuit analysis; NERC TPL-001-4 requirements R2.3 and R2.8. | IN |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | Central | IPL | 9222 | 2015-06-23 |  | 20840 | 2015-06-23 | CB | 2016-12-31 | Thompson |  |  | 138 |  |  | Replacement of 138 kV line breaker on 132-68 line due to results of annual short circuit analysis; NERC TPL-001-4 requirements R2.3 and R2.8. | IN |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | Central | IPL | 9223 | 2015-06-23 |  | 20839 | 2015-06-23 | CB | 2018-12-31 | River Road |  |  | 138 |  |  | Replacement of 138 kV bus-tie breaker due to results of annual short circuit analysis; NERC TPL-001-4 requirements R2.3 and R2.8. | IN |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | Central | IPL | 9602 | 2015-09-03 |  | 20935 | 2015-09-03 | CB | 2016-12-31 | Mooresville |  |  | 138 |  |  | Replacement of 138 kV 132-84 Line breaker due to results of J238 GIP and annual short circuit analysis; NERC TPL-001-4 requirements R2.3 and R2.8. | IN |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | Central | IPL | 9602 | 2015-09-03 |  | 20937 | 2015-09-03 | CB | 2016-12-31 | Mooresville |  |  | 138 |  |  | Replacement of 138 kV bus-tie breaker due to results of J238 GIP and annual short circuit analysis; NERC TPL-001-4 requirements R2.3 and R2.8. | IN |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | Central | IPL | 9602 | 2015-09-03 |  | 20936 | 2015-09-03 | CB | 2016-12-31 | Mooresville |  |  | 138 |  |  | Replacement of 138 kV 132-24 Line breaker due to results of J238 GIP and annual short circuit analysis; NERC TPL-001-4 requirements R2.3 and R2.8. | IN |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | Central | IPL | 11123 | 2016-04-26 |  | 21714 | 2016-04-26 | RLY | 2017-07-15 | Guion 345 kV |  |  | 345 |  |  | Addition of redundant relay on Guion 345kV south bus section to mitigate P55 contingency. | IN |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | Central | IPL | 11523 | 2016-08-17 |  | 21784 | 2016-07-15 | LNup | 2021-06-30 | Stout CT | Stout North | 98 | 138 |  |  | Increase line rating to345 MVA | IN |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | Central | IPL | 11643 | 2016-08-10 |  | 21803 | 2016-07-29 | TX | 2017-06-01 | Stout North |  |  | 345 |  |  | Replace Failed Stout Auto | IN |  |  | Under Construction |  |  |  | N | N | N | Y
A in MTEP16 | B>A | Central | PPI | 9564 | 2015-09-14 | 2016-12,38,39,43 | 20930 | 2015-09-01 | SwSta | 2020-12-01 | 4Elkhart Jct (348950) | 4Turris Coal (348909) | 1 | 138 |  | 287 | 4 breaker ring bus at Turris Coal | IL |  | 5 | Planned | 4124000 | Budgetary |  | N | N | N | Y
A in MTEP16 | B>A | Central | PPI | 9564 | 2015-09-14 | 2016-12,38,39,43 | 20933 | 2015-09-01 | SwSta | 2020-12-01 | Athens Tap |  |  | 69 |  |  | Athens Tap 69 kV breaker station to sectionalize the Amos-Athens-East Lanesville 69 kV line | IL |  |  | Planned | 2204000 | Budgetary |  | N | N | N | NT
A in MTEP16 | B>A | Central | PPI | 9564 | 2015-09-14 | 2016-12,38,39,43 | 20932 | 2015-09-01 | SUB | 2020-12-01 | Athens 138 kV | Athens 69 kV |  | 138 | 69 | 75 | Athens 138/69 kV substation | IL |  |  | Planned | 4653000 | Budgetary |  | N | N | N | NT
A in MTEP16 | B>A | Central | PPI | 9564 | 2015-09-14 | 2016-12,38,39,43 | 20931 | 2015-09-01 | LN | 2019-12-01 | Turris W-ICG Viper Mine | Athens | 1 | 138 |  | 229 | New 138 kV transmission line | IL |  |  | Planned | 5316000 | Budgetary |  | N | N | N | Y
A in MTEP16 | B>A | Central | Vectren | 4393 | 2016-08-10 | 2013SIGE7 | 8410 | 2016-05-19 | LNrb | 2018-12-31 | Dubois 69 | Huntingburg 69 | 67-2 | 69 |  | 103 MVA | Rebuild and Reconductor approx. 3.5 miles | IN | 3.54 | 0 | Planned | 2625000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | Central | Vectren | 9940 | 2016-04-01 | 2016SIGE1 | 21379 | 2016-04-01 | LN | 2015-12-31 | Elliott | Sunbeam | Y52 | 69 |  |  | Y52 69kV loop from Elliott sub to Sunbeam sub | IN |  |  | M2a_Pre-Project Approval | 150000 | Engineering |  | N | N | N | NT
A in MTEP16 | B>A | Central | Vectren | 9940 | 2016-04-01 | 2016SIGE1 | 21381 | 2016-04-01 | Dist | 2015-12-31 | Elliott | Elliott Distribution | Y52 | 69 | 12 |  | New Distribution Substation with 9.375MVA 69kV/12kV transformer | IN |  |  | M2a_Pre-Project Approval | 1200000 | Engineering |  | N | N | N | NT
A in MTEP16 | B>A | Central | Vectren | 9942 | 2016-06-16 | 2016SIGE2 | 21384 | 2015-09-15 | LNrl | 2016-12-31 | GRIMM ROAD | WARRICK NORTH | Z85 | 138 |  |  | Public Roadway relocation of 1.25 miles of Z85 138kV line | IN |  |  | Planned | 1200000 | Budgetary |  | N | N | N | Y
A in MTEP16 | B>A | Central | Vectren | 9946 | 2016-08-10 | 2016SIGE11 | 21392 | 2016-05-18 | Dist | 2018-12-31 | ANGEL MOUNDS | HEIDELBACH | Z85 | 138 | 12 |  | 138kV/69kV/12kV Substation | IN |  |  | Planned | 2100000 | Budgetary |  | N | N | N | NT
A in MTEP16 | B>A | Central | Vectren | 9948 | 2016-08-25 | 2016SIGE11 | 21395 | 2016-05-18 | LNrb | 2019-12-31 | Pelzer | Chrisney | Y56 | 69 |  |  | Rebuild of 14 miles of Y56 69kV line from Pelzer Sub to Chrisney Sub | IN |  |  | Planned | 6800000 | Budgetary |  | N | N | N | NT
A in MTEP16 | B>A | Central | Vectren | 9952 | 2016-08-25 | 2016SIGE13 | 21400 | 2016-05-19 | LN | 2018-12-31 | HEIDELBACH | PIGEON CREEK | Y43 | 69 |  |  | Y43 69kV loop to Berry substation | IN |  |  | Planned | 300000 | Budgetary |  | N | N | N | NT
A in MTEP16 | B>A | East | CETO | 9543 | 2016-03-30 |  | 20926 | 2016-06-28 | CB | 2016-06-30 | Stamping Plant |  |  | 138 |  |  | Increase short-circuit capacity of the 177 and 188 circuit breakers | MI |  |  | M5_In Service | 560000 | Construction |  | N | N | N | Y
A in MTEP16 | B>A | East | CETO | 9544 | 2015-09-14 |  | 20925 | 2015-09-14 | CB | 2017-12-31 | CE Breaker Replacement Program - 2017 |  |  | 138 |  |  | Replace damaged or defective circuit breakers across the system. | MI |  |  | Planned | 1240000 |  |  | N | N | N | Y
A in MTEP16 | B>A | East | CETO | 9545 | 2015-09-14 |  | 20927 | 2015-09-14 | CB | 2016-12-31 | CE Breaker Replacement Program - 2016 |  |  | 138 |  |  | Replace damaged or defective circuit breakers across the system. | MI |  |  | Planned | 1380000 |  |  | N | N | N | Y
A in MTEP16 | B>A | East | CETO | 9859 | 2015-09-14 |  | 21240 | 2015-09-14 | LNup | 2016-12-31 | CE Line Equipment Replacement Program - 2016 |  |  | 138 |  |  | Replace cross arms, insulators, guying, and switches as needed to maintain the lines' condition | MI |  |  | Planned | 160000 |  |  | N | N | N | Y
A in MTEP16 | B>A | East | CETO | 9860 | 2015-09-14 |  | 21241 | 2015-09-14 | LNup | 2017-12-31 | CE Line Equipment Replacement Program - 2017 |  |  | 138 |  |  | Replace cross arms, insulators, guying, and switches as needed to maintain the lines' condition | MI |  |  | Planned | 160000 | Planning Preliminary |  | N | N | N | Y
A in MTEP16 | B>A | East | CETO | 9861 | 2015-09-14 |  | 21242 | 2015-09-14 | LNup | 2016-12-31 | CE Pole Replacement Program - 2016 |  |  | 138 |  |  | Replace damaged or defective poles with new poles | MI |  |  | Planned | 360000 |  |  | N | N | N | Y
A in MTEP16 | B>A | East | CETO | 9862 | 2015-09-14 |  | 21243 | 2015-09-14 | LNup | 2017-12-31 | CE Pole Replacement Program - 2017 |  |  | 138 |  |  | Replace damaged or defective poles with new poles | MI |  |  | Planned | 680000 | Planning Preliminary |  | N | N | N | Y
A in MTEP16 | B>A | East | CETO | 9863 | 2015-09-14 |  | 21244 | 2015-09-14 | LNup | 2016-12-31 | CE Line Sag Remediation - 2016 |  |  | 138 |  |  | Install poles or replace spans of conductor to remediate sag limits | MI |  |  | Planned | 400000 |  |  | N | N | N | Y
A in MTEP16 | B>A | East | CETO | 9865 | 2015-09-14 |  | 21245 | 2015-09-14 | RLY | 2016-12-31 | CE Relay Replacement Program - 2016 |  |  | 138 |  |  | Replace electromechanical and/or defective relays with new digital relays | MI |  |  | Planned | 240000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | East | CETO | 9866 | 2015-09-14 |  | 21246 | 2015-09-14 | RLY | 2017-12-31 | CE Relay Replacement Program - 2017 |  |  | 138 |  |  | Replace electromechanical and/or defective relays with new digital relays | MI |  |  | Planned | 480000 | Planning Preliminary |  | N | N | N | Y
A in MTEP16 | B>A | East | CETO | 9868 | 2015-09-14 |  | 21252 | 2015-09-14 | TEQ | 2016-12-31 | CE Substation Equipment Replacements - 2016 |  |  | 138 |  |  | Replace damaged or defective substation equipment, not including breakers or relays, with new equipment | MI |  |  | Planned | 560000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | East | CETO | 9870 | 2015-09-14 |  | 21253 | 2015-09-14 | TEQ | 2017-12-31 | CE Substation Equipment Replacements - 2017 |  |  | 138 |  |  | Replace damaged or defective substation equipment, not including breakers or relays, with new equipment | MI |  |  | Planned | 500000 | Planning Preliminary |  | N | N | N | Y
A in MTEP16 | B>A | East | CETO | 9871 | 2016-05-20 |  | 21254 | 2016-05-20 | LNrb | 2017-12-31 | Edenville | Edenville Jct | 1 | 138 |  |  | Rebuild the north portion of the Edenville-Edenville Jct 138 kV Line, approximately 9.8 miles, utilizing 138 kV single circuit construction and 336.4 ACSR conductor. | MI | 9.8 |  | Planned | 4170000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | East | CETO | 9872 | 2016-05-20 |  | 21255 | 2016-05-20 | LNrb | 2016-12-31 | Edenville | Edenville Jct | 1 | 138 |  |  | Rebuild the south portion of the Edenville-Edenville Jct 138 kV Line, approximately 2.0 miles, utilizing 138 kV single circuit construction and 336.4 ACSR conductor. | MI | 2 |  | Planned | 850000 | Engineering Preliminary |  | N | N | N | Y
A in MTEP16 | B>A | East | CETO | 9874 | 2015-09-14 |  | 21258 | 2015-09-14 | LNrb | 2017-12-31 | Cole Creek | Cole Creek Jct | 1 | 138 |  |  | Rebuild the Cole Creek-Cole Creek Jct 138 kV Line, approximately 4.7 miles, utilizing 138 kV single circuit construction and 795 ACSR conductor. | MI | 4.7 |  | Planned | 1960000 | Planning Preliminary |  | N | N | N | Y
A in MTEP16 | B>A | East | CETO | 9875 | 2016-09-30 |  | 21259 | 2016-06-28 | SUB | 2017-12-31 | Chase |  |  | 138 |  |  | Rebuild the 138 kV portion of Chase Substation to a three breaker ring bus | MI |  |  | Planned | 3200000 | Engineering Preliminary |  | N | N | N | Y
A in MTEP16 | B>A | East | CETO | 9878 | 2015-09-14 |  | 21263 | 2015-09-14 | SUB | 2018-06-01 | Vrooman |  |  | 138 |  |  | Complete the 138 kV bus as a ring by adding one 138 kV breaker | MI |  |  | Planned | 800000 | Planning Preliminary |  | N | N | N | Y
A in MTEP16 | B>A | East | CETO | 10046 | 2015-09-17 |  | 21447 | 2015-09-17 | SUB | 2018-03-01 | Beaver Creek |  |  | 138 |  |  | Construct a 138 kV three breaker ring bus at Beaver Creek Substation | MI |  |  | Planned | 3200000 | Planning Preliminary |  | N | N | N | Y
A in MTEP16 | B>A | East | CETO | 10046 | 2015-09-17 |  | 21448 | 2015-09-17 | RLY | 2018-03-01 | Higgins |  |  | 138 |  |  | Replace the relaying on the Higgins end of the line to Beaver Creek | MI |  |  | Planned | 300000 | Planning Preliminary |  | N | N | N | Y
A in MTEP16 | B>A | East | CETO | 10763 | 2016-05-04 |  | 21661 | 2016-06-28 | TEQ | 2016-06-17 | Emmet |  |  | 138 |  |  | Add a wavetrap and upgrade relaying on the Emmet-Livingston 138 kV Line to a dual-pilot scheme. | MI |  |  | M5_In Service | 874000 | Pre-Construction |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 9685 | 2015-09-10 | ITC_15_016 | 21008 | 2015-09-10 | LNup | 2019-12-31 | Jacob | St. Clair | 1 | 120 |  |  | Remediate the Sag Limit on Jacob-St. Clair 120 kV to 292 MVA (1405 Amp) | MI |  |  | Planned | 139000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 9692 | 2015-09-10 | ITC_15_022 | 21016 | 2015-09-10 | LNup | 2018-12-31 | Seneca | Spokane | 1 | 120 |  |  | Raise the Sag Limit on Seneca-Spokane 120 kV to 283 MVA (1362 Amp) | MI |  |  | Planned | 339000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 9883 | 2015-09-14 | ITC_15_025 | 21271 | 2015-10-01 | CB | 2019-12-31 | Ironton |  |  | 120 |  |  | Install two 120 kV breakers to terminate the two River Rouge–Ironton 120 kV connections at Ironton | MI |  |  | Planned | 910000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 9884 | 2016-09-30 | ITC_15_015 | 21272 | 2015-11-24 | LNup | 2019-12-31 | Belle River | Pontiac | 1 | 345 |  |  | Raise the Sag Limit on Belle River-Pontiac 345 kV to 1414 MVA (2366 Amp) | MI |  |  | Planned | 340000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 9887 | 2016-09-30 | ITC_15_019 | 21276 | 2015-10-01 | LNup | 2019-12-31 | Pontiac | Wxom | 1 | 345 |  |  | Raise the Sag Limit on Pontiac-Wixom 345 kV to 1185 MVA (1983 Amp) | MI |  |  | Planned | 305000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 9900 | 2015-09-15 | ITC_15_020 | 21301 | 2015-10-01 | LNup | 2018-12-31 | River Rouge | Ironton | 2 | 120 |  |  | Raise the Sag Limit on River Rouge-Ironton #2 120 kV to 271 MVA (1304 Amps) | MI |  |  | Planned | 340000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 9902 | 2015-09-15 | ITC_15_030 | 21308 | 2015-12-02 | SUB | 2018-12-31 | Sterling |  |  | 120 |  |  | Install a new 120 kV bus and one 120 kV breaker to convert Sterling to a ring bus. Also move the Sterling transformer #201 connection to the new bus and install a disconnect switch on the low side. Breaker “HT” will become the bus-tie between bus #101 and #104 | MI |  |  | Planned | 1100000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 9994 | 2015-12-04 | ITC_15_007 | 21418 | 2015-10-01 | LNrb | 2019-12-31 | Custer | Monroe | 1 | 120 |  |  | Rebuild the entire Custer – Monroe 120 kV line. Pre-build it to 230 kV construction to facilitate future 230 kV expansion in southern Michigan. Replace the existing assets (all structures and 954 ACSR 45/7 conductor) with new double-circuit structures that are designed for bundled 2-954 ACSR 54/7 conductor and install this conductor along with an OPGW path for the existing line only. | MI |  |  | Planned | 14500000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 9998 | 2015-09-15 |  | 21420 | 2015-09-15 | SUB | 2017-12-31 | ITCT Asset Replacement Program - 2017 |  |  | 345 | 120 |  | Replace aging and outdated equipment on a cycle that will ensure each piece of equipment is replaced near its expected end of life. Modern equipment can improve reliability, use state of the art technology, and typically will allow for longer maintenance intervals. New equipment is also commonly equipped with better monitoring and alarming functionality giving improved remote supervision. All of this will help to reduce overall maintenance costs | MI |  |  | Planned | 47970000 | Budgetary |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 9999 | 2015-09-15 |  | 21421 | 2015-09-15 | SUB | 2018-12-31 | ITCT Asset Replacement Program - 2018 |  |  | 345 | 120 |  | Replace aging and outdated equipment on a cycle that will ensure each piece of equipment is replaced near its expected end of life. Modern equipment can improve reliability, use state of the art technology, and typically will allow for longer maintenance intervals. New equipment is also commonly equipped with better monitoring and alarming functionality giving improved remote supervision. All of this will help to reduce overall maintenance costs. | MI |  |  | Planned | 53250000 | Budgetary |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 10000 | 2015-09-15 |  | 21423 | 2015-09-15 | SUB | 2019-12-31 | ITCT Asset Replacement Program - 2019 |  |  | 345 | 120 |  | Replace aging and outdated equipment on a cycle that will ensure each piece of equipment is replaced near its expected end of life. Modern equipment can improve reliability, use state of the art technology, and typically will allow for longer maintenance intervals. New equipment is also commonly equipped with better monitoring and alarming functionality giving improved remote supervision. All of this will help to reduce overall maintenance costs. | MI |  |  | Planned | 53310000 | Budgetary |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 10010 | 2016-03-23 |  | 21433 | 2015-09-15 | Dist | 2019-12-31 | Blanket for Customer Interconnections 2019 | Througout System |  | 120 |  |  | Connect interconnecting entities as requested | MI |  |  | Planned | 2000000 | Budgetary |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 10243 | 2015-10-16 |  | 21501 | 2015-11-24 | CB | 2018-06-30 | Navarre |  |  | 120 |  |  | Upgrade the existing Navarre 120 kV breaker HX to have an interrupting capability of 50 kA. | MI |  |  | Planned | 70000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 10270 | 2016-09-30 | ITC_15_053 | 21516 | 2015-10-28 | LNup | 2018-12-31 | Apache | Seneca | 1 | 120 |  |  | The proposed solution is to remediate the sag limit on the Apache – Seneca 120 kV line to 230 MVA (1107 Amp). | MI |  |  | Planned | 202000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 10425 | 2016-09-14 |  | 21581 | 2016-09-14 | SUB | 2017-09-01 | Grassmere |  |  | 345 |  |  | Install a 345 kV breaker w/ associated disconnects | MI |  |  | Under Construction | 1421500 | Engineering |  | N | Y | Y | Y
A in MTEP16 | B>A | East | ITCT | 10425 | 2016-09-14 |  | 22187 | 2016-09-14 | SUB | 2017-09-01 | Grassmere |  |  | 120 |  |  | 120 kV breakers and associated disconnects | MI |  |  | Under Construction | 1496500 |  |  | N | Y | N | Y
A in MTEP16 | B>A | East | ITCT | 10425 | 2016-09-14 |  | 21583 | 2016-09-14 | LN | 2017-09-01 | J340 Substation | Grassmere | 1 | 120 |  |  | Rebuild 5.3 miles of the existing 120 kV Cosmo tap using double circuit structures, and string 954 ACSR conductor between the J340 Interconnection substation and Grassmere. Relocate the Harvest Wind tap point to the new line to create the J340-Havest Wind-Grassmere 120 kV 3 terminal line. | MI | 5.3 |  | Under Construction | 7170000 | Engineering |  | N | Y | N | Y
A in MTEP16 | B>A | East | ITCT | 10425 | 2016-09-14 |  | 21582 | 2016-09-14 | TX | 2017-09-01 | Grassmere |  |  | 345 | 120 |  | Install a 345/120 kV transformer at Grassmere | MI |  |  | Under Construction | 5062000 | Engineering |  | N | Y | N | Y
A in MTEP16 | B>A | East | ITCT | 10723 | 2016-02-10 |  | 21650 | 2016-05-13 | SUB | 2017-12-01 | Skylark 120 kV |  |  | 120 |  |  | Construct the 120 kV Skylark substation and install 2-120 kV line breakers and 2-120 kV section breakers, along with a control house, associated disconnects, and all other required 120 kV equipment. | MI |  |  | Planned | 3487000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 10723 | 2016-02-10 |  | 21654 | 2016-05-13 | RLY | 2017-12-01 | Sloan 120 kV |  |  | 120 |  |  | Upgrade relaying at Sloan to accommodate the Skylark substation | MI |  |  | Planned | 117000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 10723 | 2016-02-10 |  | 21653 | 2016-05-13 | RLY | 2017-12-01 | Northeast 120kV |  |  | 120 |  |  | Upgrade relaying at Northeast to accommodate the new Skylark Substation. | MI |  |  | Planned | 223000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 10723 | 2016-02-10 |  | 21652 | 2016-05-13 | LN | 2017-12-01 | Skylark | Sloan | 1 | 120 |  |  | Line created by looping the existing Northeast-Sloan 120 kV circuit into Skylark. Install approx. 3.2 miles of OPGW on the line | MI | 3.1 | 0.1 | Planned | 627000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 10723 | 2016-02-10 |  | 21651 | 2016-05-13 | LN | 2017-12-01 | Northeast | Skylark | 1 | 120 |  |  | Line created by looping the existing Northeast-Sloan 120 kV circuit into Skylark. Install approx. 4.7 miles of OPGW on the line | MI | 4.6 | 0.1 | Planned | 941000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 10923 | 2016-03-21 |  | 21690 | 2016-03-21 | TEQ | 2016-12-31 | Throughout System |  |  | 120 |  |  | Install a new GOAB switch or replace an existing 120 kV, full-load-break pole top switch at necessary tap points. | MI |  |  | Planned | 2400000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 10924 | 2016-03-21 |  | 21691 | 2016-03-21 | TEQ | 2018-12-31 | Throughout System |  |  | 120 |  |  | Install a new GOAB switch or replace an existing 120 kV, full-load-break pole top switch at necessary tap points. | MI |  |  | Planned | 2400000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 11003 | 2016-04-12 | ITC_16_001 | 21698 | 2016-04-07 | SUB | 2017-12-01 | Mercury 120 kV |  |  | 120 |  |  | 120 kV, 3-breaker substation in a straight bus configuration. | MI |  |  | Planned | 2721000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 11003 | 2016-04-12 | ITC_16_001 | 21703 | 2016-04-07 | RLY | 2017-12-01 | Arctic | Ranger | 1 | 120 |  |  | Install 4.7 miles of OPGW (fiber) on the existing structures of the Arctic-Ranger 120 kV line. | MI | 4.7 |  | Planned | 1116000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 11003 | 2016-04-12 | ITC_16_001 | 21702 | 2016-04-07 | RLY | 2017-12-01 | Crestwood |  |  | 120 |  |  | Upgrade relaying equipment at Crestwood Substation | MI |  |  | Planned | 206000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 11003 | 2016-04-12 | ITC_16_001 | 21701 | 2016-04-07 | RLY | 2017-12-01 | Ranger |  |  | 120 |  |  | Upgrade relaying equipment at Ranger substation | MI |  |  | Planned | 127000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 11003 | 2016-04-12 | ITC_16_001 | 21700 | 2016-04-07 | LN | 2017-12-01 | Crestwood | Mercury | 1 | 120 |  |  | Line created by looping the existing Arctic-Crestwood 120 kV line into the new Mercury substation. | MI |  | 0.8 | Planned | 2965000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 11003 | 2016-04-12 | ITC_16_001 | 21699 | 2016-04-07 | LN | 2017-12-01 | Arctic | Mercury | 1 | 120 |  |  | Line created by looping the existing Arctic-Crestwood 120 kV line into the new Mercury substation. | MI |  | 0.8 | Planned | 2965000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 11043 | 2016-09-30 | ITC_13_052 | 21712 | 2016-08-11 | TEQ | 2016-04-04 | Monroe | Bay Shore |  | 345 |  |  | Replace 345kV terminal equipment at Monroe on the Monroe - Bay Shore circuit | MI |  |  | M5_In Service | 250000 | Engineering |  | N | Y | Y | Y
A in MTEP16 | B>A | East | ITCT | 11443 | 2016-09-30 |  | 21775 | 2016-06-30 | SUB | 2017-12-01 | Ranger |  |  | 120 |  |  | Install 2-3000A 120kV 40 kA min. int capability line breakers and associated equipment. Breakers are for the Elm - Ranger, and Ranger - Arctic 120kV lines. | MI | 0 |  | Planned | 1899000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 11443 | 2016-09-30 |  | 21778 | 2016-06-30 | SUBmisc | 2017-12-01 | Warren |  |  | 120 |  |  | Replace Trainers on River Rogue - Warren #2 120 kV line with 1590 SAC. | MI | 0 |  | Planned | 7000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 11443 | 2016-09-30 |  | 21777 | 2016-06-30 | SUBmisc | 2017-12-01 | River Rouge Power Plant |  |  | 120 |  |  | Replace Trainers on River Rogue - Warren #2 120 kV line with 1590 SAC. | MI | 0 |  | Planned | 7000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 11443 | 2016-09-30 |  | 21776 | 2016-06-30 | RLY | 2017-12-01 | ELM |  |  | 120 |  |  | Install line differential and breaker control relaying for position HO. | MI | 0 |  | Planned | 260000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 11583 | 2016-09-14 |  | 21787 | 2016-09-14 | SUB | 2017-09-01 | Kirk 345 kV |  |  | 345 |  |  | New 345 kV, 3-breaker substation laid out in a ring bus configuration | MI |  |  | Planned | 7559500 | GIA |  | N | Y | Y | Y
A in MTEP16 | B>A | East | ITCT | 11583 | 2016-09-14 |  | 21790 | 2016-09-14 | TEQ | 2017-09-01 | Kirk 345 kV |  |  | 345 |  |  | TOIFs associated with the J301 Project. This includes a 345 kV disconnect switch and entrance structure at the POI. | MI |  |  | Planned | 685000 | GIA |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 11583 | 2016-09-14 |  | 21789 | 2016-09-14 | LN | 2017-09-01 | Kirk | Bauer | 1 | 345 |  |  | New 345 kV line created by looping the Bauer-Ringle 345 kV line into Kirk. | MI |  | 0.1 | Planned | 626250 | GIA |  | N | Y | Y | Y
A in MTEP16 | B>A | East | ITCT | 11583 | 2016-09-14 |  | 21788 | 2016-09-14 | LN | 2017-09-01 | Kirk | Ringle | 1 | 345 |  |  | New 345 kV line created by looping the Bauer-Ringle 345 kV line into Kirk. | MI |  | 0.1 | Planned | 626250 | GIA |  | N | Y | Y | Y
A in MTEP16 | B>A | East | ITCT | 11584 | 2016-09-30 |  | 21791 | 2016-09-14 | SUB | 2017-09-01 | Helena 345 kV |  |  | 345 |  |  | New 345 kV, 3-breaker substation laid out in a ring bus configuration. | MI |  |  | Planned | 7495000 | GIA |  | N | Y | Y | Y
A in MTEP16 | B>A | East | ITCT | 11584 | 2016-09-30 |  | 21794 | 2016-09-14 | TEQ | 2016-09-01 | Helena 345 kV |  |  | 345 |  |  | TOIFs for the J308 Project. These include a 345 kV disconnect switch and entrance structure at the POI. | MI |  |  | Planned | 673000 | GIA |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 11584 | 2016-09-30 |  | 21793 | 2016-09-14 | LN | 2017-09-01 | Helena | Greenwood | 1 | 345 |  |  | New 345 kV line created by looping in the Greenwood-Rapson #2 line into Helena. | MI |  | 0.1 | Planned | 626500 | GIA |  | N | Y | Y | Y
A in MTEP16 | B>A | East | ITCT | 11584 | 2016-09-30 |  | 21792 | 2016-09-14 | LN | 2017-09-01 | Helena | Rapson | 1 | 345 |  |  | New 345 kV line created by looping in the Greenwood-Rapson #2 line into Helena. | MI |  | 0.1 | Planned | 626500 | GIA |  | N | Y | Y | Y
A in MTEP16 | B>A | East | ITCT | 11603 | 2016-09-14 |  | 21795 | 2016-09-14 | SUB | 2017-09-01 | Stringer 345 kV |  |  | 345 |  |  | New 345 kV, 3 breaker substation laid out in a ring bus configuration. | MI |  |  | Planned | 7411000 | GIA |  | N | Y | Y | Y
A in MTEP16 | B>A | East | ITCT | 11603 | 2016-09-14 |  | 21799 | 2016-09-14 | RLY | 2017-09-01 | Greenwood 345 |  |  | 345 |  |  | Upgrade relaying at pos. HI at Greenwood substation | MI |  |  | Planned | 36000 | GIA |  | N | Y | Y | Y
A in MTEP16 | B>A | East | ITCT | 11603 | 2016-09-14 |  | 21798 | 2016-09-14 | TEQ | 2017-09-01 | Stringer 345 kV |  |  | 345 |  |  | TOIFs for the J321 project. These include a 345 kV disconnect switch and entrance structure at the POI. | MI |  |  | Planned | 666000 | GIA |  | N | N | N | Y
A in MTEP16 | B>A | East | ITCT | 11603 | 2016-09-14 |  | 21797 | 2016-09-14 | LN | 2017-09-01 | Stringer | Greenwood | 1 | 345 |  |  | New 345 kV line created by looping the Greenwood-Rapson #2 345 kV line into Stringer substation. | MI |  | 0.1 | Planned | 626500 | GIA |  | N | Y | Y | Y
A in MTEP16 | B>A | East | ITCT | 11603 | 2016-09-14 |  | 21796 | 2016-09-14 | LN | 2017-09-01 | Stringer | Rapson | 1 | 345 |  |  | New 345 kV line created by looping the Greenwood-Rapson #2 345 kV line into Stringer substation. | MI |  | 0.1 | Planned | 626500 | GIA |  | N | Y | Y | Y
A in MTEP16 | B>A | East | ITCT | 11604 | 2016-09-14 |  | 21800 | 2016-09-14 | SUBmisc | 2018-06-30 | Milan 120 kV |  |  | 120 |  |  | Extend 120 kV Bus 103 at Milan substation | MI |  |  | Planned | 136000 | GIA |  | N | Y | N | Y
A in MTEP16 | B>A | East | ITCT | 11604 | 2016-09-14 |  | 21801 | 2016-09-14 | SUB | 2018-06-30 | Milan 120 kV |  |  | 120 |  |  | TOIFs for the J419 project. These include a 120 kV breaker and associated disconnects at pos. HD at Milan | MI |  |  | Planned | 667000 | GIA |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 2809 | 2015-10-02 | 87 | 336 | 2015-10-02 | LNrb | 2019-12-31 | Garfield Avenue | Hemphill | 1 | 138 |  |  | Rebuild a ~9.5 mile-long portion of 336 ACSR conductor utilizing 1431 ACSR conductor on double-circuit, 138 kV structures, relocate a portion of the Weadock – Hemphill 138 kV line to the other side of the new structures | MI | 9.5 |  | Planned | 11000000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 3133 | 2015-09-15 | METC_15_022 | 5510 | 2015-10-01 | LNrb | 2019-12-31 | Bell Road | Cornell | 1 | 138 |  |  | Rebuild a ~4.3 mile-long portion of the Claremont – Cornell 2 line between Bell Road and Cornell. | MI | 4.3 |  | Planned | 4350000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 9422 | 2016-09-30 | METC_15_017 | 20906 | 2016-06-07 | SUB | 2017-04-01 | Newton 138 kV |  |  | 138 |  |  | Construct a 138 kV, 4 breaker substation laid out in a ring bus configuration | MI |  |  | M3_Long Lead Materials | 5222000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 9422 | 2016-09-30 | METC_15_017 | 22384 | 2016-09-30 | CAP | 2018-06-01 | Newton 138 kV |  |  | 138 |  |  | Add an 18 MVAR switched capacitor bank at the new Newton Substation with a 138 kV synchronizing breaker. | MI |  |  | M1_Final SPM or OOC | 1220000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 9422 | 2016-09-30 | METC_15_017 | 20914 | 2016-06-07 | LN | 2017-04-30 | Michigan Ave | Newton | 1 | 138 |  |  | Construct an approx. 3 mile, 138 kV line between Michigan Ave and Newton, using 954 ACSR conductor | MI |  | 3 | M3_Long Lead Materials | 5868000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 9695 | 2015-09-10 | METC_15_028 | 21019 | 2015-09-10 | TEQ | 2018-12-31 | Bullock |  |  | 138 |  |  | Upgrade terminal equipment at Bullock on the Dow Corning 138 kV line | MI |  |  | Planned | 300000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 9705 | 2015-09-10 | METC_15_024 | 21036 | 2015-10-01 | LNup | 2018-12-31 | Alma | Regal | 2 | 138 |  |  | Remediate the sag limit on the Alma – Regal 2 138 kV line to a minimum of 208 MVA / 871 Amps | MI |  |  | Planned | 200000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 9876 | 2015-10-14 | METC_15_027 | 21261 | 2015-11-24 | LNup | 2018-12-31 | Karn | Manning | 1 | 138 |  |  | Remediate the sag limit on the Karn - Manning 138 kV line to a minimum of 396 MVA / 1657 Amps | MI |  |  | Planned | 470000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 9876 | 2015-10-14 | METC_15_027 | 21262 | 2015-11-24 | TEQ | 2018-12-31 | Karn |  |  | 138 |  |  | Upgrade terminal equipment at Karn | MI |  |  | Planned | 150000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 9932 | 2015-09-15 | METC_14_026 | 21345 | 2015-11-24 | LNrb | 2019-12-31 | Karn | Saginaw River | 1 | 138 |  |  | Rebuild a ~2.7 mile-long portion of the Karn – Saginaw River 138 kV line that is comprised of only 2-3/0 copper conductor in a six-wired configuration utilizing 1431 ACSR conductor on single-circuit, 138 kV structures | MI | 16 |  | Planned | 4500000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 9932 | 2015-09-15 | METC_14_026 | 21348 | 2015-11-24 | TEQ | 2019-12-31 | Saginaw River |  |  | 138 |  |  | Upgrade terminal equipment at Saginaw River | MI |  |  | Planned | 2920000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 9932 | 2015-09-15 | METC_14_026 | 21347 | 2015-11-24 | TEQ | 2019-12-31 | Karn |  |  | 138 |  |  | Upgrade terminal equipment at Karn | MI |  |  | Planned | 162000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 9932 | 2015-09-15 | METC_14_026 | 21346 | 2015-11-24 | LNup | 2019-12-31 | Karn | Saginaw River | 1 | 138 |  |  | Remediate the sag limit on the existing 1431 ACSR conductor to at least the planned target summer normal/summer emergency rating of 412 MVA/1724 Amps | MI |  |  | Planned | 918000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 9945 | 2015-09-15 |  | 21365 | 2015-09-15 | SUB | 2017-12-31 | METC Asset Replacement Program - 2017 |  |  | 345 | 138 |  | Replace aging and outdated equipment on a cycle that will ensure each piece of equipment is replaced near its expected end of life. Modern equipment can improve reliability, use state of the art technology, and typically will allow for longer maintenance intervals. New equipment is also commonly equipped with better monitoring and alarming functionality giving improved remote supervision. All of this will help to reduce overall maintenance costs | MI |  |  | Planned | 54276000 | Budgetary |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 9956 | 2015-09-15 |  | 21371 | 2015-09-15 | SUB | 2018-12-31 | METC Asset Replacement Program - 2018 |  |  | 345 | 138 |  | Replace aging and outdated equipment on a cycle that will ensure each piece of equipment is replaced near its expected end of life. Modern equipment can improve reliability, use state of the art technology, and typically will allow for longer maintenance intervals. New equipment is also commonly equipped with better monitoring and alarming functionality giving improved remote supervision. All of this will help to reduce overall maintenance costs | MI |  |  | Planned | 49398000 | Budgetary |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 9959 | 2016-03-23 |  | 21373 | 2015-09-15 | Dist | 2017-12-31 | Blanket for Customer Interconnections 2019 | Throughout System |  | 138 |  |  | Connect interconnecting entities as requested | MI |  |  | Planned | 2500000 | Budgetary |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 9960 | 2015-09-15 |  | 21374 | 2015-09-15 | SUB | 2019-12-31 | METC Asset Replacement Program - 2019 |  |  | 345 | 138 |  | Replace aging and outdated equipment on a cycle that will ensure each piece of equipment is replaced near its expected end of life. Modern equipment can improve reliability, use state of the art technology, and typically will allow for longer maintenance intervals. New equipment is also commonly equipped with better monitoring and alarming functionality giving improved remote supervision. All of this will help to reduce overall maintenance costs. | MI |  |  | Planned | 49398000 | Budgetary |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 9972 | 2016-06-16 |  | 21389 | 2016-04-01 | RLY | 2017-12-31 | Four Mile |  |  | 138 |  |  | Replace METC relaying and controls at Four Mile Substation. Locate the new relaying and controls in a new dedicated METC control center. Install dedicated METC AC and DC systems. | MI |  |  | Planned | 3520000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 9975 | 2016-06-16 |  | 21393 | 2016-04-01 | RLY | 2017-12-31 | Verona |  |  | 138 |  |  | Replace METC relaying and controls at Verona Substation. Locate the new relaying and controls in a new dedicated METC control center. Install dedicated METC AC and DC systems. | MI |  |  | Planned | 2940000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 9978 | 2015-09-15 |  | 21399 | 2015-11-24 | SUB | 2018-06-30 | Eureka |  |  | 138 |  |  | Replace the Eureka 138 kV circuit switcher 256 with a synchronous breaker that has a continuous rating of 3000 amp and a minimum interrupting capability of 40 kA | MI |  |  | Planned | 510000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 9984 | 2015-09-15 |  | 21407 | 2015-11-24 | SUB | 2018-06-30 | Tittabawassee |  |  | 345 |  |  | Replace the Tittabawassee 345 kV breaker 38H9 with a breaker that has a continuous rating of 3000 amp and a minimum interrupting capability of 40 kA. | MI |  |  | Planned | 790000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 10286 | 2016-07-18 | METC_12_001 | 21531 | 2016-07-18 | TEQ | 2018-12-31 | Campbell |  |  | 138 |  |  | Remove the Campbell 508 disconnect switch. Modify the relaying to remove 588 breaker sparing capability. | MI |  |  | Planned | 88000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 10323 | 2016-09-30 |  | 21673 | 2016-09-01 | SUB | 2018-05-31 | Michigan Ave 138kV |  |  | 138 |  |  | Install 2-138 kV line breakers and associated disconnect switches, along with a new control house at Michigan Ave substation | MI |  |  | Planned | 2137000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 10323 | 2016-09-30 |  | 21744 | 2016-05-12 | LN | 2018-05-31 | Batavia | Wagner | 1 | 138 |  |  | Line created by looping the Alder Creek-Batavia 138 kV circuit into Wagner substation. | MI |  | 0.1 | Planned | 412000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 10323 | 2016-09-30 |  | 21743 | 2016-05-12 | LN | 2018-05-31 | Alder Creek | Wagner | 1 | 138 |  |  | Line created by looping the Alder Creek-Batavia 138 kV circuit into Wagner substation. | MI |  | 0.1 | Planned | 412000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 10323 | 2016-09-30 |  | 21742 | 2016-09-01 | LN | 2018-05-31 | Newton | Wagner | 1 | 138 |  |  | Construct an approx. 13 mile, 138 kV line, on new future double circuit structures, using 954 ACSR between Newton and Wagner substations | MI |  | 13 | Planned | 26117000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 10323 | 2016-09-30 |  | 21741 | 2016-09-01 | RLY | 2018-05-31 | Coldwater 138 kV |  |  | 138 |  |  | Upgrade relaying on pos. 3040 @ Coldwater substation. | MI |  |  | Planned | 188000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 10323 | 2016-09-30 |  | 21740 | 2016-09-01 | RLY | 2018-05-31 | Batavia 138 kV |  |  | 138 |  |  | Upgrade relaying at pos. BM37 @ Batavia substation | MI |  |  | Planned | 21000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 10323 | 2016-09-30 |  | 21739 | 2016-09-01 | SUB | 2018-05-31 | Wagner 138 kV |  |  | 138 |  |  | Add a 138 kV, 3 breaker substation laid out in a ring bus configuration named Wagner, in Union City, MI | MI |  |  | Planned | 5122000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 10384 | 2015-11-23 | METC_15_018 | 21576 | 2016-06-07 | LNup | 2017-06-01 | VERONA | BARNUM CREEK JCT. | 138 | 138 |  |  | Fully remediate the sag limit on the 266.8 ACSR conductor from the Verona – Barnum Creek Jct. section of the Verona – Batavia 138 kV circuit to the conductor rating of 730 Amps / 174 VMVA (summer emergency) using new future double circuit (FDC) structures capable of supporting 954 ACSR in order to facilitate a rebuild of this circuit in the near future. | MI |  |  | M3_Long Lead Materials | 1070000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 10743 | 2016-09-30 |  | 21655 | 2016-09-14 | RLY | 2015-09-30 | Palisades 345 kV |  |  | 345 |  |  | Construct a new control house at Palisades substation and replace relaying to accommodate the interconnection request. | MI |  |  | M5_In Service | 3482000 | Engineering |  | N | Y | Y | Y
A in MTEP16 | B>A | East | METC | 10743 | 2016-09-30 |  | 21657 | 2016-09-14 | LNrb | 2015-09-30 | Palisades | Segreto | 1 | 345 |  |  | Install OPGW on the Palisades-Segreto #1 line (formerly Cook-Palisades) | MI | 1.5 |  | M5_In Service | 112000 | Engineering |  | N | Y | Y | Y
A in MTEP16 | B>A | East | METC | 10743 | 2016-09-30 |  | 21656 | 2016-09-14 | RLY | 2015-09-30 | Covert |  |  | 345 |  |  | Remove METC SCADA equipment from Covert substation | MI |  |  | M5_In Service | 11000 | Engineering |  | N | Y | Y | Y
A in MTEP16 | B>A | East | METC | 10744 | 2016-09-14 |  | 21658 | 2016-09-14 | SUB | 2016-05-09 | Van Tyle 138 kV |  |  | 138 |  |  | New 138 kV, 4 row, 11 breaker substation to be fed by looping in the Livingston-Stover 138 kV line and adding a Livingston-Van Tyle #2 line. | MI |  |  | M5_In Service | 7947200 | GIA |  | N | Y | N | Y
A in MTEP16 | B>A | East | METC | 10744 | 2016-09-14 |  | 21697 | 2016-09-14 | RLY | 2016-05-06 | Gaylord |  |  | 138 |  |  | Upgrade relaying at Gaylord | MI |  |  | M5_In Service | 20000 | GIA |  | N | Y | N | Y
A in MTEP16 | B>A | East | METC | 10744 | 2016-09-14 |  | 21696 | 2016-09-14 | SUB | 2016-06-11 | Livingston |  |  | 138 |  |  | Create 2 new rows and install 5-138 kV breakers with associated disconnect switches at Livingston substation | MI | 2.8 |  | M5_In Service | 3630000 | GIA |  | N | Y | N | Y
A in MTEP16 | B>A | East | METC | 10744 | 2016-09-14 |  | 21660 | 2016-09-14 | LN | 2016-05-09 | Livingston | Van Tyle | 2 | 138 |  |  | New 138 kV line created by rebuilding the Livingston-Van tyle line to double circuit structures and adding a second line between the substation using 1431 ACSR conductor | MI | 2.8 | 0.1 | M5_In Service | 3245000 | GIA |  | N | Y | N | Y
A in MTEP16 | B>A | East | METC | 10744 | 2016-09-14 |  | 21659 | 2016-09-14 | LN | 2016-05-09 | Livingston | Van Tyle | 1 | 138 |  |  | New 138 kV line created by looping the Livingston-Stover line into Van Tyle | MI | 2.8 | 0.1 | M5_In Service | 3245000 | GIA |  | N | Y | N | Y
A in MTEP16 | B>A | East | METC | 11243 | 2016-05-13 | METC_15_019 | 21747 | 2016-05-13 | LNrb | 2018-05-31 | Verona | Barnum Creek Jct. |  | 138 |  |  | Rebuild the Verona – Barnum Creek Jct. section of the Verona – Batavia 138 kV circuit using 954 ACSR and OGPW on new 230 kV future double circuit structures. Replace PTS 3186. Upgrade terminal equipment at the Verona station. | MI | 6.2 |  | Planned | 13300000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 11243 | 2016-05-13 | METC_15_019 | 21748 | 2016-05-13 | LNrc | 2018-05-31 | Verona | Convis Jct. |  | 138 |  |  | Reconductor approximately 0.6 miles of the Verona – Foundry 138 kV circuit where it shares common structures with the Verona – Batavia 138 kV circuit. | MI | 0.6 |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 11683 | 2016-09-30 |  | 21814 | 2016-08-22 | LNup | 2018-05-31 | Barnum Creek | Alder Creek | 1 | 138 |  |  | Remediate Sag on the Barnum Creek Jct. – Alder Creek 138 kV section up to the conductor rating of 174 MVA (730 Amp.). | MI |  |  | Planned | 400000 | Engineering Preliminary |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 11684 | 2016-09-30 |  | 21815 | 2016-08-22 | LNup | 2018-05-31 | Alder Creek | Wagner | 1 | 138 |  |  | Remediate Sag on the Alder Creek – Wagner 138 kV section up to the conductor rating of 174 MVA (730 Amp.). | MI |  |  | Planned | 365000 | Engineering Preliminary |  | N | N | N | Y
A in MTEP16 | B>A | East | METC | 11704 | 2016-09-30 |  | 21817 | 2016-08-19 | LNup | 2018-05-31 | Denso J. | Vrooman | 1 | 138 |  |  | Remediate the sag limit on the Denso J.–Vrooman 138 kV section to at least 150 MVA (628 Amp). | MI |  |  | Planned | 195000 | Engineering Preliminary |  | N | N | N | Y
A in MTEP16 | B>A | East | WPSC | 4385 | 2015-11-23 | BP-FV | 8400 | 2015-09-15 | LNrb | 2018-12-31 | Burnips | Drenthe | 1 | 69 |  | 143.4MVA | Rebuild Overloaded line (Peak case) | MI | 10.5 |  | Planned | 3150000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | East | WPSC | 4385 | 2015-11-23 | BP-FV | 8401 | 2013-12-16 | LNrb | 2018-12-31 | Drenthe | Fairview | 1 | 69 |  | 143.4MVA | Rebuild Overloaded line (Peak case) | MI | 1.1 |  | Planned | 350000 |  |  | N | N | N | Y
A in MTEP16 | B>A | East | WPSC | 9899 | 2016-07-07 | RW-SV Rebuild | 21302 | 2015-09-15 | LNrb | 2018-12-31 | Redwood | Crystal Valley Junction | 1 | 69 |  | 143.4 | Rebuild the Redwood to Scottville 69kV line, install new poles and hardware with 795ACSS conductor | MI | 6.92 |  | Planned | 3075000 | Budgetary |  | N | N | N | NT
A in MTEP16 | B>A | East | WPSC | 9899 | 2016-07-07 | RW-SV Rebuild | 21305 | 2015-09-15 | LNrb | 2018-12-31 | Riverton | Scottville | 1 | 69 |  |  | Rebuild the Redwood to Scottville 69kV line, install new poles and hardware with 795ACSS conductor | MI | 0.1 |  | Planned | 500000 | Budgetary |  | N | N | N | NT
A in MTEP16 | B>A | East | WPSC | 9899 | 2016-07-07 | RW-SV Rebuild | 21304 | 2016-09-15 | LNrb | 2018-12-31 | Eden | Riverton | 1 | 69 |  |  | Rebuild the Redwood to Scottville 69kV line, install new poles and hardware with 795ACSS conductor | MI | 6.12 |  | Planned | 3325000 | Budgetary |  | N | N | N | NT
A in MTEP16 | B>A | East | WPSC | 9899 | 2016-07-07 | RW-SV Rebuild | 21303 | 2015-09-15 | LNrb | 2018-12-01 | Crystal Valley Junction | Eden | 1 | 69 |  | 143.4 | Rebuild the Redwood to Scottville 69kV line, install new poles and hardware with 795ACSS conductor | MI | 7.45 |  | Planned | 3600000 | Budgetary |  | N | N | N | NT
A in MTEP16 | B>A | East | WPSC | 9913 | 2015-09-15 | 2017 Battery Bank Replacement Project | 21324 | 2015-09-15 | BAT | 2017-12-31 | System Need |  |  | 69 |  |  | 2017 Battery Bank replacement program | MI |  |  | Planned | 70000 | Budgetary |  | N | N | N | NT
A in MTEP16 | B>A | East | WPSC | 9915 | 2015-09-15 | OE Relay Upgrade | 21329 | 2015-09-15 | RLY | 2017-12-31 | Oden |  |  | 69 |  |  | Upgrade relaying at Oden on the Oden - Emmet terminal | MI |  |  | Planned | 35000 | Budgetary |  | N | N | N | NT
A in MTEP16 | B>A | East | WPSC | 11023 | 2016-04-11 |  | 21704 | 2016-04-11 | SUB | 2016-05-16 | Advance |  |  | 138 | 69 |  | Add 138kV bus and 138/69kV transformer to Wolverine's Advance station | MI |  |  | Under Construction | 4213420 | Budgetary |  | N | N | N | NT
A in MTEP16 | B>A | East | WPSC | 11023 | 2016-04-11 |  | 21711 | 2016-04-11 | LNrb | 2016-04-30 | Gaylord (WPSC) | Livingston |  | 138 |  |  | Rebuild existing line with 795ACSS conductor | MI | 2.03 |  | Under Construction | 891442 | Budgetary |  | N | N | N | Y
A in MTEP16 | B>A | East | WPSC | 11023 | 2016-04-11 |  | 21710 | 2016-04-11 | LNcnv | 2016-05-15 | Gaylord | Advance | 1 | 138 |  |  | Convert operating voltage on the the Gaylord to Advance line from 69kV to 138kV. Existing 23.74mi line in constructed for 138kV operation. New lines will be Gaylord - Van Tyle 138kV and Van Tyle - Advance 138kV | MI | 21.75 | 1 | Under Construction | 806493 | Budgetary |  | N | N | N | Y
A in MTEP16 | B>A | East | WPSC | 11023 | 2016-04-11 |  | 21709 | 2016-04-11 | SUB | 2016-05-15 | Deer Lake |  |  | 138 | 13.09 |  | Upgrade Deer Lake distribution station from 69kV to 138kV operation | MI |  |  | Under Construction | 639544 | Budgetary |  | N | N | N | NT
A in MTEP16 | B>A | East | WPSC | 11023 | 2016-04-11 |  | 21708 | 2016-04-11 | SUB | 2016-05-15 | Alpine Distribution |  |  | 138 | 13.09 |  | Upgrade Alpine distribution substation from 69kV to 138kV operation | MI |  |  | Under Construction | 1404228 | Budgetary |  | N | N | N | NT
A in MTEP16 | B>A | East | WPSC | 11023 | 2016-04-11 |  | 21707 | 2016-04-11 | SUB | 2016-05-15 | Elmira |  |  | 138 | 13.09 |  | Upgrade the Elmira distribution station from 69kV to 138kV operation | MI |  |  | Under Construction | 1234872 | Budgetary |  | N | N | N | NT
A in MTEP16 | B>A | East | WPSC | 11023 | 2016-04-11 |  | 21706 | 2016-04-11 | SUB | 2018-10-31 | Gaylord (WPSC) |  |  | 138 |  |  | Phase II - Convert Gaylord 138kV bus to 6 breaker ring bus design to accommodate 2nd 138/69kV transformer. | MI |  |  | Under Construction | 2244651 | Budgetary |  | N | N | N | Y
A in MTEP16 | B>A | East | WPSC | 11023 | 2016-04-11 |  | 21705 | 2016-04-11 | SUB | 2016-04-30 | Gaylord (WPSC) |  |  | 138 | 96 |  | Phase I - Convert 138kV bus to 4 terminal ring bus design. Additional terminal required to bring 3rd 138kV line into the bus. | MI |  |  | Under Construction | 2545422 | Budgetary |  | N | N | N | NT
A in MTEP16 | B>A | South | AECC | 9662 | 2015-10-13 |  | 20987 | 2016-05-09 | TX | 2017-01-01 | Harrison South |  |  | 161 |  |  | Upgrade transformer at Harrison South. | AR |  |  | Planned | 600000 | Planning Preliminary |  | N | N | N | Y
A in MTEP16 | B>A | South | AECC | 9663 | 2015-10-13 |  | 20988 | 2016-05-09 | SUB | 2017-07-01 | Newport East |  |  | 161 | 13.2 |  | Construct 20 MVA, 161/13.2 kV substation. | AR |  |  | Planned | 500000 | Planning Preliminary |  | N | N | N | NT
A in MTEP16 | B>A | South | AECC | 10204 | 2016-05-06 |  | 21491 | 2016-05-06 | SUB | 2018-06-01 | Hunter North 161/13.2kV Substation |  |  | 161 |  |  | 161/13.2kV Hunter North substation | AR |  |  | Planned | 500000 | Planning Preliminary |  | N | N | N | Y
A in MTEP16 | B>A | South | AECC | 10205 | 2015-11-12 |  | 21492 | 2016-05-06 | SwSta | 2017-02-28 | AECC Bee Branch |  |  | 161 |  |  | 161kV Tap Breaker | AR |  |  | Planned | 500000 |  |  | N | N | N | Y
A in MTEP16 | B>A | South | AECC | 10205 | 2015-11-12 |  | 21494 | 2016-05-06 | SUB | 2017-02-28 | Damascus |  |  | 161 |  |  | 161/13.2kV substation | AR |  |  | Planned | 2000000 |  |  | N | N | N | Y
A in MTEP16 | B>A | South | AECC | 10205 | 2015-11-12 |  | 21493 | 2016-05-06 | LN | 2017-02-28 | AECC Bee Branch | AECC Damascus | 1 | 161 |  |  | 6.8 mile 161kV line from the existing AECC Bee Branch substation to the proposed Damascus substation | AR |  |  | Planned | 5500000 |  |  | N | N | N | Y
A in MTEP16 | B>A | South | AECC | 10206 | 2016-05-06 |  | 21495 | 2016-05-06 | SwSta | 2020-12-01 | Clinton West |  |  | 161 |  |  | 5 position ring bus | AR |  |  | Planned | 5000000 |  |  | N | N | N | Y
A in MTEP16 | B>A | South | AECC | 10206 | 2016-05-06 |  | 21497 | 2016-05-06 | SUB | 2020-12-01 | Partain |  |  | 161 | 69 | 100MVA | build 3 position ring bus and 100MVA 161/69kV stepdown station with 2 69kV breakers | AR |  |  | Planned | 4000000 | Planning Preliminary |  | N | N | N | NT
A in MTEP16 | B>A | South | AECC | 10206 | 2016-05-06 |  | 21496 | 2016-05-06 | LN | 2020-12-01 | Clinton West | Partain |  | 161 |  |  | 14.0 mile line from the existing Clinton West to the proposed Partain substation | AR |  |  | Planned | 18000000 | Planning Preliminary |  | N | N | N | Y
A in MTEP16 | B>A | South | AXLA | 10122 | 2015-10-15 | AXLA PRJ_01_MTEP16 | 21469 | 2016-05-16 | LNrc | 2017-06-01 | Hunter | Downtown | 1 | 138 |  |  | Reconductor the existing Hunter - Downtown 138kV transmission line | LA |  |  | Planned | 340000 |  |  | N | N | N | Y
A in MTEP16 | B>A | South | AXLA | 10123 | 2015-10-15 | AXLA PRJ_02_MTEP16 | 21470 | 2016-05-16 | LNrc | 2017-06-01 | Prescott | Sterks | 1 | 138 |  |  | Reconductor the existing Prescott - Sterkx 138kV transmission line | LA |  |  | Planned | 490000 |  |  | N | N | N | Y
A in MTEP16 | B>A | South | CLECO | 9542 | 2015-09-11 | 19944 | 20924 | 2015-08-31 | SUB | 2016-12-01 | DoletHills Mine |  |  | 230 |  |  | Tap existing Dolet Hills to Mansfield compressor 8.4 miles from Dolet Hills to serve new load. | LA |  |  | Planned | 5000000 | Budgetary |  | N | N | N | Y
A in MTEP16 | B>A | South | CLECO | 9713 | 2015-09-11 |  | 21093 | 2015-09-11 | CB | 2016-11-01 | Dolet Hills |  |  | 345 |  |  | Replace one of the 345kV breakers at Dolet Hills | LA |  |  | Planned | 294580 | Budgetary |  | N | N | N | Y
A in MTEP16 | B>A | South | CLECO | 9715 | 2015-09-11 |  | 21094 | 2015-09-11 | CB | 2016-10-01 | Wax Lake |  |  | 138 |  |  | Replaced existing MOS for Cap bank 1 and 2 with new Cap Switchers | LA |  |  | Planned | 406013 |  |  | N | N | N | Y
A in MTEP16 | B>A | South | CLECO | 10983 | 2016-04-04 |  | 21695 | 2016-04-04 | CB | 2017-05-01 | HOPKINS |  |  | 138 |  |  | Add a breaker in series with Hopkins Breaker 8061 | LA |  |  | Planned | 300000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-AR | 4665 | 2015-09-28 | 12-EAI-019 | 8845 | 2015-10-05 | TX | 2017-12-01 | Mabelvale 500 kV Substation | Mabelvale 115 kV Substation | 1 | 500 | 115 | 598 | Replace transformer | AR |  |  | Planned | 17417000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-AR | 4665 | 2015-09-28 | 12-EAI-019 | 8846 | 2015-10-05 | TX | 2017-12-01 | Mabelvale 500 kV Substation | Mabelvale 115 kV Substation | 2 | 500 | 115 | 598 | Replace transformer | AR |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-AR | 7942 | 2016-08-23 | 15-EAI-004 | 20193 | 2015-09-09 | LNrb | 2019-06-01 | Mayflower 115kV substation | Morgan 115kV substation | 1 | 115 |  | 390MVA | Rebuild 5 miles of 115kV line from Mayflower to Morgan. | AR | 5 |  | Planned | 4877301 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-AR | 7944 | 2015-09-16 | 15-EAI-007 | 20195 | 2016-09-14 | LNrb | 2018-01-30 | Stuttgart Ricuskey | Stuttgart Industrial | 1 | 115 |  | 259MVA | Rebuild 2.6 miles of 115kV line from Stuttgart Ricuskey - Stuttgart Industrial. | AR | 2.6 |  | Planned | 2526158 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-AR | 9673 | 2015-09-09 | 16-EAI-002 | 20991 | 2015-09-09 | TX | 2018-06-01 | El Dorado EHV |  |  | 500 | 115 |  | 598 MVA - 500/115 kV autotransformer | AR |  |  | Planned | 16446045 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-AR | 9691 | 2015-09-24 | 16-EAI-009 | 21015 | 2016-09-14 | CAP | 2017-06-01 | Lonoke East 115kV |  |  | 115 |  |  | Add a 20.5 MVAR capacitor bank at Lonoke East 115 kV station to provide voltage support upon contingency | AR |  |  | Planned | 1456861 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-AR | 9693 | 2015-09-10 | 16-EAI-014 | 21017 | 2016-09-14 | IND | 2017-10-01 | Pleasant Hill |  |  | 500 | 161 |  | Add three 30 MVAR reactors on the tertiary windings of the 500/161/13.8 kV transformer at the Pleasant Hill EHV substation | AR |  |  | Planned | 2184660 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-AR | 9696 | 2016-09-28 | 16-AI-017 | 21020 | 2016-09-14 | SwSta | 2018-06-01 | Newport SS |  |  | 161 |  |  | Build a 4-breaker switching station near Newport Industrial and re-terminate the Newport-Swifton 161 kV line into the new switching station. Build a new 161 kV line between the Newport switching station and Newport Industrial to eliminate the voltage issue. | AR |  |  | Planned | 15150000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-AR | 9697 | 2015-09-10 | 16-EAI-001 | 21021 | 2016-09-14 | LNrb | 2018-06-01 | Trumann 161kV | Trumann West 161kV |  | 161 |  |  | Re-build 6.5 mile long line to a minimum rating of 1300A. | AR | 6.5 |  | Planned | 12115000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-AR | 9698 | 2016-02-03 | 16-EAI-006 | 21022 | 2016-09-14 | LNrb | 2018-06-01 | El Dorado East 115kV | El Dorado Jackson 115kV |  | 115 |  |  | Re-build the 2.92 mile long 115 kV line to a minimum rating of 259 MVA (1300 Amps) to eliminate the thermal constraints | AR | 2.92 |  | Planned | 4926295 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-AR | 9703 | 2015-09-10 | 16-EAI-007 | 21031 | 2016-09-14 | SUB | 2017-10-01 | Bono |  |  | 161 |  |  | Purchase substation Site with enough land for future second transformer. Install 1-40 MVA - 161/13.8 kV - LTC substation transformer and three (3) breaker bays. Construct the feeder bays for overhead exits. Install one 2000 amp / 15 kV main breaker and three 1200 amp / 15kV feeder breakers. Install SCADA and metering in accordance with Entergy standards. Build new circuit N310- Replace 2 miles of 1/0 Acsr with 795 AA from substation south on Highway 285 to Highway 225. Build new circuit N320 - build new 2 miles of 795AA and reconductor 1.67 miles of 1/0 Acsr with 795 AA from substation south on Highway 285 to Highway 25. Build new circuit N330 - 500 feet of 795 to tie into existng 1/0 Acsr to the north on Highway 285 to pick up Republican Road.. Install 3-1200 amp Air breaks(Republican Road, Highway 225, and Highway 25) to be normally OPEN.Install 3-1200 amp getaway disconnects on each circuit. | AR |  |  | Planned | 9380200 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-AR | 9704 | 2015-09-10 | 16-EAI-008 | 21035 | 2016-09-14 | SUB | 2017-10-01 | London North 161kV |  |  | 161 |  |  | Purchase substation Site with enough land for future second transformer. Install 1-40 MVA - 161/13.8 kV - LTC substation transformer and three (3) breaker bays. Construct the feeder bays for overhead exits. Install one 2000 amp / 15 kV main breaker and three 1200 amp / 15kV feeder breakers. Install SCADA and metering in accordance with Entergy standards. Build 300 feet of 795 AA for new circuit XXXX from substation north to Highway 64. Replace 1.4 miles of 3 phase #6 copper with 336 acsr from substation site west on Highway 64 to the town of London. Replace Recloser 7Y21with a 600 amp air break to be normally OPEN.. Build 500 feet of 795 for new circuit XXXX to tie in to 336 Acsr that travels south via Transmission Line to the ANO plant. Build 300 feet of 795 AA for new circuit XXXX from substation north to Highway 64 to tie into the existing 336 east toward Russellville North substation. Reconductor 0.8 mile of 336 Acssr with 795 AA from substation east on Highway 64 to Mill creek Road. Install 2-1200 amp Air breaks on Highway 64. Install 1200 amp getaway disconects on each feeder circuit. | AR |  |  | Planned | 9244000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-AR | 9707 | 2015-09-10 | 16-EAI-011 | 21040 | 2016-09-14 | SUB | 2017-06-01 | Camden Maguire 115kV |  |  | 115 |  |  | Reconfigure Camden Maguire 115 kV substation so that a single bus failure will not open all the elements in the Camden Maguire substation. Some potential configurations are double bus double breaker, breaker and a half, and ring bus. The final configuration will be decided during project scoping. | AR |  |  | Planned | 5772470 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-AR | 9708 | 2015-09-10 | 16-EAI-004 | 21041 | 2016-09-14 | SUB | 2017-10-01 | Independence 161kV |  |  | 161 |  |  | Reconfiguring the Independence 161 kV station to a breaker-and-a-half configuration or a double bus/double breaker configuration will help eliminate area thermal and voltage violations. The specific configuration will be determined in project scoping. | AR |  |  | Under Construction | 9100851 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-AR | 9709 | 2015-09-10 | 16-EAI-012 | 21042 | 2016-09-14 | SUB | 2019-06-01 | Mabelvale 115kV |  |  | 115 |  |  | Reconfigure the Mabelvale 115 kV substation so that a single bus tie breaker failure will not open all the elements in the Mabelvale 115 kV substation. Some potential configurations are double bus double breaker, breaker and a half, and ring bus. The final configuration will be decided during project scoping. | AR |  |  | Planned | 17446076 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-AR | 10044 | 2015-09-17 | 16-EAI-018 | 21446 | 2015-09-17 | SwSta | 2018-01-30 | Goodwin |  |  | 115 |  |  | New 115 kV breaker switching station | AR |  |  | Planned | 10064000 | GIA |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-AR | 11483 | 2016-06-30 | 16-EAI-023 | 21774 | 2016-06-30 | SUB | 2017-05-01 | Hurricane Lake |  |  | 115 |  |  | New delivery point on River Ridge - Mabelvale 115 kV line. | AR |  |  | Planned | 1589494 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 4634 | 2015-09-11 | 13-ELL-006 | 8797 | 2016-05-10 | LNrc | 2018-06-01 | Ninemile 115 kV substation | Westwego 115 kV substation | 1 | 115 |  | 320 MVA | Reconductor Line | LA | 5.65 |  | Planned | 9026000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 4634 | 2015-09-11 | 13-ELL-006 | 8798 | 2016-05-10 | TEQ | 2018-06-01 | Ninemile 115 kV substation | Westwego 115 kV substation | 1 | 115 |  | 320 MVA | Upgrade terminal equipment | LA |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 4639 | 2015-09-13 | 14-ELL-006 | 8804 | 2016-05-10 | LNrc | 2018-06-01 | Ninemile 115 kV substation | Harvey2 115 kV substation | 1 | 115 |  | 320 MVA | Reconductor Line | LA | 9.5 |  | Planned | 15121000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 4639 | 2015-09-13 | 14-ELL-006 | 8805 | 2016-05-10 | TEQ | 2018-06-01 | Ninemile 115 kV substation | Harvey2 115 kV substation | 1 | 115 |  | 320 MVA | Upgrade terminal equipment | LA |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 7949 | 2016-05-10 | 15-EGL-010 | 20209 | 2015-09-13 | TX | 2018-06-01 | SOLAC 230 | SOLAC 69 | 1 | 230 | 69 | 300 | "NERC TPL-001-4 Reliability Standards and Entergy's Planning Guidelines. Each of the 138-69 kV Solac autotransformers will exceed their thermal rating during the single contingency (P1-3) transformer loss of one autotransformer on the other. This project will mitigate the thermal load violations on the two autotransformers by installing a third 138-69 kV Autotransformer at Solac." | LA |  |  | Planned | 8457000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | South | Entergy-LA | 7949 | 2016-05-10 | 15-EGL-010 | 21135 | 2015-09-13 | TX | 2018-06-01 | Solac 230 | Solac 69 | 2 | 230 | 69 | 300 | Upgrade AT2 | LA |  |  | Planned |  |  |  | N | N | N | NT
A in MTEP16 | B>A | South | Entergy-LA | 7950 | 2015-11-06 | 15-EGL-011 | 20210 | 2015-09-13 | LNrc | 2018-06-01 | 335235 East Broad 69 | 335237 Ford 69 | 1 | 69 |  | 143 MVA | "NERC TPL-001-4 Reliability Standards and Entergy's Planning Guidelines. The East Broad to Ford 69 kV line will exceed its thermal rating during the single contingency (P1-2) breaker to breaker loss of the Contraband to Solac 69 kV line. This project will result in an increase in the thermal rating of the circuit by upgrading the line conductor." | LA | 1.49 |  | Planned | 1474000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | South | Entergy-LA | 7952 | 2015-09-13 | 15-EGL-012 | 20212 | 2015-09-13 | LNrc | 2018-06-01 | 335239 SOLAC 69 | 335240 SOLAC 69 | 1 | 69 |  | 143 MVA | "NERC TPL-001-4 Reliability Standards and Entergy's Planning Guidelines. The Contraband to Solac 69 kV line will exceed its thermal rating during the single contingency (P2-1) open breaker at East Broad toward Ford 69 kV line. This project will result in an increase in the thermal rating of the circuit by upgrading the line conductor." | LA | 2.26 |  | Planned | 4125000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | South | Entergy-LA | 9682 | 2015-09-10 | 16-ELN-001 | 20997 | 2015-09-10 | LNrb | 2020-06-01 | Vienna | Trussell Crossing | 1 | 115 |  |  | Upgrade line rating. | LA | 6.9 |  | Planned | 8823757 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 9684 | 2015-11-06 | 16-ELN-004 | 21006 | 2015-09-14 | Dist | 2018-06-01 | Cadeville |  |  | 115 |  |  | 115 kV distribution substation | LA |  |  | Planned | 41643000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 9684 | 2015-11-06 | 16-ELN-004 | 21007 | 2015-09-10 | LN |  | Rilla | Cadeville | 1 | 115 |  |  | 15 mile 115 kV line constructed to 230 kV specs | LA |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 9686 | 2015-09-10 | 16-ELN-005 | 21009 | 2015-11-18 | Dist | 2020-06-01 | Lake Providence |  |  | 115 |  |  | New Lake Providence distribution sub. | LA |  |  | Planned | 31830074 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 9686 | 2015-09-10 | 16-ELN-005 | 21010 | 2015-09-10 | LN |  | OakGrove | Lake Providence | 1 | 115 |  | 176 | New 115 kV line to new distribution substation. | LA |  | 15 | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 9690 | 2015-09-10 | 16-ELN-010 | 21014 | 2015-09-14 | Dist | 2018-12-01 | Hodge |  |  | 230 |  |  | 230 kV substation | LA |  |  | Planned | 14121450 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 9763 | 2015-09-13 | 16-EGL-004 | 21137 | 2015-09-13 | LNrc | 2018-06-01 | Baker | Blount | 1 | 69 |  |  | Upgrade Line | LA |  |  | Planned | 5182000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | South | Entergy-LA | 9765 | 2015-09-13 | 16-EGL-006 | 21139 | 2015-09-13 | LNrc | 2018-12-01 | Harelson | Line 369 Tap | 1 | 69 |  |  | Upgrade Line | LA |  |  | Planned | 3165000 |  |  | N | N | N | NT
A in MTEP16 | B>A | South | Entergy-LA | 9770 | 2015-09-13 | 16-EGL-011 | 21144 | 2016-05-10 | TEQ | 2016-11-18 | Goosport | L673 Tp | 1 | 69 |  |  | Upgrade Line | LA |  |  | Planned | 145205 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | South | Entergy-LA | 9771 | 2015-09-13 | 16-EGL-012-1 | 21145 | 2015-09-13 | SUB | 2019-06-01 | Jefferson Davis |  |  | 138 | 69 |  | Build new Sub | LA |  |  | Planned | 76570000 |  |  | N | N | N | NT
A in MTEP16 | B>A | South | Entergy-LA | 9772 | 2015-09-13 | 16-EGL-012-2 | 21146 | 2015-09-13 | LN | 2019-06-01 | Colonial Welsh Tap | Jefferson Davis | 1 | 138 |  |  | Construct New Line | LA |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 9773 | 2015-09-13 | 16-EGL-012-3 | 21147 | 2015-09-18 | LN | 2019-06-01 | Jefferson Davis | Carter | 1 | 69 |  |  | Build new line | LA |  |  | Planned |  |  |  | N | N | N | NT
A in MTEP16 | B>A | South | Entergy-LA | 9774 | 2016-03-11 | 16-EGL-012-4 | 21148 | 2016-03-11 | LN | 2019-06-01 | Jefferson Davis | L-13 | 1 | 69 |  |  | Cut L-13 in and out of Jeff Davis 69 kV sub | LA |  |  | Planned |  |  |  | N | N | N | NT
A in MTEP16 | B>A | South | Entergy-LA | 9775 | 2015-09-13 | 16-EGL-012-5 | 21149 | 2015-09-18 | TAP | 2019-06-01 | Derouen |  |  | 69 |  |  | Cut Derouen into Line 11 | LA |  |  | Planned |  |  |  | N | N | N | NT
A in MTEP16 | B>A | South | Entergy-LA | 9776 | 2015-09-13 | 16-EGL-012-6 | 21150 | 2015-09-18 | TAP | 2019-06-01 | Lawtag |  |  | 69 |  |  | Cut Lawtag sub in and out of Line 13. | LA |  |  | Planned |  |  |  | N | N | N | NT
A in MTEP16 | B>A | South | Entergy-LA | 9777 | 2015-09-13 | 16-EGL-012-7 | 21151 | 2015-09-18 | TAP | 2019-06-01 | Welsh |  |  | 69 |  |  | Cut Welsh in and out of line 13A | LA |  |  | Planned |  |  |  | N | N | N | NT
A in MTEP16 | B>A | South | Entergy-LA | 9778 | 2015-09-13 | 16-EGL-012-8 | 21152 | 2015-09-18 | LNrc | 2019-06-01 | Colonial Welsh Tap | Jefferson Davis | 1 | 138 |  |  | Reconductor Line | LA |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 9779 | 2015-09-13 | 16-EGL-013 | 21153 | 2015-09-13 | LNrc | 2018-12-01 | Carter | Serpent | 1 | 69 |  |  | Reconductor Line | LA |  |  | Planned | 19235078 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | South | Entergy-LA | 9780 | 2015-09-13 | 16-EGL-014 | 21154 | 2015-09-13 | LNrc | 2019-12-01 | Compton | Elton | 1 | 69 |  |  | Reconductor Line | LA |  |  | Planned | 12782000 |  |  | N | N | N | NT
A in MTEP16 | B>A | South | Entergy-LA | 9782 | 2015-09-13 | 16-EGL-016 | 21156 | 2016-05-10 | SUBmisc | 2022-06-01 | Lake Arthur |  |  | 69 |  |  | Adjust Normally Open Point | LA |  |  | Planned |  |  |  | N | N | N | NT
A in MTEP16 | B>A | South | Entergy-LA | 9786 | 2015-10-21 | 16-EGL-020 | 21160 | 2015-09-13 | CB | 2017-06-01 | Nelson |  |  | 138 |  |  | Add a breaker on line 274. | LA |  |  | Planned | 1142000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 9787 | 2015-09-13 | 16-EGL-021 | 21161 | 2015-09-13 | TEQ | 2016-06-01 | Air Products | Giegy | 1 | 138 |  |  | Upgrade line | LA |  |  | Planned | 300000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 9788 | 2015-09-13 | 16-EGL-022 | 21162 | 2015-09-13 | CAP | 2018-06-01 | Port Barre |  |  | 69 |  |  | Add Cap Bank | LA |  |  | Planned | 786000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | South | Entergy-LA | 9790 | 2015-12-03 | 16-EGL-026 | 21164 | 2015-12-03 | Dist | 2017-06-01 | Swisco |  |  | 138 |  |  | Construct new distribution Substation | LA |  |  | Planned | 8191000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 9791 | 2015-09-13 | 16-EGL-027 | 21165 | 2015-09-13 | Dist | 2018-06-01 | Thompson Road |  |  | 230 |  |  | New distribution substation | LA |  |  | Planned | 9252000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 9792 | 2015-09-13 | 16-EGL-028 | 21166 | 2015-09-13 | Dist | 2019-06-01 | Lowe Grout Road |  |  | 138 |  |  | New Distribution Substation | LA |  |  | Planned | 6989000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 9794 | 2016-09-14 | 16-EGL-032 | 21168 | 2015-09-13 | TEQ | 2018-06-01 | Repapco | Port Hudson | 1 | 230 |  |  | Upgrade line | LA |  |  | Planned | 101000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 9795 | 2015-09-13 | 16-EGL-033 | 21169 | 2015-09-13 | CAP | 2017-12-01 | Nesser |  |  | 69 |  |  | Add Capacitor bank | LA |  |  | Planned | 1053000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | South | Entergy-LA | 9801 | 2015-09-13 | 16-ELL-004 | 21175 | 2015-09-13 | CAP | 2017-12-01 | North Norco |  |  | 115 |  |  | New Capacitor Bank | LA |  |  | Planned | 1826000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 9805 | 2015-09-13 | 16-ENO-001 | 21179 | 2015-09-13 | LNrc | 2018-12-01 | Patterson | Pontchartrain Park | 1 | 115 |  |  | Upgrade Line | LA |  |  | Planned | 11851000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 9847 | 2015-09-14 | 16-EGL-030-1 | 21224 | 2015-09-14 | CB | 2017-12-01 | Mossville |  |  | 69 |  |  | Replace breaker | LA |  |  | Planned | 700000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | South | Entergy-LA | 9848 | 2015-09-14 | 16-EGL-030-2 | 21225 | 2015-09-14 | CB | 2017-12-01 | Mossville |  |  | 69 |  |  | Replace breaker | LA |  |  | Planned |  | Planning |  | N | N | N | NT
A in MTEP16 | B>A | South | Entergy-LA | 9849 | 2015-09-14 | 16-EGL-030-3 | 21226 | 2015-09-14 | CB | 2017-12-01 | Carlyss |  |  | 69 |  |  | Replace breaker | LA |  |  | Planned |  | Planning |  | N | N | N | NT
A in MTEP16 | B>A | South | Entergy-LA | 10008 | 2016-06-22 | 15-EGL-023 | 21432 | 2016-06-22 | LN | 2020-06-01 | Nelson 230 kV | Menena 230 kV | 1 | 230 |  | 779 | Approximately 5.5 miles of 1272 ACSS single conductor. | LA | 0 | 5.5 | Planned | 15500000 | Planning Preliminary |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 10223 | 2015-11-17 | 16-ELN-011 | 21500 | 2015-10-14 | TAP | 2016-12-31 | HollyRidge |  |  | 115 |  |  | New cut-in for LAGEN Holly Ridge substation | LA |  |  | Planned | 254833 | Facility Study |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 10583 | 2016-01-12 | 16-EGL-037 | 21605 | 2016-01-12 | CB | 2018-06-01 | Coly 230 |  |  | 230 |  |  | Add 230 kV Breaker at Coly | LA |  |  | Planned | 1692865 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 10584 | 2016-01-12 | 16-EGL-038 | 21606 | 2016-01-12 | CB | 2018-06-01 | Tiger 230 |  |  | 230 |  |  | Add breaker at Tiger 230 kV | LA |  |  | Planned | 1692865 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 10585 | 2016-01-12 | 16-EGL-039 | 21607 | 2016-01-12 | CB | 2018-06-01 | Harelson 230 |  |  | 230 |  |  | Add breaker at Harelson 230 kV | LA |  |  | Planned | 1692865 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 10588 | 2016-03-01 | 16-ELL-010 | 21616 | 2016-01-12 | SUB | 2018-12-31 | Fleur 230 |  |  | 230 |  |  | Construct new substation on the Oakville to Alliance 230 kV line. | LA |  |  | Planned | 11100000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 10588 | 2016-03-01 | 16-ELL-010 | 21669 | 2016-03-01 | LNrb | 2018-12-31 | Ninemile | Barataria | 1 | 115 |  |  | Rebuild Line | LA |  |  | Planned | 31605000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 10588 | 2016-03-01 | 16-ELL-010 | 21617 | 2016-01-12 | CAP | 2018-12-31 | Fleur |  |  | 230 |  |  | Add cap bank to support the customer load | LA |  |  | Planned |  | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 10591 | 2016-01-12 | 16-EGL-041 | 21622 | 2016-01-12 | TX | 2016-06-01 | Willow Glen 500 | Willow Glen 138 |  | 500 | 138 |  | Adjust Tap on Auto | LA |  |  | Planned | 15027 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 10623 | 2016-06-22 | 16-EGL-042 | 21626 | 2016-06-22 | SUB | 2018-06-01 | Sadie |  |  | 230 |  |  | Construct New 230 kV Substation on the PPG to Rosebluff line | LA |  |  | Planned | 24814742 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 10624 | 2016-06-22 | 16-EGL-043 | 21627 | 2016-06-22 | SUB | 2019-06-01 | Big Lake |  |  | 230 |  |  | Construct 230 kV substation on the Vincent to Graywood 230 kV line. | LA |  |  | Planned | 28000000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 11423 | 2016-06-22 | 16-EGL-044 | 21769 | 2016-06-29 | SUB | 2017-12-01 | PPG | Rosebluff | 1 | 230 |  |  | Construct a new 230 kV substation on the PPG to Rosebluff 230 kV line. | LA |  |  | Planned | 7290000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 12016 | 2016-09-13 |  | 22087 | 2016-09-13 | TEQ | 2020-01-01 | Minden | Sarepta |  | 115 |  |  | Upgrade line terminal equipment on Minden – Sarepta 115kV to increase the MVA rating to 176MW | LA |  |  | Planned | 1900000 |  |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 12017 | 2016-09-13 |  | 22088 | 2016-09-13 | SUB | 2022-01-01 | NSUB1 |  |  | 230 |  |  | New substation south of Ninemile substation | LA |  |  | Planned | 13687330 |  |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 12017 | 2016-09-13 |  | 22091 | 2016-09-13 | CB | 2022-01-01 | Michoud |  |  | 115 |  |  | Add breaker and reconfigure 115 kV bus at Michoud | LA |  |  | Planned | 1700000 |  |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 12017 | 2016-09-13 |  | 22090 | 2016-09-13 | TEQ | 2022-01-01 | Waterford |  |  | 230 |  |  | Waterford Substation Modifications | LA |  |  | Planned | 2568610 |  |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-LA | 12017 | 2016-09-13 |  | 22089 | 2016-09-13 | LN | 2022-01-01 | Waterford | NSUB1 |  | 230 |  |  | New 230 kV transmission line connecting existing Waterford 230 kV to the new (NSUB1) substation | LA |  | 27 | Planned | 69700811 |  |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-MS | 9822 | 2015-09-14 | 16-EMI-001 | 21197 | 2015-09-14 | SwSta | 2018-12-01 | Harper |  |  | 115 |  |  | New 115 kV switching station on the Gloster - Crosby 115 kV. The Gloster - Centreville line will be rerouted from Gloster to Harper. | MS |  |  | Planned | 5300000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-MS | 9833 | 2015-09-14 | 16-EMI-007 | 21209 | 2015-09-14 | CAP | 2018-06-01 | Greenville North |  |  | 115 |  |  | Install 2nd capacitor bank | MS |  |  | Planned | 1185857 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-MS | 9839 | 2015-09-14 | 16-EMI-005 | 21218 | 2015-09-14 | SUBmisc | 2018-03-01 | Gerald Andrus 230 kV |  |  | 230 |  |  | Reteriminate line node. | MS |  |  | Planned | 310000 |  |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-MS | 9949 | 2015-09-15 |  | 21826 | 2016-08-16 | SwSta |  | International Paper |  |  | 115 |  |  | The Cloverdale DP will be served from the existing Entergy IP to Johns Manville 115kV transmission line via a looped transmission feed into a new switching station to be constructed at the DP site. | MS |  |  | Planned | 900000 |  |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-MS | 9955 | 2015-09-15 |  | 21749 | 2016-05-17 | SwSta |  | Shaw Switching Station |  |  | 115 |  |  | Near EMI’s 115 kV transmission line number 107.5 between South Cleveland and Shaw Switching Station approximately 1.6 miles Northeast of the Shaw Switching Station between structure numbers 109 and 110. | MS |  |  | Planned | 810000 |  |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-MS | 10863 | 2016-03-08 | 16-EMI-013 | 21674 | 2016-09-14 | LNrb | 2017-06-01 | Attala | Conehoma Creek | 1 | 115 |  |  | Upgrade line path rating to minimum 1303 A. | MS | 2 |  | Planned | 1716001 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-MS | 10864 | 2016-09-14 | 16-EMI-014 | 21675 | 2016-09-14 | LNrb | 2017-12-31 | Pelahatchie | Morton | 1 | 115 |  |  | Upgrade Pelahatchie - Morton 115 kV to minimum 1303 A. | MS | 6.07 |  | Planned | 5593224 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-MS | 10865 | 2016-09-14 | 16-EMI-015 | 21676 | 2016-09-14 | LNrb | 2018-06-01 | Morton | Forest Ind | 1 | 115 |  |  | Upgrade to 1303 A. | MS | 9 |  | Planned | 10987197 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-MS | 10943 | 2016-09-14 | 16-EMI-016 | 21692 | 2016-09-14 | SUB | 2019-06-01 | Norrel Road |  |  | 230 |  |  | New 230 kV delivery point | MS |  |  | Planned | 9197916 | Facility Study |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-MS | 11623 | 2016-08-09 | 16-EMI-017 | 21802 | 2016-07-25 | SwSta | 2016-12-31 | Gallman |  |  | 115 |  |  | Install 115 kV breakers at Gallman | MS |  |  | Under Construction | 2988936 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-MS | 11705 | 2016-08-09 | 16-EMI-018 | 21818 | 2016-08-24 | TX | 2017-12-31 | Wynndale |  |  | 115 | 13.8 |  | Install distribution facilities in switching station to serve area/customer load | MS |  |  | Planned | 7789909 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-MS | 11783 | 2016-09-27 | 16-EMI-019 | 21828 | 2016-08-22 | TX | 2020-06-01 | McAdams |  |  | 500 | 230 |  | Replace current autotransformers at McAdams with autotransformers that have at least a 700 MVA rating. | MS |  |  | Planned | 12633990.04 | Facility Study |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-MS | 11783 | 2016-09-27 | 16-EMI-019 | 21829 | 2016-08-18 | TX |  | McAdams |  |  | 500 | 230 |  | Replace current autotransformers at McAdams with autotransformers that have at least a 700 MVA rating. | MS |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-MS | 12015 | 2016-09-13 |  | 22086 | 2016-09-13 | TX | 2020-01-01 | Lakeover |  |  | 500 | 230 |  | Relocate existing 500/230kV transformer from McAdams to Lakeover | MS |  |  | Planned | 6700000 |  |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-TX | 4620 | 2016-05-10 | 12-ETI-006 | 8777 | 2016-01-20 | CAP | 2017-06-01 | Kolbs 230 kV Substation |  |  | 230 |  |  | Add capacitor bank | TX |  |  | Planned | 3000000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-TX | 7930 | 2016-06-22 | 15-ETI-008 | 20186 | 2016-06-22 | Dist | 2019-06-01 | Heights |  |  | 230 | 34.5 | 75 | Construct new substation | TX |  |  | Planned | 14208000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | South | Entergy-TX | 9806 | 2016-09-14 | 16-ETI-001 | 21180 | 2015-09-13 | TX | 2019-06-01 | Bryan 138 | Bryan 69 | 1 | 138 | 69 |  | Replace Auto | TX |  |  | Planned | 8268000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | South | Entergy-TX | 9806 | 2016-09-14 | 16-ETI-001 | 21181 | 2016-05-02 | TX | 2019-06-01 | Bryan 138 | Bryan 69 | 2 | 138 | 69 |  | Replace Auto | TX |  |  | Planned |  |  |  | N | N | N | NT
A in MTEP16 | B>A | South | Entergy-TX | 9807 | 2015-09-13 | 16-ETI-002 | 21182 | 2015-09-13 | SwSta | 2018-12-01 | Pintail |  |  | 138 |  |  | New Switching Station | TX |  |  | Planned | 9524000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-TX | 9808 | 2015-09-14 | 16-ETI-005 | 21183 | 2015-09-14 | CAP | 2018-06-01 | Kirbyville |  |  | 69 |  |  | New Capacitor bank | TX |  |  | Planned | 1000000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | South | Entergy-TX | 9809 | 2015-09-14 | 16-ETI-007 | 21184 | 2015-09-14 | LNrc | 2019-06-01 | Hull | Sour Lake |  | 69 |  |  | Upgrade Line | TX |  |  | Planned | 30759000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | South | Entergy-TX | 9810 | 2015-09-14 | 16-ETI-008 | 21185 | 2015-09-14 | LNrc | 2019-12-01 | Raywood | Daisetta | 1 | 69 |  |  | Upgrade Line | TX |  |  | Planned | 8655000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | South | Entergy-TX | 9812 | 2015-09-14 | 16-ETI-014-1 | 21187 | 2016-05-10 | SwSta | 2019-06-01 | Garden |  |  | 230 |  |  | Build New Substation | TX |  |  | Planned | 65835000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-TX | 9813 | 2015-09-14 | 16-ETI-014-2 | 21188 | 2015-09-18 | LN | 2019-06-01 | Garden | Legend | 1 | 230 |  |  | Build new line | TX |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-TX | 9814 | 2016-05-10 | 16-ETI-014-3 | 21189 | 2015-09-18 | SwSta | 2019-06-01 | Legend |  |  | 230 |  |  | Build New Substation | TX |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-TX | 9817 | 2015-09-14 | 16-ETI-016 | 21192 | 2015-09-14 | CB | 2018-12-01 | Helbig |  |  | 230 |  |  | Add Circuit Breakers | TX |  |  | Planned | 7196000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-TX | 9818 | 2016-09-14 | 16-ETI-017 | 21193 | 2015-12-16 | LNcnv | 2019-06-01 | Stowell | Himex | 1 | 138 |  |  | Convert line to 138 kV | TX |  |  | Planned | 13600000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-TX | 9852 | 2015-09-14 | 16-ETI-018 | 21229 | 2015-09-14 | CB | 2017-06-01 | Grimes |  |  | 345 |  |  | Install new breaker | TX |  |  | Planned | 1142000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-TX | 10823 | 2016-03-01 | 16-ETI-021 | 21668 | 2016-03-01 | SUB | 2017-06-01 | Moscow |  |  | 138 |  |  | Construct New Customer substation | TX |  |  | Planned | 7004002 | Facility Study |  | N | N | N | Y
A in MTEP16 | B>A | South | Entergy-TX | 11363 | 2016-08-09 | 16-ETI-023 | 21763 | 2016-06-08 | TEQ | 2017-06-01 | Hartburg |  |  | 500 |  |  | Re-position line bays Hartburg-Cottonwood 500 kV line 1 & Hartburg-Cypress 500 kV line | TX |  |  | Planned | 2000000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | South | LAFA | 8821 | 2015-08-21 |  | 20746 | 2016-02-01 | LN | 2019-12-31 | Northeast | Peck |  | 69 |  |  | 69kv line connecting Northeast station to Peck station. | LA |  |  | Planned | 4230000 |  |  | N | N | N | NT
A in MTEP16 | B>A | South | SMEPA | 9957 | 2016-04-27 |  | 21378 | 2016-05-17 | SUB | 2017-03-23 | Origis Sub | Origis Gen | 1 | 69 | 26.4 | 60 MVA | The Origis Energy solar plant will tap SMEPA's existing 69kV Line 42 (Sumrall to Rawls Springs) approximately 5.6 miles from Sumrall with a new 69kV switching station and a 69/26.4 kV GSU. | MS |  |  | Planned | 1590000 |  |  | N | N | N | NT
A in MTEP16 | B>A | South | SMEPA | 9957 | 2016-04-27 |  | 21715 | 2016-04-27 | GEN | 2017-03-23 | Origis Gen |  |  | 69 | 26.4 | 52MW | The Origis Energy solar plant will tap SMEPA's existing 69kV Line 42 (Sumrall to Rawls Springs) approximately 5.6 miles from Sumrall with a new 69kV switching station and a 69/26.4 kV GSU. | MS |  |  | Planned |  |  |  | N | N | N | NT
A in MTEP16 | B>A | South | SMEPA | 9969 | 2016-05-08 |  | 21382 | 2016-05-17 | LNrb |  | Sumrall | Rawls Springs | 1 | 69 |  | 71 MVA | Rebuild L42 to final conductor temperature of 100C (71 MVA). | MS |  |  | Planned | 2202498 |  |  | N | N | N | NT
A in MTEP16 | B>A | South | SMEPA | 9969 | 2016-05-08 |  | 21386 | 2016-05-17 | LNrb |  | Sumrall | Columbia | 1 | 69 |  | 71 MVA | Rebuild L43 to a final conductor temperature of 100C (71 MVA). | MS |  |  | Planned | 2579502 |  |  | N | N | N | NT
A in MTEP16 | B>A | West | ATC | 3190 | 2016-02-02 | PR05190 | 5631 | 2015-01-13 | LN | 2016-04-29 | Sunset Point | Winneconne | 1 | 69 |  | 70 | Rebuild line Y-103 from Sunset Point to Winneconne to SN/SE = 200/300 deg F | WI | 10.5 |  | Planned | 3868404 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 7583 | 2016-07-13 | PR04985 | 20011 | 2014-07-07 | LNrb | 2018-12-31 | Lone Rock | Richland | 1 | 69 |  |  | Rebuild Y-78 Lone Rock - Richmond 69 kV | WI | 11.28 |  | Planned | 41848961 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 7583 | 2016-07-13 | PR04985 | 20017 | 2014-07-07 | LNrb | 2018-12-31 | Blue River Tap | Boscobel | 1 | 69 |  | 79 | Rebuild Y-124 Blue River Tap - Boscobel 69 kV | WI | 6.1 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 7583 | 2016-07-13 | PR04985 | 20016 | 2014-07-07 | LNrb | 2018-12-31 | Muscoda | Blue River Tap | 1 | 69 |  | 79 | Rebuild Y-124 Muscoda - Blue River Tap 69 kV | WI | 8.9 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 7583 | 2016-07-13 | PR04985 | 20015 | 2014-07-07 | LNrb | 2015-12-31 | Avoca Tap | Muscoda Ind. Park | 1 | 69 |  | 79 | Rebuild Y-124 Avoca Tap - Muscoda Ind. Park 69 kV | WI | 4.32 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 7583 | 2016-07-13 | PR04985 | 20014 | 2014-07-07 | LNrb | 2018-12-31 | Muscoda Ind. Park | Muscoda | 1 | 69 |  | 79 | Rebuild Y-124 Muscoda Ind. Park - Muscoda 69 kV | WI | 0.33 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 7583 | 2016-07-13 | PR04985 | 20013 | 2014-07-07 | LNrb | 2018-12-31 | Avoca Tap | Avoca | 1 | 69 |  | 79 | Rebuild Y-124 Avoca Tap - Avoca 69 KV | WI | 0.87 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 7583 | 2016-07-13 | PR04985 | 20012 | 2014-07-07 | LNrb | 2018-12-31 | Lone Rock | Avoca Tap | 1 | 69 |  | 79 | Rebuild Y-124 Lone Rock - Avoca Tap 69 kV | WI | 7.93 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 7983 | 2015-09-15 | PR05247 | 20253 | 2016-01-26 | CB | 2017-06-01 | Canal |  |  | 138 | 69 |  | Canal 138-69 kV transformer high/low side breaker additions | WI |  |  | Planned | 5100000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 7985 | 2015-09-18 | PR04578 F3720 WO:69613 | 20255 | 2014-09-11 | RLY | 2017-06-01 | Canal |  |  | 138 |  |  | Installing redundant bus differential protection on the two Canal 138-kV buses. | WI |  |  | Planned | 221116 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 8442 | 2015-10-13 | PR05503 | 20670 | 2014-11-11 | TX | 2016-12-31 | Arnott |  | 1 | 138 | 69 | 60 | Replace the Arnott 138/69 kV Transformer with a 60 MVA Unit | WI |  |  | Planned | 4545000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 8640 | 2015-09-15 |  | 20710 | 2016-01-26 | BUS | 2017-12-31 | City Limits |  | 1 | 138 |  | 332 | Replace bus conductor at City Limits bus 1-2 with 2500 kcmil Lupine | WI |  |  | Planned | 500000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 8640 | 2015-09-15 |  | 20711 | 2015-01-08 | BUS | 2017-12-31 | City Limits |  | 2 | 138 |  | 484 | Replace bus conductor at City Limits bus 2-3 with 2500 kcmil Lupine | WI |  |  | Planned |  | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 8841 | 2015-03-16 | PR04988 | 20752 | 2016-01-26 | LNrb | 2019-12-01 | Finger Rd | Luxemburg | 1 | 69 |  | 39 | Rebuild J-10 Finger Road 69 - Luxemburg 69 with T2 4/0 ACSR | WI | 12.49 |  | Planned | 74000000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 8841 | 2015-03-16 | PR04988 | 20758 | 2015-03-16 | LNrb | 2019-12-01 | Canal | Algoma | 1 | 69 |  | 39 | Rebuild J-10 Canal 69 - Algoma 69 with 4/0 T2 ACSR. | WI | 18.73 |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 8841 | 2015-03-16 | PR04988 | 20757 | 2015-03-16 | LNrb | 2019-12-01 | Algoma | Algoma | 1 | 69 |  | 39 | Rebuild J-10 Algoma 69 - Algoma S Tap 69 with 4/0 T2 ACSR. | WI | 1.74 |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 8841 | 2015-03-16 | PR04988 | 20756 | 2015-03-16 | LNrb | 2019-12-01 | Algoma | Barnett | 1 | 69 |  | 46 | Rebuild J-10 Algoma S Tap 69 - Barnett 69 with 4/0 T2 ACSR. | WI | 7.01 |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 8841 | 2015-03-16 | PR04988 | 20755 | 2015-03-16 | LNrb | 2019-12-01 | Barnett | Beardsley | 1 | 69 |  | 46 | Rebuild J-10 Barnett 69 - Beardsley 69 with 4/0 T2 ACSR. | WI | 3.32 |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 8841 | 2015-03-16 | PR04988 | 20754 | 2015-03-16 | LNrb | 2019-12-01 | Booster | Beardsley | 1 | 69 |  | 46 | Rebuild J-10 Booster 69 - Beardsley 69 with 4/0 T2 ACSR. | WI | 5.51 |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 8841 | 2015-03-16 | PR04988 | 20753 | 2015-03-16 | LNrb | 2019-12-01 | Luxemburg | Booster | 1 | 69 |  | 46 | Rebuild J-10 Luxemburg 69 - Booster 69 with 4/0 T2 ACSR. | WI | 6.23 |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 9423 | 2016-08-17 | PR04968, F3633 & F363 WO: 069403-55, | 20899 | 2015-07-28 | LNrb | 2019-12-01 | Plover | Whiting Avenue | 1 | 115 |  | 205 | Rebuild line B-106 (Plover-Okray-Whiting 115) using existing conductor 795 ACSR. | WI | 5.8 |  | Planned | 6217603 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 9896 | 2015-09-15 |  | 21307 | 2016-01-26 | SUB | 2015-12-31 | Lyndon |  |  | 138 |  |  | Install 2 line breakers to sectionalize. | WI |  |  | M5_In Service | 3100000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 9911 | 2015-09-15 | PR#5981 | 21322 | 2016-01-26 | SUB | 2016-04-22 | Maes |  |  | 138 |  |  | Maes substation: Install 2 line breakers to sectionalize | WI |  |  | Planned | 1800000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 9917 | 2016-06-10 | PR04727, PR04726, F3576, WO064898 | 21331 | 2016-01-26 | SUB | 2016-12-31 | Bloomington |  |  | 69 |  |  | Install SCADA controlled breakers to sectionalize | WI |  |  | Planned | 1600000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 9918 | 2015-09-15 | PR#6143 | 21332 | 2016-01-26 | SUB | 2016-06-01 | Red Maple |  |  | 138 |  |  | Install a bus tie breaker. | WI |  |  | Planned | 1200000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 9921 | 2015-09-15 | PR#6142 | 21334 | 2016-01-26 | SUB | 2017-12-31 | Birchwood |  |  | 138 |  |  | Install a bus tie breaker. | WI |  |  | Planned | 700000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 9923 | 2015-09-15 |  | 21335 | 2016-01-26 | SUB | 2017-12-01 | Mukwonago |  |  | 138 |  |  | Install line breaker on line 67K61. | WI |  |  | Planned | 600000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 9934 | 2016-07-13 | PR07285 | 21349 | 2016-02-23 | LNup | 2018-06-30 | Oak Creek | Hayes | 1 | 138 |  | 310 | Oak Creek - Hayes 138-kV line 811 upgrade and reconfiguration. | WI |  |  | Planned | 21000000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 9938 | 2015-09-15 | PR04754 | 21360 | 2016-01-26 | TX | 2016-12-01 | Sunset Point |  |  | 138 |  |  | Replace Sunset Point 138-69 kV Transformer | WI |  |  | Planned | 6000000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 9944 | 2015-09-15 |  | 21364 | 2016-01-26 | TX | 2017-12-31 | Erdman |  |  | 138 |  |  | Replace Erdman T31 Transformer. | WI |  |  | Planned | 6000000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 9954 | 2015-12-03 | PR07375 | 21369 | 2016-01-26 | TX | 2018-12-01 | Lost Dauphin |  |  | 138 |  |  | Replace Lost Dauphin T1 Transformer. | WI |  |  | Planned | 6700000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 9958 | 2015-09-15 |  | 21370 | 2015-09-15 | TX | 2017-12-31 | East Krok |  |  | 138 |  |  | Replace East Krok Transformer. | WI |  |  | Planned | 2500000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 9961 | 2015-09-15 |  | 21372 | 2016-01-26 | TX | 2018-12-31 | Nelson Dewey |  |  | 138 |  |  | Replace Nelson Dewey T31/T32 Transformers. | WI |  |  | Planned | 6000000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 9977 | 2016-07-13 |  | 21394 | 2016-09-14 | LNrb | 2020-06-30 | Goodman | Caldron Falls | 1 | 69 |  |  | Rebuild 69KV Line J-88 Goodman - Caldron Falls Substation. | WI |  |  | Planned | 35000000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 9986 | 2016-02-12 | PR07410 | 21408 | 2016-01-26 | LNrb | 2021-12-31 | Port Washington | Saukville | 1 | 138 |  |  | Rebuild 138KV Line 762 Port Washington - Saukville Substation. | WI |  |  | Planned | 15000000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 10403 | 2016-05-04 | PR07285,F4849, WO 602023 | 21577 | 2016-04-29 | LNup | 2017-04-21 | Kegonsa | Sun Prairie | 1 | 69 |  |  | Re-rate Y -81 69kV line between Kegonsa - Sun Prairie. | WI |  |  | Planned | 5000000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 10404 | 2016-05-04 | PR07333,F4812, WO601919 | 21578 | 2016-05-04 | LNup | 2017-03-17 | 9 Mile | Detour | 1 | 69 |  |  | Re-rate Approximately 56.87 miles (6950) 69kV Line between 9 Mile - Detour substations. | MI | 56.87 |  | Planned | 7000000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 10484 | 2015-12-16 | PR07373 | 21588 | 2015-12-16 | LN | 2019-06-01 | HWY V | Eaton | 1 | 138 |  | 690 | Construct a new ATC 138KV loop through at Eaton Substation. | WI | 6.54 |  | Planned | 2500000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 10484 | 2015-12-16 | PR07373 | 21590 | 2015-12-16 | SUB | 2019-06-01 | Eaton |  |  | 138 | 24.9 |  | New Eaton 138 KV substation | WI |  |  | Planned |  |  |  | N | N | N | NT
A in MTEP16 | B>A | West | ATC | 10484 | 2015-12-16 | PR07373 | 21589 | 2015-12-16 | LN | 2019-06-01 | Eaton | East Krok | 1 | 138 |  |  | Construct a new ATC 138KV loop through at Eaton Substation. | WI | 14.92 |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 10485 | 2015-12-16 | PR007372 | 21591 | 2015-12-16 | LN | 2022-06-01 | HWY V | BAY RIDGE | 1 | 138 |  | 526 | Construct a new ATC 138KV loop through at Bay Ridge Substation. | WI | 1.06 |  | Planned | 2000000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 10485 | 2015-12-16 | PR007372 | 21593 | 2015-12-16 | SUB | 2022-06-01 | BAYRIDGE |  |  | 138 | 24.9 |  | Construct a new ATC 138KV loop through at Bay Ridge Substation. | WI |  |  | Planned |  |  |  | N | N | N | NT
A in MTEP16 | B>A | West | ATC | 10485 | 2015-12-16 | PR007372 | 21592 | 2015-12-16 | LN | 2022-06-01 | BAY RIDGE | ONTARIO | 1 | 138 |  |  | Construct a new ATC 138KV loop through at Bay Ridge Substation. | WI | 1.61 |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 10543 | 2016-01-05 | PR07390 | 21603 | 2016-05-25 | TAP | 2017-01-01 | Escanaba2 ESC North Tap | West Side Tap | 1 | 69 |  | 390 | Construct T-D Escanaba North Substation (GOAB) | MI |  | 0.99 | Planned | 1000000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 10543 | 2016-01-05 | PR07390 | 21604 | 2016-05-25 | TAP | 2017-01-01 | Escanaba2 | Northshore Tap | 1 | 69 |  | 390 | Construct T-D Escanaba North Substation (GOAB) | MI |  | 0.3 | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 10563 | 2016-01-12 | PR07397 | 21618 | 2016-01-12 | SUB | 2018-06-01 | Oakview |  |  | 138 |  | 2000 | Construct T-D Escanaba North Substation | WI |  |  | Planned | 4900000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 10589 | 2016-01-12 | PR07388 | 21619 | 2016-01-12 | LNup | 2017-06-09 | Whitcomb | Tigerton Tap | 1 | 69 |  | 335 | Rerate Whitcomb - Tigerton Tap 69kV | WI |  |  | Planned | 1400000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 10603 | 2016-01-13 | PR07299 | 21623 | 2016-01-13 | LN | 2019-12-31 | Wild Rose | Springwater | 1 | 69 |  | 660 | Construct T - D Springwater Substation. | WI |  | 1.25 | Planned | 7100000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 10643 | 2016-02-12 | PR07400 | 21628 | 2016-02-29 | BUS | 2018-01-01 | St. Martins |  |  | 138 |  | 2000 | Bus expansion. | WI |  |  | Planned | 2300000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 10643 | 2016-02-12 | PR07400 | 21630 | 2016-02-29 | LNrb | 2017-01-01 | St. Martins |  |  | 138 |  | 1030 | Relocate line 3025. | WI |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 10643 | 2016-02-12 | PR07400 | 21629 | 2016-02-29 | CB | 2018-01-01 | St. Martins |  |  | 138 |  | 2000 | Install a bus-tie circuit breaker. | WI |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 10683 | 2016-02-02 | PR07394 | 21643 | 2016-02-02 | LNup | 2017-06-09 | Lone Rock | Richland Center | 1 | 69 |  |  | Uprate Y-78 Lone Rock - Richland Center. | WI |  |  | Planned | 1700000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 10684 | 2016-02-02 | PR07396 | 21644 | 2016-03-09 | TX | 2017-06-01 | Ellinwood |  |  | 138 | 24.9 |  | T-D distribution transformer addition at Ellinwood Substation. | WI |  |  | Planned | 100000 |  |  | N | N | N | NT
A in MTEP16 | B>A | West | ATC | 10685 | 2016-02-02 | PR07393 | 21645 | 2016-02-02 | SUB | 2017-06-01 | Tomahawk |  |  | 115 |  | 2000 | Install Tomahawk Substation Bus-Tie Breaker. | WI |  |  | Planned | 700000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 10686 | 2016-02-02 | PR07392 | 21646 | 2016-02-02 | BUS | 2018-06-01 | Roosevelt Road |  |  | 138 |  | 1391 | ATC bus expansion and T-D distribution transformer addition. | WI |  |  | Planned | 200000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 10703 | 2016-02-08 | PR07050 | 21648 | 2016-02-08 | CB | 2016-11-15 | Jefferson SS |  |  | 138 |  |  | Replace Jefferson SS 138 kV Circuit Breakers. | WI |  |  | Planned | 2200000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 10703 | 2016-02-08 | PR07050 | 21649 | 2016-02-08 | CAP | 2016-11-15 | Jefferson SS |  |  | 138 |  |  | Replace Jefferson SS 138 kV Capacitor Bank. | WI |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 11223 | 2016-07-13 | PR07437, F4934, WO602202 | 21745 | 2016-05-12 | TAP | 2017-06-01 | Y-32 Tap | Townhall | 1 | 69 |  | 40 | New T-D Townhall Substation - GOAB on Y-32 and approx. 2 miles of new 69 kV ROW. | WI | 2 |  | Planned | 3900000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | ATC | 11224 | 2016-07-13 | PR07471 | 21746 | 2016-05-12 | CB | 2017-11-01 | White Lake |  |  | 138 |  | 2000 | White Lake Line Breaker. | WI |  |  | Planned | 908000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | CFU-PMEU | 11383 | 2016-06-15 | Pella RRHD | 21764 | 2016-06-15 | CAP | 2017-08-01 | Pella West sub | Pella Clark St. sub | na | 69 |  |  | Move the capacitor from the Pella West Sub to Pella Clark St. Sub to make room for J329 interconnection at Pella West. | IA |  |  | Under Construction | 169250 | GIA |  | N | N | N | NT
A in MTEP16 | B>A | West | CFU-PMEU | 11383 | 2016-06-15 | Pella RRHD | 21767 | 2016-06-15 | RLY | 2017-08-01 | Pella West Substation |  |  | 69 |  |  | Line relaying for G329 including relaying changes for capacitor bank move to Pella clark st sub. | IA |  |  | Planned | 74400 | GIA |  | N | N | N | NT
A in MTEP16 | B>A | West | CFU-PMEU | 11383 | 2016-06-15 | Pella RRHD | 21766 | 2016-06-15 | TEQ | 2017-08-01 | Pella West Substation |  |  | 69 |  |  | Terminal for J329 69kV line into the Pella West substation. | IA |  |  | Under Construction | 800050 | GIA |  | N | N | N | NT
A in MTEP16 | B>A | West | GRE | 4378 | 2016-08-11 | 202970 | 8387 | 2013-09-13 | CB | 2020-09-01 | Long Lake |  |  | 115 |  |  | Circuit breakers for new lines related to Hubbard-Potato Lake line | MN |  |  | Planned | 835000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | GRE | 4378 | 2016-08-11 | 202970 | 20790 | 2016-08-11 | LN | 2017-04-01 | Blueberry | Red Eye |  | 115 |  |  | Construct a new 115 kV transmission line from the Blueberry substation to Koch Pipeline's new pumping substation (approximately 8 miles). | MN |  | 8 | Planned | 13655748.68 | Planning Preliminary |  | N | N | N | Y
A in MTEP16 | B>A | West | GRE | 4378 | 2016-08-11 | 202970 | 8891 | 2016-08-11 | SUB | 2017-04-01 | Blueberry |  |  | 115 | 34.5 |  | New Blueberry 115/34.5 kV substation using Hubbard transformer | MN |  |  | Planned | 2400000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | GRE | 4378 | 2016-08-11 | 202970 | 8890 | 2016-08-11 | CB | 2017-04-01 | Hubbard |  |  | 115 |  |  | Circuit breakers for new lines to Cat River and Potato Lake | MN |  |  | Planned | 1670000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | GRE | 7884 | 2015-03-30 | 203079 | 20114 | 2016-04-14 | SUB | 2018-12-10 | Riverview |  |  | 345 | 115 | 448 | Construct the new Riverview 345/115/69 kV substation directly off the CapX 345 kV line between the Melrose East and Millwood 69 kV substations. The transformers will be a 448 MVA, 345/115 kV transformer and a 70 MVA 115/69 MVA transformer. This substation will initially have two 345 line terminating breakers, a single 345 kV breaker on the high side of the transformer, two 69 kV line termination breakers in addition to a low side 69 kV breaker. The substation should be designed for future development and be laid out for nine 345 breaker (3 rows of 345 kV breakers in a breaker and half scheme), six 115 kV (2 rows of 115 kV breakers in a breaker and half scheme), and four 69 kV breakers in a straight bus configuration. | MN |  |  | Planned | 13425055.97 | Planning Preliminary |  | N | N | N | Y
A in MTEP16 | B>A | West | GRE | 7884 | 2015-03-30 | 203079 | 20129 | 2016-04-14 | LNrb | 2018-12-10 | Melrose | Riverview | 1 | 69 | 69 |  | Rebuild E Melrose to Millwood Tap 4.6 mile line. | MN | 4.6 |  | Planned | 2042956.93 | Planning Preliminary |  | N | N | N | NT
A in MTEP16 | B>A | West | GRE | 7884 | 2015-03-30 | 203079 | 20128 | 2016-04-14 | SUB | 2018-12-10 | Riverview |  |  | 115 | 69 | 70 | Construct the new Millwood (Riverview Road ) 345/115/69 kV substation directly off the CapX 345 kV line between the Melrose East and Millwood 69 kV substations. The transformers will be a 448 MVA, 345/115 kV transformer and a 70 MVA 115/69 MVA transformer. This substation will initially have two 345 line terminating breakers, a single 345 kV breaker on the high side of the transformer, two 69 kV line termination breakers in addition to a low side 69 kV breaker. The substation should be designed for future development and be laid out for nine 345 breaker (3 rows of 345 kV breakers in a breaker and half scheme), six 115 kV (2 rows of 115 kV breakers in a breaker and half scheme), and four 69 kV breakers in a straight bus configuration.. Please see the online diagram included in this PDR. This project will also be coordinated with Xcel Energy for rebuilding the existing Melrose-Millwood 69 kV line with 795 ACSS and 115 kV design. Desired in-service date is spring 2017. | MN |  |  | Planned | 4583671.1 | Planning Preliminary |  | N | N | N | Y
A in MTEP16 | B>A | West | GRE | 7896 | 2015-03-30 | 202987 | 20133 | 2016-09-15 | LN | 2017-08-31 | Fish Trap Pumping Station |  | 1 | 115 | 115 |  | Construct a new 115 kV transmission line from the Wing River to Long Prairie ( #47 Line) 115 kV transmission line to Koch Pipeline?s new Fish Trap pumping substation (approximately 20 miles). | MN |  | 20 | Planned | 10855000.26 | Planning Preliminary |  | N | N | N | Y
A in MTEP16 | B>A | West | GRE | 10423 | 2015-12-01 | 20418 | 21579 | 2015-12-01 | Dist | 2017-03-30 | Randolph |  |  | 115 |  |  | New distribution substation | MN |  | 0.25 | Planned | 525000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | GRE | 10424 | 2015-12-01 | 20559 | 21580 | 2015-12-01 | Dist | 2017-10-31 | Savage |  |  | 115 |  |  | New distribution substation | MN |  | 0.5 | Planned | 1000000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | GRE | 11463 | 2016-07-25 | 204473 | 21773 | 2016-06-29 | TEQ | 2016-11-01 | Leland Olds | Stanton | 1 | 230 |  |  | Replace 31RB3 jumpers to increase line rating above 313 MVA. | ND |  |  | Planned | 33033 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | GRE, MP | 4378 | 2016-08-11 | 202970 | 8383 | 2016-08-11 | LN | 2017-04-01 | Hubbard | Blueberry | 1 | 115 |  |  | Build new 115 kV line from Hubbard to new Blueberry substation | MN |  | 15 | Planned | 10800000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9664 | 2015-09-09 | Guthrie-Panora 34 to 69 Conv | 21050 | 2016-05-25 | SwSta | 2017-12-31 | White Pole Road | Switch Station |  | 69 | 69 |  | Construct a new 3 terminal switch station named White Pole Road. | IA |  |  | Planned | 2341176 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9664 | 2015-09-09 | Guthrie-Panora 34 to 69 Conv | 21071 | 2015-09-11 | LNcnv | 2017-12-31 | Panorama REC Tap | Panorama REC | 1 | 69 | 69 |  | Convert Panorama REC Tap - Panorama REC to 69 kV (existing 34.5 kV line built to 69 kV construction) | IA | 0.8 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9664 | 2015-09-09 | Guthrie-Panora 34 to 69 Conv | 21070 | 2015-09-11 | LNcnv | 2017-12-31 | Panora Muni Tap | Panorama REC Tap | 1 | 69 | 69 |  | Convert Panora Muni Tap - Panorama REC Tap to 69 kV (existing 34.5 kV line built to 69 kV construction) | IA | 1.57 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9664 | 2015-09-09 | Guthrie-Panora 34 to 69 Conv | 21069 | 2015-09-11 | LNcnv | 2017-12-31 | Panora Muni Tap | Panora Muni | 1 | 69 | 69 |  | Convert Panora Muni Tap - Panora Muni to 69 kV (existing 34.5 kV line built to 69 kV construction) | IA | 0.61 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9664 | 2015-09-09 | Guthrie-Panora 34 to 69 Conv | 21068 | 2015-09-11 | LNcnv | 2017-12-31 | Panora Switch Station | Panora Muni Tap | 1 | 69 | 69 |  | Convert Panora Switch Station - Panora Muni Tap to 69 kV (existing 34.5 kV line built to 69 kV construction) | IA | 5.72 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9664 | 2015-09-09 | Guthrie-Panora 34 to 69 Conv | 21067 | 2015-09-11 | LNcnv | 2017-12-31 | Panora Switch Station | Panora REC | 1 | 69 | 69 |  | Convert Panora Switch Station - Panora REC to 69 kV (existing 34.5 kV line built to 69 kV construction) | IA | 0.7 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9664 | 2015-09-09 | Guthrie-Panora 34 to 69 Conv | 21066 | 2015-09-11 | LNcnv | 2017-12-31 | Panora Switch Station | Guthrie | 1 | 69 | 69 |  | Convert Panora Switch Station - Guthrie to 69 kV (existing 34.5 kV line built to 69 kV construction) | IA | 6 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9664 | 2015-09-09 | Guthrie-Panora 34 to 69 Conv | 21065 | 2015-09-11 | SwSta | 2017-12-31 | Paonra Switch Station | Switch Station |  | 69 | 69 |  | CIPCO will construct a new Panora 69 kV 3 terminal switch station | IA |  |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9664 | 2015-09-09 | Guthrie-Panora 34 to 69 Conv | 21064 | 2015-09-11 | LNcnv | 2017-12-31 | Redfield Tap | Panora Switch Station | 1 | 69 | 69 |  | Convert Redfield Tap - Panora Switch Station to 69 kV | IA | 10 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9664 | 2015-09-09 | Guthrie-Panora 34 to 69 Conv | 21063 | 2015-09-11 | LNcnv | 2017-12-31 | Redfield Tap | Redfield | 1 | 69 | 69 |  | Convert Redfield Tap - Redfield to 69 kV (existing 34.5 kV line built to 69 kV construction) | IA | 0.7 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9664 | 2015-09-09 | Guthrie-Panora 34 to 69 Conv | 21062 | 2015-09-11 | LNcnv | 2017-12-31 | Diamondhead REC Tap | Redfield Tap | 1 | 69 | 69 |  | Convert Diamondhead REC Tap - Redfield Tap to 69 kV (existing 34.5 kV line built to 69 kV construction) | IA | 1.85 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9664 | 2015-09-09 | Guthrie-Panora 34 to 69 Conv | 21061 | 2015-09-11 | LNcnv | 2017-12-31 | Diamondhead REC Tap | Diamondhead REC | 1 | 69 | 69 |  | Convert Diamondhead REC Tap - Diamondhead REC to 69 kV (existing 34.5 kV line built to 69 kV construction | IA | 1.75 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9664 | 2015-09-09 | Guthrie-Panora 34 to 69 Conv | 21060 | 2015-09-11 | LNcnv | 2017-12-31 | Stuart Muni Tap | Diamondhead REC Tap | 1 | 69 | 69 |  | Convert Stuart Muni Tap - Diamondhead REC Tap to 69 kV (existing 34.5 kV line built to 69 kV construction) | IA | 8 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9664 | 2015-09-09 | Guthrie-Panora 34 to 69 Conv | 21059 | 2015-11-13 | LNcnv | 2017-12-31 | Stuart Muni Tap | Stuart Muni | 1 | 69 | 69 |  | Convert Stuart Muni Tap - Stuart Muni to 69 kV (existing 34.5 kV line built to 69 kV construction) | IA | 0.8 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9664 | 2015-09-09 | Guthrie-Panora 34 to 69 Conv | 21058 | 2015-09-11 | LNcnv | 2017-12-31 | Stuart REC Tap | Stuart Muni Tap | 1 | 69 | 69 |  | Convert Stuart REC Tap - Stuart Muni Tap to 69 kV (existing 34.5 kV line built to 69 kV construction) | IA |  |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9664 | 2015-09-09 | Guthrie-Panora 34 to 69 Conv | 21057 | 2015-09-11 | LNcnv | 2017-12-31 | Stuart Muni South Tap | Stuart REC | 1 | 69 | 69 |  | Convert Stuart Muni South Tap - Stuart REC to 69 kV (existing 34.5 kV line built to 69 kV construction) | IA |  |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9664 | 2015-09-09 | Guthrie-Panora 34 to 69 Conv | 21056 | 2015-09-11 | LNcnv | 2017-12-31 | Stuart Muni South Tap | Stuart Muni South | 1 | 69 | 69 |  | Convert Stuart Muni South Tap - Stuart Muni South Sub to 69 kV (existing 34.5 kV line built to 69 kV construction | IA |  |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9664 | 2015-09-09 | Guthrie-Panora 34 to 69 Conv | 21055 | 2015-09-11 | LNcnv | 2017-12-31 | Stuart REC Tap | Stuart Muni South Tap | 1 | 69 | 69 |  | Convert Stuart REC Tap - Stuart Muni South Tap to 69 kV (existing 34.5 kV line built to 69 kV construction) | IA |  |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9664 | 2015-09-09 | Guthrie-Panora 34 to 69 Conv | 21054 | 2016-05-25 | LNcnv | 2017-12-31 | Hawkeye REC | Stuart REC Tap | 1 | 69 | 69 |  | Convert Hawkeye REC - Stuart REC Tap to 69 kV (existing 34.5 kV line built to 69 kV construction) Add load break capability and SCADA controlled motor operators at Hawkeye REC. | IA |  |  | Planned | 264000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9664 | 2015-09-09 | Guthrie-Panora 34 to 69 Conv | 21053 | 2015-09-11 | LNcnv | 2017-12-31 | White Pole Raod | Hawkeye REC | 1 | 69 | 69 |  | Convert White Pole Rd - Hawkeye REC to 69 kV (existing 34.5 kV line built to 69 kV construction) | IA |  |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9664 | 2015-09-09 | Guthrie-Panora 34 to 69 Conv | 21052 | 2016-05-25 | LNcnv | 2017-12-31 | Guthrie | White Pole Road | 1 | 69 | 69 |  | Convert Guthrie - White Pole Rd to 69 kV (existing 34.5 kV line built to 69 kV construction) | IA |  |  | Planned | 240000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9664 | 2015-09-09 | Guthrie-Panora 34 to 69 Conv | 21051 | 2015-09-11 | TAP | 2017-12-31 | White Pole Road | Switch Station |  | 69 | 69 |  | 69 kV line taps for the new White Pole Road station | IA |  |  | Planned | 540000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9665 | 2015-09-09 | PCI-Oak Hill 34 to 69 Conv | 21037 | 2015-09-10 | SUB | 2017-12-31 | PCI | Substation |  | 69 | 69 |  | Convert PCI-Oak Hill to 69 kV operation | IA |  |  | Planned | 12000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9665 | 2015-09-09 | PCI-Oak Hill 34 to 69 Conv | 21039 | 2016-05-25 | LN | 2017-12-31 | PCI | Oak Hill | 1 | 69 | 69 |  | Convert to 69 kV operation (already built for 69 kV). | IA | 4.5 |  | Planned | 21600 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9665 | 2015-09-09 | PCI-Oak Hill 34 to 69 Conv | 21038 | 2015-09-10 | Dist | 2017-12-31 | Oak Hill | Substation |  | 69 | 69 |  | Convert to 69 kV operation | IA |  |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9666 | 2015-09-09 | Emerald Isle-Beverly 34 to 69 kV Conv | 21027 | 2015-09-10 | LNcnv | 2018-12-31 | Emerald Isle | Harrison | 1 | 69 | 69 | 77 MVA | Convert Emerald Isle-Harrison line to 69 kV operation (already built for 69 kV) | IA | 3.5 |  | Planned | 240000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9666 | 2015-09-09 | Emerald Isle-Beverly 34 to 69 kV Conv | 21034 | 2015-09-10 | SUB | 2018-12-31 | Beverly | Substation |  | 69 | 69 |  | Add two new 69 kV line terminals and a 69 kV bus tie breaker at the Beverly substation. | IA |  |  | Planned | 1461539 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9666 | 2015-09-09 | Emerald Isle-Beverly 34 to 69 kV Conv | 21033 | 2015-09-10 | LNrb | 2018-12-31 | PCI | Beverly | 1 | 69 | 69 | 103 MVA | Rebuild a portion of the PCI-Beverly line to double circuit 69 kV. | IA | 1.2 |  | Planned | 1466754 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9666 | 2015-09-09 | Emerald Isle-Beverly 34 to 69 kV Conv | 21032 | 2015-09-10 | LNcnv | 2018-12-31 | Taylor | Beverly | 1 | 69 | 69 | 77 MVA | Convert the Beverly-Taylor line to 69kV operation | IA | 5.15 |  | Planned | 1502754 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9666 | 2015-09-09 | Emerald Isle-Beverly 34 to 69 kV Conv | 21030 | 2015-09-10 | Dist | 2018-12-31 | Taylor | Substation |  | 69 | 69 |  | New Taylor 69kV/distribution substation | IA |  |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9666 | 2015-09-09 | Emerald Isle-Beverly 34 to 69 kV Conv | 21029 | 2015-09-10 | LNcnv | 2018-12-31 | Harrison | Taylor | 1 | 69 | 69 |  | Convert Harrison-Taylor line to 69 kv operation (already built for 69 kV) | IA |  |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9666 | 2015-09-09 | Emerald Isle-Beverly 34 to 69 kV Conv | 21028 | 2015-09-10 | SUB | 2018-12-31 | Emerald Isle | Substation |  | 69 | 69 |  | Add 69 kV terminal at Emerald Isle | IA |  |  | Planned | 443671 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9667 | 2015-09-09 | Wapello Reliability Rebuild | 20989 | 2016-01-29 | BUS | 2017-12-31 | Wapello | Substation |  | 161 | 69 | 558 MVA | Rebuild the 161kV to breaker and 1/2 design and upgrade 69kV ring bus. | IA |  |  | Planned | 9094680 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9667 | 2015-09-09 | Wapello Reliability Rebuild | 21638 | 2016-01-29 | LNup | 2017-12-31 | Jefferson | Wapello Co | 1 | 161 | 161 |  | Line work for sub reconfiguration. | IA |  |  | Planned | 226200 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9667 | 2015-09-09 | Wapello Reliability Rebuild | 21637 | 2016-01-29 | LNup | 2017-12-31 | OGS | Wapello Co | 2 | 161 | 161 |  | Line work for sub reconfiguration | IA |  |  | Planned | 118200 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9667 | 2015-09-09 | Wapello Reliability Rebuild | 21636 | 2016-01-29 | LNup | 2017-12-31 | Appanoose County | Wapello Co | 1 | 161 | 161 |  | Line work for sub reconfiguration. | IA |  |  | Planned | 118200 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9667 | 2015-09-09 | Wapello Reliability Rebuild | 21635 | 2016-01-29 | LNup | 2017-12-31 | OGS | Wapello Co | 1 | 161 | 161 |  | Line work for sub reconfiguration. | IA |  |  | Planned | 550200 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9667 | 2015-09-09 | Wapello Reliability Rebuild | 21634 | 2016-01-29 | SUB | 2017-12-31 | OGS | Substation |  | 161 | 161 |  | Upgrades required at OGS for the Wapello Co upgrades | IA |  |  | Planned | 7985 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9668 | 2015-09-11 | CR-North Liberty-Hills | 21079 | 2016-01-29 | SUB | 2019-12-31 | New Hills area | Substation |  | 345 | 69 |  | Construct a new substation in the Hills area. | IA |  |  | Planned | 19029110 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9668 | 2015-09-11 | CR-North Liberty-Hills | 21092 | 2015-09-11 | LN | 2025-12-31 | Conroy | Homestead | 1 | 69 | 69 |  | New CIPCO owned Conroy-Homestead 69 kV line | IA |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9668 | 2015-09-11 | CR-North Liberty-Hills | 21091 | 2016-01-29 | SwSta | 2025-12-31 | Conroy | Switch Station |  | 69 | 69 |  | New Conroy 69 kV switching station | IA |  |  | Planned | 3979450 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9668 | 2015-09-11 | CR-North Liberty-Hills | 21090 | 2016-01-29 | SwSta | 2025-12-31 | Homestead | Switch Station |  | 69 | 69 |  | New Homestead 69 kV switching station | IA |  |  | Planned | 3979450 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9668 | 2015-09-11 | CR-North Liberty-Hills | 21089 | 2016-01-29 | SUB | 2022-12-31 | Fairfax | Substation |  | 161 | 161 |  | Add a 161 kV terminal for the new North Liberty-Fairfax 161 kV line | IA |  |  | Planned | 904828 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9668 | 2015-09-11 | CR-North Liberty-Hills | 21088 | 2016-01-29 | LN | 2022-12-31 | North Liberty | Tharp | 1 | 69 | 69 |  | Re-build existing North Liberty REC - Tharp line (double circuit with new North Liberty - Fairfax 161 kV) | IA |  |  | Planned | 11080800 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9668 | 2015-09-11 | CR-North Liberty-Hills | 21087 | 2016-01-29 | LN | 2022-12-31 | North Liberty | Fairfax | 1 | 161 | 161 | 446 MVA | New 161 kV line from North Liberty-Fairfax (double circuit with new North Liberty-Tharp 69 kV line). | IA |  |  | Planned | 27788400 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9668 | 2015-09-11 | CR-North Liberty-Hills | 21086 | 2015-09-11 | TX | 2019-12-31 | New North Liberty | Transformer | 1 | 161 | 69 | 200 MVA | New CIPCO owned 161/69 kV 200 MVA transformer. | IA |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9668 | 2015-09-11 | CR-North Liberty-Hills | 21085 | 2015-09-11 | SUB | 2019-12-31 | New North Liberty | Substation |  | 161 | 69 |  | New CIPCO owned 161/69 kV North Liberty sub | IA |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9668 | 2015-09-11 | CR-North Liberty-Hills | 21084 | 2016-01-29 | LN | 2019-12-31 | New Hills area | Clear Creek | 1 | 69 | 69 |  | New ITC owned 69 kv line double circuit with the new Hills area to North Liberty 161 kv line owned by CIPCO. | IA |  |  | Planned | 8678400 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9668 | 2015-09-11 | CR-North Liberty-Hills | 21083 | 2015-09-11 | LN | 2019-12-31 | New Hills area | North Liberty | 1 | 161 | 161 |  | CIPCO will own a new 161 kV line from the new Hills area sub to the new North Liberty sub. The new line will be double circuit with a new 69 kV line owned by ITC. | IA |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9668 | 2015-09-11 | CR-North Liberty-Hills | 21082 | 2015-09-11 | SwSta | 2019-12-31 | ClearCreek | Switch Station |  | 69 | 69 |  | CIPCO will construct a new switch station | IA |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9668 | 2015-09-11 | CR-North Liberty-Hills | 21081 | 2015-09-11 | TX | 2019-12-31 | New Hills area | Transformer | 1 | 161 | 69 | 150 MVA | CIPCO will install a new 161/69kV 150 MVA tranformer | IA |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9668 | 2015-09-11 | CR-North Liberty-Hills | 21080 | 2015-09-11 | TX | 2019-12-31 | New Hills area sub | Transformer | 1 | 345 | 161 | 450 MVA | Install a new 345/161 kV 450 MVA transformer. | IA |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9669 | 2015-11-18 | St. Ansgar Industrial | 21047 | 2016-05-24 | TAP | 2017-11-17 | St. Ansgar Industrial | Substation |  | 69 | 69 |  | 69 kV line taps for the new 69/distribution St. Ansgar Industrial substation. | IA |  |  | Planned | 213240 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9669 | 2015-11-18 | St. Ansgar Industrial | 21048 | 2016-05-24 | SUB | 2017-11-11 | St. Ansgar Industrial | Substation |  | 69 | 69 |  | ITCM has proposed the addition of a box structure, line breakers, and the construction of line taps to reach the proposed location. Due to the size of the load, and having two transformers in the future to back-up the load, ITCM has proposed the addition of the breakers as opposed to tapping the line with no breakers. The in-service date spans from the beginning of the year to a date prior to the 2017 summer peak season, actual in-service date will be dependent on Alliant Energy progress. | IA |  |  | Planned | 2295577 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9670 | 2015-09-09 | Columbus Junction Breaker add | 21049 | 2015-11-18 | SUB | 2020-12-31 | Columbus Junction | Substation |  | 69 | 69 |  | Install a second 69 kV breaker at Columbus Jct | IA |  |  | Planned | 932101 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9671 | 2015-09-09 | Amber Creamery Capacitor | 20990 | 2015-11-18 | CAP | 2016-12-31 | Amber Creamery | Capacitor |  | 69 | 69 |  | Add a 7.2 MVAR cap bank at the Amber Creamery substation. | IA |  |  | Planned | 515076 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9672 | 2015-09-09 | 76th AVE SW | 20992 | 2016-05-26 | SUB | 2019-12-31 | 76th AVE SW | Substation |  | 69 | 69 |  | Construct a new four (4) terminal, four (4) break 69 kV substation southeast of the city of Cedar Rapids | IA |  |  | Planned | 3757232 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9672 | 2015-09-09 | 76th AVE SW | 20995 | 2016-05-26 | CAP | 2019-12-31 | 76th AVE SW | Capacitor |  | 69 | 69 | 13.2 MVAR | Install a 13.2MVAR cap bank at the new 76th AVE SW substation | IA |  |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9672 | 2015-09-09 | 76th AVE SW | 20994 | 2016-05-26 | LN | 2019-12-31 | Prairie Creek | CKT 0210 | 1 | 69 | 69 |  | Tap the 69kV Prairie Creek CKT 0210 | IA |  |  | Planned | 149536 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9672 | 2015-09-09 | 76th AVE SW | 20993 | 2016-05-26 | LN | 2019-12-31 | PCI | Tharp | 1 | 69 | 69 |  | Tap PCI-Tharp 69kV line for 2 of the new line terminals | IA |  |  | Planned | 149536 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9706 | 2015-09-10 | Huntley 69 kV Maintenance | 21072 | 2015-09-11 | SUB | 2016-12-31 | Huntley | Substation |  | 69 | 69 |  | Relocate the 161/69 kV T1 Adams transformer to Huntley and replace the 161/69 kV T2 transformer and 69 kV breakers to the new Huntley substation that is currently proposed for the MVP #3 project. | IA |  |  | Planned | 5014447 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9706 | 2015-09-10 | Huntley 69 kV Maintenance | 21078 | 2015-09-11 | TX | 2016-12-31 | Huntley | Transformer | 2 | 161 | 69 |  | Relocate the Adams 161/69 kV 75 MVA transformer to the new Huntley sub for transformer #2 and retire the Winnebago 30 MVA unit. | MN |  |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9706 | 2015-09-10 | Huntley 69 kV Maintenance | 21077 | 2015-09-11 | TX | 2016-12-31 | Huntley | Transformer | 1 | 161 | 69 | 75 MVA | Relocate the Winnebago Jct 161/69 kV 75 MVA transformer to the new Huntley sub. | IA |  |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9706 | 2015-09-10 | Huntley 69 kV Maintenance | 21076 | 2015-09-11 | LN | 2016-12-31 | Huntley | Blue Earth | 1 | 69 | 69 |  | Connect the Huntley 69kV to the Blue Earth 69 kV sub | MN |  |  | Planned | 1272000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9706 | 2015-09-10 | Huntley 69 kV Maintenance | 21075 | 2015-09-11 | LN | 2016-12-31 | Huntley | Walters | 1 | 69 | 69 |  | Connect the new Huntley sub to the Walter 69 kV sub | MN |  |  | Planned | 1792800 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9706 | 2015-09-10 | Huntley 69 kV Maintenance | 21074 | 2015-09-11 | LN | 2016-12-31 | Huntley | Winnebago Local | 1 | 69 | 69 |  | Connect the new Huntley 69kV to the Winnebago Local 69kV sub | MN |  |  | Planned | 676000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9706 | 2015-09-10 | Huntley 69 kV Maintenance | 21073 | 2015-09-11 | SUB | 2016-12-31 | Winnebago Jct. | Substation |  | 161 | 69 |  | Retire the Winnebago Jct 69kV portion of the sub. | IA |  |  | Planned | 300000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9711 | 2015-10-19 | Traer 161 kV Ring Bus | 21044 | 2016-05-26 | BUS | 2017-12-31 | Traer | Substation |  | 161 | 161 |  | Convert the 161 kV to a ring bus | IA |  |  | Planned | 3667882 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9711 | 2015-10-19 | Traer 161 kV Ring Bus | 21759 | 2016-05-26 | TAP | 2017-12-31 | Traer | 161 kV line taps |  | 161 | 161 |  | Reroute 161 kV lines and new dead ends near the Traer substation for the new ring bus configuration. | IA |  |  | Planned | 1344000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9711 | 2015-10-19 | Traer 161 kV Ring Bus | 21045 | 2016-05-26 | SUBmisc | 2017-12-31 | Dysart | Substation |  | 161 | 161 |  | Upgrade 161 kV switch | IA |  |  | Planned | 54000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9712 | 2015-09-10 |  | 21046 | 2015-09-10 | SUB | 2017-06-01 | Burlington Gnerating Station | Substation |  | 161 | 69 |  | Modify the Burlington Generating Station’s substation for increased reliability and to accommodate the required NERC PRC-005 maintenance testing of the BGS relaying schemes. Replace 161 kV circuit switcher 1272 with a breaker to isolate the BGS - Denmark #2 161 kV line from 161/69 kV T2 transformer. The 69 kV motor-operated switches will be replaced with 69 kV main circuit breakers to create separately relayed 161/69 kV transformer and 69 kV bus sections. Additional three-phase 161 kV voltage transformers will be added. A new control enclosure will be added outside the BGS power plant. All ITC relaying will be replaced and be installed in this new enclosure. The existing schemes in the BGS plant control room will be retired and removed. | IA |  |  | Planned | 3114346 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9714 | 2015-09-11 | Doud-Lyon 34 to 69 kV Conv | 21291 | 2016-05-26 | SwSta | 2019-12-31 | Lyon | Switch Station |  | 69 | 69 |  | Construct a new 3 terminal switch station near Lyon (official name TBD). | IA |  |  | Planned | 3420000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9714 | 2015-09-11 | Doud-Lyon 34 to 69 kV Conv | 21632 | 2016-05-26 | SUB | 2019-12-31 | Lyon | Substation |  | 69 | 69 |  | Retire the old Lyon 34kV substation. | IA |  |  | Planned | 180000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9714 | 2015-09-11 | Doud-Lyon 34 to 69 kV Conv | 21631 | 2016-05-26 | LN | 2019-12-31 | Boone CKT 2230 |  | 1 | 69 | 69 |  | Retire the 34kV Boone CKT 2230. | IA |  |  | Planned | 360000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9714 | 2015-09-11 | Doud-Lyon 34 to 69 kV Conv | 21300 | 2016-05-26 | LNcnv | 2019-12-31 | Jewell | Lyon | 1 | 69 | 69 |  | Jewell to Lyon Breaker Station 34.5 to 69 kV line conversion | IA | 0.96 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9714 | 2015-09-11 | Doud-Lyon 34 to 69 kV Conv | 21298 | 2016-05-26 | LNcnv | 2019-12-31 | Stanhope Muni Tap | Jewell | 1 | 69 | 69 |  | Stanhope Muni Tap to Jewell 34.5 to 69 kV line conversion | IA | 10.22 |  | Planned | 257505 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9714 | 2015-09-11 | Doud-Lyon 34 to 69 kV Conv | 21297 | 2016-05-26 | LNcnv | 2019-12-31 | Stanhope Muni Tap | Stanhope Muni | 1 | 69 | 69 |  | Stanhope Muni Tap to Stanhope Muni 34.5 to 69 kV line conversion | IA | 0.25 |  | Planned | 420974 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9714 | 2015-09-11 | Doud-Lyon 34 to 69 kV Conv | 21296 | 2016-05-26 | LNcnv | 2019-12-31 | Stratford REC Tap | Stanhope Muni Tap | 1 | 69 | 69 |  | Startford REC Tap to Stanhoep Muni Tap 34.5 to 69 kV line conversion | IA | 4.98 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9714 | 2015-09-11 | Doud-Lyon 34 to 69 kV Conv | 21294 | 2016-05-26 | LNcnv | 2019-12-31 | Stratford REC Tap | Stratford REC | 1 | 69 | 69 |  | Stratford REC Tap to Startford REC 34.5 to 69 kV line conversion | IA | 2.7 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9714 | 2015-09-11 | Doud-Lyon 34 to 69 kV Conv | 21293 | 2016-05-26 | LNcnv | 2019-12-31 | Ridgeport REC | Stratford REC Tap | 1 | 69 | 69 |  | Ridgeport REC to Stratford REC Tap 34.5 to 69 kV line conversion | IA | 4.94 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9714 | 2015-09-11 | Doud-Lyon 34 to 69 kV Conv | 21292 | 2016-05-26 | LNcnv | 2019-12-31 | Doud | Ridgeport REc | 1 | 69 | 69 |  | Doud to Ridgeport REC 34.5 to 69 kV line conversion | IA | 11.15 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9901 | 2015-11-18 | Mount Ayr 69 kV Sub Rebuild | 21306 | 2015-11-18 | SUB | 2018-12-31 | Kneedler | Substation |  | 69 | 69 |  | New sub north of Mt. Ayr instead of rebuilding the Mount Ayr 69 kV substation. | IA |  |  | Planned | 4291794 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9901 | 2015-11-18 | Mount Ayr 69 kV Sub Rebuild | 21753 | 2016-05-24 | CAP | 2018-12-31 | Mt Ayr (Kneedler) | Substation |  | 69 | 69 |  | Add a 21.42 MVAr cap at Kneedler sub. (Three stages of 7.1 MVAr) | IA |  |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9901 | 2015-11-18 | Mount Ayr 69 kV Sub Rebuild | 21752 | 2016-05-24 | TAP | 2018-12-31 | Mt Ayr (Kneedler) | Substation |  | 69 | 69 |  | 69kV line tap work for the new Kneedler substation | IA |  |  | Planned | 652800 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9904 | 2015-09-15 | Appanoose Co 161 kV Rebuild | 21311 | 2015-11-18 | SUB | 2019-12-31 | Appanoose County | Substation |  | 161 | 69 |  | Due to a lack of voltage support in Southwest Iowa and an aging transformer at Appanoose County substation, ITC will replace it with a unit equipped with a Load Tap Changer (LTC). The 100 MVA (equipped with a LTC) 161:69kV transformer at Fernald will be relocated to Appanoose County after the MGS upgrades are completed. In addition, to increase reliability, ITC will rebuild the existing 161kV bus to a ring configuration. | IA |  |  | Planned | 4944594 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9907 | 2015-09-15 | Summit to Dovray 69 kV Rebuild | 21315 | 2016-05-26 | LNrb | 2022-12-31 | Summit | Dovray | 1 | 69 | 69 |  | Rebuild ~12.9 miles of old line to new T2-4/0 ACSR | MN | 12.89 |  | Planned | 9162091 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9908 | 2015-09-15 | Dovray to Fulda 69 kV Rebuild | 21316 | 2016-05-26 | LNrb | 2023-12-31 | Dovray | Fulda |  | 69 | 69 |  | Rebuild 69kV line from Dovrey substation to the Fulda Junction | MN | 14.5 |  | Planned | 9410124 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9910 | 2015-09-15 | Fulda to Heron Lake 69 kV Rebuild | 21318 | 2016-05-26 | LNrb | 2024-12-31 | Fulda Junction | Heron Lake | 1 | 69 | 69 |  | Rebuild 69kV line from Fulda Junction to Heron Lake | MN | 20.14 |  | Planned | 14976652 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9937 | 2015-09-15 | J233 Network Upgrades | 21353 | 2016-05-25 | TX | 2016-11-30 | Fernald | Transformer | 1 | 161 | 69 | 150 MVA | Replace existing 161/69 kV transformer with 150 MVA unit | IA |  |  | Planned | 2392800 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9937 | 2015-09-15 | J233 Network Upgrades | 21640 | 2016-01-29 | SUB | 2015-12-15 | Marshalltown | Substation |  | 161 | 161 |  | Network upgrades for the J233 project | IA |  |  | M5_In Service | 4095731 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9937 | 2015-09-15 | J233 Network Upgrades | 21359 | 2015-09-15 | LNrb | 2017-03-30 | Newton | Prairie City | 1 | 69 | 69 | 40 MVA | Rebuild ITCM portion of jointly-owned line with T2-4/0 conductor. Rating to increase to MEC limit of 40 MVA | IA |  |  | Planned | 4647247 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9937 | 2015-09-15 | J233 Network Upgrades | 21358 | 2015-09-15 | LNup | 2016-12-31 | Jasper | Newton | 1 | 161 | 161 | 276 MVA | Raise structure to allow operation at 276 MVA | IA |  |  | Planned | 108000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9937 | 2015-09-15 | J233 Network Upgrades | 21357 | 2015-09-15 | LNrc | 2016-12-31 | Jasper | Laurel | 1 | 161 | 161 | 361 MVA | Replace conductor to allow operation at 361 MVA | IA |  |  | Planned | 151037 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9937 | 2015-09-15 | J233 Network Upgrades | 21356 | 2016-03-30 | LNup | 2015-09-15 | Marshalltown | Blairstown Junction | 1 | 115 | 115 | 90 MVA | Raise/Replace structures to allow operation at 90 MVA | IA |  |  | M5_In Service | 1560000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9937 | 2015-09-15 | J233 Network Upgrades | 21355 | 2016-03-30 | TX | 2016-02-01 | Newton | Transformer | 1 | 161 | 69 | 150 MVA | Replace existing 161/69 kV transformer with 150 MVA unit | IA |  |  | M5_In Service | 2392800 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9937 | 2015-09-15 | J233 Network Upgrades | 21354 | 2016-05-25 | TX | 2016-04-22 | Jasper | Transformer | 1 | 161 | 69 | 150 MVA | Replace existing 161/69 kV transformer with 150 MVA unit | IA |  |  | M5_In Service | 2392800 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9939 | 2015-09-15 | H009-Jasper-Aurora 69 kV | 21361 | 2015-09-15 | LNrb | 2016-12-31 | Jasper | Aurora Heights | 1 | 69 | 69 | 140 NVA | Rebuild line with T2-477 ACSR conductor to allow operation of line at 140 MVA | IA |  |  | Planned | 3720000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9941 | 2015-09-15 | H021-Traer-Traer Tap 69 kV | 21362 | 2015-09-15 | TEQ | 2016-06-01 | Traer | Traer Tap | 1 | 69 | 69 | 61 MVA | Upgrade terminal/replace breaker to increase rating to bus conductor limit of 61 MVA | IA |  |  | Planned | 293449 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9985 | 2015-09-15 | Newhall-Williamsburg 161 kV | 21411 | 2016-05-25 | LNrb | 2018-12-31 | Newhall | Willaimsburg | 1 | 161 | 161 |  | Rebuild Williamsburg 115kV tap to 161kV | IA | 23 | 3 | Planned | 40174153 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9988 | 2015-09-15 | Newhall 161 kV Breaker Station | 21409 | 2015-09-15 | SwSta | 2018-12-31 | Newhall | Switch Station |  | 161 | 161 |  | Construct 3 position 161kV Breaker Station | IA |  |  | Planned | 6924478 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 9988 | 2015-09-15 | Newhall 161 kV Breaker Station | 21757 | 2016-05-26 | TAP | 2018-12-31 | Newhall | Line Taps |  | 161 | 161 |  | Construct 161kV line taps for 3 position 161kV Breaker Station | IA |  |  | Planned | 1166404 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 10022 | 2015-09-15 | PCI-Mt.Vernon-Lisbon-76thAVE Conv | 21434 | 2016-05-26 | SUB | 2019-12-31 | Lisbon North | Substation | 1 | 69 | 69 |  | Two (2) 69 kV breakers and associated equipment will be installed at the Lisbon North substation | IA |  |  | Planned | 598171 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 10022 | 2015-09-15 | PCI-Mt.Vernon-Lisbon-76thAVE Conv | 21633 | 2016-05-26 | LNcnv | 2019-12-31 | PCI | Mt. Vernon | 1 | 69 | 69 |  | Convert to 69kV operation. | IA |  |  | Planned | 661200 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 10022 | 2015-09-15 | PCI-Mt.Vernon-Lisbon-76thAVE Conv | 21437 | 2016-05-26 | LNup | 2019-12-31 | 76th AVE (Eagle) | Tharp | 1 | 69 | 69 |  | OPGW will need to be installed. | IA |  |  | Planned | 2175600 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 10022 | 2015-09-15 | PCI-Mt.Vernon-Lisbon-76thAVE Conv | 21436 | 2016-05-26 | LN | 2019-12-31 | PCI | 76th AVE (Eagle) | 1 | 69 | 69 |  | approximately 0.6 mile of new 69 kV transmission line will be constructed to complete the PCI to 76th Ave circuit | IA |  |  | Planned | 2037600 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 10022 | 2015-09-15 | PCI-Mt.Vernon-Lisbon-76thAVE Conv | 21435 | 2016-05-26 | SUB | 2019-12-31 | PCI | Substation | 1 | 69 | 69 |  | A 69 kV breaker and associated equipment will be installed at the PCI substation | IA |  |  | Planned | 321361 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 10023 | 2015-09-17 | ITCM Asset Blanket | 21441 | 2016-05-25 | LN | 2017-12-31 | ITCM Asset Blanket for 2017 | Throughout system |  | 345 | 69 |  | Replace aging and outdated equipment on a cycle that will ensure each system is replaced near its expected end of life. Modern equipment can improve reliability, use state of the art technology, and will typically use longer maintenance intervals which reduces maintenance costs. Equipment is commonly equipped with better monitoring and alarming functionality giving improved remote supervision. | IA,MN,IL |  |  | Planned | 37200000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 10023 | 2015-09-17 | ITCM Asset Blanket | 21443 | 2016-05-25 | LN | 2019-12-31 | ITCM Asset Blanket for 2019 | Throughout system |  | 345 | 69 |  | Replace aging and outdated equipment on a cycle that will ensure each system is replaced near its expected end of life. Modern equipment can improve reliability, use state of the art technology, and will typically use longer maintenance intervals which reduces maintenance costs. Equipment is commonly equipped with better monitoring and alarming functionality giving improved remote supervision. | IA,MN,IL |  |  | Planned | 37200000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 10023 | 2015-09-17 | ITCM Asset Blanket | 21442 | 2016-05-25 | LN | 2018-12-31 | ITCM Asset Blanket for 2018 | Throughout system |  | 345 | 69 |  | Replace aging and outdated equipment on a cycle that will ensure each system is replaced near its expected end of life. Modern equipment can improve reliability, use state of the art technology, and will typically use longer maintenance intervals which reduces maintenance costs. Equipment is commonly equipped with better monitoring and alarming functionality giving improved remote supervision. | IA,MN,IL |  |  | Planned | 37200000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 10024 | 2015-09-15 | Cust Interconnet Blanket | 21438 | 2015-09-15 | LN | 2019-12-31 | Blanket for Customer Interconnections under $1 million for 2019 | Throughout system |  | 345 | 69 |  | These projects are being done at the request of an interconnection customer in order to facilitate new load, re-distribute existing load, improve the performance of the sub-transmission and distribution systems, or to accommodate a new Transmission-to-Transmission connection request. | IA,MN,IL |  |  | Planned | 2000000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 10268 | 2015-10-28 | DBQ 8th ST dist TRFs | 21511 | 2016-05-25 | SUB | 2017-04-30 | Dubuque 8th Street | Substation |  | 69 | 69 |  | Sub upgrades associated with the Alliant Energy distribution transformer change outs. | IA |  |  | Planned | 1290000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 10268 | 2015-10-28 | DBQ 8th ST dist TRFs | 21513 | 2015-10-28 | LN | 2017-04-30 | Dubuque 8th Street | Sandridge | 1 | 69 | 69 |  | Re-terminate Sandridge 69kV line. | IA |  |  | Planned | 156696 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 10268 | 2015-10-28 | DBQ 8th ST dist TRFs | 21512 | 2015-10-28 | LN | 2017-04-30 | Dubuque 8th Street | Bunker Hill | 1 | 69 | 69 |  | Replcace guyed structure with self-suporting structure. | IA |  |  | Planned | 156697 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 10269 | 2015-10-30 | Lore-Hickory 161 | 21514 | 2016-05-25 | LNrb | 2017-12-31 | Lore | Hickory Creek | 1 | 161 | 161 |  | Rebuild 6.81 miles of the Lore-Hiclory Creek 161 kV line. | IA |  |  | Planned | 12471467 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 10269 | 2015-10-30 | Lore-Hickory 161 | 21639 | 2016-02-18 | TEQ | 2017-12-31 | Hickory Creek | Substation |  | 161 | 161 |  | Remove the wave trap | IA |  |  | Planned | 101400 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 10269 | 2015-10-30 | Lore-Hickory 161 | 21515 | 2016-02-18 | TEQ | 2017-12-31 | Lore | Hickory Creek | 1 | 161 | 161 |  | Upgrade the Lore 161kV terminal and remove the wave trap | IA |  |  | Planned | 127980 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 10303 | 2015-11-05 | Willaimsburg 161kV Temp Conv | 21559 | 2015-11-05 | SUB | 2017-12-31 | Williamsburg | Substation |  | 161 | 34 |  | The two aging and miss-matched 115/34.5kV transformers will be replaced with a newer and larger 161/36kV transformer from the Hiawatha Substation. This will provide an increased level of reliability to Williamsburg by serving the high-side from a newly rebuilt and shorter 161kV line compared to an older and longer 115kV line. | IA |  |  | Planned | 1204368 | Engineering |  | N | N | N | NT
A in MTEP16 | B>A | West | ITCM | 10303 | 2015-11-05 | Willaimsburg 161kV Temp Conv | 21560 | 2015-11-05 | LN | 2017-12-30 | Parnell | Williamsburg | 1 | 161 | 161 |  | To provide a reliable conversion to 69kV the 34.5kV will need temporary configurations to provide a reliable transition. The Williamsburg 115kV high side will be converted to 161kV. | IA |  |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 11163 | 2016-08-03 | Devils Creek | 21722 | 2016-05-02 | SUB | 2017-12-31 | Ft. Madison Devils Creek | Substation |  | 69 |  |  | New Ft. Madison Devils Creek Distribution Substation | IA |  |  | Planned | 1718107 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 11163 | 2016-08-03 | Devils Creek | 21725 | 2016-05-02 | SUB | 2017-12-31 | Dial | Substation |  | 69 |  |  | Retire the Dial substation. | IA |  |  | Planned | 9187 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 11163 | 2016-08-03 | Devils Creek | 21724 | 2016-05-02 | LN | 2017-12-31 | Viele 9660 Ckt | Viele 9660 Ckt | 1 | 69 |  |  | Retire the Viele 9660 Ckt (~3.6 miles) and the Viele bkr 9660 | IA |  |  | Planned | 38333 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 11163 | 2016-08-03 | Devils Creek | 21723 | 2016-05-02 | LN | 2017-12-31 | Ft. Madison Devils Creek | Substation |  | 69 |  |  | Line work for new 69kV line taps to the new Devil's Creek distribution substation. | IA |  |  | Planned | 260596 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 11164 | 2016-08-03 | Oelwein Hub | 21726 | 2016-05-02 | SUB | 2017-04-30 | Oelwein Hub | New Substation |  | 69 |  |  | New Oelwein Hub Distribution Substation | IA |  |  | Planned | 2067518 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 11164 | 2016-08-03 | Oelwein Hub | 21729 | 2016-05-02 | LNrb | 2017-04-30 | Hazleton | Oelwein | 1 | 69 |  |  | Rebuild 1.42 miles of the existing Hazleton-Oelwein 69kV line due to condition. | IA | 1.42 |  | Planned | 3526841 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 11164 | 2016-08-03 | Oelwein Hub | 21728 | 2016-05-02 | TEQ | 2017-04-30 | Hazleton | Substation |  | 69 |  |  | Upgrade terminal equipment at Hazleton on breakers 940, 941, and 947. | IA |  |  | Planned | 120600 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 11164 | 2016-08-03 | Oelwein Hub | 21727 | 2016-05-02 | CAP | 2017-04-30 | Oelwein | Capacitor |  | 69 |  |  | Install new 11.2 MVAr capacitor at the Oelwein Substation | IA |  |  | Planned | 602509 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 11763 | 2016-08-16 | J344 Network Upgrades | 21823 | 2016-08-16 | SwSta | 2017-09-01 | Irvine | Switch Station |  | 161 | 161 |  | Build a new 161 kV three terminal switch station tapping the Beacon-Poweshiek 161 kV line. | IA |  |  | Planned | 4277540 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 11763 | 2016-08-16 | J344 Network Upgrades | 21827 | 2016-08-16 | LNup | 2017-09-01 | Beacon | Irvine | 1 | 161 | 161 |  | Raise the structures on the Beacon-Irvine-Poweshiek 161 kV line. | IA |  |  | Planned | 300000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 11763 | 2016-08-16 | J344 Network Upgrades | 21825 | 2016-08-16 | TAP | 2017-09-01 | Irvine | Poweshiek | 1 | 161 | 161 |  | Install 161 kV line taps for the new Irvine Switch Station. | IA |  |  | Planned | 480000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 11763 | 2016-08-16 | J344 Network Upgrades | 21824 | 2016-08-16 | TAP | 2017-09-01 | Beacon | Irvine | 1 | 161 | 161 |  | Install 161 kV line taps for the new Irvine Switch Station. | IA |  |  | Planned | 480000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | ITCM | 11883 | 2016-08-31 |  | 21852 | 2016-09-20 | SUBmisc | 2022-01-01 | Huntley |  |  | 345 |  |  | Substation modifications at Huntley | MN |  |  | M2a_Pre-Project Approval | 2471713 |  |  | N | Y | Y | Y
A in MTEP16 | B>A | West | MDU | 4140 | 2015-06-10 | Bowdle | 7871 | 2014-12-12 | SUB | 2017-06-30 | Bowdle Jct |  |  | 115 | 41.6 |  | A new 115/41.6 kV substation | SD |  |  | Planned | 5500000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | MDU | 9120 | 2015-07-13 |  | 20815 | 2015-06-10 | LN | 2017-10-31 | Ellendale Jct | Leola Jct | 1 | 115 |  | 127 | New Ellendale Jct-Leola Jct 115 kV line | SD,ND |  | 45 | Planned | 8830000 | Budgetary |  | N | N | N | Y
A in MTEP16 | B>A | West | MDU | 9120 | 2015-07-13 |  | 20816 | 2015-06-10 | SUB | 2017-10-31 | Leola Jct |  |  | 115 | 41.6 | 50 | New 115/41.6 kV substation connecting to the Ellendale Jct - Bowdle Jct 41.6 kV line | SD |  |  | Planned | 4005000 | Budgetary |  | N | N | N | NT
A in MTEP16 | B>A | West | MDU | 9121 | 2015-06-10 |  | 20817 | 2015-11-05 | TEQ | 2016-12-31 | Heskett 115 Switchyard |  |  | 115 |  | 159 | Replace switches 7097, 7002 & 7005 | ND |  |  | Planned | 125000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | MDU | 11403 | 2016-06-20 |  | 21768 | 2016-06-20 | LNrc | 2015-12-31 | Coyote Jct | Beulah Jct | 1 | 115 |  |  | Reconductor Coyote Jct-Beulah Jct 115 kV line | ND | 4.3 |  | M5_In Service | 350000 | Facility Study |  | N | N | N | Y
A in MTEP16 | B>A | West | MEC | 8108 | 2015-09-15 |  | 20445 | 2014-09-22 | LNup | 2017-06-01 | Sub 73 | Dumont Tap |  | 69 |  | 72 | Replace structures increasing line clearance and rating | IA | 0.63 |  | Planned | 40000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | West | MEC | 8110 | 2015-09-15 |  | 20447 | 2014-09-22 | LNup | 2017-06-01 | Sub 73 | Elvira Tap |  | 69 |  | 72 | Replace structures, increasing line clearance and rating. | IA | 1.95 | 0 | Planned | 50000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | West | MEC | 8112 | 2015-09-15 | G7055 | 20448 | 2014-09-22 | LNup | 2017-06-01 | Buffalo Bill Tap | Elvira Tap |  | 69 |  | 72 | Replace structures to increase line clearance and rating. | IA | 6.36 | 0 | Planned | 25000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | West | MEC | 9947 | 2015-09-15 |  | 21366 | 2016-09-16 | SUB | 2018-06-01 | Polk City |  |  | 161 | 13 | 33 | New Polk City 33 MVA 161-13 kV distribution substation | IA |  |  | Planned | 1300000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | West | MEC | 9947 | 2015-09-15 |  | 21368 | 2016-09-16 | LN | 2018-06-01 | Polk City | NE Ankeny | 1 | 161 |  |  | New 3 mile line from Polk City Substation to existing Bittersweet-NE Ankeny 161 kV line. | IA |  | 3 | Planned | 2500000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | MEC | 9947 | 2015-09-15 |  | 21367 | 2016-09-16 | LN | 2018-06-01 | Polk City | Bittersweet | 1 | 161 |  | 210 | Build four miles of new 161 kV line from Polk City to the existing Bittersweet - NE Ankeny 161 kV line | IA |  | 4 | Planned | 3200000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | MEC | 9973 | 2016-06-07 |  | 21390 | 2016-06-07 | TX | 2017-10-01 | Manawa |  |  | 161 | 13 | 33 | Add a second 33 MVA 161-13 kV transformer at Manawa Substation. | IA |  |  | Planned | 1100000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | West | MEC | 9976 | 2016-06-07 |  | 21396 | 2016-06-07 | CB | 2016-12-01 | Avoca |  |  | 69 |  |  | Add a new 69 kV breaker on transformer 8T1 at Avoca Substaiton. | IA |  |  | Planned | 415000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | West | MEC | 9980 | 2015-09-15 |  | 21398 | 2016-03-21 | IND | 2016-10-01 | Teakwood |  |  | 34.5 |  | 20 | Add two 10 MVAR 34.5 kV reactors at Teakwood Substation. | IA |  |  | Planned | 850000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | West | MEC | 9981 | 2015-09-15 |  | 21403 | 2015-09-15 | LNrb | 2017-06-01 | Sub 701 | Honey Creek | 1 | 69 |  |  | Rebuild the Sub 701 to Honey Creek 69 kV line. | IA | 10.2 | 0 | Planned | 3250000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | West | MEC | 9987 | 2015-09-15 |  | 21410 | 2015-09-15 | SUB | 2016-11-30 | Johnston |  |  | 161 | 13 | 33 | New Johnston 33 MVA 161-13 kV distribution substation and two 161 kV tap lines approximately 0.5 miles each. | IA |  |  | Planned | 2130000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | West | MEC | 9992 | 2015-09-15 |  | 21414 | 2016-06-07 | LNup | 2016-07-01 | Lake Cornelia | Coulter | 1 | 69 |  | 44 | Replace limiting structures to increase line rating. | IA |  |  | Planned | 59000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | West | MEC | 9993 | 2015-09-15 |  | 21416 | 2016-06-07 | LNup | 2016-04-13 | Humboldt East | Thor | 1 | 69 |  | 44 | Replace limiting structures to increase line rating. Mitigates overloads for n-1-1 contingencies. | IA |  |  | Planned | 61000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | West | MEC | 9996 | 2016-09-13 |  | 21419 | 2016-06-07 | TX | 2016-12-09 | Eagle Grove |  |  | 69 | 13 | 25 MVA | Install second 69-13 kV Transformer & 69 kV bus tie breaker | IA |  |  | Planned | 2440000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | West | MEC | 10004 | 2016-09-16 |  | 21427 | 2016-09-16 | TX | 2018-06-01 | Sub 18 |  |  | 161 | 69 | 167 | Replace Sub 18 161-69 kV transformer with a 167 MVA unit. | IA |  |  | Planned | 1080000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | West | MEC | 10005 | 2015-09-18 |  | 21428 | 2016-09-14 | CB | 2015-12-08 | Plymouth |  |  | 161 |  | 40 kA/2000A continuous | Replace 161kV circuit breaker 9610 at Plymouth Substation. | IA |  |  | M5_In Service | 264000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | MEC | 10006 | 2015-09-18 |  | 21429 | 2015-09-18 | CB | 2016-12-31 | Sycamore |  |  | 161 |  | 40 kA | Replace 161 kV circuit breakers AG805, AG812 and AG816 at Sycamore Substation to maintain adequate current interrupting capability. | IA |  |  | Planned | 685000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | MEC | 10009 | 2015-09-18 |  | 21430 | 2016-06-07 | CB | 2016-10-31 | Bondurant |  |  | 161 |  | 40 kA | Replace 161 kV circuit breaker AH810 at Bondurant Substation. | IA |  |  | Planned | 325000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | MEC | 10503 | 2015-12-21 | Q1138 | 21601 | 2016-09-13 | CB | 2016-10-20 | Tate & Lyle |  |  | 161 |  |  | Add 161 kV bus tie breaker | IA |  |  | Planned | 443000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | MEC | 10663 | 2016-01-29 |  | 21641 | 2016-01-29 | TX | 2016-12-31 | Willow Creek | Willow Creek |  | 161 | 13.2 | 50 | Add three new 161 kV breakers to convert the substation to breaker and one-half configuration and to accommodate the addition of a new 50 MVA 161-13 kV transformer to meet increasing customer load. | IA | 0 | 0 | Planned | 120000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | West | MEC | 10664 | 2016-01-29 |  | 21642 | 2016-01-29 | TX | 2016-12-01 | 34th Ave. NW |  |  | 161 | 13.2 | 62 | Add a new 62 MVA 161-13 kV transformer at the 34th Ave. NW Substation to serve increasing customer load. | IA | 0 | 0 | Planned | 90000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | West | MEC | 10803 | 2016-02-29 |  | 21667 | 2016-02-29 | CAP | 2016-12-01 | Sub J Iowa City |  |  | 161 |  | 37.8 | Reducing the size of the Sub J capacitor bank to 37.8 MVAR provides increased operational flexibility while maintaining voltage within criteria. Replace the capacitor relays. | IA |  |  | Planned | 300000 | Budgetary |  | N | N | N | Y
A in MTEP16 | B>A | West | MEC | 10867 | 2016-09-14 |  | 21677 | 2016-09-14 | CB | 2016-08-15 | Obrien County |  |  | 345 |  |  | New 345 kV circuit breaker position for J285 generator interconnection. | IA |  |  | Under Construction | 3000000 | Planning |  | N | Y | Y | Y
A in MTEP16 | B>A | West | MEC | 10868 | 2016-09-14 |  | 21678 | 2016-09-14 | SUB | 2016-07-15 | Ida County |  |  | 345 |  |  | Ida County 345 kV Substation to bisect the Raun-Lehigh 345 kV line for the J411 generator interconnection. | IA |  |  | Under Construction | 5750000 | Planning |  | N | Y | Y | Y
A in MTEP16 | B>A | West | MEC | 11103 | 2016-05-12 | T90D4 | 21716 | 2016-06-07 | CAP | 2016-11-15 | 636201 |  |  | 69 |  |  | Two 69 kV, 15 MVAR capacitors | IA |  |  | Under Construction | 1180000 | Engineering |  | N | N | N | NT
A in MTEP16 | B>A | West | MEC | 11143 | 2016-06-07 | T90D9 | 21717 | 2016-06-07 | LNup | 2016-12-01 | 635645 | 652560 | 1 | 161 |  |  | structure replacements | IA |  |  | Planned | 175000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | MEC | 11144 | 2016-04-27 | T90DK | 21718 | 2016-06-07 | TEQ | 2016-06-24 | 636020 |  |  | 161 |  |  | Replace 161 kV switch | IA |  |  | Under Construction | 88000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | MEC | 11145 | 2016-06-07 | T905K | 21719 | 2016-06-07 | LNup | 2016-06-30 | 631079 | 636020 | 1 | 161 |  |  | structure replacements | IA |  |  | Planned | 173000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | MEC | 11146 | 2016-04-27 | T90LA | 21720 | 2016-06-07 | LNup | 2017-06-01 | 635034 | 635038 | 1 | 161 |  |  | structure replacements | IA |  |  | Planned | 200000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | MEC | 11203 |  |  | 21738 |  | SUB | 2012-11-01 | Lehigh |  |  | 345 |  | 3000 A | Add two 345 kV circuit breakers and complete a 345 kV ring bus to accommodate Generator Interconnection Project R42 | IA |  |  | M5_In Service | 2882000 | Actual |  |  | Y | Y | Y
A in MTEP16 | B>A | West | MEC | 11204 |  |  | 21737 |  | SUB | 2011-12-30 | Rolling Hills |  |  | 345 |  | 3000 A | Add a new 345 kV circuit breaker and associated switchgear to accommodate Generator Interconnection Project J191. | IA |  |  | M5_In Service | 754100 | Actual |  |  | Y | Y | Y
A in MTEP16 | B>A | West | MEC | 11283 | 2016-07-25 | T90L8 | 21754 | 2016-05-25 | LNup | 2017-06-01 | 541251 MARYVLE5 161.00 | 635034 CLRNDA 5 161.00 | 1 | 161 |  |  | Replace three structures. | IA |  |  | Planned | 100100 | Budgetary |  | N | N | N | Y
A in MTEP16 | B>A | West | MEC | 11284 | 2016-07-25 | T90KU | 21755 | 2016-05-25 | TEQ | 2017-06-01 | 541251 MARYVLE5 161.00 | 635034 CLRNDA 5 161.00 | 1 | 161 |  |  | Network Upgrades for J343 Adams County Wind. | IA |  |  | Planned | 80500 | Budgetary |  | N | N | N | Y
A in MTEP16 | B>A | West | MEC | 11285 | 2016-07-25 | T90M4 | 21756 | 2016-05-25 | TEQ | 2017-09-01 | 631113 POWESHK5 161.00 | 635870 BEACON 5 161.00 | 1 | 161 |  |  | Non-Stand Alone Network Upgrade for J344 wind interconnection request. | IA |  |  | Planned | 25000 | GIA |  | N | N | N | Y
A in MTEP16 | B>A | West | MP | 7910 | 2015-09-04 | 5 Line Upgrade | 20153 | 2015-04-02 | LNrc | 2019-11-01 | Brainerd | Mud Lake | 1 | 115 |  | 182 | Reconductor Brainerd - Mud Lake 115 kV Line with 636 ACSR @ 100C | MN | 4.41 | 0 | Planned | 1900000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | MP | 7996 | 2015-09-11 | 15 Line Upgrade | 20269 | 2015-09-04 | LNrb | 2017-12-31 | FondDuLac | Hibbard | 1 | 115 |  | 122 | Fond Du Lac - Hibbard 115 kV Line | MN | 11.3 | 0 | Planned | 5500000 | Planning Preliminary |  | N | N | N | Y
A in MTEP16 | B>A | West | MP | 7997 | 2015-09-04 | 15th Ave West | 20271 | 2015-09-04 | TEQ | 2018-12-31 | 15th Avenue West |  |  | 115 | 13.8 | 39.2 | 115 kV substation improvements (fencing, grounding, relocations, misc. equipment) | MN | 0 | 0 | Planned | 3500000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | MP | 7997 | 2015-09-04 | 15th Ave West | 20939 | 2015-09-04 | TX | 2018-05-01 | 15th Avenue West |  | 1 | 114 | 13.8 | 39.2 | New 115/14 kV transformer | MN | 0 | 0 | Planned | 750000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | West | MP | 7997 | 2015-09-04 | 15th Ave West | 20938 | 2015-09-04 | CB | 2018-05-01 | 15th Avenue West |  |  | 115 |  |  | 115 kV "21-71MW" breaker replacement | MN | 0 | 0 | Planned | 250000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | MP | 7997 | 2015-09-04 | 15th Ave West | 20276 | 2015-09-04 | CB | 2018-12-31 | 15th Avenue West |  | 1 | 115 |  |  | 115 kV "21L" breaker replacement | MN | 0 | 0 | Planned | 250000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | MP | 7997 | 2015-09-04 | 15th Ave West | 20274 | 2015-09-04 | CB | 2018-12-31 | 15th Avenue West |  | 1 | 115 |  |  | 115 kV "71L" breaker replacement | MN | 0 | 0 | Planned | 250000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | MP | 7997 | 2015-09-04 | 15th Ave West | 20273 | 2015-09-04 | Dist | 2018-12-31 | 15th Avenue West |  |  | 13.8 |  |  | New 14 kV switchgear, 14 kV bus, & 14 kV feeder relocations (includes removals) | MN | 0 | 0 | Planned | 5000000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | West | MP | 9064 | 2015-09-08 | Arrowhead Bus Reconfiguration | 20809 | 2016-08-15 | BUS | 2017-12-31 | Arrowhead |  |  | 115 |  |  | Expand and reconfigure 115 kV bus | MN | 0 | 0 | Planned | 600000 | Budgetary |  | N | N | N | Y
A in MTEP16 | B>A | West | MP | 9622 | 2015-09-04 | 83 Line Upgrade | 20940 | 2015-09-04 | TEQ | 2019-06-01 | Boswell |  |  | 230 |  |  | Replace limiting switches at Boswell | MN | 0 | 0 | Planned | 250000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | MP | 9622 | 2015-09-04 | 83 Line Upgrade | 20941 | 2015-09-04 | TEQ | 2019-06-01 | Blackberry |  |  | 230 |  |  | Replace limiting switches at Blackberry | MN | 0 | 0 | Planned | 250000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | MP | 9623 | 2015-09-04 | 95 Line Upgrade | 20942 | 2015-09-04 | TEQ | 2019-06-01 | Boswell |  |  | 230 |  |  | Replace limiting switches at Boswell | MN | 0 | 0 | Planned | 250000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | MP | 9623 | 2015-09-04 | 95 Line Upgrade | 20943 | 2015-09-04 | TEQ | 2019-06-01 | Blackberry |  |  | 230 |  |  | Replace limiting switches at Blackberry | MN | 0 | 0 | Planned | 250000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | MP | 9624 | 2015-09-04 | Bear Creek Transformer | 20944 | 2015-09-04 | Dist | 2017-12-31 | Bear Creek |  |  | 69 | 46 | 18.7 | Add 69/46 kV transformer | MN | 0 | 0 | Planned | 2000000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | West | MP | 9625 | 2015-09-04 | Nemadji | 20945 | 2015-09-04 | SwSta | 2017-12-31 | Nemadji |  |  | 115 |  |  | NEW Nemadji Switching Station | WI | 0 | 0 | Planned | 4630000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | MP | 9625 | 2015-09-04 | Nemadji | 20953 | 2015-09-04 | LN | 2017-12-31 | Nemadji | Gary | 1 | 115 |  | 235 | Extend existing 115 kV line from Gary into Nemadji | WI | 0 | 0.08 | Planned | 50000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | MP | 9625 | 2015-09-04 | Nemadji | 20952 | 2015-09-04 | LN | 2017-12-31 | Nemadji | Enbridge South | 1 | 115 |  | 182 | Nemadji - South 115 kV Line | WI | 0 | 0.2 | Planned | 100000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | MP | 9625 | 2015-09-04 | Nemadji | 20951 | 2015-09-04 | LN | 2017-12-31 | Enbridge East | Enbridge South | 1 | 115 |  | 182 | Replace switch structure in East - South 115 kV Line | WI | 0 | 0 | Planned | 150000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | MP | 9625 | 2015-09-04 | Nemadji | 20950 | 2015-09-04 | LN | 2016-06-01 | Enbridge North | Enbridge East |  | 115 |  | 182 | North - East 115 kV Line (partial double ckt with Nemadji - Stinson) | WI | 0 | 0.72 | Planned | 200000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | MP | 9625 | 2015-09-04 | Nemadji | 20949 | 2015-09-04 | LN | 2014-12-31 | Nemadji | Enbridge North | 1 | 115 |  | 182 | Nemadji - North 115 kV Line (double ckt with Nemadji - Stinson) | WI | 0 | 0.64 | Planned | 150000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | MP | 9625 | 2015-09-04 | Nemadji | 20948 | 2015-09-04 | LN | 2017-12-31 | Nemadji | Stinson | 1 | 115 |  | 235 | Nemadji - Stinson 115 kV Line (double circuit with Nemadji - North - East) | WI | 0 | 1.2 | Planned | 1500000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | MP | 9625 | 2015-09-04 | Nemadji | 20947 | 2015-09-04 | TEQ | 2017-12-31 | Various Customer-Owned |  |  | 115 |  |  | Enbridge Substation Modifications | WI | 0 | 0 | Planned | 1530000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | MP | 9625 | 2015-09-04 | Nemadji | 20946 | 2015-09-04 | CAP | 2017-12-31 | Nemadji |  |  | 115 |  |  | Nemadji Cap Bank | WI | 0 | 0 | Planned | 380000 | Engineering |  | N | N | N | Y
A in MTEP16 | B>A | West | MP | 10284 | 2015-10-30 | 28 Line Upgrade | 21522 | 2016-09-29 | TEQ | 2017-05-01 | Boswell 115 |  |  | 115 |  | 150 | Disconnect switch, Jumpers, and wave Trap | MN |  |  | Planned | 120000 | Engineering Preliminary |  | N | N | N | Y
A in MTEP16 | B>A | West | MP | 10284 | 2015-10-30 | 28 Line Upgrade | 21523 | 2016-09-29 | LNup | 2017-05-01 | Boswell | Canisteo |  | 115 |  | 144 | Increase operating temperature from 65C to 90C | MN |  |  | Planned | 670000 | Engineering Preliminary |  | N | N | N | Y
A in MTEP16 | B>A | West | MP | 10383 | 2015-12-02 | Voltage Conversion | 21570 | 2015-11-23 | BUS | 2017-12-31 | Laskin |  |  | 115 |  | 144 | Remove 138/115 kV transformer and bus through transformer position to reconnect Laskin - Hoyt Lakes 115 kV Line (43 Line) | MN | 0 | 0 | Planned | 100000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | MP | 10383 | 2015-12-02 | Voltage Conversion | 21584 | 2015-12-02 | CAP | 2017-07-01 | Dunka Road |  |  | 115 |  | 15 | New 15 MVAr cap bank at Dunka Road Substation | MN | 0 | 0 | Planned | 400000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | MP | 10383 | 2015-12-02 | Voltage Conversion | 21575 | 2015-11-23 | BUS | 2017-12-31 | Taconite Harbor |  |  | 115 |  |  | Convert Taconite Harbor 138 kV Main Bus to 115 kV and connect to existing 115 kV bus | MN | 0 | 0 | Planned | 419000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | MP | 10383 | 2015-12-02 | Voltage Conversion | 21574 | 2015-11-23 | TEQ | 2017-12-31 | Hoyt Lakes |  |  | 115 |  |  | Replace 138 kV equipment with 115 kV | MN | 0 | 0 | Planned | 250000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | MP | 10383 | 2015-12-02 | Voltage Conversion | 21573 | 2015-11-23 | TX | 2017-12-31 | Hoyt Lakes |  |  | 115 | 13.8 | 50 | Replace existing Hoyt Lakes 138/13.8 kV transformer with 115/13.8 kV transformers (customer-funded) | MN | 0 | 0 | Planned | 1000000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | West | MP | 10383 | 2015-12-02 | Voltage Conversion | 21572 | 2015-11-23 | TX | 2017-12-31 | Skibo |  |  | 115 | 13.8 | 33.6 | Replace Skibo 138/13.8 kV transformer with a 115/13.8 kV transformer (Relocate existing) | MN | 0 | 0 | Planned | 65000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | West | MP | 10383 | 2015-12-02 | Voltage Conversion | 21571 | 2015-11-23 | TEQ | 2017-12-31 | Skibo |  |  | 115 |  |  | Replace 138 kV equipment with 115 kV | MN | 0 | 0 | Planned | 250000 | Planning |  | N | N | N | Y
A in MTEP16 | B>A | West | OTP | 9990 | 2016-09-27 |  | 21415 | 2016-09-27 | RLY | 2017-12-31 | Devils Lake East 41.6 |  |  | 41.6 |  |  | Relay upgrades | ND |  |  | Planned | 37500 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | West | OTP | 9995 | 2015-12-30 |  | 21417 | 2015-12-30 | RLY | 2017-12-31 | Devils Lake SW 41.6 kV |  |  | 41.6 |  |  | Relay upgrades | ND |  |  | Planned | 37500 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | West | OTP | 10003 | 2016-09-01 |  | 21426 | 2016-09-01 | SUB | 2016-12-31 | Rugby 230/115/41.6 kV |  |  | 230 | 41.6 |  | Install four 41.6 kV Breakers in the Rugby area to re-terminate existing OTP-owned 41.6 kV circuits from CPEC-owned Rugby substation to 230 kV delivery. | ND |  |  | Planned | 2000000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | West | OTP | 10007 | 2016-09-21 |  | 21431 | 2016-09-21 | LNrb | 2018-12-31 | Max 41.6 kV | Ryder 41.6 kV | 1 | 41.6 |  |  | To correct this material failure problem with the conductor, a project has been scoped and scheduled out for four years. The project will start in 2015 and be completed in 2018. The project will replace failing insulation, cross arms and poles identified through patrols and inspections and replace the failing 1/0 ACSR conductor for approximately 34 miles between Max, ND and Ryder, ND. | ND | 34 |  | Planned | 2500000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | West | OTP | 11743 | 2016-09-29 |  | 21820 | 2016-09-29 | SwSta | 2016-12-31 | Coleharbor 41.6 kV |  |  | 41.6 |  |  | Single in-line circuit breaker addition | ND |  |  | Planned | 175000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | West | OTP | 11743 | 2016-09-29 |  | 21822 | 2016-09-29 | SwSta | 2016-12-31 | Granville 41.6 |  |  | 41.6 |  |  | Three circuit breaker addition | ND |  |  | Planned | 1150000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | West | OTP | 11743 | 2016-09-29 |  | 21821 | 2016-09-29 | SwSta | 2016-12-31 | Drake 41.6 |  |  | 41.6 |  |  | Single in-line circuit breaker addition | ND |  |  | Planned | 175000 | Planning |  | N | N | N | NT
A in MTEP16 | B>A | West | RPU | 10443 | 2016-02-01 |  | 21585 | 2016-02-01 | SUB | 2017-04-01 | 161 KV Tap | Douglas Trail Substation |  | 161 |  |  | New 161kV Douglas Trail Substation fed from tapping the immediately adjacent Q5 161kV line | MN |  | 0.07 | Planned | 7000000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | XEL | 4696 | 2015-10-22 |  | 8880 | 2016-06-15 | LNrb | 2018-01-31 | Prentice | Medford |  | 69 |  | 71.7 | Rebuild this line to 795 ACSR due to age and condition of the line | WI | 33.5 |  | Planned | 20145714 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | XEL | 10045 | 2015-09-17 |  | 21484 | 2016-06-15 | SUB | 2016-06-30 | City of Chaska |  |  | 115 |  |  | This is the new substation associated with the City of Chaska's new interconnection. | MN |  |  | Planned | 1200000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | XEL | 10045 | 2015-09-17 |  | 21527 | 2016-06-15 | TAP | 2016-06-30 | Bluff Creek | City of Chaska |  | 115 |  |  | Install line tapping double circuit South of Bluff Creek to new City of Chaska Sub | MN |  |  | Planned | 2000000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | XEL | 10062 | 2015-09-18 |  | 21525 | 2016-06-15 | TAP | 2016-06-30 | Tyrone Tap |  |  | 69 |  |  | Install a 3-way switch on NSP’s St. Thomas Tap to Boright #2 69 kV line | MN |  |  | Planned | 375000 |  |  | N | N | N | NT
A in MTEP16 | B>A | West | XEL | 10063 | 2015-09-18 |  | 21528 | 2016-06-15 | LNrb | 2016-07-30 | Jackson Co | DPC Merrillan Tap | 1 | 69 |  |  | Rebuild 6.1 miles from Jackson Co to DPC Merrillan Tap to 565.3 ACSR/TW. | WI | 6.1 |  | Planned | 3300000 |  |  | N | N | N | NT
A in MTEP16 | B>A | West | XEL | 10065 | 2015-09-18 |  | 21529 | 2016-06-15 | CB | 2016-04-30 | Rogers Lake |  |  | 115 |  |  | Replace the four existing gas 40 kA breakers at Rogers Lake with with gas 63 kA breakers. | MN |  |  | Planned | 940847 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | XEL | 10066 | 2015-09-18 |  | 21547 | 2016-06-15 | TEQ | 2016-12-01 | Southtown | Cedarvale |  | 115 |  |  | Upgrade the Southtown-Cedarvale 115 kV line to a minimum of 290 MVA emergency. | MN |  |  | Planned | 750000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | XEL | 10066 | 2015-09-18 |  | 21549 | 2016-06-15 | CAP | 2017-12-30 | Hiawatha |  |  | 115 |  |  | Add a 80 MVAR cap to the Hiawatha substation. | MN |  |  | Planned | 1995000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | XEL | 10066 | 2015-09-18 |  | 21548 | 2016-06-15 | TEQ | 2016-06-01 | Southtown | Shepard |  | 115 |  |  | Upgrade the Southtown-Shepard 115 kV line to a minimum of 270 MVA emergency. | MN |  |  | Planned | 750000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | XEL | 10067 | 2015-09-18 |  | 21526 | 2016-06-15 | SUB | 2018-01-01 | Prairie |  |  | 115 |  |  | Breaker and a half conversion to accomidate Fossum 115 kV interconnection | ND |  |  | Planned | 17261500 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | XEL | 10068 | 2015-09-18 |  | 21546 | 2016-06-15 | SUB | 2017-06-01 | Baytown |  |  | 115 | 13.8 |  | Install a 2nd transformer and switchgear at Baytown substation. | MN |  |  | Planned | 1625468 |  |  | N | N | N | NT
A in MTEP16 | B>A | West | XEL | 10069 | 2015-09-18 |  | 21545 | 2016-06-15 | SUB | 2019-11-01 | Twin Creek |  |  | 69 |  |  | Install a 2 position 69 kV breaker station | WI |  |  | Planned | 2866000 |  |  | N | N | N | NT
A in MTEP16 | B>A | West | XEL | 10071 | 2015-10-22 |  | 21530 | 2016-06-15 | SUB | 2016-09-30 | Prescott |  |  | 69 |  |  | Install second 69/12.47 kV 28 MVA transformer | WI |  |  | Planned | 750000 |  |  | N | N | N | NT
A in MTEP16 | B>A | West | XEL | 10071 | 2015-10-22 |  | 21532 | 2016-06-15 | CAP | 2016-09-30 | Prescott |  |  | 69 |  |  | Install a second 10 MVAR cap bank. | WI |  |  | Planned | 424000 |  |  | N | N | N | NT
A in MTEP16 | B>A | West | XEL | 10072 | 2015-09-18 |  | 21533 | 2016-06-15 | SUB | 2016-12-31 | Dean Lake |  |  | 115 |  |  | Add 4 new breakers to complete the ring bus. | WI |  |  | Planned | 4904100 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | XEL | 10072 | 2015-09-18 |  | 21534 | 2016-06-15 | TX | 2016-08-01 | Dean Lake |  |  | 115 | 13.8 |  | Install third distribution transformer (City of Shakopee) | MN |  |  | Planned |  |  |  | N | N | N | NT
A in MTEP16 | B>A | West | XEL | 10073 | 2015-09-18 |  | 21538 | 2016-06-15 | SUBmisc | 2016-04-30 | Quarry |  |  | 345 | 115 |  | Install GIC monitoring | MN |  |  | Planned | 37298 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | XEL | 10073 | 2015-09-18 |  | 21541 | 2016-06-15 | SUBmisc | 2016-12-31 | Eau Claire |  |  | 345 | 161 |  | Install GIC monitoring | WI |  |  | Planned | 250000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | XEL | 10073 | 2015-09-18 |  | 21540 | 2016-06-15 | SUBmisc | 2016-04-30 | Elm Creek |  |  | 345 | 115 |  | Install GIC monitoring | MN |  |  | Planned | 47852 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | XEL | 10073 | 2015-09-18 |  | 21539 | 2016-06-15 | SUBmisc | 2016-12-31 | Adams |  |  | 345 | 161 |  | Install GIC monitoring | MN |  |  | Planned | 250000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | XEL | 10074 | 2015-09-18 |  | 21536 | 2016-06-15 | LNrb | 2019-05-30 | Airport | Rogers Lake |  | 115 |  |  | rebuilds the Airport - Rogers Lake 115 kV line using 795 ACSS conductor. | MN | 3.4 |  | Planned | 4092000 |  |  | N | N | N | Y
A in MTEP16 | B>A | West | XEL | 10075 | 2015-09-18 |  | 21542 | 2016-06-15 | TX | 2017-12-30 | Waconia |  |  | 69 | 13.8 |  | Install a 2nd distribution transformer at Waconia substation. | MN |  |  | Planned | 420000 |  |  | N | N | N | NT
A in MTEP16 | B>A | West | XEL | 10076 | 2015-09-18 |  | 21535 | 2016-06-15 | LNrb | 2019-05-30 | West St. Cloud | Milwood Tap |  | 69 |  |  | Rebuild 24 miles of line from West St. Cloud to Millwood Tap using 477 ACSR conductor. | MN | 24 |  | Planned | 10400000 |  |  | N | N | N | NT
A in MTEP16 | B>A | West | XEL | 10077 | 2015-09-18 |  | 21537 | 2016-06-15 | TAP | 2016-12-01 | St. James |  |  | 69 |  |  | Install a new three-way switch on line 0714. | MN |  |  | Planned | 390800 |  |  | N | N | N | NT
A in MTEP16 | B>A | West | XEL | 10288 | 2015-10-30 |  | 21550 | 2016-06-15 | SUB | 2018-09-01 | Osprey |  |  | 69 |  |  | Install 69 kV straight bus with 3 x 69 kV breakers | WI |  |  | Planned | 1850000 |  |  | N | N | N | NT
A in MTEP16 | B>A | West | XEL | 10288 | 2015-10-30 |  | 21552 | 2016-06-15 | LN | 2018-09-01 | Osprey | Whitetail Tap |  | 69 |  |  | Reterminate line from Whitetail Tap into Osprey. Rebuild last 0.4 miles of 69 kV line | WI |  |  | Planned | 710000 |  |  | N | N | N | NT
A in MTEP16 | B>A | West | XEL | 10288 | 2015-10-30 |  | 21551 | 2016-06-15 | LN | 2018-09-01 | Osprey | Flambeau |  | 69 |  |  | Reterminate line from DPC Flambeau | WI |  |  | Planned | 320000 |  |  | N | N | N | NT
A in MTEP16 | B>A | West | XEL | 10289 | 2015-10-30 |  | 21553 | 2016-06-15 | LNrb | 2015-12-01 | Elmwood | Comfort | 1 | 69 |  |  | Rebuild the existing 2/0 conductor to 477 ACSR due to age and condition | WI |  |  | Planned | 1109095 |  |  | N | N | N | NT
A in MTEP16 | B>A | West | XEL | 10289 | 2015-10-30 |  | 21554 | 2016-06-15 | LNrb | 2016-12-01 | Comfort | Eau Galle | 1 | 69 |  |  | Rebuild the existing 2/0 conductor to 477 ACSR due to age and condition | WI |  |  | Planned | 1000000 |  |  | N | N | N | NT
A in MTEP16 | B>A | West | XEL | 10290 | 2015-10-30 |  | 21555 | 2016-06-15 | SUB | 2017-08-30 | Gravel Island |  |  | 161 | 12.5 |  | Install a 28 MVA distribution TR and associated breaker and bus work | WI |  |  | Planned | 2983000 |  |  | N | N | N | NT
A in MTEP16 | B>A | West | XEL | 10291 | 2015-10-30 |  | 21556 | 2016-06-15 | SUB | 2018-12-01 | Stasik | LCO Hydro |  | 34.5 | 23.9 |  | Install single 34.5/23.9 kV TR to connect the Lac Courte Oreilles (LCO) hydro facility to the NCP system near Radisson | WI |  |  | Planned | 180000 |  |  | N | N | N | NT
A in MTEP16 | B>A | West | XEL | 11883 | 2016-08-31 |  | 21848 | 2016-09-20 | LN | 2022-01-01 | Huntley | Wilmarth |  | 345 |  |  | 38.5 miles of 345 kV Single Ckt | MN |  | 38.5 | M2a_Pre-Project Approval | 103056574 |  | Generator | N | Y | Y | Y
A in MTEP16 | B>A | West | XEL | 11883 | 2016-08-31 |  | 21853 | 2016-09-20 | SUBmisc | 2022-01-01 | Wilmarth |  |  | 345 |  |  | Substation modifications at Wilmarth | MN |  |  | M2a_Pre-Project Approval | 2471713 |  | Generator | N | Y | Y | Y
B in MTEP16 | B | Central | AmerenIL | 9719 | 2016-09-15 |  | 21100 | 2015-09-11 | SUB | 2018-06-01 | Cahokia |  |  | 138 | 138 | 717 | Upgrade Bus-Tie 3-4 capability to 3000 A. | IL |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 9723 | 2015-12-14 |  | 21107 | 2015-09-11 | SUB | 2018-12-31 | Fishhook |  |  | 138 | 138 | 240 | Construct 138 kV breaker station in East Quincy-Meredosia-2 138 kV lline. | IL |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 9724 | 2016-09-15 |  | 21108 | 2016-05-23 | SUB | 2018-06-01 | Newton |  |  | 345 | 138 | 450 | Relocate Newton 345/138 kV Transformer #1 connection point. | IL |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 9729 | 2015-09-11 |  | 21113 | 2015-09-11 | LNrc | 2019-06-01 | North Decatur | Clinton Rt. 54 | 1 | 138 | 138 | 240 | Reconductor to 1200 A summer emergency capability. | IL | 5.4 |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 9734 | 2015-09-11 |  | 21119 | 2015-09-11 | SUB | 2019-06-01 | North Utica |  |  | 138 | 34.5 | 255 | Construct 138 kV breaker station in North LaSalle-Fox River-1646 138 kV line. | IL |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 9738 | 2016-09-16 |  | 21125 | 2016-09-16 | LNrc | 2025-06-01 | Grand Tower | Carbondale, Northwest | 1 | 138 | 138 | 240 | Reconductor to 1200 A summer emergency capability. | IL | 16.66 |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 9739 | 2016-09-16 |  | 21126 | 2016-09-16 | LNrc | 2025-06-01 | Carbondale, Northwest | West Frankfort | 1 | 138 | 138 | 240 | Reconductor to 1200 A summer emergency capability. | IL | 3.18 |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 9740 | 2016-09-16 |  | 21127 | 2016-09-16 | LNrc | 2025-06-01 | Grand Tower | Campbell Hill | 1 | 138 | 138 | 240 | Reconductor to 1200 A summer emergency capability. | IL | 7.94 |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 9743 | 2015-09-11 |  | 21130 | 2016-05-23 | LNrc | 2021-06-01 | Pana, North | Route 51D | 1 | 138 | 138 | 399 | Reconductor to 2000 A summer emergency capability | IL | 1.43 |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 9745 | 2016-09-15 |  | 21132 | 2015-09-11 | TX | 2018-06-01 | Ramsey |  |  | 345 | 138 | 560 | Replace existing 345/138 kV Transformer | IL |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 9746 | 2016-09-15 |  | 21133 | 2016-03-18 | LNrc | 2018-06-01 | Midway | Schram City | 1 | 138 | 138 | 240 | Reconductor to 1200 A summer emergency capability | IL | 5.19 |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 9826 | 2016-09-15 |  | 21201 | 2015-09-14 | TX | 2018-06-01 | Neoga |  |  | 345 | 138 | 560 | Install 2nd. 345/138 kV Transformer | IL |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 9832 | 2015-09-14 |  | 21208 | 2015-09-14 | LNrc | 2027-06-01 | Casey | Kansas | 1 | 345 | 345 | 1793 | Reconductor to 3000 A summer emergency capability. | IL | 21.16 |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 9838 | 2015-09-14 |  | 21215 | 2016-03-03 | TEQ | 2022-06-01 | Kincaid | Austin | 1 | 345 | 345 | 1195 | Upgrade terminal equipment to minimum 2600 A summer emergency capability | IL |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 9840 | 2015-09-14 |  | 21216 | 2015-09-14 | SUB | 2020-05-01 | Washington Street |  |  | 138 | 138 | 478 | Establish 138 kV ring bus | IL |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 9841 | 2015-09-14 |  | 21217 | 2015-09-14 | TX | 2019-05-01 | South Bloomington |  |  | 138 | 34.5 | 112 | Install 138-34.5 kV transformer | IL |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 9842 | 2015-09-14 |  | 21219 | 2015-09-14 | TX | 2020-05-01 | Normal East |  |  | 138 | 69 | 112 | Install 138-69 kV transformer | IL |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 9843 | 2015-09-14 |  | 21220 | 2015-09-14 | TX | 2019-05-01 | Normal East |  |  | 138 | 34.5 | 112 | Install 138-34.5 kV transformer. | IL |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 9844 | 2015-09-14 |  | 21221 | 2015-09-14 | LN | 2020-05-01 | Normal East | McLean | 1 | 138 | 138 | 399 | Construct 138 kV Line | IL |  | 10 | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 9851 | 2015-09-14 |  | 21228 | 2015-09-14 | LNrc | 2019-06-01 | Edwards | Kewanee | 1 | 138 | 138 | 190 | Reconductor Ameren portion to 1200 A summer emergency capability | IL | 1.51 |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 9857 | 2016-09-13 | AMRN51 | 21234 | 2015-09-14 | SUB | 2019-06-01 | Liberty |  |  | 345 | 138 | 560 | Establish 345/138 kV Substation. Connect to Prairie State-Stallings 345 kV line | IL |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 9857 | 2016-09-13 | AMRN51 | 21237 | 2015-09-14 | LNrb | 2019-06-01 | Liberty | E. Collinsville | 1 | 138 | 138 | 269 | Connect 138 kV outlet from Liberty Sub to E. Collinsville-Porter Road-1432 138 kV line. | IL |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 9857 | 2016-09-13 | AMRN51 | 21236 | 2015-09-14 | LN | 2019-06-01 | Liberty | Highland | 1 | 138 | 138 | 269 | Rebuild radial 138 kV line from Liberty Sub to Highland, IL | IL |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 9857 | 2016-09-13 | AMRN51 | 21235 | 2015-09-14 | LN | 2019-06-01 | Liberty | Canteen | 1 | 138 | 138 | 399 | Construct 138 kV line from new Liberty Substation. | IL |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 10883 | 2016-09-07 |  | 21679 | 2016-09-06 | TEQ | 2019-06-01 | Ina | Benton, NW | 1 | 138 | 138 | 159 | Install 2000 A, 138 kV PCB at Ina terminal | IL |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 10883 | 2016-09-07 |  | 21680 | 2016-09-06 | TEQ | 2019-06-01 | Ina | Mt. Vernon | 1 | 138 |  | 159 | Remove metering set | IL |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 10885 | 2016-09-15 |  | 21683 | 2016-03-11 | TEQ | 2018-06-01 | Cahokia |  |  | 138 |  | 240 | Upgrade terminal equipment | IL |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 10885 | 2016-09-15 |  | 21684 | 2016-03-11 | TEQ | 2018-06-01 | Ridge |  |  | 138 |  | 240 | Upgrade terminal equipment | IL |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenIL | 10886 | 2016-09-06 |  | 21685 | 2016-09-06 | LNrc | 2018-06-01 | Centerville | Belleville 17th Street | 1 | 138 |  | 240 | Reconductor to 1200 A summer emergency capability. | IL |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenMO | 3020 | 2016-09-15 | AMRN49 | 5230 | 2015-09-11 | TEQ | 2018-06-01 | Overton | Columbia | 1 | 161 |  | 250 | Overton-Huntsdale-Columbia 161 kV - Upgrade terminal equipment. | MO |  |  | Proposed |  |  |  | N | N | N | Y
B in MTEP16 | B | Central | AmerenMO | 3020 | 2016-09-15 | AMRN49 | 21098 | 2015-09-11 | SUB | 2018-06-01 | Overton |  |  | 161 | 161 | 557 | Replace bus-tie breaker at Overton. | MO |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenMO | 3020 | 2016-09-15 | AMRN49 | 21097 | 2015-09-11 | TEQ | 2018-06-01 | Overton | Loy Martin | 1 | 161 | 161 | 250 | Upgrade terminal equipment at Overton. | MO |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenMO | 3020 | 2016-09-15 | AMRN49 | 21096 | 2015-09-11 | TEQ | 2018-06-01 | Overton | Moberly | 1 | 161 | 161 | 223 | Upgrade terminal equipment at Overton | MO |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenMO | 9717 | 2016-05-23 |  | 21099 | 2016-05-23 | TEQ | 2040-06-01 | Moberly | Thomas Hill | 1 | 161 | 161 | 314 | Upgrade terminal equipment at Moberly Substation. | MO |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenMO | 9721 | 2015-10-14 | AMRN46 | 21104 | 2015-10-14 | LNrc | 2020-06-01 | Tegeler | Franklin | 1 | 138 | 138 | 240 | Reconductor to 1200 A summer emergency capability | MO | 18.25 |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenMO | 9721 | 2015-10-14 | AMRN46 | 21105 | 2015-10-14 | LNrc | 2020-06-01 | Bland | Tegeler | 1 | 138 | 138 | 240 | Reconductor to 1200 A summer emergency capability | MO | 16.75 |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenMO | 9728 | 2015-09-11 |  | 21112 | 2015-09-11 | TEQ | 2018-11-15 | Adair | Appanoose | 1 | 161 | 161 | 251 | Upgrade terminal equipment | MO |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenMO | 9730 | 2016-02-29 |  | 21114 | 2016-09-13 | SUB | 2019-12-01 | Gray | Wildwood | 1 | 138 | 138 | 240 | Replace overstressed breaker at Gray Summit | MO |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenMO | 9731 | 2016-02-29 |  | 21115 | 2016-09-13 | SUB | 2019-06-01 | Marshall |  |  | 138 | 138 | 478 | Replace overstressed Bus 3-4 tie breaker | MO |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenMO | 9732 | 2016-05-20 |  | 21116 | 2016-09-13 | SUB | 2021-12-01 | Mason |  |  | 138 | 138 | 717 | Replace overstressed Bus 1-2 tie breaker | MO |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenMO | 9733 | 2016-05-23 | AMRN47 | 21117 | 2016-09-13 | SUB | 2021-12-01 | Page | Warson | 5 | 138 | 138 | 399 | Replace overstressed breaker at Page. | MO |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenMO | 9733 | 2016-05-23 | AMRN47 | 21118 | 2016-09-13 | SUB | 2021-12-01 | Page | Berkeley | 1 | 138 | 138 | 240 | Replace overstressed breaker at Page. | MO |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenMO | 9735 | 2016-05-23 | AMRN48 | 21120 | 2016-09-13 | SUB | 2021-12-01 | Tyson | Marshall | 1 | 138 | 138 | 399 | Replace overstressed breaker at Tyson | MO |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenMO | 9735 | 2016-05-23 | AMRN48 | 21122 | 2016-09-13 | SUB | 2021-12-01 | Tyson | Arnold | 3 | 138 | 138 | 240 | Replace overstressed breaker at Tyson | MO |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenMO | 9735 | 2016-05-23 | AMRN48 | 21121 | 2016-09-13 | SUB | 2021-12-01 | Tyson | Marshall | 2 | 138 | 138 | 399 | Replace overstressed breaker at Tyson. | MO |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenMO | 9824 | 2016-09-15 |  | 21198 | 2016-09-27 | TEQ | 2017-06-01 | Huster | Sioux | 3 | 138 | 138 | 241 | Upgrade terminal equipment at Huster on Sioux-Huster-3. | MO |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenMO | 9825 | 2015-09-14 |  | 21200 | 2015-09-14 | TEQ | 2021-06-01 | Tegeler | Osage | 1 | 138 | 138 | 128 | Upgrade terminal equipment at Osage. | MO |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenMO | 9828 | 2015-09-14 | AMRN50 | 21202 | 2015-09-14 | LNup | 2022-06-01 | Joachim | St. Francois | 2 | 138 | 138 | 210 | Increase ground clearance | MO | 18.79 |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenMO | 9828 | 2015-09-14 | AMRN50 | 21203 | 2015-09-14 | LNup | 2022-06-01 | Boyd Branch | St. Francois | 1 | 138 | 138 | 212 | Increase ground clearance | MO | 7.07 |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | AmerenMO | 9830 | 2016-05-23 |  | 21206 | 2016-05-23 | LNrc | 2022-06-01 | Meramec | Joachim | 2 | 138 | 138 | 322 | Reconductor to 1600 A summer emergency capability. | MO | 15.91 |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | IPL | 10786 | 2016-02-18 |  | 21666 | 2016-02-18 | SUB | 2017-12-31 | Stout Substation |  |  | 138 | 13.8 |  | Stout Battery Energy Storage System interconnection at the existing Stout 138 kV Substation. Connected through existing 13.8 kV Bus/Breaker and existing 138/13.8 kV step-up transformer. | IN |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | Central | IPL | 10786 | 2016-02-18 |  | 21721 | 2016-05-02 | RLY | 2017-12-31 | Lilly South |  |  | 138 |  |  | Change relay tap settings at Lilly South to increase Lilly South-Southwest ckt 10 line rating to 345 MVA. Line rating increase due to MISO J401 NRIS Constraint mitigation on the Lilly South-Southwest ckt 10 line. | IN |  |  | Proposed | 4000 | Planning |  | N | N | N
B in MTEP16 | B | Central | PPI | 9563 | 2016-08-12 | 2016-13 | 20928 | 2015-09-01 | LN | 2017-12-01 | 4TUSCOLA W (348350) | 4CRONUS W | 1 | 138 |  | 229 | 2.7 mile 138 kV transmission line | IL |  | 2.7 | Proposed | 1620000 | Budgetary |  | N | N | N | Y
B in MTEP16 | B | Central | PPI | 9563 | 2016-08-12 | 2016-13 | 20929 | 2015-09-01 | LN | 2017-12-01 | 4TUSCOLA W (348350) | 4CRONUS E | 1 | 138 |  | 229 | 3.3 mile 138 kV transmission line | IL |  | 3.3 | Proposed | 1980000 | Budgetary |  | N | N | N | Y
B in MTEP16 | B | Central | Vectren | 9943 | 2016-05-18 | 2016SIGE14 | 21387 | 2016-05-18 | TX | 2023-12-31 | LEONARD ROAD |  |  | 138 | 69 |  | 138/69kV transformer addition at existing Leonard Road switching station | IN |  |  | Proposed | 3000000 | Budgetary |  | N | N | N
B in MTEP16 | B | Central | Vectren | 9943 | 2016-05-18 | 2016SIGE14 | 21388 | 2016-05-18 | LN | 2023-12-31 | AB BROWN | FARM BUREAU | Z94 | 138 |  |  | Z94 138kV line loop from AB Brown Sub to Farm Bureau Sub for load growth | IN |  |  | Proposed | 100000 | Budgetary |  | N | N | N
B in MTEP16 | B | Central | Vectren | 9950 | 2016-08-25 | 2016SIGE15 | 21397 | 2016-08-29 | LNrb | 2018-12-31 | New Harmony | Northwest | Y76 | 69 |  |  | Rebuild of 19 miles of Y76 69kV line from New Harmony sub to Northwest sub | IN |  |  | Planned | 10000000 | Budgetary |  | N | N | N | NT
B in MTEP16 | B | Central | Vectren | 9953 | 2016-05-18 | 2016SIGE16 | 21404 | 2016-05-18 | Dist | 2020-12-31 | FRANCISCO | TOYOTA | Z76 | 138 | 12 |  | New 138kV/12kV distribution substation | IN |  |  | Proposed | 2500000 | Budgetary |  | N | N | N
B in MTEP16 | B | East | CETO | 9879 | 2015-09-14 |  | 21264 | 2016-05-04 | LN | 2019-06-01 | Moore Road | Vrooman | 1 | 138 |  |  | Construct a new approximately 22 mile 138 kV line between Moore Road and Vrooman Substations, utilizing existing 46 kV line route. | MI |  | 22 | Proposed | 20600000 | Budgetary |  | N | N | N
B in MTEP16 | B | East | CETO | 9879 | 2015-09-14 |  | 21266 | 2016-05-04 | SUB | 2019-06-01 | Vrooman |  |  | 138 |  |  | Add a 138 kV circuit breaker to the existing ring bus and install other supporting terminal equipment for the Moore Road-Vrooman 138 kV Line. | MI |  |  | Proposed | 700000 | Budgetary |  | N | N | N
B in MTEP16 | B | East | CETO | 9879 | 2015-09-14 |  | 21265 | 2016-05-04 | SUB | 2019-06-01 | Moore Road |  |  | 138 |  |  | Add a 138 kV circuit breaker to the existing ring bus and install other supporting terminal equipment for the Moore Road-Vrooman 138 kV Line. | MI |  |  | Proposed | 700000 | Budgetary |  | N | N | N
B in MTEP16 | B | East | ITCT | 9864 |  |  | 21249 |  | LNrb | 2018-06-30 | Whiting | Custer |  | 120 |  |  | Rebuild 1.26 miles of 636 ACSR from the ITCT portion of the Whiting – Custer 120 kV circuit using 1431 ACSR and OPGW on new 230 kV future double circuit structures | MI |  |  | Proposed | 3196500 | Engineering |  |  | N | N | Y
B in MTEP16 | B | East | ITCT | 9885 | 2016-09-30 | ITC_15_017 | 21273 | 2015-10-01 | LNup | 2019-12-31 | Jewell | St.Clair | 1 | 345 |  |  | Raise the Sag Limit on Jewell-St.Clair 345 kV to 1965 MVA (3288 Amp) | MI |  |  | Proposed | 5380000 | Engineering |  | N | N | N | Y
B in MTEP16 | B | East | ITCT | 9909 | 2015-09-15 |  | 21317 | 2015-11-24 | LN | 2018-12-31 | Trenton Channel | Jefferson | 4 | 120 |  |  | Six-wiring the Trenton Channel - Jefferson #4 120 kV line with the decommissioned circuit on the other side of its common structures | MI |  |  | Proposed | 104000 | Engineering |  | N | N | N
B in MTEP16 | B | East | ITCT | 9909 | 2015-09-15 |  | 21328 | 2015-11-24 | SUB | 2018-12-31 | Riverview |  |  | 120 |  |  | Upgrade station equipment at position "HD" | MI |  |  | Proposed | 142000 | Engineering |  | N | N | N
B in MTEP16 | B | East | ITCT | 9909 | 2015-09-15 |  | 21326 | 2015-11-24 | SUB | 2018-12-31 | Jefferson |  |  | 120 |  |  | Install a 120 kV bus-tie breaker and upgrade station equipment | MI |  |  | Proposed | 1450000 | Engineering |  | N | N | N
B in MTEP16 | B | East | ITCT | 9909 | 2015-09-15 |  | 21325 | 2015-11-24 | SUB | 2018-12-31 | Horn |  |  | 120 |  |  | Upgrade station equipment | MI |  |  | Proposed | 65500 | Engineering |  | N | N | N
B in MTEP16 | B | East | ITCT | 9909 | 2015-09-15 |  | 21323 | 2015-11-24 | SUB | 2018-12-31 | Trenton Channel |  |  | 120 |  |  | Upgrade station equipment at position "JG" and "HG" | MI |  |  | Proposed | 328000 | Engineering |  | N | N | N
B in MTEP16 | B | East | ITCT | 9909 | 2015-09-15 |  | 21321 | 2015-11-24 | LN | 2018-12-31 | Jefferson | Riverview | 2 | 120 |  |  | Rebuild approximately 0.2 mile of 954 ACSR conductor to 1431 ACSR to match with the rest of the circuit | MI | 0.2 |  | Proposed | 102500 | Engineering |  | N | N | N
B in MTEP16 | B | East | ITCT | 9909 | 2015-09-15 |  | 21320 | 2015-11-24 | LN | 2018-12-31 | Horn | Jefferson | 1 | 120 |  |  | Six-wiring the Horn - Jefferson 120 kV line with the decommissioned circuit on the other side of its common structures and construct two spans of new double-circuit 954 ACSR and six-wire it to complete the loop in-and-out of Horn toward Jefferson | MI |  | 0.16 | Proposed | 104000 | Engineering |  | N | N | N
B in MTEP16 | B | East | ITCT | 9909 | 2015-09-15 |  | 21319 | 2015-11-24 | LN | 2018-12-31 | Trenton Channel | Horn | 1 | 120 |  |  | Six-wiring the Trenton Channel - Horn 120 kV line with the decommissioned circuit on the other side of its common structures | MI |  |  | Proposed | 104000 | Engineering |  | N | N | N
B in MTEP16 | B | East | METC | 9864 |  |  | 21248 |  | LNrb | 2018-06-30 | Whiting | Custer |  | 120 |  |  | Rebuild 7.87 miles of 636 ACSR from the METC portion of the Whiting – Custer 120 kV circuit using 1431 ACSR and OPGW on new 230 kV future double circuit structures | MI |  |  | Proposed | 11096500 | Engineering |  |  | N | N | Y
B in MTEP16 | B | East | METC | 9864 |  |  | 21250 |  | TEQ | 2018-06-30 | Whiting |  |  | 120 |  |  | Replace limiting terminal equipment at the Whiting station | MI |  |  | Proposed | 2000 | Engineering |  |  | N | N | Y
B in MTEP16 | B | East | METC | 9864 |  |  | 21257 |  | TEQ | 2018-06-30 | Custer |  |  | 120 |  |  | Replace limiting terminal equipment at the Custer station | MI |  |  | Proposed | 5000 | Engineering |  |  | N | N | Y
B in MTEP16 | B | East | METC | 9880 | 2016-09-30 | METC_15_025 | 21267 | 2015-11-24 | LNup | 2018-12-31 | Claremont | Manning | 1 | 138 |  |  | Remediate the sag limit on the Portsmouth Tap – Manning 138 kV section of the Claremont – Manning 1 138 kV line to a minimum of 378 MVA / 1581 Amps and remediate the sag limit on the Claremont – Portsmouth Tap 138 kV section of the Claremont – Manning 1 138 kV line to a minimum of 362 MVA / 1514 Amps | MI |  |  | Proposed |  |  |  | N | N | N | Y
B in MTEP16 | B | East | METC | 9880 | 2016-09-30 | METC_15_025 | 21268 | 2015-11-24 | TEQ | 2018-12-31 | Claremont |  |  | 138 |  |  | Upgrade terminal equipment at Claremont | MI |  |  | Proposed | 330000 | Engineering |  | N | N | N | Y
B in MTEP16 | B | East | METC | 9881 | 2016-09-30 | METC_15_026 | 21269 | 2015-11-24 | LNup | 2018-12-31 | Claremont | Manning | 2 | 138 |  |  | Remediate the sag limit on the Claremont – Manning 2 138 kV line to a minimum of 369 MVA / 1544 Amps | MI |  |  | Proposed | 1040000 | Engineering |  | N | N | N | Y
B in MTEP16 | B | East | METC | 9881 | 2016-09-30 | METC_15_026 | 21270 | 2015-11-24 | TEQ | 2018-12-31 | Claremont |  |  | 138 |  |  | Upgrade terminal equipment at Claremont | MI |  |  | Proposed | 360000 | Engineering |  | N | N | N | Y
B in MTEP16 | B | East | METC | 9929 | 2016-09-30 | METC_15_29 | 21339 | 2015-12-04 | LN | 2019-12-31 | Donaldson Creek | Pere Marquette | 1 | 138 |  |  | Build new ~21 mile circuit from Donaldson Creek to Pere Marquette using 954 ACSR and OPGW | MI |  |  | Proposed | 7400000 | Engineering |  | N | N | N | Y
B in MTEP16 | B | East | METC | 9929 | 2016-09-30 | METC_15_29 | 21341 | 2015-12-04 | TEQ | 2019-12-31 | Pere Marquette |  |  | 138 |  |  | Upgrade terminal equipment at Pere Marquette | MI |  |  | Proposed | 760000 | Engineering |  | N | N | N | Y
B in MTEP16 | B | East | METC | 9929 | 2016-09-30 | METC_15_29 | 21340 | 2015-12-04 | TEQ | 2019-12-31 | Donaldson Creek |  |  | 138 |  |  | Upgrade terminal equipment at Donaldson Creek | MI |  |  | Proposed | 540000 | Engineering |  | N | N | N | Y
B in MTEP16 | B | East | WPSC | 9895 | 2015-11-23 | GRX-CT | 21290 | 2016-09-15 | LNrb | 2022-12-31 | Graves Crossing | Central Lake | 1 | 69 |  | 75.2 | Rebuild the Graves Crossing to Central Lake 69kV line, install new poles and hardware with 336ACSR conductor | MI | 7.9 |  | Proposed | 3200000 | Budgetary |  | N | N | N
B in MTEP16 | B | East | WPSC | 9903 | 2016-09-15 | WC-RG Rebuild | 21309 | 2015-09-15 | LNrb | 2020-12-31 | White Cloud | Wrights Creek | 1 | 69 |  | 143.4 | Rebuild the White Cloud to Rogers 69kV line, install new poles and hardware with 795ACSS conductor | MI | 14.36 |  | Proposed | 7200000 | Budgetary |  | N | N | N
B in MTEP16 | B | East | WPSC | 9903 | 2016-09-15 | WC-RG Rebuild | 21312 | 2016-09-15 | LNrb | 2020-12-31 | Hesperia | Rogers | 1 | 69 |  |  | Rebuild the White Cloud to Rogers 69kV line, install new poles and hardware with 795ACSS conductor | MI | 13.96 |  | Proposed | 7200000 | Budgetary |  | N | N | N
B in MTEP16 | B | East | WPSC | 9903 | 2016-09-15 | WC-RG Rebuild | 21310 | 2016-09-15 | LNrb | 2020-12-31 | Wrights Creek | Hesperia | 1 | 69 |  |  | Rebuild the White Cloud to Rogers 69kV line, install new poles and hardware with 795ACSS conductor | MI | 7.68 |  | Proposed | 4100000 | Budgetary |  | N | N | N
B in MTEP16 | B | East | WPSC | 9916 | 2015-09-15 | Fairview Station Upgrade | 21330 | 2016-09-15 | SwSta | 2022-12-31 | Fairview |  |  | 69 |  |  | Upgrade equipment at the Fairview station | MI |  |  | Proposed | 900000 | Budgetary |  | N | N | N
B in MTEP16 | B | East | WPSC | 9920 | 2015-09-15 | GRX Station Upgrade | 21333 | 2015-09-15 | SwSta | 2020-12-31 | Gravese Crossing |  |  | 69 |  |  | Upgrade the Graves Crossing station | MI |  |  | Proposed | 500000 | Budgetary |  | N | N | N
B in MTEP16 | B | East | WPSC | 10264 | 2015-10-28 | Pellston to Cross Village | 21507 | 2016-09-15 | LNrb | 2022-12-31 | Pellston | Cross Village |  | 138 |  |  | Pellston to Cross Village line rebuild | MI | 9.08 |  | Proposed | 3600000 | Budgetary |  | N | N | N
B in MTEP16 | B | East | WPSC | 10265 | 2015-10-28 |  | 21508 | 2015-10-28 | RLY | 2019-12-31 | Gaylord |  |  | 138 |  |  | Gaylord relay replacement - 138kV Livingston line | MI |  |  | Proposed | 35000 | Budgetary |  | N | N | N
B in MTEP16 | B | East | WPSC | 10266 | 2016-09-15 |  | 21509 | 2016-09-15 | SwSta | 2019-12-31 | East Jordan |  |  | 69 |  |  | East Jordan Station Rebuild | MI |  |  | Proposed | 350000 | Budgetary |  | N | N | N
B in MTEP16 | B | East | WPSC | 10267 | 2016-09-15 |  | 21510 | 2016-09-15 | SwSta | 2019-12-31 | Black Lake |  |  | 69 |  |  | Black Lake Station Rebuild | MI |  |  | Proposed | 350000 | Budgetary |  | N | N | N
B in MTEP16 | B | South | AECC | 10203 | 2015-10-12 |  | 21489 | 2015-11-12 | SwSta |  | AECC Sardis |  |  | 115 |  |  | 4 position ring bus | AR |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | South | AECC | 10203 | 2015-10-12 |  | 21490 | 2015-11-12 | LN |  | AECC Shaw | AECC Sardis |  | 115 |  |  | 12 mile 115kV transmission line | AR |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | South | AECC | 10207 | 2016-07-01 |  | 21498 | 2016-05-06 | SwSta | 2021-06-01 | Heber Springs North |  |  | 161 |  |  | Build 5 position ring bus at the existing AECC Heber Springs North substation | AR |  |  | Proposed | 5000000 | Planning Preliminary |  | N | N | N | Y
B in MTEP16 | B | South | AECC | 10207 | 2016-07-01 |  | 21499 | 2016-05-06 | LN | 2021-06-01 | Heber Spriongs North | Partain | 1 | 161 |  |  | Build 26 mile 161kV line form the existing AECC Heber Springs North substation to the proposed 161/69kV Partain substaiton | AR |  |  | Proposed | 18000000 | Planning Preliminary |  | N | N | N | Y
B in MTEP16 | B | South | CLECO | 9718 | 2015-09-11 |  | 21101 | 2015-09-11 | SUB |  | Ashmore Rd. |  |  | 230 |  |  | Build a new 230 kV substation Tapped into the Hineston to Cocodrie 230 kV line 24 miles from Cocodrie | LA |  |  | Proposed | 7000000 | Planning Preliminary |  | N | N | N
B in MTEP16 | B | South | CLECO | 9718 | 2015-09-11 |  | 21102 | 2015-09-11 | LN |  | Ashmore Rd. | Rork | 1 | 230 |  |  | Build a new 64 mile 230 kV line from Ashmore Rd. to Rork routed through Oakdale, Kinder and Basile areas. | LA |  | 64 | Proposed | 108000000 | Planning Preliminary |  | N | N | N
B in MTEP16 | B | South | Entergy-AR | 9694 | 2016-05-12 | 16-EAI-003 | 21018 | 2016-05-12 | LNrb | 2024-06-01 | Camden Maguire 115kV | Smackover 115kV |  | 115 |  |  | The 14.32 mile long line will be upgraded to a minimum rating of 176 MVA (882 Amps). | AR | 14.32 |  | Proposed | 20706029 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-AR | 9699 | 2016-09-15 | 16-EAI-005 | 21023 | 2016-09-15 | CAP | 2019-06-01 | El Dorado Donan 115kV |  |  | 115 |  |  | Add one 30 MVAR capacitor bank at El Dorado Donan 115 kV substation | AR |  |  | Proposed | 871182 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-AR | 9700 | 2016-09-14 | 16-EAI-015 | 21024 | 2016-09-14 | LNrb | 2022-06-01 | Blakely 115kV | Mt. Pine South 115kV |  | 115 |  |  | Re-build the 2.92 mile long 115 kV line to a minimum line rating of 259 MVA (1300 Amps) | AR | 2.92 |  | Proposed | 3972886 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-AR | 9701 | 2016-09-14 | 16_EAI-010 | 21025 | 2016-09-15 | LNrb | 2020-06-01 | LynchWest 115kV | NLR Galloway 115kV |  | 115 |  |  | Upgrade 4.12mi Lynch – NLR Galloway line to a minimum rating of 259 MVA (1300 Amps). | AR | 4.12 |  | Proposed | 4785896 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-AR | 9702 | 2016-09-14 | 16-EAI-016 | 21026 | 2016-09-15 | TEQ | 2018-06-01 | Sylvan Hills115kV | Jacksonville North 115kV |  | 115 |  |  | Upgrade line bay bus at Sylvan Hills. | AR |  |  | Proposed | 26626 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-AR | 9710 | 2015-09-10 | 16-EAI-013 | 21043 | 2015-09-10 | SUB | 2025-06-01 | Little Rock South 115kV |  |  | 115 |  |  | Reconfigure Little Rock South 115 kV station configuration into a double bus double breaker, breaker and a half, or a ring bus configuration. Configuration will be determined during project scoping. | AR |  |  | Proposed | 5463000 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-AR | 10163 | 2015-10-06 |  | 21483 | 2015-10-06 | Dist | 2017-03-01 | Jonesboro North |  |  | 161 | 13.2 | 40 | CECC is adding a second 161 to 13.2 kV transformer due to normal load growth. | AR |  |  | Proposed | 800000 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-LA | 4611 | 2016-09-14 | 16-EGL-024 | 8761 | 2015-09-13 | SUB | 2026-06-01 | Waddill 230 kV substation |  |  | 230 |  | 200 MVA | Construct new substation | LA |  |  | Proposed | 15859000 | Planning |  | N | N | N | Y
B in MTEP16 | B | South | Entergy-LA | 4611 | 2016-09-14 | 16-EGL-024 | 8763 | 2015-09-13 | TX | 2026-06-01 | Waddill 230 kV substation | Waddill 69 kV substation | 1 | 230 | 69 | 200 MVA | Install transformer | LA |  |  | Proposed |  |  |  | N | N | N | Y
B in MTEP16 | B | South | Entergy-LA | 4611 | 2016-09-14 | 16-EGL-024 | 8762 | 2015-09-13 | SUB | 2026-06-01 | Waddill 69 kV substation |  |  | 69 |  | 200 MVA | Construct new substation | LA |  |  | Proposed |  |  |  | N | N | N | Y
B in MTEP16 | B | South | Entergy-LA | 7970 | 2015-09-10 | 15-ELL-002 | 20247 | 2015-11-30 | SUB | 2026-06-01 | (New) MINDEN EAST 115 |  |  | 115 |  |  | Cut Arcadia to Minden REA 115 kV line into New Minden East 115 kV substation. | LA |  |  | Proposed | 9592834 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-LA | 7970 | 2015-09-10 | 15-ELL-002 | 20250 | 2015-09-10 | LNrl | 2026-06-01 | Minden East 115 kV | Ada 115 kV | 1 | 115 |  |  | Cut existing Minden to Sailes into new Minden East 115 kV substation | LA |  |  | Proposed |  | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-LA | 7970 | 2015-09-10 | 15-ELL-002 | 20249 | 2015-09-10 | LNrl | 2026-06-01 | Minden 115 | Minden East 115 | 1 | 115 |  |  | Cut existing Minden to Sailes 115 kV line and route it into new Minden East 115 kV substation | LA |  |  | Proposed |  | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-LA | 9683 | 2016-09-28 | 16-ELN-002 | 20998 | 2016-09-14 | SwSta | 2021-06-01 | Perryville |  |  | 230 |  |  | Perryville 230 kV sub | LA |  |  | Proposed | 78902650 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-LA | 9683 | 2016-09-28 | 16-ELN-002 | 21005 | 2015-09-10 | TX |  | Dunn |  |  | 230 | 115 |  | 230/115 transformer | LA |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | South | Entergy-LA | 9683 | 2016-09-28 | 16-ELN-002 | 21004 | 2015-09-10 | TX |  | Rilla |  |  | 230 | 115 |  | New 230/115 AT | LA |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | South | Entergy-LA | 9683 | 2016-09-28 | 16-ELN-002 | 21003 | 2015-09-10 | TX |  | Selman Field |  |  | 230 | 69 |  | Change out auto from 115/69 to 230/69 | LA |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | South | Entergy-LA | 9683 | 2016-09-28 | 16-ELN-002 | 21002 | 2015-09-10 | LN |  | Selman Field | Rilla | 1 | 230 |  | 640 | Utilizing existing 115 kV Rilla - Selman Field built to 230 kV specifications. | LA |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | South | Entergy-LA | 9683 | 2016-09-28 | 16-ELN-002 | 21001 | 2016-09-14 | LN | 2021-06-01 | Perryville | Selman Field | 1 | 230 |  |  | Utilizing existing 115 kV Sterlington - Selman Field - Rilla 230 kV constructed line. | LA |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | South | Entergy-LA | 9683 | 2016-09-28 | 16-ELN-002 | 21000 | 2016-09-14 | LN | 2021-06-01 | Perryville | Dunn | 1 | 230 |  | 779 | New 230 kV line utilizing existing Swartz - Dunn 115 kV line (constructed to 230 kV specifications) | LA |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | South | Entergy-LA | 9683 | 2016-09-28 | 16-ELN-002 | 20999 | 2016-09-14 | TX | 2021-06-01 | Perryville |  |  | 500 | 230 | 615 | 500/230 autotransformer | LA |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | South | Entergy-LA | 9687 | 2015-09-10 | 16-ELN-006 | 21011 | 2015-09-10 | CB | 2022-06-01 | Minden | Sarepta | 1 | 115 |  | 176 | Upgrade 800A circuit breaker | LA |  |  | Proposed | 553129 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-LA | 9688 | 2016-09-28 | 16-ELN-007 | 21012 | 2016-09-14 | LN | 2020-06-01 | Dunn | Winnsboro | 1 | 115 |  | 390 | New 230 kV line (115 kV energized) | LA |  | 25 | Proposed | 34998093 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-LA | 9689 | 2016-09-28 | 16-ELN-008 | 21013 | 2016-09-14 | Dist | 2020-06-01 | Beekman |  |  | 115 |  |  | New 115 kV distribution substation | LA |  |  | Proposed | 7880989 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-LA | 9764 | 2015-09-13 | 16-EGL-005 | 21138 | 2015-09-13 | LNrc | 2026-06-01 | Dixie Baker | Baker | 1 | 69 |  |  | Upgrade line | LA |  |  | Proposed | 2963000 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-LA | 9766 | 2016-09-28 | 16-EGL-007 | 21140 | 2016-09-14 | LNrc | 2019-06-01 | Gloria | Flannery REA | 1 | 69 |  |  | Upgrade Line | LA |  |  | Proposed | 2020989 |  |  | N | N | N
B in MTEP16 | B | South | Entergy-LA | 9767 | 2015-09-13 | 16-EGL-008 | 21141 | 2015-09-13 | LNrc | 2025-06-01 | Harelson | Line 371 Tap | 1 | 69 |  |  | Upgrade Line | LA |  |  | Proposed | 5143000 |  |  | N | N | N
B in MTEP16 | B | South | Entergy-LA | 9781 | 2015-09-13 | 16-EGL-015 | 21155 | 2016-02-23 | LNrc | 2022-06-01 | Jennings | Lawtag | 1 | 69 |  |  | Upgrade Line | LA |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | South | Entergy-LA | 9784 | 2015-09-13 | 16-EGL-018 | 21158 | 2015-09-13 | LNrc | 2025-06-01 | Ford | Lake | 1 | 69 |  |  | Upgrade Line | LA |  |  | Proposed | 1552000 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-LA | 9789 | 2016-09-28 | 16-EGL-025 | 21163 | 2016-09-14 | TEQ | 2026-06-01 | Port Hudson 230 | Port Hudson 69 | 1 | 230 | 69 |  | Upgrade terminal equipment | LA |  |  | Proposed | 21435 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-LA | 9793 | 2015-09-13 | 16-EGL-031 | 21167 | 2015-09-13 | LNrc | 2023-06-01 | Esso | Delmont | 1 | 230 |  |  | Reconductor line | LA |  |  | Proposed | 2136000 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-LA | 9797 | 2016-09-14 | 16-EGL-036 | 21171 | 2015-09-13 | LNrc | 2023-06-01 | Nelson | Lake Charles | 1 | 138 |  |  | Upgrade line | LA |  |  | Proposed | 11416000 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-LA | 9798 | 2016-09-14 | 16-ELL-001 | 21172 | 2016-09-14 | LNrc | 2020-06-01 | Gypsy | Claytonia | 1 | 115 |  |  | Upgrade line | LA |  |  | Proposed | 7366203 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-LA | 9802 | 2016-09-14 | 16-ell-005 | 21176 | 2015-09-13 | LNrc | 2020-06-01 | Snakefarm | Labarre | 1 | 230 |  |  | Upgrade line | LA |  |  | Proposed | 3834000 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-LA | 9803 | 2016-09-14 | 16-ELL-006 | 21177 | 2016-09-14 | LNrc | 2020-06-01 | Prospect | Goodhope | 1 | 230 |  |  | Upgrade Line | LA |  |  | Proposed | 697815 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-LA | 9804 | 2016-09-14 | 16-ELL-008 | 21178 | 2016-09-14 | LNrc | 2022-06-01 | Avenue C | Paris Tap | 1 | 115 |  |  | Upgrade Line | LA |  |  | Proposed | 220032 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-MS | 7906 | 2016-09-15 | 15-EMI-004 | 20144 | 2016-09-15 | LNrb | 2019-06-01 | Greenwood | Greenwood SS | 1 | 115 |  |  | Upgrade line to 239 MVA | MS | 10.48 |  | Proposed | 13133452 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-MS | 9823 | 2016-09-14 | 16-EMI-002 | 21199 | 2016-09-14 | SwSta | 2020-12-01 | Franklin |  |  | 500 |  |  | Reconfigure Franklin 500 kV substation | MS |  |  | Proposed | 22435508 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-MS | 9829 | 2015-09-14 | 16-EMI-004 | 21205 | 2016-09-14 | CB | 2019-06-01 | Ray Braswell |  |  | 115 |  |  | Replace 2-115 kV breakers | MS |  |  | Proposed | 1153930 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-MS | 9831 | 2016-08-08 | 16-EMI-006 | 21207 | 2016-09-14 | BUS | 2024-06-01 | Tillatoba |  |  | 230 |  |  | Reconfigure bus | MS |  |  | Proposed | 5449089 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-MS | 9837 | 2015-09-14 | 16-EMI-010 | 21213 | 2015-09-14 | LNrb | 2022-06-01 | South Grenada | Elliott | 1 | 115 |  |  | Upgrade 115 kV line | MS | 4.91 |  | Proposed | 4961042 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-TX | 9820 | 2015-09-14 | 16-ETI-019 | 21195 | 2015-09-14 | LNrc | 2020-06-01 | Hearne | Calvert | 1 | 69 |  |  | Upgrade Line | TX |  |  | Proposed | 9500000 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-TX | 9821 | 2015-09-14 | 16-ETI-020 | 21196 | 2015-09-14 | LN | 2024-06-01 | Bryan | College Station Area | 1 | 138 |  |  | New line | TX |  |  | Proposed | 31500000 | Planning |  | N | N | N
B in MTEP16 | B | South | Entergy-TX | 10080 | 2016-05-12 | HCEC_01_MTEP16 | 21452 | 2015-11-12 | SUB |  | 334126 |  |  | 138 |  |  | Magnolia Groveton station upgrades to support addition of new transmission line | TX |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | South | Entergy-TX | 10964 | 2016-04-06 | 16-ETI-022 | 21694 | 2016-03-24 | LN | 2018-06-01 | Hearne | Calvert | 2 | 69 |  |  | Construct a new line from Hearne to Calvert | TX |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | South | ETEC | 10080 | 2016-05-12 | HCEC_01_MTEP16 | 21450 | 2015-11-12 | LN |  | 334126 | TBD | 1 | 138 |  |  | Construct new 138 kV line from existing Magnolia Groveton station to new Weldon station | TX |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | South | ETEC | 10080 | 2016-05-12 | HCEC_01_MTEP16 | 21454 | 2015-11-12 | SUB |  | 509325 |  |  | 138 |  |  | Mustang Prairie station upgrades to support addition of new transmission line | TX |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | South | ETEC | 10080 | 2016-05-12 | HCEC_01_MTEP16 | 21453 | 2015-11-12 | SUB |  | TBD |  |  | 138 |  |  | New Weldon station to support load growth | TX |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | South | ETEC | 10080 | 2016-05-12 | HCEC_01_MTEP16 | 21451 | 2015-11-12 | LN |  | 509325 | TBD | 1 | 138 |  |  | Construct new 138 kV line from existing Mustang Prairie station to new Weldon station | TX |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | South | ETEC | 10081 | 2015-09-18 | SHECO_01_MTEP16 | 21455 | 2015-11-12 | SwSta |  | TBD |  |  | 138 |  |  | New switching station on Dogwood-Warren 138 kV line | TX |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | South | ETEC | 10081 | 2015-09-18 | SHECO_01_MTEP16 | 21459 | 2015-11-12 | SUB |  | 334304 |  |  | 138 |  |  | North Buna station upgrades to support addition of new transmission line | TX |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | South | ETEC | 10081 | 2015-09-18 | SHECO_01_MTEP16 | 21458 | 2015-11-12 | LN |  | 334304 | TBD |  | 138 |  |  | Construct new 138 kV line from the new Fred substation to the existing North Buna substation | TX |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | South | ETEC | 10081 | 2015-09-18 | SHECO_01_MTEP16 | 21457 | 2015-11-12 | SUB |  | TBD |  |  | 138 |  |  | Construct new 138 kV Fred substation | TX |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | South | ETEC | 10081 | 2015-09-18 | SHECO_01_MTEP16 | 21456 | 2015-11-12 | LN |  | TBD | TBD |  | 138 |  |  | Construct new 138 kV line from the new Fred switching station to new Fred substation. | TX |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | South | ETEC | 10082 | 2015-09-18 | SHECO_02_MTEP16 | 21460 | 2015-11-12 | SUB |  | TBD |  |  | 138 |  |  | Construct new 138 kV Fred substation | TX |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | South | ETEC | 10082 | 2015-09-18 | SHECO_02_MTEP16 | 21464 | 2015-11-12 | SUB |  | 334281 |  |  | 138 |  |  | Fork Creek station upgrades to support addition of new transmission line | TX |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | South | ETEC | 10082 | 2015-09-18 | SHECO_02_MTEP16 | 21463 | 2015-11-12 | SUB |  | 334304 |  |  | 138 |  |  | North Buna station upgrades to support addition of new transmission line | TX |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | South | ETEC | 10082 | 2015-09-18 | SHECO_02_MTEP16 | 21462 | 2015-11-12 | LN |  | 334281 | TBD |  | 138 |  |  | Construct new 138 kV line from the new Fred substation to the existing Fork Creek substation | TX |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | South | ETEC | 10082 | 2015-09-18 | SHECO_02_MTEP16 | 21461 | 2015-11-12 | LN |  | 334304 | TBD |  | 138 |  |  | Construct new 138 kV line from the new Fred substation to the existing North Buna substation | TX |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | West | ATC | 8443 | 2016-02-01 |  | 20671 | 2015-10-09 | TX | 2017-12-31 | Arnott |  | 1 | 345 | 115 | 500 | Replace the Rocky Run 345/115 kV T1 transformer with a 500 MVA unit | WI |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | West | ATC | 8443 | 2016-02-01 |  | 21488 | 2015-10-09 | TX | 2017-12-31 | Arnott |  | 1 | 345 | 115 | 500 | Replace the thee Rocky Run 345-115 kV transformers with two 500 MVA units. | WI |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | West | ATC | 8443 | 2016-02-01 |  | 21487 | 2016-01-26 | TX | 2017-12-31 | Arnott |  | 1 | 345 | 115 | 500 | Replace the thee Rocky Run 345-115 kV transformers with two 500 MVA units. | WI |  |  | Proposed | 22000000 |  |  | N | N | N
B in MTEP16 | B | West | ATC | 9925 | 2015-10-05 |  | 21337 | 2016-01-26 | SUB | 2018-06-01 | Pershing |  |  | 345 |  |  | Loop Stone Lake - Gardner Park 345-kV line into new Pershing 345-kV Substation. | WI |  |  | Planned | 15000000 |  |  | N | N | N | Y
B in MTEP16 | B | West | ATC | 9928 | 2015-09-15 | PR07179 | 21342 | 2016-03-30 | LNup | 2017-11-01 | Council Creek | Tomah Industrial | 1 | 69 |  | 48.6 | Re-rate 1.2 miles of 69 kV line between Council Creek and Tomah Industrial Park. | WI | 1.2 |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | West | ATC | 9930 | 2016-09-15 | PR07296, 602003, 602026 | 21343 | 2016-09-15 | LNup | 2018-12-01 | Lost Dauphin | Red Maple | 1 | 138 |  | 246 | Lost Dauphin - Red Maple 138-kV line uprate. | WI |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | West | ATC | 9935 | 2015-09-15 | PR05844 | 21352 | 2015-09-17 | CAP | 2020-06-01 | Wesmark |  | 1 | 69 |  |  | Wesmark Substation: Install 2-8 Mvar 69-kV capacitor banks. | WI |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | West | ATC | 9968 | 2016-09-14 |  | 21383 | 2015-09-15 | LNrb | 2019-12-31 | Portage | Staff | 1 | 138 |  |  | Rebuild 138KV Line X-6 Portage - Staff Substation. | WI |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | West | ATC | 9974 | 2016-09-14 |  | 21391 | 2015-09-15 | LNrb | 2019-12-31 | North Randolph | Staff | 1 | 138 |  |  | Rebuild 138KV Line X-98 Staff - North Randolph Substation. | WI |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | West | ATC | 9991 | 2015-09-15 |  | 21412 | 2015-09-15 | BUS | 2018-12-31 | Racine |  |  | 345 |  |  | Rebuild Racine 345kV Bus. | WI |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | West | ATC | 10486 | 2015-12-16 | PR06461 | 21594 | 2015-12-16 | LNrb | 2021-12-31 | Chafee Creek | ACEC Colma Tap | 1 | 69 |  | 526 | Rebuild line Y-18 Chaffee Creek - Lincoln Pump Station. | WI |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | West | ATC | 10486 | 2015-12-16 | PR06461 | 21595 | 2015-12-16 | LNrb | 2021-12-31 | ACEC Coloma Tap | Lincoln Pump Station | 1 | 69 |  | 526 | Rebuild Chaffee Creek - Lincoln Pump Station 69 kV. | WI |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | West | ATC | 10590 | 2016-08-11 | PR06462 | 21620 | 2016-01-12 | LNrb | 2023-12-31 | Academy | Columbus Tap | 1 | 69 |  | 79 | Rebuild Academy - Columbus 69kV. | WI | 1 |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | West | ATC | 10590 | 2016-08-11 | PR06462 | 21621 | 2016-01-12 | LNrb | 2023-12-31 | Columbus Tap | Columbus | 1 | 69 |  | 79 | Rebuild Academy - Columbus 69kV. | WI | 1.13 |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | West | ATC, XEL | 10183 | 2016-08-18 |  | 21485 | 2016-06-15 | SUB | 2018-06-01 | Pershing |  |  | 345 | 115 |  | New Pershing 345/115 kV substation. | WI |  |  | Proposed | 10000000 |  |  | N | N | N | Y
B in MTEP16 | B | West | GRE | 8920 | 2016-08-11 |  | 20786 | 2016-08-11 | SUB | 2022-09-01 | Elisha |  |  | 115 | 34.5 |  | New Elisha 115/34.5 kV substation using Hubbard transformer | MN |  |  | Proposed | 2400000 | Planning |  | N | N | N | Y
B in MTEP16 | B | West | GRE | 8920 | 2016-08-11 |  | 20789 | 2016-08-11 | LN | 2022-09-01 | Hubbard | Potato Lake | 1 | 115 |  |  | Build new 115 kV line from Hubbard to Elijah to Potato Lake 115 kV line | MN |  | 17.6 | Proposed | 9670000 | Planning |  | N | N | N | Y
B in MTEP16 | B | West | GRE | 8920 | 2016-08-11 |  | 20788 | 2016-08-11 | LN | 2022-09-01 | Elisha | Osage |  | 69 | 34.5 | 190 | Build 69 kV line operated at 34.5 kV from Elisha to Osage | MN |  |  | Proposed | 3312000 | Planning |  | N | N | N | Y
B in MTEP16 | B | West | GRE | 8920 | 2016-08-11 |  | 20787 | 2016-08-11 | TEQ | 2022-09-01 | Osage |  |  | 69 | 34.5 |  | Osage motor operated switch | MN |  |  | Proposed | 435000 | Planning |  | N | N | N | Y
B in MTEP16 | B | West | GRE | 9200 | 2016-08-11 | 203613 | 20831 | 2016-09-15 | LN | 2018-10-19 | Potato Lake Tap | Arago | 1 | 115 |  |  | Build ~7.5 miles of 115 kV transmission line from Potato Lake tap to Arago distribution substation. | MN |  | 7.5 | Proposed | 7344393.37 | Planning |  | N | N | N | Y
B in MTEP16 | B | West | GRE | 9201 | 2016-08-11 | 203610 | 20832 | 2016-09-15 | LN | 2018-10-31 | Bull Moose tap | Backus Pumping Station | 1 | 115 |  |  | Build 115 kV line from a new interconnection to the MP's 115 kV #142 line (Badoura - Pine River) to the Backus Pump Station. | MN |  | 3.5 | Proposed | 2105606.54 | Planning |  | N | N | N | Y
B in MTEP16 | B | West | GRE | 9202 | 2016-08-11 | 203611 | 20833 | 2016-09-15 | SwSta | 2018-10-31 | Rice River |  |  | 115 |  |  | New Rice River substation | MN |  |  | Proposed | 3223525.82 | Planning |  | N | N | N | Y
B in MTEP16 | B | West | GRE | 9202 | 2016-08-11 | 203611 | 20835 | 2016-09-15 | LN | 2018-10-31 | Rice River | Palisade | 1 | 115 |  |  | Build ~13 miles of 115 kV transmission line from the new Rice River switching station to the new Enbridge Palisade Pumping Station. | MN |  | 13 | Proposed | 9835229.37 | Planning |  | N | N | N | Y
B in MTEP16 | B | West | GRE | 9203 | 2016-08-11 | 203612 | 20834 | 2016-09-15 | LN | 2018-10-11 | Cromwell tap | Cromwell Pumping Station | 1 | 115 |  |  | Build 0.2 miles of 115 kV transmission line from Cromwell tap to Cromwell Pumping Station | MN |  | 0.2 | Proposed | 920000 | Planning |  | N | N | N | Y
B in MTEP16 | B | West | ITCM | 9100 | 2015-05-28 | Burlington Area 69kV | 20813 | 2015-05-28 | BUS | 2019-12-19 | Burlington | South Burlington | 1 | 69 |  | 103 MVA | Upgrade terminal equipment above the conductor rating. | IA |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | West | ITCM | 9100 | 2015-05-28 | Burlington Area 69kV | 20814 | 2015-05-28 | LNrb | 2019-12-31 | Burlington 4th Street | Agency | 1 | 69 |  | 101 MVA | Rebuild the 4th Street-Agency 69kV line to T2-477. | IA | 2.51 |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | West | MDU | 9122 | 2015-06-10 |  | 20818 | 2015-06-10 | TEQ | 2020-06-01 | East Bismarck |  |  | 115 |  | 191 | Replace switch 7114, 7115 & 7117 and line jumpers. | ND |  |  | Proposed | 125000 | Engineering Preliminary |  | N | N | N
B in MTEP16 | B | West | MDU | 9140 | 2015-06-12 |  | 20822 | 2015-06-12 | LNrc | 2020-09-01 | Coyote Jct | NACO | 1 | 115 |  | 120 | Reconductor line with 477 ACSS | ND | 7 |  | Proposed | 1270000 | Planning Preliminary |  | N | N | N
B in MTEP16 | B | West | MDU | 9180 | 2015-06-16 |  | 20830 | 2015-06-16 | CAP | 2020-10-01 | Green River Jct |  |  | 115 |  |  | Increase existing 15 Mvar capacitors to 20 Mvar | ND |  |  | Proposed | 400000 | Planning |  | N | N | N
B in MTEP16 | B | West | MEC | 2937 | 2016-07-22 | G0103 | 5112 | 2016-06-07 | TX | 2022-06-01 | Sub 39 | Transformer | 2 | 345 | 161 | 560 | Add 2nd 345-161 kV xfmr | IL |  |  | Proposed | 10900000 | Planning |  | N | N | N | Y
B in MTEP16 | B | West | MEC | 2938 | 2016-07-22 | G0104 | 5113 | 2016-06-07 | LNrb | 2021-12-01 | Sub 39 | Cordova | 1 | 345 |  | 1471 | Uprate 345 kV line structures. Includes reconfiguration outside of Sub 39 to accommodate planned substation expansion. | IL | 15.5 |  | Proposed | 1300000 | Planning |  | N | N | N | Y
B in MTEP16 | B | West | MP | 9642 | 2015-09-08 | 20 Line Bus Relocation | 20954 | 2015-09-08 | LN | 2019-12-31 | 20 Line Tap | Blackberry | 1 | 115 |  |  | Extend 20 Line to an existing, unoccupied line termination on Blackberry 115 kV Bus #1 | MN | 0 | 0.6 | Proposed | 1000000 | Planning |  | N | N | N
B in MTEP16 | B | West | MP | 9642 | 2015-09-08 | 20 Line Bus Relocation | 20955 | 2015-09-08 | CB | 2019-12-31 | Blackberry |  |  | 115 |  |  | New 115 kV "20L" circuit breaker at Blackberry | MN | 0 | 0 | Proposed | 500000 | Planning |  | N | N | N
B in MTEP16 | B | West | MP | 9643 | 2015-09-11 | Little Falls Tie Breaker | 20956 | 2015-09-08 | CB | 2017-06-01 | Little Falls |  |  | 115 |  |  | New 115 kV tie breaker at Little Falls & associated bus modifications | MN | 0 | 0 | Proposed | 1000000 | Planning |  | N | N | N
B in MTEP16 | B | West | MP | 9644 | 2015-09-11 | North Shore Cap Banks | 20957 | 2015-09-08 | CAP | 2017-12-31 | North Shore |  |  | 115 |  |  | New 2x20 MVAr shunt cap bank station near Silver Bay, MN | MN | 0 | 0.1 | Proposed | 2000000 | Planning |  | N | N | N
B in MTEP16 | B | West | MP | 9644 | 2015-09-11 | North Shore Cap Banks | 20958 | 2015-09-08 | CAP | 2017-12-31 | Hoyt Lakes |  |  | 115 |  |  | Additional 15 MVAr shunt cap bank connected to Hoyt Lakes Bus 1 | MN | 0 | 0 | Proposed | 500000 | Planning |  | N | N | N
B in MTEP16 | B | West | MP | 9646 | 2015-09-08 | Nashwauk 14 Line Upgrade | 20959 | 2015-09-10 | LNup | 2020-05-01 | Nashwauk | 14 Line Tap | 1 | 115 |  | 153 | Upgrade existing 636 ACSR to 80C | MN | 4.9 | 0 | Proposed | 500000 | Planning |  | N | N | N
B in MTEP16 | B | West | MP | 9647 | 2015-09-08 | 53 Line Upgrade | 20960 | 2015-09-10 | LNup | 2020-05-01 | Nashwauk | National | 1 | 115 |  | 153 | Upgrade existing 636 ACSR to 80C | MN | 6.2 | 0 | Proposed | 500000 | Planning |  | N | N | N
B in MTEP16 | B | West | MP | 10285 | 2015-10-30 | Forbes Tie Breaker Failure Relay | 21524 | 2015-10-30 | RLY | 2020-05-01 | Forbes |  |  | 115 |  |  | Install breaker failure on 38-44MW breaker | MN |  |  | Proposed |  |  |  | N | N | N
B in MTEP16 | B | West | MPC, OTP | 4813 | 2016-05-25 | OTP | 9093 | 2015-12-07 | LN | 2020-12-31 | Clearbrook West 115 kV | Bagley West 230 kV | 1 | 115 |  | 240 | Clearbrook West 115 kV to Bagley West 230 kV Build new 115 kV Tranmission Line (16 miles) | MN |  | 16 | Proposed | 6000000 | Planning Preliminary |  | N | N | N | Y
B in MTEP16 | B | West | OTP | 4813 | 2016-05-25 | OTP | 9094 | 2016-01-29 | SwSta | 2020-12-31 | Bagley North 115 kV Substation |  |  | 115 |  |  | Bagley North 115 kV Sub, Add 115 kV 3 Breaker Ring Bus | MN |  |  | Proposed | 3000000 | Planning Preliminary |  | N | N | N | Y
B in MTEP16 | B | West | OTP | 4813 | 2016-05-25 | OTP | 9095 | 2016-01-29 | SUB | 2020-12-31 | Bagley West 230/115 kV Tap | 230 kV Tap |  | 230 | 115 |  | Bagley West 230 kV tap, add 230/115 kV transformer and breakers. Transformer 140 MVA and EM Rating 175 MVA | MN |  |  | Proposed | 3300000 | Planning Preliminary |  | N | N | N | Y
B in MTEP16 | B | West | OTP | 9997 | 2016-09-01 |  | 21422 | 2016-09-01 | SUB | 2018-12-01 | Rolette 230/69/41.6 kV |  |  | 230 | 41.6 |  | Install three 230 kV Breakers, one 69 kV Breaker and one 41.6 kV Breaker. Install one 230/69/41.6 kV Transformer (60 MVA) | ND |  |  | Proposed | 9000000 | Planning |  | N | N | N | NT
B in MTEP16 | B | West | OTP | 10001 | 2016-09-01 |  | 21424 | 2016-09-01 | SUB | 2018-10-01 | Voltaire 115/41.6 kV |  |  | 115 | 41.6 |  | Build a new 115/41.6 kV substation in the Voltaire area by tapping MISO facilities and re-terminating existing OTP - owned 41.6 kV circuits from CPEC - owned Voltaire substation to new OTP - owned 115/41.6 kV delivery. Install one 56 MVA Transformer 115/41.6 kV. Install four 41.6 kV Breakers. | ND |  |  | Proposed | 5000000 | Planning |  | N | N | N | NT
B in MTEP16 | B | West | OTP | 10043 | 2015-09-17 |  | 21445 | 2015-09-18 | CB | 2020-12-31 | Jamestown 345 |  |  | 345 |  |  | Add an additional 345 kV breaker to create a 4 breaker ring bus. | ND |  |  | Proposed | 2000000 | Planning |  | N | N | N
B in MTEP16 | B | West | OTP | 10903 | 2016-09-26 |  | 21686 | 2016-08-22 | SUB | 2017-12-01 | Rugby 230 kV |  |  | 115 |  |  | Install one 115 kV breaker. | ND |  |  | Proposed | 500000 | Planning |  | N | N | N | Y
B in MTEP16 | B | West | OTP | 10903 | 2016-09-26 |  | 21687 | 2016-08-19 | LN | 2017-12-01 | Rugby 230 kV | Harvey 230 kV |  | 115 |  | 243 | Construct 2 miles of 115 kV line out of the Rugby 230 kV Substation. Conductor T2 - 266 ACSR with Summer Ratings 192 & Emergency 212. Winter Ratings 243 & Emergency 267. | ND |  | 2 | Proposed | 1000000 | Planning |  | N | N | N | Y
B in MTEP16 | B | West | XEL | 10183 | 2016-08-18 |  | 21486 | 2016-06-15 | TX | 2018-06-01 | Pershing |  |  | 345 | 115 | 448 MVA | New Pershing 345/115 kV 448 MVA transformer | WI |  |  | Proposed | 4500000 |  |  | N | N | N | Y
A in MTEP03 | A | Central | SIPC | 81 | 2011-04-22 |  | 60 | 2016-02-03 | LN | 2016-10-01 | Power Plant | Carrier Mills 161kV |  | 161 |  |  | 25-mile 161kV transmission line from Southern Illinois Power Cooperative's power plant to a new 161/69kV substation | IL |  | 25 | Under Construction | 9200000 |  |  | N | N | N | Y
A in MTEP03 | A | Central | SIPC | 81 | 2011-04-22 |  | 5339 | 2015-11-09 | LN | 2016-10-01 | Carrier Mills | 161/69 kV transformer |  | 161 | 69 |  | New 161/69kV substation located north of Carrier Mills, IL | IL |  |  | Under Construction | 1000000 |  |  | N | N | N | Y
A in MTEP06 | A | Central | AmerenIL | 739 | 2006-03-17 |  | 1432 | 2012-10-12 | LN | 2020-11-01 | Line 4561 Tap | Franklin County Power Plant | 1 | 345 |  |  | 345 kV connection (new ring bus) to new generation | IL |  |  | Planned | 6410900 | Engineering | Interconnection | N | N | N | Y
A in MTEP08 | A | Central | DEI | 1899 | 2011-09-27 | 604B5493 | 3795 | 2016-08-23 | LNrc | 2016-12-31 | Macy | Rochester Metals Jct | 1 | 69 |  | 100 | Reconductor Macy to Rochester Metals Jct section of 6957 circuit with 477ACSR - approx 9.1 miles | IN | 9.1 |  | Under Construction | 4707000 | Engineering |  | N | N | N | NT
A in MTEP08 | A | Central | HE | 1929 | 2008-01-10 | None Yet | 3808 | 2011-01-11 | SUB | 2012-09-01 | Georgetown Primary |  | 1 | 138 |  | 2000 AMP | Rebuild | IN |  |  | Planned | 1250000 |  |  | N | N | N | Y
A in MTEP08 | A | Central | Vectren | 1782 | 2014-09-30 |  | 3572 | 2016-06-30 | SUB | 2024-12-31 | Northeast Sub Bus reconfig | Substation | 1 | 138 |  |  | Rebuild existing straight bus with more reliable breaker and half scheme | IN |  |  | M2a_Pre-Project Approval | 8000000 | Budgetary |  | N | N | N | Y
A in MTEP08 | A | Central | Vectren | 1784 | 2014-09-30 |  | 3574 | 2016-06-30 | SUB | 2019-12-31 | Jasper#3 Sub Exp-Victory Line | Victory | 1 | 69 |  |  | Extend existing Victory line to new term at existing sub | IN |  |  | M2a_Pre-Project Approval | 3625000 | Budgetary |  | N | N | N | NT
A in MTEP08 | A | Central | Vectren | 1788 | 2014-09-30 |  | 3578 | 2016-03-22 | SUB | 2016-12-31 | St. Wendel Sub | Mohr Rd Sub | 34 | 69 |  |  | New 69kV line from St. Wendel Sub to Mohr Rd Sub | IN |  |  | M2a_Pre-Project Approval | 2750000 | Budgetary |  | N | N | N | NT
A in MTEP08 | A | Central | Vectren | 1789 | 2014-09-30 |  | 3579 | 2013-12-20 | SUB | 2018-12-31 | Boonville Sub | Boonville Pioneer Sub | 56 | 69 |  |  | New 69kV line from Boonville Sub to Boonville Pioneer Sub | IN |  |  | M2a_Pre-Project Approval | 1400000 | Budgetary |  | N | N | N | NT
A in MTEP08 | A | East | METC | 1448 | 2006-10-25 | 196 | 2452 | 2015-09-29 | Dist | 2019-12-31 | Simpson 138kV |  |  | 138 | 12.5 |  | Install a second distribution transformer at Simpson (Simpson) | MI |  |  | Planned | 2200000 |  |  | N | N | N | Y
A in MTEP08 | A | West | ITCM | 1744 | 2009-09-25 | GM-MAQ | 3546 | 2015-12-30 | LNrc | 2019-12-31 | Maquoketa | Grand Mound | 1 | 161 |  | 326/326 MVA | Reconductor | IA | 14.5 |  | Planned | 10150000 | Planning |  | N | N | N | Y
A in MTEP08 | A | West | NWEC | 2011 | 2009-11-16 | 2009-03 | 3992 | 2009-11-16 | LNrb | 2011-06-01 | Frederic | Lewis |  | 69 |  | 31 | Rebuild the 34.5Kv system between Frederic and Lewis sub at 69KV with 477ASCR and horizontal post construction. | WI | 2.8 | 0 | Planned | 350000 |  |  | N | N | N | Y
A in MTEP08 | A | West | NWEC | 2012 | 2009-11-16 | 2010-01 | 3993 | 2009-11-16 | LNrb | 2011-09-01 | Falun | Penta |  | 69 |  | 47 | Rebuild the 34.5Kv system between Falun and Penta sub at 69KV with 477ASCR and horizontal post construction. | WI | 4.3 | 0 | Under Construction | 538000 |  |  | N | N | N | Y
A in MTEP08 | A | West | NWEC | 2013 | 2009-11-16 | 2010-02 | 3994 | 2009-11-16 | LNrb | 2011-06-01 | Penta | Siren Tap |  | 69 |  | 15 | Rebuild the 34.5Kv system between Penta sub and Siren Tap at 69KV with 477ASCR and horizontal post construction. | WI | 1.4 | 0 | Planned | 175000 |  |  | N | N | N | Y
A in MTEP08 | A | West | NWEC | 2016 | 2009-11-16 | 2011-02 | 3997 | 2011-09-16 | LNrc | 2013-01-01 | Frederic | Coffee Cup |  | 69 |  | 84 | Reconductor 69KV line with 477ACSR | WI | 2 | 0 | Planned | 100000 |  |  | N | N | N | Y
A in MTEP08 | A | West | NWEC | 2018 | 2009-11-16 | 2012-01 | 3999 | 2009-11-16 | LN | 2011-06-01 | Eureka Tap | Centuria |  | 69 | 12.47 |  | Build new 69KV line to Centuria and build Distribution Sub | WI | 0 | 4 | Planned | 1200000 |  |  | N | N | N | Y
A in MTEP08 | A | West | XEL | 675 | 2008-06-30 |  | 1364 | 2016-09-30 | LNup | 2017-06-15 | Westgate | Scott County | 1 | 115 |  | 194 MVA | upgrade line | MN | 20.1 |  | Planned | 14000000 |  |  | N | N | N | Y
A in MTEP09 | A | Central | AmerenIL | 2273 | 2010-04-05 |  | 4187 | 2016-03-09 | LN | 2020-06-01 | LaFarge | 161 kV Supply to Customer Substation |  | 161 |  |  | Provide 161 kV supply to customer substation | IL |  |  | Planned | 570000 | Engineering |  | N | N | N | Y
A in MTEP09 | A | Central | DEI | 2154 | 2011-09-27 | AMIN0360 | 2942 | 2015-01-12 | SUB | 2019-06-01 | Carmel Rohrer Rd. | distribution sub |  | 69 | 12 |  | Carmel Rohrer Rd 69/12-22.4MVA sub to looped through the 6989 ckt. at or near the existing Carmel Shell Oil tap | IN | 0.4 | 0.4 | M2a_Pre-Project Approval | 591143 | Engineering |  | N | N | N | NT
A in MTEP09 | A | Central | Vectren | 2466 | 2014-09-30 | SIGE7 | 4430 | 2016-06-30 | SUB | 2019-06-01 | Roesner Rd 138/12kV Substation |  | 1 | 138 | 12.47 | 16/20 | New 138/12kV Substation for load growth | IN |  |  | M2a_Pre-Project Approval | 3000000 | Budgetary |  | N | N | N | NT
A in MTEP09 | A | East | METC | 662 | 2016-08-15 | METC_10_007 | 1350 | 2016-08-15 | SUB | 2016-12-15 | Weeds Lake 345/138 kV |  |  | 345 | 138 |  | Weeds Lake 345/138 kV switching station | MI |  |  | Under Construction | 17841284.4 |  |  | N | Y | N | Y
A in MTEP09 | A | East | METC | 662 | 2016-08-15 | METC_10_007 | 8991 | 2016-08-15 | SUB | 2016-12-15 | Milham 138 kV |  |  | 138 |  |  | Remote relay work to be completed at Milham 138 kV | MI |  |  | Under Construction | 553735.2 |  |  | N | N | N | Y
A in MTEP09 | A | East | METC | 662 | 2016-08-15 | METC_10_007 | 3597 | 2016-08-15 | SUB | 2016-12-15 | Argenta 138 kV |  |  | 138 |  |  | Remote relay work to be completed at Argenta 138 kV | MI |  |  | Under Construction | 1067275.2 |  |  | N | Y | N | Y
A in MTEP09 | A | East | METC | 662 | 2016-08-15 | METC_10_007 | 3596 | 2016-08-15 | LNup | 2016-12-15 | Weeds Lake | N_AVE |  | 138 |  |  | line extention on MILHAM to N_AVE circuit N_AVE side | MI |  |  | Under Construction | 5780000 |  |  | N | Y | N | Y
A in MTEP09 | A | East | METC | 662 | 2016-08-15 | METC_10_007 | 3595 | 2016-08-15 | LNup | 2016-12-15 | Weeds Lake | 12th ST |  | 138 |  |  | line extention on BRONCO to 12th ST circuit 12TST side | MI |  |  | Under Construction | 5780000 |  |  | N | Y | N | Y
A in MTEP09 | A | East | METC | 662 | 2016-08-15 | METC_10_007 | 3594 | 2016-08-15 | LNup | 2016-12-15 | Weeds Lake | MILHAM |  | 138 |  |  | line extention on MILHAM to N_AVE circuit MILHAM side | MI |  |  | Under Construction | 5780000 |  |  | N | Y | N | Y
A in MTEP09 | A | East | METC | 662 | 2016-08-15 | METC_10_007 | 3593 | 2016-08-15 | LNup | 2016-12-15 | Weeds Lake | BRONCO |  | 138 |  |  | line extention on BRONCO 12th ST circuit BRONCO side | MI |  |  | Under Construction | 5780000 |  |  | N | Y | N | Y
A in MTEP09 | A | East | METC | 662 | 2016-08-15 | METC_10_007 | 3592 | 2016-08-15 | TX | 2016-12-15 | Weeds lake 345/138 kV | Transformer |  | 345 | 138 |  | transformer | MI |  |  | Under Construction | 6665833.2 |  |  | N | Y | N | Y
A in MTEP09 | A | East | METC | 2478 | 2015-11-24 |  | 4466 | 2014-12-22 | TAP | 2017-06-01 | Capital Ave | Battle Creek | 1 | 138 |  |  | Capital Ave taps the Battle Creek-Verona 138kV circuit #2. | MI |  |  | Planned | 89094 |  |  | N | N | N | Y
A in MTEP09 | A | East | METC | 2478 | 2015-11-24 |  | 4467 | 2014-12-22 | TAP | 2017-06-01 | Capital Ave | Battle Creek | 1 | 138 |  |  | Capital Ave taps the Battle Creek-Verona 138kV circuit #2. | MI |  |  | Planned | 89094 |  |  | N | N | N | Y
A in MTEP09 | A | East | METC | 2481 | 2016-06-08 |  | 4470 | 2016-06-08 | TAP | 2018-05-31 | Forest Grove | Campbell | 1 | 138 |  |  | Forest Grove taps the Campbell-Hudsonville (toward Ransom) 138kV circuit | MI |  |  | Planned | 85000 |  |  | N | N | N | Y
A in MTEP09 | A | East | METC | 2481 | 2016-06-08 |  | 4471 | 2016-06-08 | TAP | 2018-05-31 | Forest Grove | Hudsonville | 1 | 138 |  |  | Forest Grove taps the Campbell-Hudsonville (toward Ransom) 138kV circuit | MI |  |  | Planned | 85000 |  |  | N | N | N | Y
A in MTEP09 | A | East | METC | 2482 | 2014-01-31 |  | 4472 | 2014-12-22 | TAP | 2020-05-31 | Hawthorne | Four Mile | 1 | 138 |  |  | Hawthorne taps the Four Mile-Pingree (toward Blendon) 138kV circuit | MI |  |  | Planned | 85000 |  |  | N | N | N | Y
A in MTEP09 | A | East | METC | 2482 | 2014-01-31 |  | 4473 | 2014-12-22 | TAP | 2020-05-31 | Hawthorne | Pingree | 1 | 138 |  |  | Hawthorne taps the Four Mile-Pingree (toward Blendon) 138kV circuit | MI |  |  | Planned | 85000 |  |  | N | N | N | Y
A in MTEP09 | A | East | METC | 2483 | 2016-02-29 |  | 4474 | 2016-03-22 | TAP | 2016-12-01 | Maines Road | Marshall | 1 | 138 |  |  | Maines Road taps the Marshall-Blackstone 138kV circuit | MI |  |  | M3_Long Lead Materials | 88193 |  |  | N | N | N | Y
A in MTEP09 | A | East | METC | 2483 | 2016-02-29 |  | 4475 | 2016-03-22 | TAP | 2016-12-01 | Maines Road | Blackstone | 1 | 138 |  |  | Maines Road taps the Marshall-Blackstone 138kV circuit | MI |  |  | M3_Long Lead Materials | 88193 |  |  | N | N | N | Y
A in MTEP09 | A | East | METC | 2485 | 2016-06-08 |  | 4478 | 2016-06-08 | RLY | 2019-06-01 | Ransom | Buck Creek | 1 | 138 |  |  | Relay modifications | MI |  |  | Planned | 12000 |  |  | N | N | N | Y
A in MTEP09 | A | East | METC | 2486 | 2016-08-15 |  | 4479 | 2016-08-15 | TAP | 2018-06-01 | Haakwood | Rondo | 1 | 138 |  |  | Haakwood taps the Rondo-Vanderbilt section of the Riggsville-Livingston 138kV line. | MI |  |  | Planned | 85000 |  |  | N | N | N | Y
A in MTEP09 | A | East | METC | 2486 | 2016-08-15 |  | 4480 | 2016-08-15 | TAP | 2018-06-01 | Haakwood | Vanderbilt | 1 | 138 |  |  | Haakwood taps the Rondo-Vanderbilt section of the Riggsville-Livingston 138kV line. | MI |  |  | Planned | 85000 |  |  | N | N | N | Y
A in MTEP09 | A | East | METC | 2501 | 2015-02-26 |  | 4501 | 2015-02-26 | CAP | 2030-06-01 | Plum | [5 empty] | Install 25.2 MVAR capacitor | MI |  |  | Planned | 435484 |  |  | N | N | N | Y
A in MTEP09 | A | East | METC | 2501 | 2015-02-26 |  | 4500 | 2015-02-26 | CAP | 2030-06-01 | Keystone | [5 empty] | Install 50.4 MVAR capacitor | MI |  |  | Planned | 740323 |  |  | N | N | N | Y
A in MTEP09 | A | East | METC | 2501 | 2015-02-26 |  | 4499 | 2015-02-26 | CAP | 2030-06-01 | New site (Wexford prime) | [5 empty] | Install 25.2 MVAR capacitor | MI |  |  | Planned | 1524194 |  |  | N | N | N | Y
A in MTEP09 | A | East | WPSC | 2736 | 2010-01-06 | EB-SB | 4758 | 2015-09-15 | LNrb | 2016-12-31 | East Bay | South Boardman Distribution | 1 | 69 |  | 143.4MVA | Rebuild Overloaded Line | MI | 15.93 |  | Planned | 7500000 |  |  | N | N | N | Y
A in MTEP09 | A | East | WPSC | 2770 | 2009-02-03 |  | 4832 | 2015-09-15 | TAP | 2017-12-31 | Hersey | Gilmore | 1 | 69 |  |  | Gilmore Taps the Hersey to Vestaburg 69kV circuit | MI |  |  | Planned | 250000 | Planning |  | N | N | N | Y
A in MTEP09 | A | East | WPSC | 2770 | 2009-02-03 |  | 4833 | 2015-09-15 | TAP | 2017-06-01 | Gilmore | Vestaburg | 1 | 69 |  |  | Gilmore Taps the Hersey to Vestaburg 69kV circuit | MI |  |  | Planned | 250000 | Planning |  | N | N | N | Y
A in MTEP09 | A | West | ITCM | 2367 | 2009-04-01 | ITCM-08-033 | 4360 | 2015-12-30 | LNrb | 2016-04-29 | Anita 161kV | Exira REC | 1 | 34 |  | 39/39 MVA | Rebuild the 34kV line to 69kV (operate at 34kV). | IA | 5 |  | Under Construction | 1250000 |  |  | N | N | N | NT
A in MTEP09 | A | West | ITCM | 2367 | 2009-04-01 | ITCM-08-033 | 4362 | 2013-06-27 | LNrb | 2016-12-31 | Anita-Wiota | Adair | 1 | 34 |  | 39/39 MVA | Rebuild 1.2 miles of the Anita-Wiota-Adair line. | IA | 1.2 |  | Planned | 300000 |  |  | N | N | N | NT
A in MTEP09 | A | West | ITCM | 2367 | 2009-04-01 | ITCM-08-033 | 4361 | 2013-06-27 | LNrb | 2016-12-31 | Anita 161kV | Anita-Wiota | 1 | 34 |  | 39/39 MVA | Rebuild the 34kV line to 69kV (operate at 34kV). | IA | 3.5 |  | Planned | 875000 |  |  | N | N | N | NT
A in MTEP09 | A | West | ITCM | 2371 | 2009-09-25 | ITCM-08-041 | 4383 | 2014-06-13 | SUB | 2016-12-31 | Marengo | new switching station | 1 | 69 |  |  | Construct a new 3-terminal 69kV switching station at the existing Marengo 34kV sub. This work needs to be completed for 69kV operation. | IA |  |  | M1_Final SPM or OOC | 1900000 | Engineering |  | N | N | N | NT
A in MTEP09 | A | West | MP | 2759 | 2009-11-13 | Laskin | 4782 | 2015-06-10 | SUB | 2017-12-31 | Laskin | Substation Equipment |  | 115 | 46 | 28 | Substation Transformer | MN |  |  | Planned | 1500000 | Engineering |  | N | N | N | Y
A in MTEP10 | A | Central | DEI | 1520 | 2009-09-17 | 502G6713 | 2596 | 2015-09-08 | SUB | 2017-06-01 | Durbin | 230/69 substation | 1 | 230 | 69 |  | Build a new 230 69kv 150mva sub with 2 69kv line terminals | IN |  |  | M3_Long Lead Materials | 9167825.75 | Engineering |  | N | N | N | Y
A in MTEP10 | A | Central | DEI | 2143 | 2011-09-27 | 602J3066 | 2929 | 2014-09-23 | TX | 2020-06-01 | Frances Creek | bank 2 | 2 | 345 | 69 | 200 | Add Frances Creek 345/69kV Bank 2 - 200MVA with LTC | IN |  |  | M1_Final SPM or OOC | 6887000 | Engineering |  | N | N | N | NT
A in MTEP10 | A | East | ITCT | 2929 | 2016-04-22 |  | 5098 | 2016-06-08 | LN | 2016-11-30 | Ariel (formerly Holland) | Holland | 1 | 120 |  |  | Distribution Interconnection to add two new 120/13.2kV transformers at Ariel (formerly Holland). Connects to the Wheeler to Troy 120kV circuit. | MI |  |  | Under Construction | 2800000 |  |  | N | N | N | Y
A in MTEP10 | A | East | ITCT | 2929 | 2016-04-22 |  | 5100 | 2016-06-08 | LNup | 2016-11-30 | Ariel (formerly Holland) | Troy | 1 | 120 |  |  | Distribution Interconnection to add two new 120/13.2kV transformers at Ariel (formerly Holland). Connects to the Wheeler to Troy 120kV circuit. | MI | 0.73 | 0.1 | Under Construction |  |  |  | N | N | N | Y
A in MTEP10 | A | East | ITCT | 2929 | 2016-04-22 |  | 5099 | 2016-06-08 | LNup | 2016-11-30 | Ariel (formerly Holland) | Wheeler | 1 | 120 |  |  | Distribution Interconnection to add two new 120/13.2kV transformers at Ariel (formerly Holland). Connects to the Wheeler to Troy 120kV circuit. | MI |  | 0.1 | Under Construction |  |  |  | N | N | N | Y
A in MTEP10 | A | West | GRE | 2564 | 2016-09-08 | 20225 | 4566 | 2016-09-08 | LN | 2017-11-08 | St. Wendel | Le Sauk | 1 | 115 |  |  | Sartell Disribution Sub, 795 ACSS 115 kV radial line and switch | MN |  | 3 | Under Construction | 1500000 | Engineering |  | N | N | N | Y
A in MTEP10 | A | West | GRE | 2577 | 2016-02-10 | 20312 | 4588 | 2016-06-29 | SUB | 2021-05-18 | Columbus | Columbus Tap | 1 | 69 |  |  | New Distribution | MN |  | 0 | Planned | 140000 | Planning |  | N | N | N | NT
A in MTEP10 | A | West | GRE | 2579 | 2010-09-15 | 20273 | 4590 | 2016-04-27 | SUB | 2020-10-30 | Foster Lake | Foster Lake Tap | 1 | 69 |  |  | New Distribution | MN |  | 0 | Planned | 140000 | Planning |  | N | N | N | NT
A in MTEP10 | A | West | GRE | 2589 | 2009-11-19 | 20328 | 4600 | 2016-09-08 | LN | 2023-07-20 | Rich Valley | Rich Valley Tap | 1 | 69 |  |  | New Distribution | MN |  | 2 | Planned | 115001 | Engineering |  | N | N | N | NT
A in MTEP10 | A | West | GRE | 2670 | 2012-12-04 | 20446 | 4687 | 2011-07-01 | TX | 2020-04-14 | Schuster Lake | transformer | 1 | 115 | 41.6 | 70 | North Perham land acquisition and 115/41.6 kV source | MN |  |  | Planned | 4480714.28 | Engineering |  | N | N | N | Y
A in MTEP10 | A | West | ITCM | 3048 | 2009-09-14 | Jeff-Perlee | 5266 | 2016-06-28 | LN | 2022-12-31 | Jefferson Co | Perlee | 1 | 69 | 69 | 57 MVA | Rebuild Jefferson Co-Perlee line | IA | 7.38 | 0 | Planned | 2700000 | Planning |  | N | N | N | Y
A in MTEP10 | A | West | ITCM | 3053 | 2010-06-28 | Keokuk-Carbide | 5294 | 2014-06-13 | LN | 2016-12-31 | Keokuk Hydro | Carbide | 1 | 69 | 69 | 100 MVA | Build a new Keokuk Hydro-Carbide 69 kV line. | IA |  |  | Planned | 1620000 | Planning |  | N | N | N | Y
A in MTEP10 | A | West | ITCM | 3053 | 2010-06-28 | Keokuk-Carbide | 5297 | 2014-06-13 | LN | 2016-12-31 | Commercial | Carbide | 1 | 69 | 69 | 100 MVA | Rebild to doulbe ckt 69kV | IA |  |  | Planned | 540000 | Planning |  | N | N | N | Y
A in MTEP10 | A | West | ITCM | 3053 | 2010-06-28 | Keokuk-Carbide | 5296 | 2014-06-13 | LN | 2016-12-31 | Messenger | Commercial | 1 | 69 | 69 | 100 MVA | Rebild to doulbe ckt 69kV | IA |  |  | Planned | 540000 | Planning |  | N | N | N | Y
A in MTEP10 | A | West | ITCM | 3053 | 2010-06-28 | Keokuk-Carbide | 5295 | 2014-06-13 | LN | 2016-12-31 | Keokuk Hydro | Messenger | 1 | 69 | 69 | 100 MVA | Rebild to doulbe ckt 69kV | IA |  |  | Planned | 540000 | Planning |  | N | N | N | Y
A in MTEP10 | A | West | ITCM | 3055 | 2009-09-14 | CR 34kV Plan | 5293 | 2014-06-13 | SUB | 2019-12-31 | Oak Hill | Substation | 1 | 69 | 69 |  | New 69kV/dist sub | IA |  |  | Planned | 2160000 | Planning |  | N | N | N | Y
A in MTEP10 | A | West | ITCM | 3055 | 2009-09-14 | CR 34kV Plan | 5292 | 2014-06-13 | SUB | 2015-12-31 | Emerald Isle | Substation | 1 | 69 | 69 |  | New 69kV/dist sub | IA |  |  | Planned | 2160000 | Planning |  | N | N | N | Y
A in MTEP10 | A | West | ITCM | 3055 | 2009-09-14 | CR 34kV Plan | 5291 | 2014-06-13 | SUB | 2017-12-31 | Cargil West | Substation | 1 | 69 | 69 |  | New 69kV/dist sub | IA |  |  | Planned | 2160000 | Planning |  | N | N | N | Y
A in MTEP10 | A | West | ITCM | 3055 | 2009-09-14 | CR 34kV Plan | 5283 | 2015-12-30 | LN | 2019-04-01 | Oak Hill | Marion | 1 | 69 | 69 |  | Rebuild 34kV to 69kV(operate at 34kV until 69kV/dist subs are ready) | IA | 8 |  | Planned | 1010000 | Planning |  | N | N | N | Y
A in MTEP10 | A | West | ITCM | 3055 | 2009-09-14 | CR 34kV Plan | 5282 | 2015-12-30 | LN | 2018-10-01 | PCI | Oak Hill | 1 | 69 | 69 |  | Rebuild 34kV to 69kV(operate at 34kV until 69kV/dist subs are ready) | IA | 5 |  | Planned | 1010000 | Planning |  | N | N | N | Y
A in MTEP10 | A | West | ITCM | 3055 | 2009-09-14 | CR 34kV Plan | 5279 | 2015-12-30 | LN | 2019-04-16 | Cargil West | PCI | 1 | 69 | 69 |  | Rebuild 34kV to 69kV and new 69kV section | IA | 6 |  | Planned | 810000 | Planning |  | N | N | N | Y
A in MTEP10 | A | West | ITCM | 3057 | 2010-06-28 | WB 34kV Shift | 5301 | 2015-12-30 | LN | 2019-12-31 | Moscow | Moscow Tap | 1 | 69 | 69 | 77 MVA | Build a new 3.75 mile 69kV tap to Moscow & retire 7 mile 34kV tap. | IA | 0 | 3.75 | M1_Final SPM or OOC | 1313000 | Engineering |  | N | N | N | Y
A in MTEP10 | A | West | ITCM | 3057 | 2010-06-28 | WB 34kV Shift | 6419 | 2014-06-13 | LN | 2018-12-31 | New Liberty | New Liberty Tap | 1 | 34 | 34 |  | Retire the New Liberty 34kV 9.4 mile tap | IA |  |  | M1_Final SPM or OOC | 282000 | Engineering |  | N | N | N | Y
A in MTEP10 | A | West | ITCM | 3057 | 2010-06-28 | WB 34kV Shift | 6418 | 2015-12-30 | LN | 2019-12-31 | Moscow Tap | Moscow | 1 | 34 | 34 |  | Retire the Moscow 34kV 7 mile tap | IA |  |  | M1_Final SPM or OOC | 210000 | Engineering |  | N | N | N | Y
A in MTEP10 | A | West | ITCM | 3057 | 2010-06-28 | WB 34kV Shift | 5306 | 2014-06-13 | LN | 2018-12-31 | New Liberty Tap | Dixon Jct | 1 | 69 | 69 |  | Tap the Bennett Switch Station to Dixon Jct 69kV line for a new 69kV tap to New Liberty. | IA | 0 | 0 | M1_Final SPM or OOC |  | Planning |  | N | N | N | Y
A in MTEP10 | A | West | ITCM | 3057 | 2010-06-28 | WB 34kV Shift | 5305 | 2014-06-13 | LN | 2018-12-31 | Bennett | New Liberty Tap | 1 | 69 | 69 |  | Tap the Bennett Switch Station to Dixon Jct 69kV line for a new 69kV tap to New Liberty. | IA | 0 | 0 | M1_Final SPM or OOC |  | Planning |  | N | N | N | Y
A in MTEP10 | A | West | ITCM | 3057 | 2010-06-28 | WB 34kV Shift | 5304 | 2014-06-13 | LN | 2018-12-31 | New Liberty | New Liberty Tap | 1 | 69 | 69 | 77 MVA | Build a new 2 mile 69kV tap to New Liberty & retire 9.4 mile 34kV tap. | IA | 0 | 2 | M1_Final SPM or OOC | 700000 | Engineering |  | N | N | N | Y
A in MTEP10 | A | West | ITCM | 3057 | 2010-06-28 | WB 34kV Shift | 5303 | 2015-12-30 | LN | 2019-12-31 | Moscow Tap | Magmet T | 1 | 69 | 69 |  | Tap the Muscatine Switch Station to Magmet T69kV line for new tap to Moscow. | IA | 0 | 0 | M1_Final SPM or OOC |  | Engineering |  | N | N | N | Y
A in MTEP10 | A | West | ITCM | 3057 | 2010-06-28 | WB 34kV Shift | 5302 | 2015-12-30 | LN | 2019-12-31 | Muscatine Switch Station | Moscow Tap | 1 | 69 | 69 |  | Tap the Muscatine Switch Station to Magmet T69kV line for new tap to Moscow. | IA | 0 | 0 | M1_Final SPM or OOC |  | Engineering |  | N | N | N | Y
A in MTEP10 | A | West | ITCM | 3058 | 2009-09-14 | Vinton 34kV Plan | 5323 | 2015-04-13 | SUB | 2016-12-31 | Urbana | Substation | 1 | 69 | 69 |  | New 69kV/dist sub | IA |  |  | M1_Final SPM or OOC |  | Planning |  | N | N | N | Y
A in MTEP10 | A | West | ITCM | 3058 | 2009-09-14 | Vinton 34kV Plan | 5322 | 2015-04-13 | SUB | 2016-12-31 | Lafayette | Substation | 1 | 69 | 69 |  | New 69kV/dist sub | IA |  |  | M1_Final SPM or OOC |  | Planning |  | N | N | N | Y
A in MTEP10 | A | West | ITCM | 3058 | 2009-09-14 | Vinton 34kV Plan | 5321 | 2015-04-13 | SUB | 2016-12-31 | Walker REC | Substation | 1 | 69 | 69 |  | New 69kV/dist sub | IA |  |  | M1_Final SPM or OOC |  | Planning |  | N | N | N | Y
A in MTEP10 | A | West | ITCM | 3058 | 2009-09-14 | Vinton 34kV Plan | 5318 | 2015-04-13 | SUB | 2016-12-31 | Brandon | Substation | 1 | 69 | 69 |  | New 69kV/dist sub | IA |  |  | M1_Final SPM or OOC |  | Planning |  | N | N | N | Y
A in MTEP10 | A | West | ITCM | 3058 | 2009-09-14 | Vinton 34kV Plan | 5317 | 2015-04-13 | SUB | 2016-12-31 | Shellsburg | Substation | 1 | 69 | 69 |  | New 69kV/dist sub | IA |  |  | M1_Final SPM or OOC |  | Planning |  | N | N | N | Y
A in MTEP10 | A | West | ITCM | 3058 | 2009-09-14 | Vinton 34kV Plan | 5316 | 2015-04-13 | SUB | 2016-12-31 | Palo | Substation | 1 | 69 | 69 |  | New 69kV/dist sub | IA |  |  | M1_Final SPM or OOC |  | Planning |  | N | N | N | Y
A in MTEP10 | A | West | ITCM | 3058 | 2009-09-14 | Vinton 34kV Plan | 5308 | 2014-06-13 | LN | 2015-06-01 | Palo | Todville REC | 1 | 69 | 69 |  | New 69kV | IA | 0 | 4.5 | M1_Final SPM or OOC | 5160000 | Engineering |  | N | N | N | Y
A in MTEP10 | A | West | MP | 2547 | 2009-12-08 | Essar | 5438 | 2015-06-10 | SUB | 2027-04-01 | Blackberry | Substation Equipment |  | 230 |  | 632 | line entrance & breaker | MN |  |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP10 | A | West | MP | 2547 | 2009-12-08 | Essar | 4557 | 2015-06-10 | LN | 2027-04-01 | Blackberry | Essar Steel Sub (McCarthy Lake) | 1 | 230 |  | 632 | Essar new Line and new bay at McCarthy Lake (facility #4558) | MN |  | 15 | Planned | 14000000 | Engineering |  | N | N | N | Y
A in MTEP10 | A | West | MP | 2761 | 2009-11-13 | Dunka Rd | 4780 | 2015-06-10 | SUB | 2017-01-31 | Northmet | Substation Equipment |  | 138 | 14 |  | Substation Equipment & Transformer | MN |  |  | Planned | 3242847 | Engineering |  | N | N | N | Y
A in MTEP10 | A | West | MPW | 2934 | 2016-09-15 | MPW-SS | 5106 | 2016-06-28 | TX | 2016-12-01 | South 161/69 kV | transformer | 2 | 161 | 69 | 134 | Add transformer in parallel with existing 75 MVA transformer | IA |  |  | Planned | 5400000 | Planning |  | N | N | N | Y
A in MTEP10 | A | West | NWEC | 3092 | 2009-11-16 | 2012-02 | 5410 | 2011-09-16 | LNrb | 2012-06-01 | Lake 26 | Webb Lake |  | 69 |  | 15 | Rebuild 34.5KV line to Webb Lake at 69KV with horizontal post construction and #4/0 ACSR | WI | 2.6 | 0 | Planned | 425000 |  |  | N | N | N | Y
A in MTEP11 | A | Central | AmerenIL | 2237 | 2011-11-03 | 11 Prop. MVP Port.1 (62) | 4104 | 2015-03-25 | LN | 2016-11-15 | Pana | Faraday | 1 | 345 |  | 1793 | new line - 35.9 miles of 345 kV | IL |  | 35.9 | Planned | 77050763 |  |  | N | Y | Y | Y
A in MTEP11 | A | Central | AmerenIL | 2237 | 2011-11-03 | 11 Prop. MVP Port.1 (62) | 20828 | 2015-06-15 | LN | 2016-11-15 | Faraday | Mt. Zion PPG | 2 | 138 |  | 399 | Build 2 miles of 138 kV line between Faraday 138 kV Substation (formerly Mt. Zion area Substation) and Mt. Zion PPG 138 kV Substation. The new line needs to have a 2000 A summer emergency capability. | IL |  | 2 | Planned | 12759396 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | Central | AmerenIL | 2237 | 2011-11-03 | 11 Prop. MVP Port.1 (62) | 20827 | 2015-06-15 | LN | 2016-11-15 | Faraday | Mt. Zion PPG | 1 | 138 |  | 399 | Build 2 miles of 138 kV line between Faraday 138 kV Substation (formerly Mt. Zion area Substation) and Mt. Zion PPG 138 kV Substation. The new line needs to have a 2000 A summer emergency capability. | IL |  | 2 | Planned | 14386687 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | Central | AmerenIL | 2237 | 2011-11-03 | 11 Prop. MVP Port.1 (62) | 20826 | 2015-06-15 | CB | 2016-11-15 | PPG Substation | Install 4-138 kV breakers |  | 138 |  |  | Install 4 138 kV, 2000 A breakers to accommodate connection of the Faraday (formerly Mt. Zion) 345/138 kV Substation. | IL |  |  | Planned | 4509333 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | Central | AmerenIL | 2237 | 2011-11-03 | 11 Prop. MVP Port.1 (62) | 20825 | 2015-06-15 | LNrb | 2017-06-01 | Mt. Zion PPG | Route 51 |  | 138 |  | 399 | Rebuild 4.43 miles of 795 kcmil ACSR with conductor capable of carrying 2000 A under summer emergency conditions. | IL | 4.43 |  | Planned | 4248992 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | Central | AmerenIL | 2237 | 2011-11-03 | 11 Prop. MVP Port.1 (62) | 20824 | 2015-06-15 | LNrb | 2017-06-01 | Mt. Zion PPG | Mt. Zion Rt. 121 |  | 138 |  | 399 | Rebuild 2.37 miles of 795 kcmil ACSR conductor with conductor capable of carrying 2000 A under summer emergency conditions. | IL | 2.37 |  | Planned | 2345666 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | Central | AmerenIL | 2237 | 2011-11-03 | 11 Prop. MVP Port.1 (62) | 20773 | 2015-03-25 | LNrl | 2018-11-15 | Kansas | Area Connection Work |  | 345 |  |  | Rerouting of existing lines and work at remote ends | IL |  |  | Planned | 5341519 |  |  | N | N | N | Y
A in MTEP11 | A | Central | AmerenIL | 2237 | 2011-11-03 | 11 Prop. MVP Port.1 (62) | 20772 | 2015-03-25 | LNrl | 2018-11-15 | Faraday | Area Connection Work |  | 345 |  |  | Rerouting of existing lines and work at remote ends | IL |  |  | Planned | 3496405 |  | Generator | N | N | N | Y
A in MTEP11 | A | Central | AmerenIL | 2237 | 2011-11-03 | 11 Prop. MVP Port.1 (62) | 4154 | 2015-04-23 | LN | 2018-11-15 | Kansas | Sugar Creek | 1 | 345 |  | 1793 | new line - 34.5 miles 345 kV; Kansas to Indiana State Line | IL |  | 34.5 | Planned | 86838538 |  |  | N | Y | Y | Y
A in MTEP11 | A | Central | AmerenIL | 2237 | 2011-11-03 | 11 Prop. MVP Port.1 (62) | 4152 | 2015-03-25 | LN | 2018-11-15 | Faraday | Kansas | 1 | 345 |  | 1793 | new line - 70.2 miles 345 kV | IL |  | 70.2 | Planned | 157278038 |  |  | N | Y | Y | Y
A in MTEP11 | A | Central | AmerenIL | 2237 | 2011-11-03 | 11 Prop. MVP Port.1 (62) | 4151 | 2015-03-25 | TX | 2016-11-15 | Faraday | Transformer | 1 | 345 | 138 | 560 | new transformer - 560 MVA, 345/138 kV, plus 345 kV ring bus | IL |  |  | M3_Long Lead Materials | 22927839 |  |  | N | Y | Y | Y
A in MTEP11 | A | Central | AmerenIL | 2239 | 2011-11-03 | 17 Prop. MVP Port.1 (64) FG9 | 20775 | 2015-03-25 | LNrl | 2016-06-01 | Sidney | Area Connection Work |  | 345 |  |  | Rerouting of existing lines and work at remote ends | IL |  |  | Planned | 3434896 |  |  | N | N | N | Y
A in MTEP11 | A | Central | AmerenIL | 2239 | 2011-11-03 | 17 Prop. MVP Port.1 (64) FG9 | 20774 | 2015-03-25 | LNrl | 2016-06-01 | Rising | Area Connection Work |  | 345 |  |  | Rerouting of existing lines and work at remote ends | IL |  |  | Planned | 5268524 |  |  | N | N | N | Y
A in MTEP11 | A | Central | AmerenIL | 3017 | 2016-01-27 | 09 Prop. MVP Port.1 | 4149 | 2015-03-25 | LN | 2017-11-15 | Meredosia | Ipava | 1 | 345 |  | 1793 | new line - 48.0 miles 345 kV; Includes 1.1 mile Illinois river crossing | IL |  | 48 | M3_Long Lead Materials | 139715270 |  |  | N | Y | Y | Y
A in MTEP11 | A | Central | AmerenIL | 3017 | 2016-01-27 | 09 Prop. MVP Port.1 | 20780 | 2015-03-31 | LNrl | 2016-11-15 | Meredosia | Area Connection Work |  | 345 |  |  | Rerouting of existing lines and work at remote ends | IL |  |  | Planned | 13604236 |  | Generator | N | N | N | Y
A in MTEP11 | A | Central | AmerenIL | 3017 | 2016-01-27 | 09 Prop. MVP Port.1 | 20779 | 2015-03-31 | LNrl | 2017-06-01 | Ipava | Area Connection Work |  | 345 |  |  | Rerouting of existing lines and work at remote ends | IL |  |  | Planned | 13131584 |  |  | N | N | N | Y
A in MTEP11 | A | Central | AmerenIL | 3017 | 2016-01-27 | 09 Prop. MVP Port.1 | 20778 | 2015-12-03 | LNrl | 2016-01-10 | Austin | Area Connection Work |  | 345 |  |  | Rerouting of existing lines and work at remote ends | IL |  |  | Under Construction | 4960087 |  |  | N | N | N | Y
A in MTEP11 | A | Central | AmerenIL | 3017 | 2016-01-27 | 09 Prop. MVP Port.1 | 20777 | 2015-12-03 | LNrl | 2016-01-10 | Herleman | Area Connection Work |  | 345 |  |  | Rerouting of existing lines and work at remote ends | IL |  |  | Under Construction | 6730984 |  |  | N | N | N | Y
A in MTEP11 | A | Central | AmerenIL | 3017 | 2016-01-27 | 09 Prop. MVP Port.1 | 6968 | 2015-03-31 | TX | 2016-11-15 | Meredosia | Install 345/138 kV Xfmr | 1 | 345 | 138 | 560 | Meredosia 345/138 kV Substation - Install 345/138 kV Xfmr, 345 kV ring bus. | IL |  |  | Under Construction | 29111231 |  |  | N | Y | Y | Y
A in MTEP11 | A | Central | AmerenIL | 3017 | 2016-01-27 | 09 Prop. MVP Port.1 | 6597 | 2015-03-31 | LN | 2017-06-01 | Ipava |  | 1 | 345 |  | 1793 | Substation work for new Meredosia-Ipava 345 kV line | IL |  |  | M3_Long Lead Materials | 30284809 |  |  | N | Y | Y | Y
A in MTEP11 | A | Central | AmerenIL | 3017 | 2016-01-27 | 09 Prop. MVP Port.1 | 6430 | 2015-03-31 | TX | 2017-11-15 | Austin | Transformer | 2 | 345 | 138 | 560 | 2nd. 345/138, 560 MVA Xfmr, establish 345 kV breaker-and-a-half arrangement at Pawnee | IL |  |  | M3_Long Lead Materials | 40230142 |  |  | N | Y | Y | Y
A in MTEP11 | A | Central | AmerenIL | 3017 | 2016-01-27 | 09 Prop. MVP Port.1 | 5227 | 2015-03-31 | LN | 2016-11-15 | Herleman | Meredosia | 1 | 345 |  | 1793 | new line - 46.6 miles 345 kV; Includes 0.8 mile Illinois river crossing | IL |  | 46.6 | M3_Long Lead Materials | 147551577 |  |  | N | Y | Y | Y
A in MTEP11 | A | Central | AmerenIL | 3017 | 2016-01-27 | 09 Prop. MVP Port.1 | 5203 | 2015-03-31 | TX | 2016-11-15 | Herleman | Xfmr Addition | 1 | 345 | 138 | 450 | Quincy Area 345/138 kV Substation - 1-560 MVA transformer, 345 kV ring bus. | IL |  |  | Under Construction | 29311011 |  |  | N | Y | Y | Y
A in MTEP11 | A | Central | AmerenIL | 3017 | 2016-01-27 | 09 Prop. MVP Port.1 | 5202 | 2015-03-31 | LN | 2016-11-15 | Maywood | Herleman | 1 | 345 |  | 1793 | new line - 15.2 miles 345 kV; Includes 1.6 mile Mississippi river crossing | IL |  | 15.2 | M3_Long Lead Materials | 73857213 |  |  | N | Y | Y | Y
A in MTEP11 | A | Central | AmerenIL | 3017 | 2016-01-27 | 09 Prop. MVP Port.1 | 4150 | 2015-03-31 | LN | 2017-11-15 | Meredosia | Austin | 1 | 345 |  | 1793 | new line - 76.5 miles 345 kV | IL |  | 76.5 | M3_Long Lead Materials | 176912468 |  |  | N | Y | Y | Y
A in MTEP11 | A | Central | AmerenIL | 3022 | 2015-04-02 | 16 Prop. MVP Port.1 | 5232 | 2015-04-02 | LN | 2018-11-15 | Fargo | Sandburg | 1 | 345 |  |  | Fargo-Sandburg 345 kV Line - New 39 mile, 3000 A summer emergency capability line. | IL |  | 39 | Planned | 92100000 | Budgetary |  | N | Y | Y | Y
A in MTEP11 | A | Central | AmerenIL | 3022 | 2015-04-02 | 16 Prop. MVP Port.1 | 20781 | 2015-04-01 | TEQ | 2016-11-15 | Sandburg |  |  | 138 |  |  | Area Connection work associated with Sandburg. | IL |  |  | Planned | 1500000 | Budgetary |  | N | N | N | Y
A in MTEP11 | A | Central | AmerenIL | 3022 | 2015-04-02 | 16 Prop. MVP Port.1 | 6599 | 2015-04-01 | LN | 2016-12-15 | Fargo |  | 1 | 345 |  |  | Fargo substation work - add a new 345 kV ring bus | IL |  |  | Planned | 14500000 | Budgetary |  | N | Y | Y | Y
A in MTEP11 | A | Central | AmerenIL | 3022 | 2015-04-02 | 16 Prop. MVP Port.1 | 6554 | 2015-04-02 | TX | 2016-11-15 | Sandburg | 345/138 kV transformer | 1 | 345 | 138 | 560 MVA | new 560 MVA, 345/138 kV xfmr, 345 kV ring bus, and 138 kV breaker-and-a-half at Sandburg | IL |  |  | Planned | 38200000 | Budgetary |  | N | Y | Y | Y
A in MTEP11 | A | Central | AmerenIL | 3169 | 2011-11-03 | 10 Prop. MVP Port.1 | 5600 | 2015-04-01 | LN | 2018-11-15 | Pana | Austin | 1 | 345 |  | 1793 | new line - 33.6 miles 345 kV | IL |  | 33.6 | Planned | 78331104 |  |  | N | Y | Y | Y
A in MTEP11 | A | Central | AmerenIL | 3169 | 2011-11-03 | 10 Prop. MVP Port.1 | 20782 | 2015-04-01 | LNrl | 2016-11-15 | Pana | Area Connection Work |  | 345 |  |  | Rerouting of existing lines and work at remote ends | IL |  |  | Planned | 14519558 |  |  | N | N | N | Y
A in MTEP11 | A | Central | AmerenIL | 3169 | 2011-11-03 | 10 Prop. MVP Port.1 | 6431 | 2015-04-01 | TX | 2016-11-15 | Pana | Transformer | 2 | 345 | 138 | 560 | Install 2nd. 345/138 kV Xfmr at Pana Sub., 345 kV breaker-and-a-half arrangement at Pana. | IL |  |  | M3_Long Lead Materials | 42645696 |  |  | N | Y | Y | Y
A in MTEP11 | A | Central | AmerenMO | 2248 | 2015-03-24 | 07 Prop. MVP Port.1 | 4160 | 2015-03-25 | LN | 2018-11-15 | Ottumwa | Zachary | 1 | 345 |  | 1793 | AmerenMOs portion of new line - 345 kV, 36 mile single circuit | MO |  | 36 | Planned | 66000000 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | Central | AmerenMO | 2248 | 2015-03-24 | 07 Prop. MVP Port.1 | 20771 | 2015-03-25 | TEQ | 2018-11-15 | Zachary |  |  | 161 |  |  | Area Connection work associated with Zachary Substation | MO |  |  | Planned | 9870000 | Budgetary |  | N | Y | Y | Y
A in MTEP11 | A | Central | AmerenMO | 2248 | 2015-03-24 | 07 Prop. MVP Port.1 | 5187 | 2015-03-24 | SUB | 2018-11-15 | Zachary | Install Transformer | 1 | 345 | 161 | 560 | Adair Substation - New 560 MVA, 345/161 kV Transformer, 345 kV ring bus.capability | MO |  |  | Planned | 27000000 |  |  | N | Y | Y | Y
A in MTEP11 | A | Central | AmerenMO | 3170 | 2015-04-01 | 08 Prop. MVP Port.1 | 5601 | 2015-04-01 | LN | 2018-11-15 | Zachary | Maywood | 1 | 345 |  | 1793 | Construct new 60 mile, 345 kV Line | MO |  | 60 | Planned | 122000000 | Budgetary |  | N | Y | Y | Y
A in MTEP11 | A | Central | AmerenMO | 3170 | 2015-04-01 | 08 Prop. MVP Port.1 | 6603 | 2016-02-04 | SUB | 2016-01-10 | Maywood | Establish 345 kV Sub |  | 345 |  | 1793 | New Maywood Substation - Establish with breaker-and-a-half arrangement | MO |  |  | Under Construction | 31369959 |  |  | N | Y | Y | Y
A in MTEP11 | A | Central | DEI | 2202 | 2015-11-02 | 14 Prop. MVP Port.1 | 7286 | 2015-09-04 | LNrc | 2018-06-01 | Wabash | Wabash Container | 1 | 69 |  | 100 | Reconductor Wabash to Wabash Container section of the 6986 ckt. with 477ACSR @ 100C. | IN | 0.8 |  | M3_Long Lead Materials | 625000 | Engineering |  | N | Y | Y | NT
A in MTEP11 | A | Central | DEI | 2202 | 2015-11-02 | 14 Prop. MVP Port.1 | 7287 | 2015-09-04 | LNup | 2018-06-01 | Kokomo Delco | Greentown | 1 | 138 |  | 179 | Uprate 397ACSR conductor from Kokomo Delco to Greentown section of 13810 ckt. to 100C | IN | 10.22 |  | M3_Long Lead Materials | 142000 | Engineering |  | N | Y | Y | Y
A in MTEP11 | A | Central | DEI | 2237 | 2011-11-03 | 11 Prop. MVP Port.1 (62) | 8313 | 2016-09-08 | LN | 2018-11-15 | IL/IN State Line | Sugar Creek | 1 | 345 |  | 1793 | Sugar Creek 345kV ring breaker addition and 1.5 mile - 3000A - 345kV line to IL/IN state line. | IN |  | 1.5 | M1_Final SPM or OOC | 8809000 | Engineering |  | N | N | N | Y
A in MTEP11 | A | Central | DEI | 3379 | 2012-03-23 | AMIN0138 | 6252 | 2013-09-11 | Dist | 2017-06-01 | Shelbyville McKay Rd. | new distribution sub |  | 69 | 12 |  | Shelbyville McKay Rd. - add new 69/12kV distribution sub in the 6976 ckt. Loop through with 954acsr and a set of 1200A line switches. | IN |  |  | M3_Long Lead Materials | 553710 | Engineering |  | N | N | N | NT
A in MTEP11 | A | Central | DEI | 3386 | 2010-09-15 | AMIN0379 | 6259 | 2013-09-11 | LN | 2019-06-01 | Carmel Springmill Rd. | Hortonville | 1 | 69 |  | 143 | Carmel Springmill Rd. Sub - Add 3-69kV breakers; straight bus config; build .23 mi 69kV 954ACSS@200C from Springmill to old Springmill Jct. Completes circuit to Hortonville. Change operating mode at Homeplace to close loop from 146th to Springmill. | IN |  | 0.23 | M1_Final SPM or OOC | 1866000 | Engineering |  | N | N | N | NT
A in MTEP11 | A | Central | DEI, NIPS | 2202 | 2015-11-02 | 14 Prop. MVP Port.1 | 4074 | 2016-03-03 | LN | 2018-06-01 | Reynolds | Greentown | 1 | 765 |  | 6750 | new line | IN |  | 69.44 | M4_Pre-Construction | 318106854 | Engineering |  | N | Y | Y | Y
A in MTEP11 | A | Central | DEI, NIPS | 2202 | 2015-11-02 | 14 Prop. MVP Port.1 | 4073 | 2015-09-28 | TX | 2018-06-01 | Reynolds | Transformer | 1 | 765 | 345 | 2600 | new transformer | IN |  |  | M4_Pre-Construction | 68619519 | Engineering |  | N | Y | Y | Y
A in MTEP11 | A | Central | IPL | 3273 | 2015-12-01 |  | 6105 | 2014-12-08 | LNup | 2018-06-30 | Southwest | Stout CT | 1 | 138 |  | 345 | Line Survey and Potential Modifications | IN | 2.9 |  | Planned | 300000 | Planning |  | N | N | N | Y
A in MTEP11 | A | East | ITCT | 3281 | 2016-02-22 | 7 | 6113 | 2016-02-22 | LN | 2016-12-31 | Majestic | Chelsea (formerly Lima) | 1 | 120 |  |  | Construct new 120 kV line between Majestic and Lima, along with associated breakers and terminal equiment at each termination. | MI |  | 5 | M4_Pre-Construction | 6500000 | Planning |  | N | N | N | Y
A in MTEP11 | A | East | ITCT | 3285 | 2016-07-14 | ITCT_12_007 | 6516 | 2016-07-14 | SUB | 2016-11-30 | Shoal | 33.3 Mvar capacitor |  | 120 |  |  | Install a 33.3 Mvar Capacitor at Shoal 120kV station as well as two line breakers and a tie breaker. | MI |  |  | Under Construction | 3430000 | Engineering |  | N | N | N | Y
A in MTEP11 | A | East | ITCT | 3285 | 2016-07-14 | ITCT_12_007 | 8994 | 2016-07-14 | LNup | 2016-11-30 | Shoal | Custer | 1 | 120 |  |  | OPGW installation | MI |  |  | Under Construction | 900000 |  |  | N | N | N | Y
A in MTEP11 | A | East | NIPS | 3203 | 2011-11-03 | 12 Prop. MVP Port.1 | 5949 | 2016-06-30 | LN | 2019-12-31 | Reynolds | Hiple | 2 | 345 |  |  | new line tap at Burr Oak | IN |  |  | Under Construction | 388000000 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | East | WPSC | 3331 | 2010-09-15 | RW-HT | 6196 | 2015-09-15 | LNrb | 2016-12-31 | Redwood | Hart | 1 | 69 |  | 143.4MVA | Rebuild Overloaded Line to 795ACSS | MI | 1.77 |  | Planned | 1000000 |  |  | N | N | N | Y
A in MTEP11 | A | East | WPSC | 3335 | 2010-09-15 | Burnips Xmsn | 6200 | 2016-09-15 | SUB | 2022-12-31 | Burnips | Substation Upgrade |  | 69 |  |  | Replace bus work, breakers, relays, and any other necessary components | MI |  |  | Planned | 800000 |  |  | N | N | N | Y
A in MTEP11 | A | West | OTP, XEL | 2221 | 2014-03-24 | 01 Prop. MVP Port.1 (46) | 4117 | 2014-06-10 | LN | 2017-09-30 | Big Stone South | Brookings | 1 | 345 |  | 1800 MVA | Single circuit on double circuit towers | SD |  | 65 | Planned | 165000000 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ATC | 3127 | 2014-09-22 | PR04030 F3398 WO68924, WO68924 | 20607 | 2016-06-30 | TX | 2023-12-31 | Eden |  |  | 345 | 138 |  | Eden 345/138 kV transformer | WI |  |  | M1_Final SPM or OOC | 6100000 | Engineering |  | N | Y | Y | Y
A in MTEP11 | A | West | ATC | 3127 | 2014-09-22 | PR04030 F3398 WO68924, WO68924 | 20581 | 2016-06-30 | SUB | 2023-12-31 | Cardinal |  |  | 345 |  |  | Cardinal Substation modifications | WI |  |  | M1_Final SPM or OOC | 3200000 | Engineering |  | N | Y | Y | Y
A in MTEP11 | A | West | ATC | 3127 | 2014-09-22 | PR04030 F3398 WO68924, WO68924 | 20580 | 2016-06-30 | SUB | 2023-12-31 | Eden |  |  | 345 | 138 |  | Eden Substation modifications | WI |  |  | M1_Final SPM or OOC | 19200000 | Engineering |  | N | Y | Y | Y
A in MTEP11 | A | West | ATC | 3127 | 2014-09-22 | PR04030 F3398 WO68924, WO68924 | 5484 | 2015-10-19 | SUB | 2017-12-31 | Cardinal | Substation |  | 345 | 138 |  | Cardinal substation modifications | WI |  |  | M1_Final SPM or OOC | 3990000 | Engineering |  | N | Y | Y | Y
A in MTEP11 | A | West | ATC | 3206 | 2013-07-05 | PR04117 F2676 WO068196 | 5973 | 2014-09-29 | LN | 2018-12-31 | Branch River | Sheboygan Energy Center | 1 | 345 |  | 1096 | Loop the Point Beach-Sheboygan Energy Center 345 kV line into the Branch River SS | WI |  | 1 | M1_Final SPM or OOC |  | Engineering |  | N | Y | Y | Y
A in MTEP11 | A | West | ATC | 3206 | 2013-07-05 | PR04117 F2676 WO068196 | 5972 | 2014-09-29 | LN | 2018-12-31 | Branch River | Point Beach | 1 | 345 |  | 1096 | Loop the Point Beach-Sheboygan Energy Center 345 kV line into the Branch River SS | WI |  | 1 | M1_Final SPM or OOC |  | Engineering |  | N | Y | Y | Y
A in MTEP11 | A | West | ATC | 3206 | 2013-07-05 | PR04117 F2676 WO068196 | 5971 | 2015-10-19 | LN | 2018-12-31 | Branch River | Forest Jct | 1 | 345 |  | 883 | Loop the Point Beach-Forest Juction into the Branch River SS | WI |  |  | M1_Final SPM or OOC |  | Engineering |  | N | Y | Y | Y
A in MTEP11 | A | West | ATC | 3206 | 2013-07-05 | PR04117 F2676 WO068196 | 5970 | 2014-09-29 | LN | 2018-12-31 | Branch River | Point Beach | 1 | 345 |  | 1096 | Loop the Point Beach-Forest Juction into the Branch River SS | WI |  |  | M1_Final SPM or OOC |  | Engineering |  | N | Y | Y | Y
A in MTEP11 | A | West | ATC | 3206 | 2013-07-05 | PR04117 F2676 WO068196 | 5955 | 2015-03-30 | SUB | 2018-12-31 | Branch River | substation |  | 345 |  |  | Construct a new Branch River substation | WI |  |  | M1_Final SPM or OOC | 46647000 | Engineering |  | N | Y | Y | Y
A in MTEP11 | A | West | ATC, DPC | 3127 | 2014-09-22 | PR04030 F3398 WO68924, WO68924 | 20578 | 2016-07-05 | LN | 2023-12-31 | Eden | Cardinal | 1 | 345 |  | 1399 | New line | WI |  | 60 | M1_Final SPM or OOC | 230900000 | Engineering |  | N | Y | Y | Y
A in MTEP11 | A | West | ATC, XEL | 3127 | 2014-09-22 | PR04030 F3398 WO68924, WO68924 | 5626 | 2014-06-13 | LN | 2018-12-31 | Briggs Road | North Madison | 1 | 345 |  | 1446 | Construct a Briggs Road - North Madison 345-kV line | WI |  | 161.8 | M1_Final SPM or OOC | 491035000 | Engineering |  | N | Y | Y | Y
A in MTEP11 | A | West | ATC, XEL | 3127 | 2014-09-22 | PR04030 F3398 WO68924, WO68924 | 5628 | 2015-10-19 | LN | 2017-12-31 | North Madison | Cardinal | 1 | 345 |  | 1446 | Construct a North Madison - Cardinal 345-kV line | WI |  | 19.9 | M1_Final SPM or OOC | 71455000 | Engineering |  | N | Y | Y | Y
A in MTEP11 | A | West | ATC, XEL | 3127 | 2014-09-22 | PR04030 F3398 WO68924, WO68924 | 5627 | 2015-10-19 | LNrb | 2017-12-31 | North Madison | Cardinal | 1 | 138 |  | 272 | Reconductor with T2-477 HAWK ACSR | WI | 19.9 |  | M1_Final SPM or OOC | 6010000 | Engineering |  | N | Y | Y | Y
A in MTEP11 | A | West | ATC, XEL | 3127 | 2014-09-22 | PR04030 F3398 WO68924, WO68924 | 6573 | 2014-03-31 | SUB | 2018-12-31 | Briggs Road (North LaCrosse) | Substation |  | 345 |  |  | Terminate North Madison - North LaCrosse 345 kV line into Briggs Road, create 345 kV breaker ring bus, and 50 MVAR of 34.5 kV reactors on the tertiary | WI |  |  | Planned | 7300000 | Engineering |  | N | Y | Y | Y
A in MTEP11 | A | West | DPC, ITCM | 3127 | 2014-09-22 | PR04030 F3398 WO68924, WO68924 | 20577 | 2016-08-24 | LN | 2023-12-31 | Eden | Hickory Creek | 1 | 345 |  | 1399 | New circuit | WI,IA |  | 49 | M1_Final SPM or OOC | 193305000 | Engineering |  | N | Y | Y | Y
A in MTEP11 | A | West | GRE | 2679 | 2010-09-15 | 200331 | 4696 | 2013-09-25 | LN | 2021-05-31 | Ramsey | Grand Forks | 1 | 230 |  |  | 230 kV rebuild | MN | 81.02 |  | Under Construction | 41496024.63 | Planning |  | N | N | N | Y
A in MTEP11 | A | West | GRE | 3454 | 2014-09-12 | 201035 | 6267 | 2016-06-29 | SUB | 2017-06-13 | Medina | 115 kV breaker station |  | 115 |  | 0 | Convert WHCEA?s Median 69 kV distribution substation to 115 kV. Retire the 69 kV portion of the Medina 115/69 kV substation, reconfigure Medina to a straight bus breaker station and re-terminate the existing 115kV lines and the new Median ? Pomerleau Lake | MN | 0 | 0 | Planned | 1726608.36 | Engineering |  | N | N | N | Y
A in MTEP11 | A | West | GRE | 3454 | 2014-09-12 | 201035 | 6659 | 2016-09-08 | LN | 2017-10-27 | Pomerleau Lake | Plymouth/Parkers Lake | 1&2 | 115 |  |  | In and Out tap to Pomerleau Lake substation | MN |  | 0.25 | Planned | 399999 | Engineering |  | N | N | N | Y
A in MTEP11 | A | West | ITCM | 2248 | 2015-03-24 | 07 Prop. MVP Port.1 | 20770 | 2015-03-24 | LN | 2017-06-01 | Ottumwa | IA/MO Border | 1 | 345 | 161 | 1793 | 345/161kV double circuit line. ITC Midwest portion ~20 miles | IA |  | 20 | M1_Final SPM or OOC | 40640000 | Engineering |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3127 | 2014-09-22 | PR04030 F3398 WO68924, WO68924 | 20579 | 2016-07-13 | SUB | 2023-12-31 | Hickory Creek |  |  | 345 |  |  | Hickory Creek Substation modifications | IA |  |  | M1_Final SPM or OOC | 13000000 | Engineering |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3205 | 2014-03-31 | 03 Prop. MVP Port.1 | 6520 | 2013-12-20 | SUB | 2016-12-31 | Huntley (formerly Winnebago) | Substation |  | 345 | 161 | 1800 MVA | Construt a new sub with a 345kV ring bus with 2 line terminals and one 345/161kV TRF. Relocate Winnebago to the new Huntley substation. | IA |  |  | M1_Final SPM or OOC | 27360000 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3205 | 2014-03-31 | 03 Prop. MVP Port.1 | 6535 | 2013-12-20 | LN | 2017-06-01 | Winnebago | Fairbault Co | 1 | 161 |  | 446 MVA | Construct 345-161kV double circuit | IA | 15.13 |  | M1_Final SPM or OOC |  | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3205 | 2014-03-31 | 03 Prop. MVP Port.1 | 6534 | 2013-12-20 | LN | 2017-06-01 | Winnco | Fairbault Co | 1 | 161 |  | 446 MVA | Construct 345-161kV double circuit | MN,IA | 22 |  | M1_Final SPM or OOC |  | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3205 | 2014-03-31 | 03 Prop. MVP Port.1 | 6533 | 2013-12-20 | LN | 2018-06-01 | Ledyard | Burt | 1 | 345 |  | 1800 MVA | Construct 345kV circuit | IA |  | 19 | M1_Final SPM or OOC | 41225660 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3205 | 2014-03-31 | 03 Prop. MVP Port.1 | 6532 | 2013-12-20 | LN | 2017-06-01 | Huntley (formerly Winnebago) | Ledyard | 1 | 161 |  |  | Retire existing 161kV H frame circuit | MN,IA |  |  | M1_Final SPM or OOC | 1105632 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3205 | 2014-03-31 | 03 Prop. MVP Port.1 | 6531 | 2013-12-20 | LN | 2017-06-01 | Huntley (formerly Winnebago) | Ledyard | 1 | 345 |  | 1800 MVA | Construct 345-161kV double circuit | MN,IA |  | 22 | M1_Final SPM or OOC | 47734975 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3205 | 2014-03-31 | 03 Prop. MVP Port.1 | 6530 | 2013-12-20 | SUB | 2017-06-01 | Ledyard | substation | 1 | 345 |  | 1800 MVA | Construct a new Ledyard (formerly Winnco West) 3-terminal 345kV switch station. | IA |  |  | M1_Final SPM or OOC | 10980000 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3205 | 2014-03-31 | 03 Prop. MVP Port.1 | 6529 | 2013-12-20 | SUB | 2016-12-31 | Lakefield | Substation |  | 345 |  | 1800 MVA | Add a 345kV terminal at Lakefield including 2 new 345kv bkrs | IA |  |  | M1_Final SPM or OOC | 5000000 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3205 | 2014-03-31 | 03 Prop. MVP Port.1 | 6528 | 2013-12-20 | LN | 2016-12-31 | Rutland | Winnebago | 1 | 161 |  |  | Retire existing 161kV H frame circuit | MN |  |  | M1_Final SPM or OOC | 804097 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3205 | 2014-03-31 | 03 Prop. MVP Port.1 | 6527 | 2013-12-20 | LN | 2016-12-31 | Fox Lake | Rutland | 1 | 161 |  |  | Retire existing 161kV H frame circuit | MN |  |  | M1_Final SPM or OOC | 804097 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3205 | 2014-03-31 | 03 Prop. MVP Port.1 | 6526 | 2013-12-20 | LN | 2016-12-31 | Rutland | Huntley (formerly Winnebago) | 1 | 161 |  | 446 MVA | Construct 345-161kV double circuit | MN | 15.24 |  | M1_Final SPM or OOC |  | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3205 | 2014-03-31 | 03 Prop. MVP Port.1 | 6525 | 2013-12-20 | LN | 2016-12-31 | Fox Lake | Rutland | 1 | 161 |  | 446 MVA | Construct 345-161kV double circuit | MN | 16.5 |  | M1_Final SPM or OOC |  | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3205 | 2014-03-31 | 03 Prop. MVP Port.1 | 6524 | 2013-12-20 | LN | 2016-12-31 | Lakefield | Fox Lake | 1 | 161 |  | 446 MVA | Construct 345-161kV double circuit | MN | 23 |  | M1_Final SPM or OOC |  | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3205 | 2014-03-31 | 03 Prop. MVP Port.1 | 6523 | 2013-12-20 | LN | 2016-12-31 | Lakefield | Fox Lake | 1 | 161 |  |  | Retire existing 161kV H frame circuit | MN |  |  | M1_Final SPM or OOC | 1155888 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3205 | 2014-03-31 | 03 Prop. MVP Port.1 | 6522 | 2013-12-20 | LN | 2016-12-31 | Lakefield | Huntley (formerly Winnebago) | 1 | 345 |  | 1800 MVA | Construct 345-161kV double circuit | MN |  | 55 | M1_Final SPM or OOC | 119337438 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3205 | 2014-03-31 | 03 Prop. MVP Port.1 | 6521 | 2013-12-20 | TX | 2016-12-31 | Huntley (formerly Winnebago) | transformer |  | 345 | 161 | 450 MVA | Add a 345/161kV TRF | IA |  |  | M1_Final SPM or OOC |  | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3213 | 2014-03-31 | 04 Prop. MVP Port.1 | 6547 | 2013-12-20 | LN | 2016-12-31 | Lime Creek | Emery | 1 | 161 |  |  | Retire existing 161kV H frame circuit | IA |  |  | M1_Final SPM or OOC | 804096 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3213 | 2014-03-31 | 04 Prop. MVP Port.1 | 6546 | 2013-12-20 | LN | 2016-12-31 | Lime Creek | Emery | 1 | 161 |  | 335 MVA | Construct 345-161kV double circuit | IA |  | 16 | M1_Final SPM or OOC |  | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3213 | 2014-03-31 | 04 Prop. MVP Port.1 | 6545 | 2013-12-20 | LN | 2016-12-31 | Lime Creek | Killdeer | 1 | 345 |  | 1800 MVA | Construct 345-161kV double circuit | IA |  | 16 | M1_Final SPM or OOC | 34716345 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3213 | 2014-03-31 | 04 Prop. MVP Port.1 | 6544 | 2013-12-20 | TX | 2016-12-31 | Killdeer | transformer |  | 345 | 161 | 450 MVA | Add a 345/161kV TRF | IA |  |  | M1_Final SPM or OOC |  | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3213 | 2014-03-31 | 04 Prop. MVP Port.1 | 6543 | 2013-12-20 | SUB | 2016-12-31 | Killdeer | Substation |  | 345 | 161 | 1800 MVA | Construt a new sub with a 345kV ring bus with 2 line terminals and one 345/161kV TRF | IA |  |  | M1_Final SPM or OOC | 19380000 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3213 | 2014-03-31 | 04 Prop. MVP Port.1 | 6542 | 2013-12-20 | TX | 2016-12-31 | Lime Creek | transformer |  | 345 | 161 | 450 MVA | Add a 345/161kV TRF | IA |  |  | M1_Final SPM or OOC |  | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3213 | 2014-03-31 | 04 Prop. MVP Port.1 | 6541 | 2013-12-20 | SUB | 2016-12-31 | Lime Creek | Substation |  | 345 | 161 | 1800 MVA | Construt a new sub with a 345kV ring bus with 2 line terminals and one 345/161kV TRF | IA |  |  | M1_Final SPM or OOC | 18930000 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3213 | 2014-03-31 | 04 Prop. MVP Port.1 | 6540 | 2013-12-20 | LN | 2018-12-31 | Lime Creek tap | Lime Creek | 1 | 161 |  |  | Retire existing 161kV H frame circuit | IA |  |  | M1_Final SPM or OOC | 226152 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3213 | 2014-03-31 | 04 Prop. MVP Port.1 | 6539 | 2013-12-20 | LN | 2018-12-31 | Worth County | Lime Creek tap | 1 | 161 |  |  | Retire existing 161kV H frame circuit | IA |  |  | M1_Final SPM or OOC | 251280 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3213 | 2014-03-31 | 04 Prop. MVP Port.1 | 6538 | 2013-12-20 | LN | 2018-12-31 | Winnco West | Winnco | 1 | 161 |  |  | Retire existing 161kV H frame circuit | IA |  |  | M1_Final SPM or OOC | 804096 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3213 | 2014-03-31 | 04 Prop. MVP Port.1 | 6537 | 2013-12-20 | LN | 2018-12-31 | Lime Creek | Worth County | 1 | 161 |  | 200 MVA | Construct 345-161kV double circuit | IA |  | 7 | M1_Final SPM or OOC |  | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3213 | 2014-03-31 | 04 Prop. MVP Port.1 | 6536 | 2013-12-20 | LN | 2018-12-31 | Ledyard | Lime Creek | 1 | 345 |  | 1800 MVA | Construct 345-161kV double circuit | IA |  | 61 | M1_Final SPM or OOC | 132356067 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM | 3412 | 2012-01-07 | FTMadison | 6299 | 2016-06-30 | SUB | 2016-10-07 | Fort Madison | Substation | 1 | 69 |  |  | Add new 69/dist TRF | IA |  |  | M4_Pre-Construction | 1740000 | Engineering |  | N | N | N | Y
A in MTEP11 | A | West | ITCM | 3413 | 2012-01-07 | Gladbrook | 6300 | 2013-06-27 | LN | 2015-12-31 | Gladbrook | Gladbrook Tap | 1 | 161 | 161 |  | Add new 69/dist TRF | IA |  |  | Planned | 300000 | Planning |  | N | N | N | Y
A in MTEP11 | A | West | ITCM | 3413 | 2012-01-07 | Gladbrook | 6302 | 2013-06-27 | LN | 2015-12-31 | Traer | Gladbrook Tap | 1 | 161 | 161 |  | Add new 69/dist TRF | IA |  |  | Planned |  | Planning |  | N | N | N | Y
A in MTEP11 | A | West | ITCM | 3413 | 2012-01-07 | Gladbrook | 6301 | 2013-06-27 | LN | 2015-12-31 | Marshalltown | Gladbrook Tap | 1 | 161 | 161 |  | Add new 69/dist TRF | IA |  |  | Planned |  | Planning |  | N | N | N | Y
A in MTEP11 | A | West | ITCM | 3418 | 2012-01-07 | Mt Vernon 6420 | 6307 | 2012-01-07 | LN | 2015-12-31 | Mt Vernon 6420 | 6420 circuit | 1 | 34 | 34 |  | Rebild ckt 69kV | IA |  |  | Planned | 7150000 | Planning |  | N | N | N | Y
A in MTEP11 | A | West | ITCM | 3422 | 2012-01-07 | S Brdwy TEQ | 6311 | 2014-06-13 | TEQ | 2015-06-30 | South Broadway | Substation | 1 | 69 |  | 195 MVA | Upgrades terminal equipment. Change out existing relays, add new control building, add 69kV bus. | IA |  |  | Planned | 852000 | Engineering |  | N | N | N | Y
A in MTEP11 | A | West | ITCM, MEC | 2248 | 2015-03-24 | 07 Prop. MVP Port.1 | 6566 | 2015-03-24 | TEQ | 2017-06-01 | Ottumwa | 345 kV terminal |  | 345 |  |  | add 345 kV terminal for Zachary line | IA |  |  | M1_Final SPM or OOC | 9360000 |  |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM, MEC | 3213 | 2014-03-31 | 04 Prop. MVP Port.1 | 6549 | 2016-04-01 | LN | 2016-12-31 | Killdeer | Blackhawk | 1 | 161 |  |  | Construct 345-161kV double circuit and transfer existing 161kV conductor | IA |  |  | Under Construction |  | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM, MEC | 3213 | 2014-03-31 | 04 Prop. MVP Port.1 | 6548 | 2013-12-20 | LN | 2016-12-31 | Killdeer | Blackhawk | 1 | 345 |  |  | Construct 345-161kV double circuit | IA |  | 29 | M1_Final SPM or OOC | 57677172 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM, MEC | 3213 | 2014-03-31 | 04 Prop. MVP Port.1 | 6557 | 2016-07-01 | LN | 2017-05-01 | Blackhawk | Killdeer | 1 | 345 |  |  | Blackhawk - Killdeer 345/161 kV double circuit line via Franklin. Includes rebuild of non-MISO 161 kV circuit from Franklin to Emery. | IA | 63 |  | Under Construction | 110626884 | with AFUDC |  | N | Y | Y | Y
A in MTEP11 | A | West | ITCM, MEC | 3213 | 2014-03-31 | 04 Prop. MVP Port.1 | 6550 | 2015-12-22 | LN | 2016-12-31 | Emery | Blackhawk | 1 | 161 |  |  | Retire existing 161kV H frame circuit | IA |  |  | Under Construction | 1457424 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | MDU, OTP | 2220 | 2015-09-29 | 06 Prop. MVP Port.1 | 4092 | 2014-06-10 | LN | 2019-09-30 | Big Stone South | Ellendale |  | 345 |  | 1800 MVA | Line (The cost increase associated with the Big Stone South ? Ellendale 345 kV project is associated with the length of the line increasing by approximately 20 miles since MTEP approval.) | SD,ND |  | 165 | Planned | 365000000 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | MDU, OTP | 2220 | 2015-09-29 | 06 Prop. MVP Port.1 | 6382 | 2016-06-27 | TX | 2019-09-30 | Ellendale 345/230 | Transformer |  | 345 | 230 |  | Substation, Transformer 345/230, Line Reactor | ND |  |  | Planned | 30670000 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | MDU, OTP, XEL | 2221 | 2014-03-24 | 01 Prop. MVP Port.1 (46) | 4116 | 2014-06-10 | TX | 2017-09-30 | Big Stone South 345/230 | Transformer | 1 | 345 | 230 | 448 MVA | Transformer #1 345/230/13.8 kV | SD |  |  | Planned | 4000000 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | MEC | 2248 | 2015-03-24 | 07 Prop. MVP Port.1 | 6565 | 2015-12-23 | LN | 2018-10-01 | Ottumwa | Iowa border | 1 | 345 | 161 |  | 345/161 double circuit line; MEC's portion | IA | 22 |  | M2a_Pre-Project Approval | 38980586.95 |  |  | N | Y | Y | Y
A in MTEP11 | A | West | MEC | 3022 | 2015-04-02 | 16 Prop. MVP Port.1 | 5989 | 2016-03-25 | LN | 2017-04-08 | Oak Grove | Sandburg | 1 | 345 | 161 |  | New 345/161 kV double circuit line. Replaces existing Oak Grove to Galesburg 161 kV line | IA |  | 32 | M2a_Pre-Project Approval | 68319117.67 |  |  | N | Y | Y | Y
A in MTEP11 | A | West | MEC | 3022 | 2015-04-02 | 16 Prop. MVP Port.1 | 6564 | 2015-12-23 | LNrc | 2017-04-30 | Sub 56 | Sub 85 |  | 161 |  | 410 | Reconductor Sub 56-Sub 85 161 kV line with T2- 556.5 ACSR conductor | IA | 7.5 |  | M1_Final SPM or OOC | 2588989.63 |  |  | N | Y | Y | Y
A in MTEP11 | A | West | MEC | 3022 | 2015-04-02 | 16 Prop. MVP Port.1 | 6562 | 2016-03-25 | TEQ | 2017-04-08 | Oak Grove | 345 kV terminal |  | 345 |  |  | add 345 kV terminal for Sandburg line | IA |  |  | M2a_Pre-Project Approval | 2046383.81 |  |  | N | Y | Y | Y
A in MTEP11 | A | West | MEC | 3205 | 2014-03-31 | 03 Prop. MVP Port.1 | 5951 | 2015-07-01 | LN | 2016-12-01 | Obrien County | Webster |  | 345 |  | 1739 | Obrien County to Webster 345/161 kV double ckt line - Candidate MVP Portfolio #1. Includes rebuild of non-MISO 161 kV circuit from Wisdom to Webster. | IA |  | 122 | Under Construction | 244590889.32 | with AFUDC |  | N | Y | Y | Y
A in MTEP11 | A | West | MEC | 3205 | 2014-03-31 | 03 Prop. MVP Port.1 | 6561 | 2016-07-01 | SUB | 2016-07-31 | Kossuth Co. |  |  | 345 |  |  | New three-way 345 kV Kossuth County Switching Station near Burt Substation | IA |  |  | Under Construction | 16238014 |  |  | N | Y | Y | Y
A in MTEP11 | A | West | MEC | 3213 | 2014-03-31 | 04 Prop. MVP Port.1 | 6425 | 2016-04-01 | LNup | 2016-12-15 | Butler | Union Tap | 1 | 161 |  | 410 | Rebuild Butler-Union Tap 161 kV line. | IA | 15.93 |  | Under Construction |  | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | MEC | 3213 | 2014-03-31 | 04 Prop. MVP Port.1 | 6424 | 2016-04-01 | LNup | 2016-09-30 | Franklin | Butler | 1 | 161 |  | 410 | Rebuild Franklin-Butler 161 kV line. | IA | 26.24 |  | Under Construction |  | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | MP | 2634 | 2012-12-04 | 20388 | 6370 | 2014-01-31 | LN | 2016-03-31 | Savanna | Floodwood Tap | 1 | 115 |  | 122 | Thermal upgrade of Savanna-9 Line tap | MN | 10 |  | Planned | 5647421 | Engineering |  | N | Y | N | Y
A in MTEP11 | A | West | OTP | 3481 | 2015-10-26 | OTP | 6434 | 2016-06-23 | TX | 2017-06-30 | Buffalo 345 kV | Buffalo 115/41.6 kV | 1 | 345 | 115 | 187 MVA | Add a second 112 MVA 345/115/41.6 kV transformer instead of a single, larger xfmr and add a four breaker 345kV ring bus | ND |  |  | Under Construction | 5600000 | Planning |  | N | Y | N | Y
A in MTEP11 | A | West | OTP, XEL | 2221 | 2014-03-24 | 01 Prop. MVP Port.1 (46) | 6383 | 2014-06-10 | LN | 2017-09-30 | Big Stone | Big Stone South | 1 | 230 |  | 674 MVA | Line #1 | SD |  | 2 | Planned | 2000000 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | OTP, XEL | 2221 | 2014-03-24 | 01 Prop. MVP Port.1 (46) | 6589 | 2013-01-03 | TX | 2017-09-30 | Big Stone 230 | Big Stone 230 |  | 230 | 230 |  | Substation Equipment | SD |  |  | Planned | 10000000 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | OTP, XEL | 2221 | 2014-03-24 | 01 Prop. MVP Port.1 (46) | 6588 | 2013-01-03 | TX | 2017-09-30 | Big Stone South Sub | Equipment |  | 345 | 230 |  | Substation Equipment | SD |  |  | Planned | 30000000 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | OTP, XEL | 2221 | 2014-03-24 | 01 Prop. MVP Port.1 (46) | 6572 | 2013-01-03 | SUB | 2017-09-30 | Brookings County | Substation |  | 345 |  |  | Termination for Big Stone - Brookings Co 345 kV line and conversion of the existing ring bus to a breaker-and-a-half | SD |  |  | Planned | 9720000 | Engineering |  | N | Y | Y | Y
A in MTEP11 | A | West | OTP, XEL | 2221 | 2014-03-24 | 01 Prop. MVP Port.1 (46) | 6387 | 2014-06-10 | TX | 2017-09-30 | Big Stone South 345/230 | Transformer | 2 | 345 | 230 | 448 MVA | Transformer #2 345/230/13.8 kV | SD |  |  | Planned | 4000000 | Planning |  | N | Y | Y | Y
A in MTEP11 | A | West | OTP, XEL | 2221 | 2014-03-24 | 01 Prop. MVP Port.1 (46) | 6384 | 2014-06-10 | LN | 2017-09-30 | Big Stone | Big Stone South | 2 | 230 |  | 674 MVA | Line #2 | SD |  | 2 | Planned | 2000000 | Planning |  | N | Y | Y | Y
A in MTEP12 | A | Central | AmerenMO | 3366 | 2015-09-11 |  | 6237 | 2015-09-11 | CB | 2018-12-01 | Wallen Creek | Install 1200 A breaker and disconnect switches |  | 138 |  | 240 | Install 2000 A breaker and 2-2000 A 138 kV motor operated disconnect switches | MO |  |  | Planned | 2635000 | Engineering |  | N | N | N | Y
A in MTEP12 | A | Central | BREC | 3792 | 2012-04-20 | Matanzas | 7127 | 2013-06-07 | LN | 2016-01-01 | BR Tap (3 terminal midpoint) | Matanzas (LKE) | 1 | 161 |  | 509 | 10.5 Mile 161 kV of line from Wilson Substation to new 161kV station - only 600 feet of new construction required. | KY |  | 0.2 | Under Construction |  | Planning |  | N | N | N | Y
A in MTEP12 | A | Central | DEI | 3542 | 2015-09-15 | AMIN0447 | 6611 | 2015-09-15 | Dist | 2017-06-01 | New Castle Ingersoll |  |  | 69 | 12 |  | New Castle Ingersoll 1 Bank 2 Repl ? Replace 34/12kV bank w/22MVA 69/12kV Bank. Add 69kV tap line to existing sub. | IN |  | 0.23 | M3_Long Lead Materials | 579657 | Engineering |  | N | N | N | NT
A in MTEP12 | A | East | ITCT | 3591 | 2016-03-22 | ITC_13_028 | 6690 | 2016-03-22 | TEQ | 2016-05-31 | St. Clair |  |  | 345 |  |  | Replace 345kV station equipment in the B, C and D rows at St. Clair. | MI |  |  | Under Construction | 924000 |  |  | N | N | N | Y
A in MTEP12 | A | East | ITCT | 3624 | 2016-03-23 |  | 6731 | 2016-03-22 | Dist | 2016-12-31 | Blanket for Customer Interconnections 2016 | Throughout system |  | 120 |  |  | Connect interconnecting entities as requested | MI |  |  | Under Construction | 2000000 |  |  | N | N | N | Y
A in MTEP12 | A | East | METC | 3590 | 2015-02-26 |  | 8297 | 2015-02-26 | SVC | 2030-06-01 | Tippy | SVC |  | 138 |  |  | Install an svc at tippy sub | MI |  |  | Planned | 28500000 |  |  | N | Y | N | Y
A in MTEP12 | A | East | METC | 3599 | 2014-03-31 |  | 6698 | 2015-09-28 | TEQ | 2018-12-31 | Palisades |  |  | 345 |  |  | Upgrade the station equipment at Palisades in rows 25, 27, and 29 for the existing configuration. | MI |  |  | M4_Pre-Construction | 4000000 |  |  | N | N | N | Y
A in MTEP12 | A | East | METC | 3625 | 2016-03-23 |  | 6732 | 2016-03-22 | Dist | 2016-12-31 | Blanket for Customer Interconnections 2016 | Throughout system |  | 138 |  |  | Connect interconnecting entities as requested | MI |  |  | Under Construction | 2500000 |  |  | N | N | N | Y
A in MTEP12 | A | West | ATC | 1270 | 2015-09-15 | PR04508, F4199,WO68710 | 1989 | 2015-10-19 | LNup | 2025-06-01 | Arcadian | Waukesha | 2 | 138 |  | 504 | Rebuild Ck 2 of Arcadian to Waukesha 138 kV Line | WI | 3.88 |  | M1_Final SPM or OOC | 23406000 | Engineering |  | N | Y | N | Y
A in MTEP12 | A | West | ATC | 1270 | 2015-09-15 | PR04508, F4199,WO68710 | 1990 | 2015-10-19 | LNup | 2025-06-01 | Arcadian | Waukesha | 1 | 138 |  | 504 | Rebuild Ck 1 of Arcadian to Waukesha 138 kV Line | WI | 4.06 |  | M1_Final SPM or OOC |  | Engineering |  | N | Y | N | Y
A in MTEP12 | A | West | ATC | 3679 | 2014-06-13 | NP-Package2_3 F3501 WO069260 | 6910 | 2015-10-19 | LN | 2016-08-13 | Holmes | Old Mead Road | 1 | 138 |  | 294 | New 138kV line from Holmes - Old Mead Road | MI |  | 65 | M1_Final SPM or OOC | 101600000 | Engineering |  | N | Y | N | Y
A in MTEP12 | A | West | ATC | 3679 | 2014-06-13 | NP-Package2_3 F3501 WO069260 | 7243 | 2016-06-30 | SUB | 2018-10-25 | Morgan |  |  | 345 |  |  | Morgan 345 kV substation expansion | WI |  |  | M1_Final SPM or OOC | 13987000 | Engineering |  | N | Y | Y | Y
A in MTEP12 | A | West | ATC | 3679 | 2014-06-13 | NP-Package2_3 F3501 WO069260 | 7242 | 2015-10-19 | TX | 2016-08-13 | Old Mead Road |  | 2 | 138 | 69 | 60 | Add new 2nd 138/69 kV Transformer at Old Mead Road | MI |  |  | M1_Final SPM or OOC | 4300000 | Engineering |  | N | N | N | Y
A in MTEP12 | A | West | ATC | 3679 | 2014-06-13 | NP-Package2_3 F3501 WO069260 | 6923 | 2016-06-30 | LN | 2017-03-31 | Morgan | Stiles | 2 | 138 |  | 294 | Debifurcate Morgan-Falls-Pioneer-Stiles 138 kV ckt to form new Morgan-Stiles 138 kV ckt | WI |  | 11 | M1_Final SPM or OOC | 6669000 | Engineering |  | N | Y | N | Y
A in MTEP12 | A | West | ATC | 3679 | 2014-06-13 | NP-Package2_3 F3501 WO069260 | 6919 | 2016-06-30 | SVC | 2017-08-01 | Benson Lake |  | 1 | 138 |  |  | New 150 MVAR SVC at Benson Lake (near Amberg) | MI |  |  | M1_Final SPM or OOC | 40213000 | Engineering |  | N | Y | N | Y
A in MTEP12 | A | West | ATC | 3679 | 2014-06-13 | NP-Package2_3 F3501 WO069260 | 6912 | 2016-06-30 | LN | 2018-10-25 | North Appleton | Morgan | 1 | 345 |  | 1204 | New 345 kV line from North Appleton - Morgan | WI |  | 40 | M1_Final SPM or OOC | 155814000 | Engineering |  | N | Y | Y | Y
A in MTEP12 | A | West | ATC | 3679 | 2014-06-13 | NP-Package2_3 F3501 WO069260 | 6911 | 2016-06-30 | SUB | 2018-05-13 | North Appleton |  |  | 345 |  |  | New 345 kV Switchyard North Appleton | WI |  |  | M1_Final SPM or OOC | 34265000 | Engineering |  | N | Y | Y | Y
A in MTEP12 | A | West | ATC | 3952 | 2014-06-13 | NP_GB-M 138, PR05016 F3501 WO069260 | 6926 | 2016-06-30 | TX | 2018-05-13 | North Appleton |  | 1 | 345 | 138 | 500 | New 345/138kV Transformer at North Appleton | WI |  |  | M1_Final SPM or OOC | 7700000 | Engineering |  | N | N | N | Y
A in MTEP12 | A | West | ATC | 3952 | 2014-06-13 | NP_GB-M 138, PR05016 F3501 WO069260 | 6927 | 2016-06-30 | LN | 2018-10-28 | North Appleton | Morgan | 1 | 138 |  | 294 | New 138 kV line from North Appleton-Morgan | WI |  | 40 | M1_Final SPM or OOC | 69011000 | Engineering |  | N | N | N | Y
A in MTEP12 | A | West | GRE | 3470 | 2011-01-11 |  | 6397 | 2014-03-25 | GEN | 2014-12-31 | G667-200987 | Round Lake Tap |  |  |  |  | Connection on GRE Round Lake tap | MN |  |  | Planned | 722000 | Engineering | Network | N | N | N | Y
A in MTEP12 | A | West | GRE | 11543 | 2016-07-25 | 200497 | 21785 | 2016-07-25 | TAP | 2018-11-01 | Glacial Ridge |  |  | 69 |  |  | Install new 69kV 3-way switch structure. | MN |  |  | Planned | 150000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | GRE | 11563 | 2016-07-25 | 202038 | 21786 | 2016-07-19 | SUB | 2017-11-01 | McHenry |  |  | 115 |  |  | Install 115 kV ring bus | ND |  |  | Planned | 4952173 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3627 | 2011-12-13 | Chariton-Corydon | 6750 | 2016-06-30 | LN | 2016-12-30 | Chariton | Derby REC | 1 | 69 |  | 77 MVA | Rebuild line section. | IA | 4.5 |  | Under Construction | 2044831 | Engineering |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3627 | 2011-12-13 | Chariton-Corydon | 6752 | 2016-06-30 | LN | 2016-12-30 | Millerton | Corydon | 1 | 69 |  | 77 MVA | Rebuild line section. | IA | 5.38 |  | Under Construction | 2444704 | Engineering |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3627 | 2011-12-13 | Chariton-Corydon | 6751 | 2016-06-30 | LN | 2016-12-30 | Millerton | Derby REC | 1 | 69 |  | 77 MVA | Rebuild line section. | IA | 8.5 |  | Under Construction | 3862451 | Engineering |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3628 | 2011-12-13 | Lehigh SS | 6733 | 2015-06-30 | LN | 2017-08-25 | General Foods | Northwest Tap | 1 | 69 |  | 77 MVA | Build a new 69kV line from the General Foods substation to the Northwest substation. | IA |  |  | M1_Final SPM or OOC | 1494000 | Engineering |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3628 | 2011-12-13 | Lehigh SS | 9083 | 2015-06-30 | LN | 2017-08-25 | Holnam | New 69kV Tap | 1 | 69 |  |  | Install new GOAB and 69kV tap | IA |  |  | M1_Final SPM or OOC | 490000 | Engineering |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3628 | 2011-12-13 | Lehigh SS | 9082 | 2015-06-30 | LN | 2017-08-25 | Nettle | Northwest Switch Station | 1 | 69 |  |  | Rebuild the Nettle to old Lehigh site 69kV line and install OPGQ to NWSS. | IA |  |  | M1_Final SPM or OOC | 1305600 | Engineering |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3628 | 2011-12-13 | Lehigh SS | 6736 | 2015-06-30 | SUB | 2017-08-25 | Lehigh | Substation | 1 | 69 |  |  | Retire the existing Lehigh switch station | IA |  |  | M1_Final SPM or OOC | 60000 | Engineering |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3628 | 2011-12-13 | Lehigh SS | 6735 | 2015-06-30 | SUB | 2017-08-25 | Nettle | Substation | 1 | 69 |  |  | New 3 terminal Nettle Lehigh area switch station | IA |  |  | M1_Final SPM or OOC | 3135600 | Engineering |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3628 | 2011-12-13 | Lehigh SS | 6734 | 2015-06-30 | LN | 2017-08-25 | Holnam | Lehigh | 1 | 69 |  | 77 MVA | Retire the existing Lehgihg to Holnam 69kV line section | IA |  |  | M1_Final SPM or OOC | 270000 | Engineering |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3629 | 2013-06-27 | 3rd DBQ CKT | 6744 | 2016-09-27 | LN | 2016-12-31 | 8th Street | Salem | 1 | 161 | 69 |  | Build 3.5 miles of new 161kV line, 8th Street sub work, Salem sub work | IA |  | 3.5 | Under Construction | 7222073 | Engineering |  | N | Y | N | Y
A in MTEP12 | A | West | ITCM | 3629 | 2013-06-27 | 3rd DBQ CKT | 6746 | 2016-09-27 | SUB | 2016-12-31 | 8th Street | Substation | 1 | 161 |  | 558 MVA | Add new 161kV terminal and reroute line to new terminal. | IA |  |  | Under Construction |  | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3629 | 2013-06-27 | 3rd DBQ CKT | 6745 | 2016-09-27 | SUB | 2016-12-31 | Salem | Substation | 1 | 161 |  | 558 MVA | Add new 161kV terminal and 161kv bus tie breaker | IA |  |  | Under Construction |  | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3630 | 2011-12-13 | Adams-Stewartville | 6739 | 2014-03-31 | LN | 2018-12-31 | Adams | Stewartvillle 6th Street | 1 | 69 |  | 77 MVA | Rebuild 69kV line to T2-4/0 ACSR | IA | 29.88 |  | Planned | 10500000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3630 | 2011-12-13 | Adams-Stewartville | 6740 | 2014-03-31 | LN | 2018-12-31 | Stewartvillle 6th Street | Stewartville Junction | 1 | 69 |  | 77 MVA | Rebuild 69kV line to T2-4/0 ACSR | IA | 4.68 |  | Planned | 1700000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3631 | 2011-12-13 | RockCrk-MillCrk | 6772 | 2015-12-30 | LN | 2017-12-31 | Rock Creek | CMP NT | 1 | 69 |  | 140 MVA | Rebuild the 69kV line section | IA | 1.2 |  | M1_Final SPM or OOC | 1250000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3631 | 2011-12-13 | RockCrk-MillCrk | 6773 | 2015-12-30 | LN | 2017-12-31 | CMP NT | Mill Creek | 1 | 69 |  | 140 MVA | Rebuild the 69kV line section | IA | 3.6 |  | M1_Final SPM or OOC | 1250000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3632 | 2011-12-13 | Arnold 161 | 6753 | 2015-06-30 | SUB | 2017-12-31 | Arnold | Substation | 1 | 161 |  |  | Add two new 161kV breakers and reroute Hiawatha line terminal off the generation bus. | IA |  |  | Planned | 2400000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3638 | 2011-12-13 | Corydon Sub Rbld | 6755 | 2016-06-30 | SUB | 2017-12-31 | Corydon | Substation | 1 | 69 |  | 143 MVA | Complte rebuild of the Corydon sub | IA |  |  | M1_Final SPM or OOC | 5129204 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3639 | 2011-12-13 | Chariton Sub Rbld | 6754 | 2016-06-30 | SUB | 2016-09-02 | Chariton | Substation | 1 | 69 |  | 143 MVA | Complte rebuild of the Chariton sub | IA |  |  | Under Construction | 7683367 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3640 | 2011-12-13 | Belmond-Meservey | 6761 | 2016-06-30 | LN | 2018-12-31 | Belmond | Meservey Tap | 1 | 69 |  | 77 MVA | Rebuild the 69kV line section | IA | 4.65 |  | M1_Final SPM or OOC | 1627500 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3643 | 2011-12-13 | Osceola-Woodburn | 6765 | 2016-06-30 | LN | 2022-12-31 | Osceola | Woodburn Junction | 1 | 69 |  | 77 MVA | Rebuild the 69kV line section | IA | 5.5 |  | M1_Final SPM or OOC | 1950000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3644 | 2011-12-13 | Knoxville-Lucas | 6766 | 2016-06-30 | LN | 2021-12-31 | Knoxville | Lucas | 1 | 69 |  | 77 MVA | Rebuild the 69kV line section | IA | 10.6 |  | M1_Final SPM or OOC | 3750000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3645 | 2011-12-13 | Tirboji-Orleans Tap | 6767 | 2014-06-13 | LN | 2017-12-31 | Triboji | Montgomery | 1 | 69 |  | 77 MVA | Rebuild the 69kV line section | IA | 5.75 |  | M1_Final SPM or OOC | 2000000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3645 | 2011-12-13 | Tirboji-Orleans Tap | 6770 | 2014-06-13 | LN | 2017-12-31 | Spirti Lake | Orleans Tap | 1 | 69 |  | 77 MVA | Rebuild the 69kV line section | IA | 0.4 |  | M1_Final SPM or OOC | 200000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3645 | 2011-12-13 | Tirboji-Orleans Tap | 6769 | 2014-06-13 | LN | 2017-12-31 | Bosworth | Spirti Lake | 1 | 69 |  | 77 MVA | Rebuild the 69kV line section | IA | 1.17 |  | M1_Final SPM or OOC | 400000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3645 | 2011-12-13 | Tirboji-Orleans Tap | 6768 | 2014-06-13 | LN | 2017-12-31 | Bosworth | Montgomery | 1 | 69 |  | 77 MVA | Rebuild the 69kV line section | IA | 2.16 |  | M1_Final SPM or OOC | 750000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3647 | 2011-12-13 | East IA Rebuilds | 7116 | 2015-12-30 | LN | 2021-12-31 | Dixon | Fulton | 1 | 34 |  | 77 MVA | Rebuild the 34kV line section to 69kV for future conversion | IA | 17 |  | M1_Final SPM or OOC | 5950000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3647 | 2011-12-13 | East IA Rebuilds | 7115 | 2014-06-13 | LN | 2015-12-31 | Zwingle | Mosalem REC | 1 | 34 |  | 77 MVA | Rebuild the 34kV line section to 69kV for future conversion | IA |  | 8 | M1_Final SPM or OOC | 2800000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3647 | 2011-12-13 | East IA Rebuilds | 7114 | 2015-12-30 | LN | 2019-12-31 | PCI | Putnam | 1 | 34 |  | 77 MVA | Rebuild the 34kV line section to 69kV for future conversion | IA |  | 0.5 | M1_Final SPM or OOC | 175000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3647 | 2011-12-13 | East IA Rebuilds | 7113 | 2016-06-30 | LN | 2017-09-28 | Mt Vernon | Lisbon | 1 | 34 |  | 77 MVA | Rebuild the 34kV line section to 69kV for future conversion | IA | 2 | 2 | M1_Final SPM or OOC | 1400000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3647 | 2011-12-13 | East IA Rebuilds | 7112 | 2015-12-30 | LN | 2018-12-31 | Manchester Tap | Manchester Industrial | 1 | 34 |  | 77 MVA | Rebuild the 34kV line section to 69kV for future conversion | IA |  | 0.5 | M1_Final SPM or OOC | 175000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3647 | 2011-12-13 | East IA Rebuilds | 7111 | 2015-12-30 | LN | 2018-12-31 | Clarence | Clarence REC | 1 | 34 |  | 77 MVA | Rebuild the 34kV line section to 69kV for future conversion | IA |  | 2 | M1_Final SPM or OOC | 700000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3647 | 2011-12-13 | East IA Rebuilds | 7110 | 2015-12-30 | LN | 2018-12-31 | Rome Tap | Rome | 1 | 34 |  | 77 MVA | Rebuild the 34kV line section to 69kV for future conversion | IA |  | 2 | M1_Final SPM or OOC | 700000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3647 | 2011-12-13 | East IA Rebuilds | 7109 | 2015-12-30 | LN | 2016-12-31 | Coggon | Manchester Industrial | 1 | 34 |  | 77 MVA | Rebuild the 34kV line section to 69kV for future conversion | IA |  | 2.5 | M1_Final SPM or OOC |  | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3647 | 2011-12-13 | East IA Rebuilds | 6816 | 2015-12-30 | LN | 2017-04-28 | Prairie Creek | Bertam JU | 1 | 34 |  | 77 MVA | Rebuild the 34kV line section to 69kV for future conversion | IA | 6 |  | M1_Final SPM or OOC | 2100000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3647 | 2011-12-13 | East IA Rebuilds | 6815 | 2015-12-30 | LN | 2018-06-01 | Clarence | Wyoming | 1 | 34 |  | 77 MVA | Rebuild the 34kV line section to 69kV for future conversion | IA | 11 |  | M1_Final SPM or OOC | 3850000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3647 | 2011-12-13 | East IA Rebuilds | 6814 | 2014-06-13 | LN | 2015-12-31 | Clarence | Clarence Tap | 1 | 34 |  | 77 MVA | Rebuild the 34kV line section to 69kV for future conversion | IA | 1 |  | M1_Final SPM or OOC | 350000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3647 | 2011-12-13 | East IA Rebuilds | 6813 | 2015-04-14 | LN | 2017-12-31 | Cascade Muni | Cascade Muni Tap | 1 | 34 |  | 77 MVA | Rebuild the 34kV line section to 69kV for future conversion | IA | 1 |  | M1_Final SPM or OOC | 350000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3647 | 2011-12-13 | East IA Rebuilds | 6812 | 2015-12-30 | LN | 2017-01-13 | Ryan REC | Ryan REC tap | 1 | 34 |  | 77 MVA | Rebuild the 34kV line section to 69kV for future conversion | IA | 1 |  | M1_Final SPM or OOC | 350000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3648 | 2011-12-13 | Marshalltown-Grand Jct | 6800 | 2014-06-13 | LN | 2015-12-31 | Story City | Ames | 1 | 34 |  | 77 MVA | Rebuild the 34kV line section to 69kV for future conversion | IA | 3.5 |  | M1_Final SPM or OOC | 1200000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3648 | 2011-12-13 | Marshalltown-Grand Jct | 6799 | 2014-06-13 | LN | 2015-12-31 | Gilbert | Ames | 1 | 34 |  | 77 MVA | Rebuild the 34kV line section to 69kV for future conversion | IA | 4.7 |  | M1_Final SPM or OOC | 2000000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3648 | 2011-12-13 | Marshalltown-Grand Jct | 6798 | 2016-06-30 | LN | 2017-03-17 | Marion | Nevada Street | 1 | 34 |  | 77 MVA | Rebuild the 34kV line section to 69kV for future conversion | IA | 1.4 |  | M1_Final SPM or OOC | 500000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3648 | 2011-12-13 | Marshalltown-Grand Jct | 6791 | 2015-12-30 | LN | 2019-12-31 | Boone Jct | Ridgeport REC | 1 | 34 |  | 77 MVA | Rebuild the 34kV line section to 69kV for future conversion | IA | 2.75 |  | M1_Final SPM or OOC | 1200000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3648 | 2011-12-13 | Marshalltown-Grand Jct | 6807 | 2014-06-13 | LN | 2016-12-31 | Ames NADC | Ames Mine Tap | 1 | 34 |  | 77 MVA | Rebuild the 34kV line section to 69kV for future conversion | IA | 2 |  | M1_Final SPM or OOC | 700000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3648 | 2011-12-13 | Marshalltown-Grand Jct | 6806 | 2015-12-30 | LN | 2016-02-12 | Boone Jct | Clear Lake Tap | 1 | 34 |  | 77 MVA | Rebuild the 34kV line section to 69kV for future conversion | IA | 3.4 |  | Under Construction | 1200000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3648 | 2011-12-13 | Marshalltown-Grand Jct | 6805 | 2016-06-30 | LN | 2019-02-28 | Valley RECTap | Odgen Muni Tap | 1 | 34 |  | 77 MVA | Rebuild the 34kV line section to 69kV for future conversion | IA | 1.7 |  | M1_Final SPM or OOC | 600000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3648 | 2011-12-13 | Marshalltown-Grand Jct | 6804 | 2016-06-30 | LN | 2016-07-11 | Boone South | Valley RECTap | 1 | 34 |  | 77 MVA | Rebuild the 34kV line section to 69kV for future conversion | IA | 1.15 |  | Under Construction | 400000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3648 | 2011-12-13 | Marshalltown-Grand Jct | 6803 | 2015-12-30 | LN | 2018-03-23 | Quartz Ave | Boone South | 1 | 34 |  | 77 MVA | Rebuild the 34kV line section to 69kV for future conversion | IA | 5.2 |  | M1_Final SPM or OOC | 1700000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3648 | 2011-12-13 | Marshalltown-Grand Jct | 6802 | 2015-12-30 | LN | 2017-03-17 | Ames Mine | Ames Mine Tap | 1 | 34 |  | 77 MVA | Rebuild the 34kV line section to 69kV for future conversion | IA | 1.5 |  | M1_Final SPM or OOC | 300000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3648 | 2011-12-13 | Marshalltown-Grand Jct | 6801 | 2014-06-13 | LN | 2015-12-31 | William Bros Pipline | Roland | 1 | 34 |  | 77 MVA | Rebuild the 34kV line section to 69kV for future conversion | IA | 2 |  | M1_Final SPM or OOC | 500000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3649 | 2011-12-13 | Plaza LI | 6758 | 2016-02-02 | SUB | 2020-12-31 | Plaza | Substation | 1 | 161 |  | 143 MVA | New Plaza 161/12.5kV substation with 161kV in and out breakers and bus tie breaker | IA |  |  | M1_Final SPM or OOC | 1550000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3649 | 2011-12-13 | Plaza LI | 6760 | 2016-02-02 | LN | 2020-12-31 | Plaza | Marshalltown | 1 | 161 |  |  | Tap the Marshalltown-Timber Creek 161kV for new Plaza sub. | IA |  |  | M1_Final SPM or OOC | 100000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | ITCM | 3649 | 2011-12-13 | Plaza LI | 6759 | 2016-02-02 | LN | 2020-12-31 | Plaza | Timber Creek | 1 | 161 |  |  | Tap the Marshalltown-Timber Creek 161kV for new Plaza sub. | IA |  |  | M1_Final SPM or OOC | 100000 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | MEC | 3710 | 2014-03-31 | T3094 | 7023 | 2016-03-30 | SUB | 2021-07-01 | Norwalk |  |  | 161 | 13.2 | 33 | Norwalk 161-13 kV XFMR | IA |  |  | Planned | 886413 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | XEL | 3769 | 2011-12-13 | Mankato - Twin Cities through flow mitigation | 7048 | 2015-06-30 | LN | 2019-03-01 | Carver County | Arlington | 1 | 69 |  |  | Rebuild 13 miles of 69 kV line to 477 ACSR to reduce impedance and increase capacity | MN | 13 |  | Planned | 4155551 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | XEL | 3775 | 2011-12-13 | Couderay - Osprey 161 kV line | 7070 | 2016-06-30 | TX | 2017-01-27 | Osprey |  |  | 161 | 115 |  | A 161/115 kV transformer will be added at Osprey and a termiation in the current 115 kV yard | WI |  |  | Under Construction | 7000000 | Scoping |  | N | Y | N | Y
A in MTEP12 | A | West | XEL | 3797 | 2012-01-07 | Maple River - Red River 2nd 115 kV circuit | 7134 | 2016-07-01 | LN | 2017-10-31 | Maple River | Red River | 2 | 115 |  |  | New 5 mile 115 kV line | ND |  |  | Planned | 11797665 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | XEL | 3797 | 2012-01-07 | Maple River - Red River 2nd 115 kV circuit | 7136 | 2016-07-01 | SUB | 2017-12-22 | Red River | substation |  | 115 |  |  | New Line and Termination Work | ND |  |  | Planned | 2338410 | Planning |  | N | N | N | Y
A in MTEP12 | A | West | XEL | 3797 | 2012-01-07 | Maple River - Red River 2nd 115 kV circuit | 7135 | 2016-07-01 | SUB | 2017-12-22 | Maple River | substation |  | 115 |  |  | New Line and Termination Work | ND |  |  | Planned | 1483410 | Planning |  | N | N | N | Y
A in MTEP13 | A | Central | AmerenIL | 2302 | 2013-02-25 |  | 4218 | 2015-09-21 | LN | 2016-12-01 | Madison Industrial | Madison State Street | 1 | 138 |  | 240 | Reconductor 795 SAC to 1200 A summer emergency capability | IL | 2.35 |  | Planned | 1637000 | Engineering |  | N | N | N | Y
A in MTEP13 | A | Central | AmerenIL | 4272 | 2012-11-09 |  | 8052 | 2015-12-03 | LN | 2016-12-01 | Grand Tower | Makanda | 1 | 138 |  | 269 | Grand Tower-Makanda-1 138 kV Line - Rebuild 16.91 miles of existing 556 kcmil ACSR conductor with conductor capable of carrying 1200 A under summer emergency conditions. | IL | 16.91 |  | Planned |  |  |  | N | N | N | Y
A in MTEP13 | A | Central | CWLP | 4270 | 2012-11-19 | NAuburn-CthmMain 138 | 8048 | 2012-11-19 | LNrc | 2014-06-01 | N Auburn | Chatham Main | 1 | 138 | 138 | 382 MVA | Reconductor N Auburn- Chatham Main 138 kV Line to 795 ACSS | IL | 2.6 |  | Planned | 130000 | Planning |  | N | N | N | Y
A in MTEP13 | A | Central | DEI | 4029 | 2012-09-12 | AMIN0705 | 7662 | 2015-12-30 | LNrb | 2016-12-31 | Sylvania | Yedo | 1 | 69 |  | 100 | Rebuild radial tap in the 6935 ckt from Sylvania to Kingman to Yedo with 477acsr @ 100C and upgrade Kingman line switches (2) to 1200A. | IN | 6.8 |  | Under Construction | 2770000 | Engineering |  | N | N | N | NT
A in MTEP13 | A | Central | DEI | 4030 | 2012-09-12 | AMIN0706 | 7663 | 2016-03-01 | LNrb | 2016-12-31 | Cayuga 69 | Gessie Jct. | 1 | 69 |  | 100 | Rebuild 6936 ckt from Cayuga 69 sub towards Gessie Jct. (str. 804-2501) with 477acsr @ 100C | IN | 6.2 |  | M4_Pre-Construction | 3100000 | Engineering |  | N | N | N | NT
A in MTEP13 | A | Central | DEI | 4032 | 2012-09-12 | AMIN0744 | 7665 | 2015-09-10 | CB | 2017-12-31 | Five Points 230kV | brkr replacements |  | 230 | 138 |  | Five Points Station Upgrade Phase I ? Install new prefabricated control building. Replace 230kV breakers and relays. Replace 230kV circuit switchers with 230kV breakers. Replace 230-138kV bank protection. Replace 230kV bus protection. 230kV wave traps | IN |  |  | M3_Long Lead Materials | 5406000 | Engineering |  | N | N | N | Y
A in MTEP13 | A | Central | DEI | 4033 | 2016-01-14 | AMIN0758 | 7666 | 2016-01-14 | LNrb | 2017-12-31 | Camp Atterbury | Edinburg |  | 69 |  | 100 | Camp Atterbury to Edinburg 6950 Reconductor 2/0 Cu (4.0 miles) to 477ACSR and uprate existing 477ACSR 80C to 477ACSR 100C (4.5 miles). | IN | 8.5 |  | M3_Long Lead Materials | 1650765 | Engineering |  | N | N | N | NT
A in MTEP13 | A | Central | DEI | 4037 | 2012-09-12 | AMIN0841 | 7670 | 2016-08-23 | SUB | 2019-12-31 | Lafayette 230 | breaker |  | 230 |  |  | Lafayette 230kV Sub Ring Bus - Phase 2, install one 230kV breaker, support structures, bus and 954KCM jumpers to complete five-breaker - 230kV ring bus. Insert between Banks 3 and 4. | IN |  |  | M3_Long Lead Materials | 1618000 | Engineering |  | N | N | N | Y
A in MTEP13 | A | Central | IPL | 4724 | 2015-04-03 |  | 8953 | 2015-09-03 | SUB | 2016-04-16 | Eagle Valley 138 kV Substation | new gen i-connect |  | 138 |  |  | J238 - 138kV - Generator interconnection substation - install 4 bay breaker and a half design substation for 725MW Eagle Valley CCGT in Morgan county Indiana at the existing Pritchard Plant site. | IN |  |  | Under Construction |  |  |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 1550 | 2016-03-23 | ITC_12_012 | 2639 | 2016-03-23 | LNug | 2016-12-31 | Hager | Sunset | 1 | 120 |  |  | Replace the 0.08 miles of underground 1500 KCM CU XLPE SSC 120 kV conductor from the Hager to Sunset 120 kV circuit with 5000 KCM CU XLPE 120 kV conductor. Also address clearance issues causing the sag limit on the 954 ACSR overhead conductor portion of this circuit | MI | 0.1 |  | M4_Pre-Construction | 2200000 | Engineering |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 3938 | 2016-04-22 | ITCT_12_008 | 7500 | 2016-04-22 | CAP | 2017-07-15 | Greenwood |  |  | 120 |  |  | Install two 120kV, 26 Mvar capacitors capacitor banks at the Greenwood substation with 2 synchronous breakers and a 120 kV line breaker. | MI |  |  | M3_Long Lead Materials | 2020000 | Engineering |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 4145 | 2016-03-23 | ITC_12_009 | 7880 | 2016-03-23 | LNug | 2016-12-31 | Quaker | Southefield |  | 120 |  |  | Reconductor the 0.36 mile Quaker to Southfield Underground cable section using 5000 KCM CU XLPE cable | MI | 0.36 |  | M4_Pre-Construction | 3960000 | Engineering |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 4153 | 2015-06-29 | ITC_13_021 | 7892 | 2015-09-28 | SwSta | 2017-12-31 | Toll Road 120kV |  |  | 120 |  |  | Construct a 120kV switching station (Toll Road). | MI |  |  | M3_Long Lead Materials | 15000000 | Engineering |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 4153 | 2015-06-29 | ITC_13_021 | 8318 | 2015-06-29 | SVC | 2018-12-31 | Toll Road |  |  | 120 |  |  | Install a 100 MVAR SVC at Toll Road. | MI |  |  | M2a_Pre-Project Approval | 25000000 | Planning |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 4153 | 2015-06-29 | ITC_13_021 | 8317 | 2015-09-28 | LN | 2017-12-31 | Toll Road | Fermi | 3 | 120 |  |  | Loop the existing Fermi - Swan Creek 120kV line into Toll Road. | MI |  |  | M3_Long Lead Materials |  |  |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 4153 | 2015-06-29 | ITC_13_021 | 7898 | 2015-09-28 | LN | 2017-12-31 | Toll Road | Swan Creek | 1 | 120 |  |  | Loop the existing Fermi - Swan Creek 120kV line into Toll Road. | MI |  |  | M3_Long Lead Materials |  |  |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 4153 | 2015-06-29 | ITC_13_021 | 7897 | 2015-09-28 | LN | 2017-12-31 | Toll Road | Fermi | 2 | 120 |  |  | Loop the existing Fermi - Radka 120kV line into Toll Road. | MI |  |  | M3_Long Lead Materials |  |  |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 4153 | 2015-06-29 | ITC_13_021 | 7896 | 2015-09-28 | LN | 2017-12-31 | Toll Road | Radka | 1 | 120 |  |  | Loop the existing Fermi - Radka 120kV line into Toll Road. | MI |  |  | M3_Long Lead Materials |  |  |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 4153 | 2015-06-29 | ITC_13_021 | 7895 | 2015-09-28 | LN | 2017-12-31 | Toll Road | Fermi | 1 | 120 |  |  | Loop the existing Fermi - Shoal 120kV line into Toll Road. | MI |  |  | M3_Long Lead Materials |  |  |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 4153 | 2015-06-29 | ITC_13_021 | 7894 | 2015-09-28 | LN | 2017-12-31 | Toll Road | Shoal | 1 | 120 |  |  | Loop the existing Fermi - Shoal 120kV line into Toll Road. | MI |  |  | M3_Long Lead Materials |  |  |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 4159 | 2014-01-31 | ITC-008 | 7906 | 2016-03-22 | LNrb | 2016-12-31 | ITCT Wood Pole Replacement 2016 | Throughout system |  |  |  |  | Replace aging wood poles with concrete poles or steel towers. | MI |  |  | Under Construction | 8500000 |  |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 4163 | 2014-01-31 | ITC-010 | 7910 | 2016-03-22 | TEQ | 2016-12-31 | ITCT Surge Arrestor Replacement 2016 | Throughout system |  |  |  |  | Replace old Silicon Carbide and Gap-type surge arresters with the new MOV gapless type ones in substations. | MI |  |  | Under Construction | 360000 |  |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 4171 | 2014-01-31 | ITC-014 | 7918 | 2016-03-22 | TEQ | 2016-12-31 | ITCT Misc Line Equipment Replacement 2016 | Throughout system |  |  |  |  | Replace cross arms that need to be replaced to maintain lines in serviceable conditions. Replace defective and damaged insulators for system reliability. Replace defective pole guying for system reliability or to meet code issues. | MI |  |  | Under Construction | 5000000 |  |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 4175 | 2016-08-30 | ITC-015 | 6706 | 2016-03-22 | TEQ | 2016-12-31 | Seville 1 & 2 |  |  | 120 |  |  | Install a new 120 kV, 3-way, full-load-break pole top switch at each tap | MI |  |  | M4_Pre-Construction |  |  |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 4175 | 2016-08-30 | ITC-015 | 7922 | 2014-11-06 | TEQ | 2014-12-31 | ITCT Pole Top Switch Additions/Replacement 2014 | Throughout system |  |  |  |  | Install a new or replace an existing120 kV, 1-way, full-load-break pole top switch at needed tap points. | MI |  |  | Under Construction | 2400000 |  |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 4175 | 2016-08-30 | ITC-015 | 6711 | 2016-03-22 | TEQ | 2016-06-30 | Topaz 2 | Peru |  | 120 |  |  | Install a new 120 kV, 1-way, full-load-break pole top switch (toward Peru) | MI |  |  | M4_Pre-Construction |  |  |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 4176 | 2016-08-30 | ITC-016 | 7923 | 2015-03-25 | TEQ | 2015-12-31 | ITCT Pole Top Switch Additions/Replacement 2015 | Throughout system |  |  |  |  | Install a new or replace an existing120 kV, 1-way, full-load-break pole top switch at needed tap points. | MI |  |  | Under Construction | 2400000 |  |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 4176 | 2016-08-30 | ITC-016 | 6705 | 2016-06-08 | TEQ | 2016-12-31 | Long Lake 1 & 2 |  |  | 120 |  |  | Install 2 new 120 kV, 1-way, full-load-break pole top switches at each tap | MI |  |  | M4_Pre-Construction |  |  |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 4177 | 2016-08-30 | ITC-017 | 7924 | 2016-03-22 | TEQ | 2016-12-31 | ITCT Pole Top Switch Additions/Replacement 2016 | Throughout system |  |  |  |  | Install a new or replace an existing120 kV, 1-way, full-load-break pole top switch at needed tap points. | MI |  |  | Under Construction | 2400000 |  |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 4181 | 2014-01-31 | ITC-019 | 7928 | 2016-03-22 | TEQ | 2016-12-31 | ITCT Instrument Transformer Replacement 2016 | Throughout system |  |  |  |  | Replace the aging potential devices including potential transformers and coupling-capacitor type potential devices. | MI |  |  | Under Construction | 360000 |  |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 4187 | 2014-01-31 | ITC-022 | 7934 | 2016-03-22 | TEQ | 2016-12-31 | ITCT NERC Protection Compliance Program 2016 | Throughout system |  |  |  |  | Upgrade relay throughout system. | MI |  |  | Under Construction | 2400000 |  |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 4191 | 2014-01-31 | ITC-024 | 7938 | 2016-03-22 | CB | 2016-12-31 | ITCT Breaker Replacement 2016 | Throughout system |  |  |  |  | Replace defective breakers throughout system | MI |  |  | Under Construction | 6250000 |  |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 4195 | 2014-01-31 | ITC-026 | 7942 | 2016-03-22 | TEQ | 2016-12-31 | ITCT Battery Replacement 2016 | Throughout system |  |  |  |  | Replace battery chargers with the new ones. | MI |  |  | Under Construction | 200000 |  |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 4199 | 2014-01-31 | ITC-31 | 7946 | 2016-03-22 | TEQ | 2016-12-31 | ITCT Disconnect Switch Replacement Program 2016 | Throughout system |  |  |  |  | Replace problematic Pennsylvania Type A6A-2, EEE, RI&E, WESTINGHOUSE, HK-PORTER, AND DELTA-STAR disconnect switches (or any disconnect switches with problematic auxiliary latch assemblies) | MI |  |  | Under Construction | 400000 |  |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 4204 | 2014-01-31 | ITC-028 | 7951 | 2016-03-22 | TEQ | 2016-12-31 | ITCT Annual Relay Betterment Program 2016 | Throughout system |  |  |  |  | Replace damaged or defective relays. | MI |  |  | Under Construction | 10400000 |  |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 4286 | 2015-04-03 | ITC_12_015 | 8093 | 2015-03-25 | LN | 2018-05-31 | Frisbie | Waterman | 1 | 120 |  |  | Loop in the Frisbie ? Waterman 120 kV underground cable to feed the Henry Ford substation. Splices and terminals will be installed and underground cable run from the existing line to the new substation. The substation is located approximated 150 feet fro | MI |  |  | M2a_Pre-Project Approval | 5000000 | Engineering |  | N | N | N | Y
A in MTEP13 | A | East | ITCT | 4287 | 2016-08-15 | ITC_12_034 | 8094 | 2016-08-15 | LN | 2017-03-31 | Lincoln | Northeast | 1 | 120 |  |  | Loop the Lincoln - Northeast 120 kV circuit to feed the new Hilton Road (formerly Ferndale) substation. The substation is located adjacent to the circuit. At the new station, 3-120 kV breakers and the associated 120 kV station equipment will be installed. | MI |  |  | M4_Pre-Construction | 3800000 | Engineering |  | N | N | N | Y
A in MTEP13 | A | East | METC | 4143 | 2016-03-22 | METC_12_017 | 7877 | 2016-03-22 | TEQ | 2016-12-31 | Verona |  | 1 | 138 |  |  | Upgrade Terminal Equipment at Verona 138 kV (position 388). | MI |  |  | M4_Pre-Construction | 80000 | Engineering |  | N | N | N | Y
A in MTEP13 | A | East | METC | 4146 | 2016-07-14 | METC_12_023 | 7881 | 2016-07-14 | LNrb | 2016-12-31 | Marshall | Blackstone | 1 | 138 |  |  | Rebuild 34.5 miles to 954 ACSR conductor | MI | 34.5 |  | Under Construction | 46300000 | Engineering |  | N | N | N | Y
A in MTEP13 | A | East | METC | 4147 | 2016-02-22 | METC_12_024 | 7882 | 2016-06-08 | LNrb | 2017-06-01 | Battle Creek | Island Road | 1 | 138 |  |  | Rebuild 23.9 miles to 954 ACSR conductor | MI | 23.9 |  | M4_Pre-Construction | 24300000 | Engineering |  | N | N | N | Y
A in MTEP13 | A | East | METC | 4149 | 2015-12-28 | METC_12_026 | 7884 | 2015-12-28 | LNup | 2016-06-30 | Argenta | Tallmadge | 1 | 345 |  |  | Remediate sag on the Argenta ? Tallmadge 345kV line to bring its thermal rating up to 2422 Amp (1447 MVA) | MI |  |  | M4_Pre-Construction | 1500000 | Engineering |  | N | N | N | Y
A in MTEP13 | A | East | METC | 4150 | 2016-03-22 | METC_12_014 | 7885 | 2016-03-22 | TEQ | 2016-12-31 | Verona |  | 1 | 138 |  |  | Upgrade station equipment at Verona 138kV (position 277). | MI |  |  | M4_Pre-Construction | 140000 | Engineering |  | N | N | N | Y
A in MTEP13 | A | East | METC | 4157 | 2013-09-13 | METC-009 | 7904 | 2016-03-22 | LNrb | 2016-12-31 | METC Wood Pole Replacement 2016 | Throughout system |  |  |  |  | Replace defective wood poles with concrete poles or steel towers. | MI |  |  | Under Construction | 9000000 |  |  | N | N | N | Y
A in MTEP13 | A | East | METC | 4161 | 2012-09-14 | METC-011 | 7908 | 2016-03-22 | TEQ | 2016-12-31 | METC Surge Arrestor Replacement 2016 | Throughout system |  |  |  |  | Replace old Silicon Carbide and Gap-type surge arresters with the new MOV gapless type ones in substations. | MI |  |  | Under Construction | 360000 |  |  | N | N | N | Y
A in MTEP13 | A | East | METC | 4167 | 2013-09-13 | METC-015 | 7914 | 2016-03-22 | LNup | 2016-12-31 | METC Misc Line Equipment Replacement 2016 | Throughout system |  |  |  |  | Replace cross arms that need to be replaced to maintain lines in serviceable conditions. Replace defective and damaged insulators for system reliability. Replace defective pole guying for system reliability or to meet code issues. | MI |  |  | Under Construction | 6000000 |  |  | N | N | N | Y
A in MTEP13 | A | East | METC | 4174 | 2016-08-30 | METC-018 | 7921 | 2016-03-22 | TEQ | 2016-12-31 | METC Pole Top Switch Additions/Replacement 2016 | Throughout system |  |  |  |  | Install or replace an existing a new 138 kV, 2-way, full-load-break pole top switch at needed tap points. | MI |  |  | Under Construction | 3600000 |  |  | N | N | N | Y
A in MTEP13 | A | East | METC | 4179 | 2013-09-13 | METC-020 | 7926 | 2016-03-22 | TEQ | 2016-12-31 | METC Instrument Transformer Replacement - Year 2016 | Throughout system |  |  |  |  | Replace the aging instrument transformers including potential transformers and coupling-capacitor type instrument transformers. | MI |  |  | Under Construction | 360000 |  |  | N | N | N | Y
A in MTEP13 | A | East | METC | 4184 | 2012-09-14 | METC-023 | 7931 | 2016-03-22 | TEQ | 2016-12-31 | METC NERC Protection Compliance Program 2016 | Throughout system |  |  |  |  | Upgrade relay throughout system. | MI |  |  | Under Construction | 2400000 |  |  | N | N | N | Y
A in MTEP13 | A | East | METC | 4189 | 2012-09-14 | METC-025 | 7936 | 2016-03-22 | CB | 2016-12-31 | METC Breaker Replacement 2016 | Throughout system |  |  |  |  | Replace defective breakers throughout system | MI |  |  | Under Construction | 9000000 |  |  | N | N | N | Y
A in MTEP13 | A | East | METC | 4193 | 2013-09-13 | METC-027 | 7940 | 2016-03-22 | TEQ | 2016-12-31 | METC Battery Replacement 2016 | Throughout system |  |  |  |  | Replace battery chargers with the new ones. | MI |  |  | Under Construction | 120000 |  |  | N | N | N | Y
A in MTEP13 | A | East | METC | 4203 | 2013-06-13 | METC-033 | 7950 | 2016-03-22 | TEQ | 2016-12-31 | METC Disconnect Switch Replacement Program 2016 | Throughout system |  |  |  |  | Replace problematic Pennsylvania Type A6A-2, EEE, RI&E, WESTINGHOUSE, HK-PORTER, AND DELTA-STAR disconnect switches (or any disconnect switches with problematic auxiliary latch assemblies) | MI |  |  | Under Construction | 900000 |  |  | N | N | N | Y
A in MTEP13 | A | East | METC | 4205 | 2012-09-14 | METC-029 | 7952 | 2016-03-22 | TEQ | 2016-12-31 | METC Annual Relay Betterment Program 2016 | Throughout system |  |  |  |  | Replace damaged or defective relays. | MI |  |  | Under Construction | 7000000 |  |  | N | N | N | Y
A in MTEP13 | A | East | METC | 4207 | 2016-08-30 | METC-031 | 7954 | 2016-03-22 | TEQ | 2016-12-31 | METC Power Plant Control Relocation 2016 | Throughout system |  |  |  |  | Replace controls for METC substations that currently exist in power plant buildings. Locate new controls in dedicated METC control houses. | MI |  |  | Under Construction | 2400000 |  |  | N | N | N | Y
A in MTEP13 | A | East | METC | 4218 | 2015-12-28 | METC_12_027 | 7965 | 2016-06-08 | LNup | 2016-06-30 | Bass Creek | Black River | 1 | 138 |  |  | Remediate the sag limit on the Bass Creek - Black River 138kV line up its conductor rating of 208 MVA (871 A) | MI |  |  | M4_Pre-Construction | 180000 | Engineering |  | N | N | N | Y
A in MTEP13 | A | East | WPSC | 4084 | 2015-04-03 | NS-VB | 7737 | 2016-09-15 | LNrb | 2018-12-31 | North Shade | Vestaburg | 1 | 69 |  | 143.4MVA | Rebuild Line (Poles have reached the end of their useful life) | MI | 19.29 |  | Planned | 10000000 |  |  | N | N | N | Y
A in MTEP13 | A | East | WPSC | 4085 | 2015-04-03 | LC-FNX | 7738 | 2015-09-15 | LNrb | 2016-12-31 | Lake County | Fountain Junction | 1 | 69 |  | 143.4MVA | Rebuild Overloaded line (Peak case) | MI | 6.35 |  | Planned | 3100000 |  |  | N | N | N | Y
A in MTEP13 | A | West | ATC | 3813 | 2014-01-31 | PR04982,F3654 | 7160 | 2014-09-26 | LNrc | 2017-12-31 | Dam Heights | Eagleview | 1 | 69 |  | 79 | Reconductor Dam Heights-Eagleview 69 kV line with T2-4/0 | WI | 0.1 |  | M1_Final SPM or OOC |  | Engineering |  | N | N | N | Y
A in MTEP13 | A | West | ATC | 3813 | 2014-01-31 | PR04982,F3654 | 7164 | 2014-06-13 | LNrc | 2017-12-31 | Caledonia | Portage | 1 | 69 |  | 41 | Reconductor Caledonia-Portage 69 kV line with T2-4/0 | WI | 7 |  | M1_Final SPM or OOC |  | Engineering |  | N | N | N | Y
A in MTEP13 | A | West | ATC | 3813 | 2014-01-31 | PR04982,F3654 | 7163 | 2014-06-13 | LNrc | 2017-12-31 | Merrimac Tap | Caledonia | 1 | 69 |  | 41 | Reconductor Merrimac Tap-Caledonia 69 kV line with T2-4/0 | WI | 8.4 |  | M1_Final SPM or OOC |  | Engineering |  | N | N | N | Y
A in MTEP13 | A | West | ATC | 3813 | 2014-01-31 | PR04982,F3654 | 7162 | 2015-09-30 | LNrc | 2017-12-31 | Merrimac Tap | Merrimac | 1 | 69 |  | 79 | Reconductor Merrimac Tap-Merrimac 69 kV line with T2-4/0 | WI | 1.8 |  | M1_Final SPM or OOC | 33700000 | Engineering |  | N | N | N | Y
A in MTEP13 | A | West | ATC | 3813 | 2014-01-31 | PR04982,F3654 | 7161 | 2014-06-13 | LNrc | 2017-12-31 | Eagleview | Merrimac Tap | 1 | 69 |  | 41 | Reconductor Eagleview-Merrimac Tap 69 kV line with T2-4/0 | WI | 8.4 |  | M1_Final SPM or OOC |  | Engineering |  | N | N | N | Y
A in MTEP13 | A | West | ATC | 3817 | 2016-01-11 | PR04856 | 7168 | 2016-09-29 | CB | 2017-12-01 | Shoto |  |  | 138 |  |  | Shoto 138-69 kV Tr highside breaker additions | WI |  |  | M3_Long Lead Materials | 4325000 |  |  | N | N | N | Y
A in MTEP13 | A | West | ATC | 3841 | 2014-01-31 | PR05179,F3680,F3681 | 7268 | 2015-10-19 | LN | 2016-12-01 | Pulliam | Liberty St | 1 | 138 |  | 246 | Existing line conversion from 69 to 138 from Pulliam to Liberty St | WI | 3.93 |  | M1_Final SPM or OOC | 22675655 | Engineering, Nominal |  | N | N | N | Y
A in MTEP13 | A | West | ATC | 3841 | 2014-01-31 | PR05179,F3680,F3681 | 7274 | 2015-10-19 | TX | 2016-03-01 | Glory Rd |  |  | 138 | 69 | 154 | New Transformer at Glory Rd | WI |  |  | M1_Final SPM or OOC |  |  |  | N | N | N | Y
A in MTEP13 | A | West | ATC | 3841 | 2014-01-31 | PR05179,F3680,F3681 | 7273 | 2015-10-19 | TX | 2016-12-01 | Pulliam |  |  | 138 | 69 | 154 | New Transformer at Pulliam | WI |  |  | M1_Final SPM or OOC |  |  |  | N | N | N | Y
A in MTEP13 | A | West | ATC | 3841 | 2014-01-31 | PR05179,F3680,F3681 | 7272 | 2015-10-19 | SUB | 2016-03-01 | Pulliam | [5 empty] | Substation work to accommodate new 138 kV line | WI |  |  | M1_Final SPM or OOC |  |  |  | N | N | N | Y
A in MTEP13 | A | West | ATC | 3841 | 2014-01-31 | PR05179,F3680,F3681 | 7269 | 2015-10-19 | LN | 2016-03-01 | Liberty St | Ashland Ave | 1 | 138 |  | 246 | Existing line conversion from 69 to 138 from Liberty St to Ashland Ave | WI | 2.81 |  | M1_Final SPM or OOC |  |  |  | N | N | N | Y
A in MTEP13 | A | West | ATC | 3892 | 2013-02-18 | PR05233 | 7437 | 2016-09-29 | LN | 2017-01-01 | Stage Coach | Black Earth | 1 | 69 |  | 83 | Uprate Stagecoach-Wick Drive 69 kV line | WI |  |  | M1_Final SPM or OOC | 3500000 |  |  | N | N | N | Y
A in MTEP13 | A | West | ATC | 3892 | 2013-02-18 | PR05233 | 7439 | 2016-03-30 | LN | 2017-01-01 | Mazomanie | Wick Drive | 1 | 69 |  | 70 | Uprate Stagecoach-Wick Drive 69 kV line | WI |  |  | M1_Final SPM or OOC |  |  |  | N | N | N | Y
A in MTEP13 | A | West | ATC | 3892 | 2013-02-18 | PR05233 | 7438 | 2016-03-30 | LN | 2017-01-01 | Black Earth | Mazomanie | 1 | 69 |  | 70 | Uprate Stagecoach-Wick Drive 69 kV line | WI |  |  | M1_Final SPM or OOC |  |  |  | N | N | N | Y
A in MTEP13 | A | West | ATC | 3895 | 2014-01-31 | PR04860,F4003,WO069303 | 7442 | 2016-06-30 | LN | 2016-06-01 | Oak Creek | Ramsey | 1 | 138 |  | 233 | Reconductor Oak Creek-Ramsey to meet line clearances needed for new rating | WI | 0.33 |  | M3_Long Lead Materials | 830000 |  |  | N | N | N | Y
A in MTEP13 | A | West | ATC | 3895 | 2014-01-31 | PR04860,F4003,WO069303 | 7443 | 2015-10-19 | LN | 2016-06-01 | Ramsey | Kansas | 1 | 138 |  | 246 | Reconductor Ramsey-Kansas to meet line clearances needed for new rating | WI |  |  | M3_Long Lead Materials |  |  |  | N | N | N | Y
A in MTEP13 | A | West | GRE | 3531 | 2015-08-10 | Deer River | 8039 | 2014-04-09 | LN | 2015-03-31 | Deer River | Enbridge-Deer River | 1 | 115 |  | 239 | GRE will provide 3 way motor-operated switch to accommodate MP 115 kV line from Enbridge | MN |  |  | Planned | 400000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | GRE | 3531 | 2015-08-10 | Deer River | 20918 | 2015-08-10 | TX | 2015-10-01 | Blackberry | Transformer |  | 115 | 69 | 70 | Upgrade the 46.7 MVA 115/69 kV Blackberry xfmr with a 70 MVA 115/69 kV xfmr. | MN |  |  | Planned | 2148264 |  |  | N | N | N | Y
A in MTEP13 | A | West | GRE | 4008 | 2014-09-15 | 201610 | 7635 | 2016-06-29 | TAP | 2016-08-31 | New Market |  | 1 | 69 |  | 190 | Replace the current 69kV switch with a manual quick whip 115kV switch | MN | 0 |  | Planned | 200000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | GRE | 4009 | 2012-09-11 | 20462 | 7641 | 2016-09-08 | SUB | 2017-02-06 | St. Bonifacius |  |  | 115 | 69 | 70 | Install second 115/69 kV transformer, 115 kV ring bus, split 69 kV bus | MN | 0 |  | Planned | 10185577.27 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4099 | 2012-09-14 | AleaW-SBroadway | 7763 | 2016-06-30 | LN | 2021-12-31 | Albert Lea Westside | South Broadway | 1 | 69 | 69 | 40 MVA | Rebuild the Albert Lea Westside-South Broadway 69kV to T2-4/0. | MN | 2 |  | M1_Final SPM or OOC | 840000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4101 | 2012-09-14 | Montgomery-Waseca | 7765 | 2016-06-30 | LN | 2016-12-31 | Montgomery | GRE-French Lake Tap | 1 | 69 | 69 | 77 MVA | Rebuild the Montgomery-French Lake tap to T2-4/0. | MN | 13.25 |  | Under Construction | 12483427 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4101 | 2012-09-14 | Montgomery-Waseca | 7766 | 2016-06-30 | LN | 2020-12-31 | GRE-French Lake Tap | Waseca Junction | 1 | 69 | 69 | 77 MVA | Rebuild the French Lake tap-Waseca Jct. to T2-4/0. | MN | 16.34 |  | M3_Long Lead Materials | 13654256 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4102 | 2012-09-14 | Columbus Jct-Newport | 7767 | 2016-06-30 | LN | 2021-12-31 | Newport | Cairo REC | 1 | 69 | 69 | 36 MVA | Rebuild the Newport-Cairo REC 69kV to T2-4/0. | IA | 8.65 |  | M1_Final SPM or OOC | 6242696 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4102 | 2012-09-14 | Columbus Jct-Newport | 7770 | 2016-06-30 | LN | 2021-12-31 | IBP Tap | Columbus Jct | 1 | 69 | 69 | 59 MVA | Rebuild the IBP Tap-Columbus Jct 69kV to T2-4/0. | IA | 0.1 |  | M1_Final SPM or OOC | 72170 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4102 | 2012-09-14 | Columbus Jct-Newport | 7769 | 2016-06-30 | LN | 2021-12-31 | Winfield Tap | IBP Tap | 1 | 69 | 69 | 77 MVA | Rebuild the Winfield Tap-IBP Tap 69kV to T2-4/0. | IA | 7.61 |  | M1_Final SPM or OOC | 5492130 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4102 | 2012-09-14 | Columbus Jct-Newport | 7768 | 2016-06-30 | LN | 2021-12-31 | Cairo REC | Winfield Tap | 1 | 69 | 69 | 77 MVA | Rebuild the Cairo REC-Winfield Tap 69kV to T2-4/0. | IA | 2.76 |  | M1_Final SPM or OOC | 1991889 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4103 | 2012-09-14 | NBurl-Mediapolis | 7771 | 2015-04-13 | LN | 2016-09-01 | North Burlington | North Burlington Tap | 1 | 69 | 69 | 69 MVA | Rebuild the North Burlington-North Burlington Tap 69kV to T2-4/0. | IA | 8.76 |  | M1_Final SPM or OOC | 5760000 | Engineering |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4104 | 2012-09-14 | Lansing-Monona | 7772 | 2016-06-29 | LN | 2020-12-31 | Lansing | Harper's Ferry Tap | 1 | 69 | 69 | 57 MVA | Rebuild the Lansing-Harper's Ferry Tap 69kV to T2-4/0. | IA | 6.57 |  | M3_Long Lead Materials | 5777996 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4104 | 2012-09-14 | Lansing-Monona | 7774 | 2016-06-29 | LN | 2020-12-31 | WatervilleTap | Monona | 1 | 69 | 69 | 48 MVA | Rebuild the Waterville Tap-Monona 69kV to T2-4/0. | IA | 15.59 |  | M3_Long Lead Materials | 13025337 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4104 | 2012-09-14 | Lansing-Monona | 7773 | 2016-06-29 | LN | 2020-12-31 | Harper's Ferry Tap | WatervilleTap | 1 | 69 | 69 | 77 MVA | Rebuild the Harper's Ferry Tap-Waterville Tap 69kV to T2-4/0. | IA | 2.63 |  | M3_Long Lead Materials | 2171703 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4105 | 2012-09-14 | Decorah-Waukon | 7775 | 2016-06-29 | LN | 2022-12-31 | Decorah | Ludlow Tap | 1 | 69 | 69 | 69 MVA | Rebuild the Decorah-Ludlow Tap 69kV to T2-4/0. | IA | 20.48 |  | M1_Final SPM or OOC | 8600000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4105 | 2012-09-14 | Decorah-Waukon | 7776 | 2016-06-29 | LN | 2022-12-31 | Ludlow Tap | Waukon - IPL | 1 | 69 | 69 | 59 MVA | Rebuild the Ludlow Tap-Waukon 69kV to T2-4/0. | IA | 2.51 |  | M1_Final SPM or OOC | 1060000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4106 | 2012-09-14 | Windsor-Richfield | 7777 | 2015-06-30 | LN | 2020-12-31 | Windsor | Hawk Tap | 1 | 69 | 69 | 48 MVA | Rebuild the Windsor-Hawk Tap 69kV to T2-4/0. | IA | 6.6 |  | M1_Final SPM or OOC | 2775000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4106 | 2012-09-14 | Windsor-Richfield | 7778 | 2015-06-30 | LN | 2020-12-31 | Hawk Tap | Richfield | 1 | 69 | 69 | 45 MVA | Rebuild the Hawk Tap-Richfield 69kV to T2-4/0. | IA | 4.64 |  | M1_Final SPM or OOC | 1975000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4107 | 2012-09-14 | Emery-Lehigh | 7782 | 2015-06-30 | LN | 2017-08-04 | Armour | Lehigh Quarry Tap | 1 | 69 | 69 | 77 MVA | Rebuild the Armour-Nettle to T2-4/0 | IA | 1.87 |  | M1_Final SPM or OOC | 1078800 | Engineering |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4107 | 2012-09-14 | Emery-Lehigh | 7784 | 2015-06-30 | LN | 2017-08-04 | Nettle | Lehigh Quarry Tap | 1 | 69 | 69 | 77 MVA | Rebuild the line from 25th Street Tap-Lehigh Quarry Tap to T2-4/0 | IA | 1.65 |  | M1_Final SPM or OOC | 600000 | Engineering |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4107 | 2012-09-14 | Emery-Lehigh | 7783 | 2015-06-30 | LN | 2017-08-04 | Nettle | Northwest Tap | 1 | 69 | 69 | 77 MVA | Rebuild the 25th Street Tap-Northwest Tap to T2-4/0 | IA | 1.01 |  | M1_Final SPM or OOC | 616800 | Engineering |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4108 | 2012-09-14 | Ellendale-WOwatonna | 7779 | 2016-06-30 | LN | 2022-12-31 | Ellendale | Steele Center Tap | 1 | 69 | 69 | 77 MVA | Rebuild the Ellendale-Steele Center Tap to T2-4/0 | MN | 1.98 |  | M1_Final SPM or OOC | 1091365 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4108 | 2012-09-14 | Ellendale-WOwatonna | 7781 | 2016-06-30 | LN | 2022-12-31 | Pratt Tap | West Owatonna | 1 | 69 | 69 | 77 MVA | Rebuild the Pratt Tap-West Owatonna to T2-4/0 | MN | 4.25 |  | M1_Final SPM or OOC | 2342576 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4108 | 2012-09-14 | Ellendale-WOwatonna | 7780 | 2016-06-30 | LN | 2022-12-31 | Steele Center Tap | Pratt Tap | 1 | 69 | 69 | 77 MVA | Rebuild the Steele Center Tap-Pratt Tap to T2-4/0 | MN | 6.98 |  | M1_Final SPM or OOC | 3847336 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4113 | 2012-09-14 | Hayward TEQ | 7794 | 2014-03-31 | TEQ | 2015-04-30 | Hayward | Substation | 1 | 161 | 69 | 250 MVA | Upgrade 69kV breaker 665 terminal equipment | MN |  |  | Planned | 15000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4114 | 2012-09-14 | Triboji TEQ | 7795 | 2014-03-31 | TEQ | 2015-04-30 | Triboji | Substation | 1 | 161 | 69 | 250 MVA | Upgrade 69kV breaker 6730 terminal equipment | IA |  |  | Planned | 15000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4114 | 2012-09-14 | Triboji TEQ | 7796 | 2014-03-31 | TEQ | 2015-04-30 | Flying Cloud | Substation | 1 | 161 | 69 | 250 MVA | Change CT ratio to increase capacity/coordinate with Triboji work | IA |  |  | Planned | 5000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4115 | 2012-09-14 | Fletcher Sub | 7808 | 2016-06-30 | SUB | 2019-12-31 | Fletcher | Substation | 1 | 161 | 69 |  | Build new Fletcher 161kV & 69kV sub | IA |  |  | M1_Final SPM or OOC | 5173600 | Engineering |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4115 | 2012-09-14 | Fletcher Sub | 7809 | 2016-06-30 | TX | 2019-12-31 | Fletcher | Transformer | 1 | 161 | 69 | 150 MVA | New Fletcher 150 MVA 161/69kV TRF | IA |  |  | M1_Final SPM or OOC | 2000000 | Engineering |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4116 | 2012-09-14 | East IA phase 2 | 7807 | 2014-06-13 | LN | 2016-12-31 | Linn TWP REC | Cornell | 1 | 69 | 69 | 77 MVA | Build a new Linn TWP REC-Cornell 69kV with T2-4/0 | IA |  | 4.2 | M1_Final SPM or OOC | 1760000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4116 | 2012-09-14 | East IA phase 2 | 7806 | 2016-06-28 | LN | 2017-12-31 | Lovell REC | Monticello Industrial | 1 | 69 | 69 | 77 MVA | Rebuild the Lovell REC-Monticello Industrial to T2-4/0 | IA | 5.4 |  | M1_Final SPM or OOC | 2270000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4116 | 2012-09-14 | East IA phase 2 | 7804 | 2016-06-28 | LN | 2017-12-31 | Springville | Amber | 1 | 69 | 69 | 77 MVA | Rebuild the Springville-Amber to T2-4/0 | IA | 21.1 |  | M1_Final SPM or OOC | 9120000 | Engineering |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4118 | 2012-09-14 | Grand Jct-Jeff WCC | 7798 | 2016-06-30 | LN | 2017-12-25 | Grand Junction | Grand Jct REC Tap | 1 | 34 | 34 | 39 MVA | Rebuild the Grand Jct-Grand Jct REC Tap to T2-4/0 | IA | 0.1 |  | M1_Final SPM or OOC | 62000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4118 | 2012-09-14 | Grand Jct-Jeff WCC | 7800 | 2016-06-30 | LN | 2017-12-25 | Grant REC Tap | Jefferson WCC | 1 | 34 | 34 | 39 MVA | Rebuild the Grant REC TapJefferson WCC to T2-4/0 | IA | 0.25 |  | M1_Final SPM or OOC | 739800 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4118 | 2012-09-14 | Grand Jct-Jeff WCC | 7799 | 2016-06-30 | LN | 2017-12-25 | Grand Jct REC Tap | Grant REC Tap | 1 | 34 | 34 | 39 MVA | Rebuild the Grand Jct REC Tap-Grant REC Tap to T2-4/0 | IA | 6.4 |  | M1_Final SPM or OOC | 5315800 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4121 | 2012-09-14 | Cust Interconnet Blanket | 7821 | 2016-06-09 | LN | 2016-12-31 | Blanket for Customer Interconnections under $1 million for 2013 | Throughout system |  |  |  |  | These projects are being done at the request of an interconnection customer in order to facilitate new load, re-distribute existing load, improve the performance of the sub-transmission and distribution systems, or to accommodate a new Transmission-to-Transmission connection request. | IA,MN |  |  | Under Construction | 2000000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4122 | 2012-09-14 | Misc Line Blanket | 7825 | 2016-06-09 | LN | 2016-12-31 | Blanket for Misc. Line Equipment Replacement 2016 | Throughout system |  |  |  |  | Replace defective cross arms, insulators, arrestors, and pole quuys | IA,MN |  |  | Under Construction | 4000000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4123 | 2012-09-14 | Breaker Blanket | 7829 | 2016-06-09 | LN | 2016-12-31 | Blanket for Breaker Replacement Program 2016 | Throughout system |  |  |  |  | Replace defective and damaged breakers | IA,MN |  |  | Under Construction | 5000000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4124 | 2012-09-14 | Fiber Optic Blanket | 7832 | 2016-06-09 | LN | 2016-12-31 | Blanket for Fiber Optic Static Wire Additions 2016 | Throughout system |  |  |  |  | Project includes the Engineering, Procurement, Construction and Commissioning of Fiber Optic Static Wire Additions for use with ITCM?s SCADA system and protective relaying. | IA,MN |  |  | Under Construction | 720000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4125 | 2012-09-14 | PCB Blanket | 7836 | 2012-09-14 | LN | 2016-12-31 | Blanket for Replacement of PCB Equipment 2016 | Throughout system |  |  |  |  | Replace known and unknown PCB equipment in substations due to environmental hazard with expensive remediation. | IA,MN |  |  | Planned | 1800000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4125 | 2012-09-14 | PCB Blanket | 7835 | 2012-09-14 | LN | 2015-12-31 | Blanket for Replacement of PCB Equipment 2015 | Throughout system |  |  |  |  | Replace known and unknown PCB equipment in substations due to environmental hazard with expensive remediation. | IA,MN |  |  | Planned | 1800000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4126 | 2012-09-14 | Pole Top Switch Blanket | 7840 | 2016-06-09 | LN | 2016-12-31 | Blanket for Pole Top Switch Replacement Program 2016 | Throughout system |  |  |  |  | Replace defective pole top switches | IA,MN |  |  | Under Construction | 960000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4127 | 2012-09-14 | Relay Blanket | 7844 | 2016-06-09 | LN | 2016-12-31 | Blanket for Relay Betterment Program 2016 | Throughout system |  |  |  |  | Replace defective cross arms, insulators, arrestors, and pole quuys | IA,MN |  |  | Under Construction | 2500000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4128 | 2012-09-14 | SMART GRID Blanket | 7848 | 2016-06-09 | LN | 2016-12-31 | Blanket for SMART GRID Project 2016 | Throughout system |  |  |  |  | Replace, upgrade, or install TELECOM, RTUs, Relay, etc. | IA,MN |  |  | Under Construction | 4800000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM | 4129 | 2012-09-14 | Wood Pole Blanket | 7852 | 2016-06-09 | LN | 2016-12-31 | Blanket for Wood Pole Replacement Program 2016 | Throughout system |  |  |  |  | Replace deteriorating wood pole | IA,MN |  |  | Under Construction | 3500000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | ITCM, MEC | 3249 | 2014-03-31 | G5566, 32337 | 6052 | 2016-09-16 | LN | 2018-12-01 | NE 54th Ave. | Bondurant | 1 | 161 |  | 410 | New 161 kV line from NE 54th Ave. to Bondurant and associated substation equipment additions. | IA | 0 | 8.3 | Planned | 11221895 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MEC | 2952 | 2016-09-16 | T3316 | 8020 | 2016-09-16 | SUB | 2018-06-01 | NE 54th Ave. | Substation |  | 161 | 13 | 33 | New 161-13 kV Substation. | IA |  |  | Planned | 1300000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MEC | 3248 | 2015-09-15 | G2705, 32335 | 6048 | 2016-09-16 | LN | 2018-06-01 | Rising Sun Substation | NE 54th Ave. | 1 | 161 |  | 410 | New 161 kV line from Rising Sun Substation on DPS-Reasnor line to East Altoona and associated substation equipment additions. | IA | 0 | 6 | Planned | 8100000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MEC | 3248 | 2015-09-15 | G2705, 32335 | 6050 | 2016-09-16 | LN | 2018-05-01 | DPS | Reasnor | 1 | 161 |  | 325 | Add 161 kV line taps to new Rising Sun Substation | IA |  | 0.1 | Planned | 736000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MEC | 3248 | 2015-09-15 | G2705, 32335 | 6049 | 2016-09-30 | SwSta | 2018-05-01 | Rising Sun Substation |  |  | 161 |  |  | New 161 kV breakered substation off the DPS-Reasnor 161 kV line | IA |  |  | Planned | 5200000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MEC | 4256 | 2015-10-01 | G4251 | 8016 | 2016-09-30 | LN | 2016-12-01 | Hwys 141 & 44 | NW 70th Avenue | 1 | 161 |  | 410 | New 161 kV line from Hwys 141 & 44 Sub to NW 70th Ave. Substation | IA |  | 3 | Planned | 3200000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MEC | 4256 | 2015-10-01 | G4251 | 8018 | 2016-09-30 | SUB | 2016-12-01 | NW 70th Avenue | Substation |  | 161 | 13 | 33 | New 161-13 kV Substation. | IA |  |  | Planned | 2670000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MEC | 4256 | 2015-10-01 | G4251 | 8017 | 2016-09-30 | LN | 2016-12-01 | NW 70th Avenue | Sycamore | 1 | 161 |  | 410 | New 161 kV line from NW 70th Avenue Sub to Sycamore Sub | IA |  | 4 | Planned | 3200000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 3531 | 2015-08-10 | Deer River | 6591 | 2015-06-12 | SUB | 2015-12-15 | Deer River Substation | Substation Equipment |  | 230 | 115 | 187 | New Substation with 230/115 kV 187 MVA Transformer (spare transformer) | MN |  |  | Under Construction | 2000000 | Engineering |  | N | N | N | Y
A in MTEP13 | A | West | MP | 3531 | 2015-08-10 | Deer River | 7685 | 2015-06-12 | LN | 2016-11-08 | GRE Deer River | MP Deer River |  | 115 |  | 122 | New 115 kV line to complete the loop in Deer River | MN | 1 | 0.75 | Under Construction | 2197441 | Engineering |  | N | N | N | Y
A in MTEP13 | A | West | MP | 3531 | 2015-08-10 | Deer River | 7673 | 2015-06-12 | Dist | 2015-12-15 | Deer River Substation | Substation Equipment |  | 115 | 23 | 10 | New 115/23 kV 10 MVA transformer | MN |  |  | Under Construction | 348488 | Engineering |  | N | N | N | Y
A in MTEP13 | A | West | MP | 3531 | 2015-08-10 | Deer River | 7672 | 2015-06-12 | TX | 2015-12-15 | Deer River Substation | Substation Equipment |  | 230 | 115 | 187 | New Substation with 230/115 kV 187 MVA Transformer | MN |  | 0.25 | Under Construction | 10309809 | Engineering |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8218 | 2015-04-13 | LNup | 2016-12-31 | Riverton 230 | Riverton 115 | 1 | 115 |  | 217 | NERC facility ratings alert mitigation | MN | 0.68 | 0 | Planned | 1200 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8216 | 2015-04-13 | LNup | 2016-12-31 | Winter Street | Fairmount Park | 1 | 115 |  | 182 | NERC facility ratings alert mitigation | MN | 3.48 | 0 | Planned | 127123.53 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8215 | 2015-04-13 | LNup | 2016-12-31 | Wing River | Long Prairie | 1 | 115 |  | 85 | NERC facility ratings alert mitigation | MN | 31.6 | 0 | Planned | 1302550 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8214 | 2015-04-13 | LNup | 2016-12-31 | Virginia | Minntac | 1 | 115 |  | 144 | NERC facility ratings alert mitigation | MN | 6.26 | 0 | Planned | 253011.76 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8212 | 2015-04-13 | LNup | 2016-12-31 | Virginia | Inland | 1 | 115 |  | 120 | NERC facility ratings alert mitigation | MN | 4.04 | 0 | Planned | 188602.94 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8211 | 2015-04-13 | LNup | 2016-12-31 | Virginia | Hibbing | 1 | 115 |  | 55 | NERC facility ratings alert mitigation | MN | 28.71 | 0 | Planned | 1236958.82 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8210 | 2015-04-13 | LNup | 2016-12-31 | Virginia | 16 Line Tap | 1 | 115 |  | 90 | NERC facility ratings alert mitigation | MN | 11.12 | 0 | Planned | 443061.76 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8209 | 2015-04-13 | LNup | 2016-12-31 | Verndale | Wing River | 1 | 115 |  | 98 | NERC facility ratings alert mitigation | MN | 1.08 | 0 | Planned | 62397.06 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8208 | 2015-04-13 | LNup | 2016-12-31 | Verndale | 24 Line Tap | 1 | 115 |  | 77 | NERC facility ratings alert mitigation | MN | 16.37 | 0 | Planned | 670761.76 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8207 | 2015-04-13 | LNup | 2016-12-31 | Thomson | Cromwell | 1 | 115 |  | 98 | NERC facility ratings alert mitigation | MN | 28.05 | 0 | Planned | 1175302.94 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8206 | 2015-04-13 | LNup | 2016-12-31 | Thomson | Potlatch | 1 | 115 |  | 84 | NERC facility ratings alert mitigation | MN | 6.88 | 0 | Planned | 302832.35 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8205 | 2015-04-13 | LNup | 2016-12-31 | Thomson | Fond Du Lac | 1 | 115 |  | 90 | NERC facility ratings alert mitigation | MN | 2.2 | 0 | Planned | 64373.53 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8204 | 2015-04-13 | LNup | 2016-12-31 | Taconite Harbor | Silver Bay | 1 | 115 |  | 159 | NERC facility ratings alert mitigation | MN | 24.86 | 0 | Planned | 1048691.18 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8201 | 2015-04-13 | LNup | 2016-12-31 | Swan Lake Road | Ridgeview | 1 | 115 |  | 144 | NERC facility ratings alert mitigation | MN | 2.87 | 0 | Planned | 126047.06 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8200 | 2015-04-13 | LNup | 2016-12-31 | Stinson | Stone Lake | 1 | 161 |  | 168 | NERC facility ratings alert mitigation | MN | 42.6 | 0 | Planned | 1794126.47 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8199 | 2015-04-13 | LNup | 2016-12-31 | Stinson | Bayfront | 1 | 115 |  | 98 | NERC facility ratings alert mitigation | MN | 25.75 | 0 | Planned | 1110752.94 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8198 | 2015-04-13 | LNup | 2016-12-31 | Stinson | Fairmount Park | 1 | 115 |  | 175 | NERC facility ratings alert mitigation | MN | 3.07 | 0 | Planned | 126400 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8197 | 2015-04-13 | LNup | 2016-12-31 | Shannon | Hibbtac Pumps | 1 | 115 |  | 217 | NERC facility ratings alert mitigation | MN | 7.53 | 0 | Planned | 315744.12 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8194 | 2015-04-13 | LNup | 2016-12-31 | Scearcyville | 24 Line Tap | 1 | 115 |  | 77 | NERC facility ratings alert mitigation | MN | 16.66 | 0 | Planned | 694802.94 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8193 | 2015-04-13 | LNup | 2016-12-31 | Savanna | 9 Line Tap | 1 | 115 |  | 98 | NERC facility ratings alert mitigation | MN | 12.98 | 0 | Planned |  | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8192 | 2015-04-13 | LNup | 2016-12-31 | Riverton | Baxter | 1 | 115 |  | 77 | NERC facility ratings alert mitigation | MN | 13.45 | 0 | Planned | 556391.18 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8191 | 2015-04-13 | LNup | 2016-12-31 | Riverton | Pequot Lakes | 1 | 115 |  | 58 | NERC facility ratings alert mitigation | MN | 19.17 | 0 | Planned | 808450 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8187 | 2015-04-13 | LNup | 2016-12-31 | Nashwauk | Blackberry | 2 | 115 |  | 144 | NERC facility ratings alert mitigation | MN | 13.11 | 0 | Planned | 555791.18 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8186 | 2015-04-13 | LNup | 2016-12-31 | Nashwauk | Blackberry | 1 | 115 |  | 144 | NERC facility ratings alert mitigation | MN | 13.16 | 0 | Planned | 555879.41 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8185 | 2015-04-13 | LNup | 2016-12-31 | Nashwauk | National | 1 | 115 |  | 144 | NERC facility ratings alert mitigation | MN | 6.23 | 0 | Planned | 252958.82 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8184 | 2015-04-13 | LNup | 2016-12-31 | Nashwauk | 14 Line Tap | 1 | 115 |  | 144 | NERC facility ratings alert mitigation | MN | 4.88 | 0 | Planned | 178320.59 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8183 | 2015-04-13 | LNup | 2016-12-31 | Mud Lake | Little Falls | 1 | 115 |  | 71 | NERC facility ratings alert mitigation | MN | 28.48 | 0 | Planned | 1176061.76 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8182 | 2015-04-13 | LNup | 2016-12-31 | Mud Lake | Brainerd | 1 | 115 |  | 98 | NERC facility ratings alert mitigation | MN | 4.4 | 0 | Planned | 189238.24 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8178 | 2015-04-13 | LNup | 2016-12-31 | Long Prairie | Douglas County | 1 | 115 |  | 98 | NERC facility ratings alert mitigation | MN | 9.37 | 0 | Planned | 367717.65 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8177 | 2015-04-13 | LNup | 2016-12-31 | Long Prairie | Pepin Lake | 1 | 115 |  | 98 | NERC facility ratings alert mitigation | MN | 12.69 | 0 | Planned | 555050 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8175 | 2015-04-13 | LNup | 2016-12-31 | Little Falls | West St. Cloud | 1 | 115 |  | 103 | NERC facility ratings alert mitigation | MN | 17.57 | 0 | Planned | 745135.29 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8174 | 2015-04-13 | LNup | 2016-12-31 | Laskin | Virginia | 1 | 115 |  | 98 | NERC facility ratings alert mitigation | MN | 25.86 | 0 | Planned | 1110947.06 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8173 | 2015-04-13 | LNup | 2016-12-31 | Laskin | Forbes | 1 | 115 |  | 113 | NERC facility ratings alert mitigation | MN | 31.41 | 0 | Planned | 1302214.71 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8172 | 2015-04-13 | LNup | 2016-12-31 | Laskin | Embarrass | 1 | 115 |  | 98 | NERC facility ratings alert mitigation | MN | 10.23 | 0 | Planned | 429726.47 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8171 | 2015-04-13 | LNup | 2016-12-31 | International Falls | Fort Frances | 1 | 115 |  | 180 | NERC facility ratings alert mitigation | MN | 2.19 | 0 | Planned | 125288.24 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8169 | 2015-04-13 | LNup | 2016-12-31 | Hoyt Lakes | Laskin | 1 | 115 |  | 168 | NERC facility ratings alert mitigation | MN | 5.75 | 0 | Planned | 252111.76 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8168 | 2015-04-13 | LNup | 2016-12-31 | Hilltop | LSPI | 1 | 115 |  | 182 | NERC facility ratings alert mitigation | MN | 2.91 | 0 | Planned | 126117.65 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8167 | 2015-04-13 | LNup | 2016-12-31 | Hilltop | 15th Ave West | 1 | 115 |  | 120 | NERC facility ratings alert mitigation | MN | 4.57 | 0 | Planned | 189538.24 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8165 | 2015-04-13 | LNup | 2016-12-31 | Hibbtac | 78 Line Tap | 1 | 115 |  | 144 | NERC facility ratings alert mitigation | MN | 7.75 | 0 | Planned | 316132.35 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8162 | 2015-04-13 | LNup | 2016-12-31 | Hibbing | 44 Line Tap | 1 | 115 |  | 91 | NERC facility ratings alert mitigation | MN | 1.72 | 0 | Planned | 63526.47 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8161 | 2015-04-13 | LNup | 2016-12-31 | Hibbing | 14 Line Tap | 1 | 115 |  | 99 | NERC facility ratings alert mitigation | MN | 5.76 | 0 | Planned | 252129.41 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8159 | 2015-04-13 | LNup | 2016-12-31 | Hibbard | Winter Street | 1 | 115 |  | 182 | NERC facility ratings alert mitigation | MN | 3.38 | 0 | Planned | 126947.06 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8158 | 2015-04-13 | LNup | 2016-12-31 | Haines Road | Swan Lake Road | 1 | 115 |  | 144 | NERC facility ratings alert mitigation | MN | 1.32 | 0 | Planned | 62820.59 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8157 | 2015-04-13 | LNup | 2016-12-31 | Grand Rapids | Riverton | 1 | 115 |  | 55 | NERC facility ratings alert mitigation | MN | 67.7 | 0 | Planned | 2843241.18 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8156 | 2015-04-13 | LNup | 2016-12-31 | Gary | Stinson | 1 | 115 |  | 207 | NERC facility ratings alert mitigation | MN | 11.05 | 0 | Planned | 491664.71 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8155 | 2015-04-13 | LNup | 2016-12-31 | Forbes | 78 Line Tap | 1 | 115 |  | 113 | NERC facility ratings alert mitigation | MN | 15.87 | 0 | Planned | 669879.41 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8154 | 2015-04-13 | LNup | 2016-12-31 | Forbes | 44 Line Tap | 1 | 115 |  | 85 | NERC facility ratings alert mitigation | MN | 17.83 | 0 | Planned | 733829.41 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8153 | 2015-04-13 | LNup | 2016-12-31 | Forbes | ETCO | 1 | 115 |  | 120 | NERC facility ratings alert mitigation | MN | 6.28 | 0 | Planned | 253047.06 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8152 | 2015-04-13 | LNup | 2016-12-31 | Fond Du Lac | Hibbard | 1 | 115 |  | 40 | NERC facility ratings alert mitigation | MN | 11.5 | 0 | Planned | 492458.82 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8151 | 2015-04-13 | LNup | 2016-12-31 | ETCO | 16 Line Tap | 1 | 115 |  | 90 | NERC facility ratings alert mitigation | MN | 1.52 | 0 | Planned | 63173.53 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8150 | 2015-04-13 | LNup | 2016-12-31 | Embarrass | Babbitt | 1 | 115 |  | 64 | NERC facility ratings alert mitigation | MN | 26.37 | 0 | Planned | 1111847.06 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8149 | 2015-04-13 | LNup | 2016-12-31 | Embarrass | Virginia | 1 | 115 |  | 90 | NERC facility ratings alert mitigation | MN | 15.34 | 0 | Planned | 620217.65 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8148 | 2015-04-13 | LNup | 2016-12-31 | Dog Lake | 24 Line Tap | 1 | 115 |  | 98 | NERC facility ratings alert mitigation | MN | 0.65 | 0 | Planned | 61638.24 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8147 | 2015-04-13 | LNup | 2016-12-31 | Cromwell | Riverton | 1 | 115 |  | 77 | NERC facility ratings alert mitigation | MN | 61.15 | 0 | Planned | 2601482.35 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8145 | 2015-04-13 | LNup | 2016-12-31 | Cloquet | 9 Line Tap | 1 | 115 |  | 78 | NERC facility ratings alert mitigation | MN | 30.25 | 0 | Planned | 1264873.53 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8144 | 2015-04-13 | LNup | 2016-12-31 | Brainerd | Riverton | 1 | 115 |  | 71 | NERC facility ratings alert mitigation | MN | 13.1 | 0 | Planned | 555773.53 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8143 | 2015-04-13 | LNup | 2016-12-31 | Boswell | Grand Rapids | 1 | 115 |  | 120 | NERC facility ratings alert mitigation | MN | 10.73 | 0 | Planned | 430608.82 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8142 | 2015-04-13 | LNup | 2016-12-31 | Boswell | Nashwauk | 1 | 115 |  | 120 | NERC facility ratings alert mitigation | MN | 36.09 | 0 | Planned | 1540673.53 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8141 | 2015-04-13 | LNup | 2016-12-31 | Boswell | Blandin | 1 | 115 |  | 120 | NERC facility ratings alert mitigation | MN | 7.78 | 0 | Planned | 316185.29 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8190 | 2015-04-13 | LNup | 2016-12-31 | Ridgeview | Colbyville | 1 | 115 |  | 120 | NERC facility ratings alert mitigation | MN | 9.1 | 0 | Planned | 367241.18 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8140 | 2015-04-13 | LNup | 2016-12-31 | Boise | International Falls | 1 | 115 |  | 85 | NERC facility ratings alert mitigation | MN | 1.4 | 0 | Planned | 62961.76 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8138 | 2015-04-13 | LNup | 2016-12-31 | Blandin | 20 Line Tap | 1 | 115 |  | 135 | NERC facility ratings alert mitigation | MN | 8.32 | 0 | Planned | 365864.71 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8137 | 2015-04-13 | LNup | 2016-12-31 | Blanchard | Little Falls | 1 | 115 |  | 90 | NERC facility ratings alert mitigation | MN | 8.4 | 0 | Planned | 366005.88 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8136 | 2015-04-13 | LNup | 2016-12-31 | Blanchard | Pepin Lake | 1 | 115 |  | 98 | NERC facility ratings alert mitigation | MN | 14.27 | 0 | Planned | 618329.41 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8135 | 2015-04-13 | LNup | 2016-12-31 | Colbyville | Two Harbors | 1 | 115 |  | 118 | NERC facility ratings alert mitigation | MN | 22.98 | 0 | Planned | 984882.35 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8134 | 2015-04-13 | LNup | 2016-12-31 | Blackberry | 9 Line Tap | 1 | 115 |  | 182 | NERC facility ratings alert mitigation | MN | 32.83 | 0 | Planned |  | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8133 | 2015-04-13 | LNup | 2016-12-31 | Badoura | Akeley | 1 | 115 |  | 122 | NERC facility ratings alert mitigation | MN | 9.41 | 0 | Planned | 367788.24 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8132 | 2015-04-13 | LNup | 2016-12-31 | Badoura | Hubbard | 1 | 115 |  | 91 | NERC facility ratings alert mitigation | MN | 14.77 | 0 | Planned | 619211.76 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8131 | 2015-04-13 | LNup | 2016-12-31 | Badoura | Dog Lake | 1 | 115 |  | 58 | NERC facility ratings alert mitigation | MN | 33.99 | 0 | Planned | 1427750 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8129 | 2015-04-13 | LNup | 2016-12-31 | Arrowhead | 15th Ave West | 1 | 115 |  | 120 | NERC facility ratings alert mitigation | MN | 11.86 | 0 | Planned | 493094.12 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8128 | 2015-04-13 | LNup | 2016-12-31 | Arrowhead | Hibbard | 1 | 115 |  | 182 | NERC facility ratings alert mitigation | MN | 10.73 | 0 | Planned | 430608.82 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8127 | 2015-04-13 | LNup | 2016-12-31 | Arrowhead | Haines Road | 1 | 115 |  | 135 | NERC facility ratings alert mitigation | MN | 7.6 | 0 | Planned | 315867.65 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8126 | 2015-04-13 | LNup | 2016-12-31 | Arrowhead | Colbyville | 1 | 115 |  | 144 | NERC facility ratings alert mitigation | MN | 19.24 | 0 | Planned | 808573.53 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8125 | 2015-04-13 | LNup | 2016-12-31 | Arrowhead | Cloquet | 1 | 115 |  | 120 | NERC facility ratings alert mitigation | MN | 10.51 | 0 | Planned | 430220.59 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | MP | 4294 | 2015-04-13 | NERC Alert Low | 8124 | 2015-04-13 | LNup | 2016-12-31 | Arrowhead | 16 Line Tap | 1 | 115 |  | 55 | NERC facility ratings alert mitigation | MN | 44.76 | 0 | Planned | 1907155.88 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | OTP | 3667 | 2012-09-28 | OTP | 6829 | 2015-05-12 | LN | 2015-11-30 | Nunda | Rutland | 1 | 41.6 | 41.6 | 34 MVA | Rebuild 8 miles of 41.6 kV line | SD | 8 |  | Under Construction | 466000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | OTP | 4233 | 2016-09-21 | OTP | 7989 | 2016-09-21 | TX | 2017-05-01 | Parshall 41.6kV sub | Parshall 41.6kv/24kV sub | 1 | 41.6 | 24 | 10 | Adding new transformer 10 MVA | ND |  |  | M3_Long Lead Materials | 500000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | XEL | 4224 | 2012-09-14 |  | 7974 | 2014-12-22 | SUB | 2020-12-01 | Ironwood | Ironwood |  | 34.5 |  |  | Relay setting updates, install 34.5 kV voltage regulator | WI |  |  | Planned | 200000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | XEL | 4224 | 2012-09-14 |  | 7973 | 2014-12-22 | LNrb | 2020-12-01 | Ironwood | Kimball (DPC) | 1 | 34.5 |  | 22 MVA | Rebuild .5 mile protion of existing line, Replace in-line disconnect with three-way GOAB switch | WI | 0.5 |  | Planned | 475000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | XEL | 4224 | 2012-09-14 |  | 7972 | 2014-12-22 | LNrb | 2020-12-01 | Ironwood | Northside | 1 | 34.5 |  | 16 MVA | Rebuild .5 mile protion of existing line, Replace in-line disconnect with three-way GOAB switch | WI | 0.5 |  | Planned | 475000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | XEL | 4305 | 2013-01-10 |  | 8236 | 2016-09-29 | SUB | 2017-03-01 | Yankee |  |  | 115 |  |  | Install 1x25 MVAr switched inductor | MN |  |  | Under Construction | 4300000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | XEL | 4305 | 2013-01-10 |  | 8237 | 2016-09-29 | SUB | 2019-06-01 | Fenton |  |  | 115 |  |  | Install 1x25 MVAr switched inductor | MN |  |  | Planned | 3800000 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | XEL | 4308 | 2013-01-10 |  | 8243 | 2015-06-30 | LNrb | 2016-12-31 | Cedar Falls | Menomonie | 1 | 69 |  |  | Rebuilding 5 miles of 4/0 and 336 ACSR conductor between Cedar Falls-Menomonie 69 kV to 795 ACSR. Also, replacing bus work at Cedar Falls from 4/0 to 1590 AAC to increase the rating | WI |  |  | Planned | 4087810 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | XEL | 4314 | 2013-01-10 |  | 8251 | 2015-12-28 | LNrb | 2021-12-01 | Bay Front | Saxon Pump | 1 | 88 |  |  | It is expected to rebuild this line to 115 kV capable 795 ACSR conductor operated at 88 kV. | WI |  |  | Planned | 26377500 | Planning |  | N | N | N | Y
A in MTEP13 | A | West | XEL | 4314 | 2013-01-10 |  | 8252 | 2015-09-30 | LNrb | 2021-12-01 | Saxon Pump | Norrie | 1 | 88 |  |  | It is expected to rebuild this line to 115 kV capable 795 ACSR conductor operated at 88 kV. | WI,MI |  |  | Planned | 9600000 | Planning |  | N | N | N | Y
A in MTEP14 | A | Central | AmerenIL | 4076 | 2014-12-17 | AMRN32 | 7725 | 2016-06-02 | LN | 2017-06-01 | Edwards Plant | ADM-Peoria (Hiram) | 1 | 138 |  | 399 | Build new 2.2 miles of 138 kV line wih 2000 A summer emergency capability. Reconnect deenergized 4.6 mile 138 kV line between Edwards Plant and Bartonville Substation. Add two new 138 kV, 2000 A PCBs at Edwards Plant. Relocate 138 kV lines outside Edwa | IL | 4.6 | 2.2 | Planned | 6320000 | Planning |  | N | N | N | Y
A in MTEP14 | A | Central | AmerenIL | 4345 | 2015-01-09 |  | 8312 | 2015-03-09 | SUB | 2019-05-22 | Gifford Sub |  |  | 138 |  |  | Establish a new 138 kV, 3-breaker ring bus at the existing Rantoul Junction in the Paxton, East-Sidney-1 138 kV Line | IL |  |  | Planned | 4775000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | Central | AmerenIL | 4471 | 2015-01-09 |  | 8570 | 2015-04-30 | LN | 2017-12-01 | Cahokia | Dupo Ferry | 1 | 138 |  |  | Replace 6.98 miles of 2-300 kcmil Copper conductor with largest size conductor existing structures will carry. (Minimum capability of 1600 A) | IL | 6.98 |  | Planned | 10403000 | Planning |  | N | N | N | Y
A in MTEP14 | A | Central | AmerenIL | 4474 | 2015-01-09 | AMRN40 | 8575 | 2015-09-21 | SUB | 2019-09-01 | Lasalle Tap (Hickok) | Install 138 kV Breaker Station |  | 138 |  |  | LaSalle Tap 138 kV Breaker Station (Hickok)- Install new 3-position breaker station in the Hennepin-Oglesby-1556 138 kV line at the tap to LaSalle Air Products and North LaSalle Substations. 3-2000A PCBs needed. | IL |  |  | Planned | 3800032 | Engineering |  | N | N | N | Y
A in MTEP14 | A | Central | AmerenIL | 4474 | 2015-01-09 | AMRN40 | 8576 | 2015-09-21 | TEQ | 2019-09-01 | Hennepin | Oglesby | 1556 | 138 |  | 255 | Upgrade disconnect switch, wave trap, relay limit at Hennepin, and 1200 A disconnect switch at ESK to match line rating. | IL |  |  | Planned | 600000 | Planning |  | N | N | N | Y
A in MTEP14 | A | Central | AmerenIL | 4477 | 2015-01-09 | AMRN42 | 8582 | 2015-09-21 | SUB | 2019-09-01 | Clayton Junction (Monument) | Install 138 kV Breaker Station |  | 138 |  |  | Install 138 kV breaker station at Clayton Junction. Needed: 3-2000 A PCBs. | IL |  |  | Planned | 4950000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | Central | AmerenIL | 4477 | 2015-01-09 | AMRN42 | 8585 | 2015-09-21 | TEQ | 2019-09-01 | Meredosia East | Monument |  | 138 |  | 240 | Upgrade relay limit | IL |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP14 | A | Central | AmerenIL | 4477 | 2015-01-09 | AMRN42 | 8584 | 2015-09-21 | TEQ | 2019-09-01 | East Quincy | Monument |  | 138 |  | 240 | Upgrade relay limit | IL |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP14 | A | Central | AmerenIL | 4477 | 2015-01-09 | AMRN42 | 8583 | 2015-09-21 | TEQ | 2019-09-01 | Macomb | Monument |  | 138 |  | 175 | Upgrade relay limit | IL |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP14 | A | Central | AmerenIL | 4479 | 2015-01-09 |  | 8587 | 2016-03-31 | SUB | 2019-09-01 | Ramsey, East | Install 345 kV Ring Bus |  | 345 |  |  | Install 345 kV ring bus. Needed: 3-3000 A PCBs | IL |  |  | Planned | 6000000 | Planning |  | N | N | N | Y
A in MTEP14 | A | Central | AmerenIL | 4480 | 2015-01-09 |  | 8588 | 2014-08-22 | SUB | 2020-11-01 | Oglesby | Rebuild Substation |  | 138 |  |  | Rebuild Oglesby Substation. Utilize a breaker-and-a-half arrangement. | IL |  |  | Planned | 14660550 | Planning |  | N | N | N | Y
A in MTEP14 | A | Central | AmerenIL | 4495 | 2015-01-09 | AMRN44 | 8606 | 2014-08-22 | LN | 2016-12-01 | Rivermines | Maries | 1 | 138 |  | 269 | Rebuild/reconductor 60 miles of 250 kcmil Copper with 556 kcmil ACSS or equivalent. | MO | 60 |  | Planned | 15500000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | Central | AmerenIL | 4495 | 2015-01-09 | AMRN44 | 8608 | 2014-08-22 | LN | 2016-12-01 | Maries | Osage | 1 | 138 |  | 269 | Rebuild/reconductor 34.3 miles of 250 kcmil Copper with 556 kcmil ACSS or equivalent. | MO | 34.3 |  | Planned | 15500000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | Central | AmerenIL | 4495 | 2015-01-09 | AMRN44 | 8607 | 2014-08-22 | LN | 2016-12-01 | Clark | Osage | 2 | 138 |  | 269 | Rebuild/reconductor 95 miles of 250 kcmil Copper with 556 kcmil ACSS or equivalent. | MO | 95 |  | Planned | 15500000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | Central | AmerenMO | 2993 | 2015-01-09 |  | 5198 | 2016-01-13 | LN | 2018-12-01 | Dupo Ferry | Buck Knob | 1 | 138 |  | 275 | Dupo Ferry-Buck Knob 138 kV Line - Replace 22 mi. of 2-300 ACSR with maximum size conductor existing towers will support. | MO | 22 |  | Planned | 31367940 | Engineering |  | N | N | N | Y
A in MTEP14 | A | Central | AmerenMO | 4723 | 2015-01-09 |  | 8952 | 2014-08-22 | LN | 2017-12-01 | Kelso | Lutesville | 1 | 345 |  | 1178 | Replace 50% of structures (17.6 miles) to maintain at least a 100 degree C conductor temperature capability on this line. | MO | 17.6 |  | Planned | 8441336 |  |  | N | N | N | Y
A in MTEP14 | A | Central | DEI | 3545 | 2014-12-17 | AMIN0465 | 6614 | 2016-03-01 | SUB | 2016-12-31 | Wabash River Sta. |  |  | 138 |  |  | Wabash Riv 138KV Gen Sta. Phase II (Bus #2 & Transfer Bus): Perform Line associated relay work. Repl. breakers: 138230-9, 13847 and DS Switches. Replace Bus Insulators. | IN |  |  | M4_Pre-Construction | 1434000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | Central | DEI | 3550 | 2016-08-03 | AMIN0499 | 6619 | 2016-08-03 | LN | 2017-12-31 | Martinsville Southeast | Martinsville E. | 1 | 69 |  | 153 | Construct approximately 1.5 mi of 69kv line to complete a normally open loop between Martinsville SE and Martinsville East distribution subs. | IN |  | 1.5 | M4_Pre-Construction | 1434000 | Engineering |  | N | N | N | NT
A in MTEP14 | A | Central | DEI | 3556 | 2014-12-17 | AMIN0573 | 6629 | 2016-08-23 | Dist | 2016-12-31 | Greenwood South | new distribution sub |  | 69 | 12 |  | Build a new 69-12kV 22.4MVA sub in the 69102 line adjacent +/- to the existing HE Gilmore 69kv sub | IN |  |  | Under Construction | 481000 | Engineering |  | N | N | N | NT
A in MTEP14 | A | Central | DEI | 4368 | 2015-01-09 | AMIN0950 | 8363 | 2016-04-15 | LN | 2017-03-31 | Dresser | Wabash River Gen. Station | 1 | 138 |  | 478 | Build a new 138kV line from Dresser to Wabash River Gen. Station with 2000A terminal equipment and 954ACSS - 200C conductor; approx. 10 miles | IN |  | 10 | Under Construction | 14500000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | Central | DEI | 4402 | 2015-01-09 | AMIN0133 | 8419 | 2016-08-23 | LNrb | 2016-12-31 | Huntington Riverfork | Huntington State St. |  | 69 |  | 100 | Huntington Riverfork to State St 69143 ckt: Reconductor 2.85 miles of 69kV transmission 2/0 Cu to 477 ACSR conductor. Begin about half mile east of Hunt Riv Fk sub at pole 823-6512 and continue to Hunt State St Sub 69kv bus. Also reconductor 4/0 ACSR river span. | IN | 2.85 |  | Under Construction | 2520282 | Engineering |  | N | N | N | Y
A in MTEP14 | A | Central | DEI | 4408 | 2015-01-09 | AMIN0837 | 8425 | 2016-08-23 | LNrb | 2016-12-30 | Huntington 138 | Huntington State St |  | 69 |  | 100 | Reconductor 2.5 miles of the 69143 ckt from Huntington 138 sub to State St with 477ACSR @ 100C | IN | 2.5 |  | Under Construction | 2600000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | Central | DEI | 4411 | 2015-01-09 | AMIN0863&4&5 | 8430 | 2016-03-01 | LNrb | 2016-12-31 | Bloomington Meadow Pk | HE Brummett Crk Jct |  | 69 |  | 154 | AMIN0865 - Reconductor 6991 ckt from Bloomington Meadow Pk to HE Brummett Crk Jct - 1.6 miles of 954ACSS@200C | IN | 1.6 |  | M4_Pre-Construction | 1843000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | Central | DEI | 4414 | 2015-01-09 | AMIN0885 | 8433 | 2016-08-23 | LN | 2016-12-31 | Chippewa | New 69132 Jct |  | 69 |  | 100 | New N.O. alternate 69kv feed from 69132 ckt over to Wabash Chippewa 69kv sub | IN |  | 4.5 | Under Construction | 2244000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | Central | DEI | 4415 | 2015-01-09 | AMIN0890 | 8434 | 2014-09-23 | TX | 2020-06-01 | Veedersburg West | xmr addition |  | 230 | 69 | 75 | Veedersburg West: Add 75MVA 230/69 Bk 2 with LTC at Veedersburg West sub; add breaker to 69kV ring bus and tie in new bank; convert 230kV bus into 4-breaker ring | IN |  |  | M1_Final SPM or OOC | 3509000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | Central | DEI | 4417 | 2015-01-09 | AMIN0988 | 8436 | 2015-11-06 | CB | 2017-12-31 | Pumpkin Center | brkr replacements |  | 69 |  |  | Pumpkin Center: Replace OCB 6952, OCB 69123, OCB 69230, (1) Ground Switch, (2) 230KV ABS and Motor Mechs, Lightning Arrestors, Line & Bus Pots, (7) 69KV Disconnect Switches and Station Service Transformer. Replace the 230kV Bk1 "230-69" Circuit Switcher w | IN |  |  | M3_Long Lead Materials | 2424000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | Central | DEI | 4418 | 2015-01-09 | AMIN1067&AMIN1316 | 8437 | 2015-09-08 | SUB | 2017-06-01 | Hillsdale North | new sub |  | 230 | 69 |  | Construct new Hillsdale North 230-69kV substation to be inserted in the 23003 ckt with high and low side ring buses, 1-200MVA bank, 2-69kv line terminals. Loop the existing 6906 ckt through. Change Normal Operational status to Open between Hillsdale Sw. S | IN |  | 2 | M3_Long Lead Materials | 12300000 | Planning |  | N | N | N | Y
A in MTEP14 | A | Central | HE | 4714 | 2015-01-09 | 1052 Ratts 138/161 kV Transformer Upgrade | 8940 | 2013-11-07 | TX | 2014-05-15 | 07Ratts 138/161 kV | 07Ratts8 138/161 kV | 1 | 161 | 138 | 322 | Replace Ratts AT3 | IN |  |  | Planned | 3500000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | Central | HE | 4715 | 2015-01-09 | 1052 Ratts 138 kV Transmission Upgrade | 8941 | 2013-11-07 | LNrc | 2014-05-15 | 07Ratts8 | 07Rattap | 1 | 138 |  | 327 | Reconductor 138 kV line | IN | 0.1 |  | Planned | 200000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | Central | PPI | 4434 | 2016-06-21 | 5 | 8468 | 2016-05-02 | TAP | 2016-12-31 | Alsey | Alsey Tap | 1 | 138 |  | 229 | Alsey 2nd 138 kV Tap to Ameren | IL | 0 | 0.33 | M4_Pre-Construction | 1039100 | Engineering |  | N | N | N | Y
A in MTEP14 | A | East | ITCT | 4499 | 2016-08-15 | ITCT_14_010 | 8618 | 2016-08-15 | CAP | 2017-03-31 | Tuscola |  |  | 120 |  |  | Install a 33.3 MVAR capacitor at the Tuscola 120 kV station. | MI |  |  | M4_Pre-Construction | 1350000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | East | ITCT | 4500 | 2015-03-26 | ITCT_13_043 | 8619 | 2015-12-28 | SwSta | 2017-12-31 | Carrigan |  |  | 120 |  |  | Construct a new 4-breaker 120 kV switching station named "Carrigan" in the Thumb area. Loop the Lee - Menlo & Wabash - Yuma 120 kV circuits into Carrigan. | MI |  |  | M3_Long Lead Materials | 4930000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | East | ITCT | 4500 | 2015-03-26 | ITCT_13_043 | 8624 | 2015-12-28 | LNup | 2017-12-31 | Carrigan | Yuma | 1 | 120 |  | 134 MVA | New line created by looping the Wabash - Yuma 120 kV circuit into Carrigan. | MI |  |  | M3_Long Lead Materials |  |  |  | N | N | N | Y
A in MTEP14 | A | East | ITCT | 4500 | 2015-03-26 | ITCT_13_043 | 8623 | 2015-12-28 | LNup | 2017-12-31 | Carrigan | Wabash | 1 | 120 |  | 274 MVA | New line created by looping the Wabash - Yuma 120 kV circuit into Carrigan and associated relay upgrades. | MI |  |  | M3_Long Lead Materials | 265000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | East | ITCT | 4500 | 2015-03-26 | ITCT_13_043 | 8622 | 2015-12-28 | LNup | 2017-12-31 | Carrigan | Menlo | 1 | 120 |  | 134 MVA | New line created by looping the Menlo - Lake Huron Pumping 1 Tap (to Lee) circuit into Carrigan and associated relay upgrades | MI |  |  | M3_Long Lead Materials | 210000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | East | ITCT | 4500 | 2015-03-26 | ITCT_13_043 | 8621 | 2015-12-28 | LNup | 2017-12-31 | Carrigan | Lake Huron Pumping 1 Tap | 1 | 120 |  | 305 MVA | New line created by looping the Menlo - Lake Huron Pumping 1 Tap (to Lee) circuit into Carrigan and associated relay upgrades | MI |  |  | M3_Long Lead Materials | 275000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | East | ITCT | 4500 | 2015-03-26 | ITCT_13_043 | 8620 | 2015-12-28 | LNrb | 2017-12-31 | Lee | Menlo | 1 | 120 |  | 305 MVA | Replace the existing structures from a one-mile segment of the Lee - Menlo 120 kV circuit with double circuit structures and install 954 ACSR on both sides. | MI | 1 | 1 | M3_Long Lead Materials | 1700000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | East | ITCT | 4518 | 2015-04-08 | ITC_15_004 | 8649 | 2015-09-28 | TX | 2017-04-01 | Monroe 345/120 kV Transformer 304 |  | 4 | 345 | 120 | 649 MVA | Replace the 345/120 kV Transformer 304 at Monroe. | MI |  |  | M3_Long Lead Materials | 3800000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | East | ITCT | 4519 | 2015-11-13 | ITCT_13_018 | 8650 | 2015-11-13 | LN | 2040-04-01 | Custer | Monroe | 2 | 120 |  | 204 MVA | Reconfigure the Custer ? Whiting 120 kV line into Monroe to create the Custer ? Monroe 2 120 kV and Monroe ? Whiting 120 kV lines. | MI |  | 2.9 | M2a_Pre-Project Approval | 12300000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | East | ITCT | 4519 | 2015-11-13 | ITCT_13_018 | 8651 | 2015-11-13 | LN | 2040-04-01 | Monroe | Whiting | 1 | 120 |  | 204 MVA | Reconfigure the Custer ? Whiting 120 kV line into Monroe to create the Custer ? Monroe 2 120 kV and Monroe ? Whiting 120 kV lines. | MI |  | 2.9 | M2a_Pre-Project Approval |  |  |  | N | N | N | Y
A in MTEP14 | A | East | ITCT | 4529 | 2015-03-26 | ITC_13_37 | 8671 | 2016-06-07 | LNup | 2016-12-31 | Brownstown | Elm | 1 | 230 |  | 743 MVA | Remediate the sag limit on the Brownstown to Elm 230kV line up to its conductor rating | MI |  |  | M4_Pre-Construction | 485000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | East | ITCT | 4530 | 2015-03-26 | ITC_13_38 | 8672 | 2016-06-07 | LNup | 2016-12-31 | Brownstown | Navarre | 1 | 230 |  | 739 MVA | Remediate the sag limit on the Brownstown to Navarre 230kV line up to a higher sag limit | MI |  |  | M4_Pre-Construction | 290000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | East | ITCT | 4531 | 2015-03-26 | ITC_13_39 | 8673 | 2016-06-07 | LNup | 2016-12-31 | Dorset | Milan | 1 | 120 |  | 196 MVA | Remediate the sag limit on the Dorset to Milan 120kV line up to its conductor rating | MI |  |  | M4_Pre-Construction | 225000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | East | ITCT | 4532 | 2015-03-26 | ITC_13_40 | 8674 | 2015-09-28 | LNup | 2016-12-31 | Wayne | Hines | 1 | 230 |  | 585 MVA | Remediate the sag limit on the Wayne to Hines 230kV line up to its conductor rating | MI |  |  | M3_Long Lead Materials | 155000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | East | ITCT | 4566 | 2016-03-23 |  | 8708 | 2014-12-29 | TEQ | 2017-12-31 | Blanket for Customer Interconnections 2017 | Throughout system |  | 120 |  |  | Connect interconnecting entities as requested | MI |  |  | M2a_Pre-Project Approval | 2000000 |  |  | N | N | N | Y
A in MTEP14 | A | East | ITCT | 4567 | 2016-03-23 |  | 8709 | 2014-12-29 | TEQ | 2018-12-31 | Blanket for Customer Interconnections 2018 | Throughout system |  | 120 |  |  | Connect interconnecting entities as requested | MI |  |  | M2a_Pre-Project Approval | 2000000 |  |  | N | N | N | Y
A in MTEP14 | A | East | ITCT | 4573 | 2014-12-17 |  | 8715 | 2016-03-22 | TEQ | 2016-12-31 | ITCT Transformer Refurbishment Program 2016 | Throughout system |  |  |  |  | Replace leaking oil pumps and valves, transformer oil, surge arresters, and bushings. | MI |  |  | Under Construction | 600000 |  |  | N | N | N | Y
A in MTEP14 | A | East | ITCT | 4584 | 2015-03-26 | ITC_13_029 | 8726 | 2015-09-28 | TEQ | 2016-12-31 | Trenton Channel 120 kV Bus 14 |  |  | 120 |  |  | Install a second independent bus protection scheme on Trenton Channel 120 kV bus 14 so that three (3) phase to ground fault on the bus will be cleared within 5 cycles when the existing single bus protection scheme is shutdown. | MI |  |  | M3_Long Lead Materials | 108000 |  |  | N | N | N | Y
A in MTEP14 | A | East | ITCT | 4585 | 2015-03-26 | ITC_13_030 | 8727 | 2015-09-28 | TEQ | 2016-12-31 | Trenton Channel 120 kV Bus 17 |  |  | 120 |  |  | Install a second independent bus protection scheme on Trenton Channel 120 kV bus 17 so that a three (3) phase to ground fault on the bus will be cleared within 5 cycles when the existing single bus protection scheme is shutdown. | MI |  |  | M3_Long Lead Materials | 360000 |  |  | N | N | N | Y
A in MTEP14 | A | East | ITCT | 4701 | 2014-12-17 |  | 8886 | 2016-03-22 | LNup | 2016-12-31 | NERC Alert Facility Ratings for 2016 | Throughout system |  |  |  |  | Verify and remediate facilities as required due to the industry-wide NERC alert | MI |  |  | Under Construction | 3600000 |  |  | N | N | N | Y
A in MTEP14 | A | East | ITCT | 4737 | 2016-07-14 | ITC_13_026 & ITC_13_036 | 9005 | 2016-07-14 | RLY | 2016-08-31 | Lapeer |  |  | 120 |  |  | Upgrade relay at the Lapeer Substation | MI |  |  | Under Construction | 110000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | East | ITCT | 4737 | 2016-07-14 | ITC_13_026 & ITC_13_036 | 9004 | 2016-07-14 | RLY | 2016-08-31 | Tuscola |  |  | 120 |  |  | Upgrade relay at the Tuscola Substation | MI |  |  | Under Construction | 210000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | East | ITCT | 4737 | 2016-07-14 | ITC_13_026 & ITC_13_036 | 9003 | 2016-07-14 | LN | 2016-08-31 | Klam | Lapeer | 1 | 120 |  | 270 | New line created by looping the Lapeer - Tuscola circuit into the new Klam substation | MI |  | 3.1 | Under Construction | 5220000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | East | ITCT | 4737 | 2016-07-14 | ITC_13_026 & ITC_13_036 | 9002 | 2016-07-14 | LN | 2016-08-31 | Klam | Bergen Tap | 1 | 120 |  | 305 | New line created by looping the Lapeer - Tuscola circuit into the new Klam substation | MI |  | 3.1 | Under Construction | 5220000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | East | ITCT | 4737 | 2016-07-14 | ITC_13_026 & ITC_13_036 | 9001 | 2016-07-14 | CAP | 2016-08-31 | Klam |  |  | 120 |  |  | Install a 33.3 MVAR capacitor at the new Klam 120 kV substation. | MI |  |  | Under Construction | 170000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | East | ITCT | 4737 | 2016-07-14 | ITC_13_026 & ITC_13_036 | 9000 | 2016-07-14 | SUB | 2016-08-31 | Klam |  |  | 120 |  |  | Construct a new 3 breaker substation for Klam. | MI |  |  | Under Construction | 3160000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | East | METC | 1803 | 2016-02-22 | METC_13_041 | 3618 | 2016-06-07 | LNrb | 2016-12-31 | Plum | Stover | 1 | 138 |  |  | Rebuild the 8.8 mile 138 kV line using 954 ACSR and OPGW (Pre-build to 230 kV construction). | MI | 8.8 |  | Under Construction | 10500000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | East | METC | 4504 | 2015-03-27 | METC_13_047 | 8630 | 2016-03-22 | LNup | 2016-12-31 | Vergennes | Marquette | 1 | 138 |  | 315 MVA | Remediate the sag limit on the 795 ACSR from the Vergennes - Marquette 138 kV circit up to the conductor limit. | MI | 17.2 |  | M3_Long Lead Materials | 345000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | East | METC | 4505 | 2014-12-17 | METC_13_048 | 8631 | 2016-03-21 | LNup | 2016-12-31 | Bass Creek | Sternberg | 1 | 138 |  | 154 MVA | Remediate the sag limits on the 336.4 and 266.8 ACSR portions of the Bass Creek - Sternberg 138 kV circuit. | MI | 15.9 |  | M3_Long Lead Materials | 1200000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | East | METC | 4521 | 2015-04-09 | METC_13_040 | 8662 | 2015-12-28 | LNup | 2016-12-31 | Riggsville | Rondo | 1 | 138 |  |  | Remediate sag on the Riggsville - Rondo 138 kV section to bring its rating up to the conductor limit (174 MVA). | MI |  |  | M3_Long Lead Materials | 324000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | East | METC | 4522 | 2014-12-17 | METC_13_042 | 8663 | 2016-06-07 | LNrb | 2016-12-31 | Lawndale | Murphy | 1 | 138 |  |  | Rebuild the 3/0 Cu & 2/0 Cu 6-wire (1.188 mile) and 336 ACSR (1.713 mile) sections on the Lawndale ? Murphy 138 kV line to 954 ACSR. | MI | 2.84 |  | M4_Pre-Construction | 2800000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | East | METC | 4537 | 2016-03-23 | METC-997 | 8679 | 2014-12-29 | Dist | 2017-12-31 | Blanket for Customer Interconnections 2017 | Throughout system |  | 138 |  |  | Connect interconnecting entities as requested | MI |  |  | M2a_Pre-Project Approval | 2500000 |  |  | N | N | N | Y
A in MTEP14 | A | East | METC | 4538 | 2016-03-23 | METC-996 | 8680 | 2014-12-29 | Dist | 2018-12-31 | Blanket for Customer Interconnections 2018 | Throughout system |  | 138 |  |  | Connect interconnecting entities as requested | MI |  |  | M2a_Pre-Project Approval | 2500000 |  |  | N | N | N | Y
A in MTEP14 | A | East | METC | 4539 | 2014-12-17 | METC-995 | 8681 | 2015-12-28 | RLY | 2017-12-31 | METC Hemphill Control Relocation Project - Years 2015, 2016, 2017 | Hemphill |  |  |  |  | Replace METC relaying and controls at Hemphill Substation. Locate the new relaying and controls in a new dedicated METC control center. Install dedicated METC AC and DC systems. | MI |  |  | M3_Long Lead Materials | 3640000 |  |  | N | N | N | Y
A in MTEP14 | A | East | METC | 4542 | 2014-12-17 | METC-990 | 8684 | 2015-06-29 | RLY | 2017-12-31 | METC Morrow Control Relocation Project - Years 2015, 2016, 2017 | Morrow |  |  |  |  | Replace METC relaying and controls at Morrow Substation. Locate the new relaying and controls in a new dedicated METC control center. Install dedicated METC AC and DC systems. | MI |  |  | M3_Long Lead Materials | 3110000 |  |  | N | N | N | Y
A in MTEP14 | A | East | METC | 4546 | 2014-12-17 | METC-986 | 8688 | 2016-03-22 | TEQ | 2016-12-31 | METC Power Transformer Refurbishment Program - Year 2016 | Throughout system |  |  |  |  | Replace leaking oil pumps and valves, transformer oil, surge arresters, and bushings | MI |  |  | Under Construction | 600000 |  |  | N | N | N | Y
A in MTEP14 | A | East | METC | 4555 | 2015-03-26 | METC_13_018 | 8697 | 2015-09-28 | TEQ | 2016-12-31 | Tippy | Stronach | 1 | 138 |  |  | Install a dual pilot relay protection system on the Tippy to Stronach 138 kV circuit so that three (3) phase to ground faults will be cleared within 5 cycles. The Tippy 138 kV BK 177 bypassing will also be removed. | MI |  |  | M3_Long Lead Materials | 575000 |  |  | N | N | N | Y
A in MTEP14 | A | East | METC | 4556 | 2016-06-07 | METC_13_032 | 8698 | 2016-06-07 | TEQ | 2017-03-31 | Blackstone |  |  | 138 |  |  | install a second bus relay scheme on Blackstone blue and white busses and install second independent relay components on Blackstone end of the Blackstone-Marshall 138 kV circuit, Blackstone-Tompkins 138 kV ckts #1 and #2 and Blackstone-Leoni 138 kV ckts # | MI |  |  | M3_Long Lead Materials | 845000 |  |  | N | N | N | Y
A in MTEP14 | A | East | METC | 4557 | 2015-03-26 | METC_13_017 | 8699 | 2016-03-22 | TEQ | 2016-12-31 | Croton | Four Mile | 1 | 138 |  |  | Add a dual pilot relay protection system on Croton to Four Mile 138 kV circuit so that 3 phase to ground faults on the circuit will be cleared within 5 cycles. | MI |  |  | M3_Long Lead Materials | 483000 |  |  | N | N | N | Y
A in MTEP14 | A | East | METC | 4558 | 2015-12-28 | METC_13_030 | 8700 | 2015-12-28 | TEQ | 2016-12-31 | Karn | Manning | 1 | 138 |  |  | Install a dual pilot relay protection scheme on the Karn to Manning 138 kV circuit | MI |  |  | M3_Long Lead Materials | 460000 |  |  | N | N | N | Y
A in MTEP14 | A | East | METC | 4559 | 2015-12-28 | METC_13_031 | 8701 | 2015-12-28 | TEQ | 2016-12-31 | Karn | Saginaw River | 1 | 138 |  |  | Install a dual pilot relay protection scheme on the Karn to Saginaw River 138 kV circuit | MI |  |  | M3_Long Lead Materials | 575000 |  |  | N | N | N | Y
A in MTEP14 | A | East | METC | 4699 | 2014-12-17 |  | 8884 | 2016-03-22 | LNup | 2016-12-31 | NERC Alert Facility Ratings for 2016 | Throughout system |  |  |  |  | Verify and remediate facilities as required due to the industry-wide NERC alert | MI |  |  | Under Construction | 11200000 |  |  | N | N | N | Y
A in MTEP14 | A | East | METC | 4814 | 2015-03-26 | METC_14_010 | 9097 | 2016-06-07 | LNup | 2016-12-31 | Morrow | Battle Creek | 1 | 138 |  | 225 MVA | Remediate sag limit on the Morrow - Battle Creek #1 138 kV line to lowest overhead line rating. | MI |  |  | M4_Pre-Construction | 366000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | East | METC | 4815 | 2015-04-03 | METC_14_011 | 9098 | 2015-12-28 | LNup | 2016-12-31 | Verona | Foundry | 1 | 138 |  | 180 MVA | Remediate sag limit on the Verona - Foundry 138 kV line to lowest overhead line rating. | MI |  |  | M3_Long Lead Materials | 815000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-AR | 4751 | 2014-12-17 | 14-EAI-020-8 | 9019 | 2016-09-15 | CB | 2016-12-01 | Jacksonville North 115 kV substation |  |  | 115 |  |  | Upgrade Circuit Breaker: Jacksonville North 115 kV B3621-CBO | AR |  |  | Planned | 279164 |  |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-AR | 4755 | 2015-09-10 | 14-EAI-022-2 | 9023 | 2016-09-15 | TEQ | 2017-06-01 | ISES 500 kV substation |  |  | 500 |  |  | EAI SPOF Projects: Modify relaying at ISES 500/161 kV | AR |  |  | Under Construction | 16215941 | Scoping |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-AR | 4756 | 2015-09-10 | 14-EAI-022-3 | 9024 | 2016-09-15 | TEQ | 2016-12-30 | Mabelvale 500 kV Substation |  |  | 500 |  |  | EAI SPOF Projects: Modify relaying at Mabelvale 500 kV | AR |  |  | Under Construction | 8013145 | Scoping |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-AR | 4757 | 2015-09-10 | 14-EAI-022-4 | 9025 | 2016-05-09 | TEQ | 2018-06-01 | El Dorado 500 kV substation |  |  | 500 |  |  | EAI SPOF Projects: Modify relaying at El Dorado 500 kV | AR |  |  | Planned | 1000000 | Scoping |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-AR | 7761 | 2016-02-16 | 14-EAI-27 | 20072 | 2016-09-15 | CAP | 2016-12-31 | Datto |  |  | 161 |  | 24 MVAR | 24 MVAR capacitor bank | AR |  |  | M3_Long Lead Materials | 1522059 | Planning |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-AR | 8040 | 2015-09-10 | 14-EAI-028 | 20313 | 2016-09-15 | TEQ | 2018-06-01 | ANO 500kV substation | Mabelvale 500kV substation | 1 | 500 |  | 2546 | ANO - Mabelvale 500kV: Replace Substation Equipment | AR |  |  | Planned | 1809881 | Planning |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-AR | 8041 | 2015-09-10 | 14-EAI-029 | 20314 | 2016-09-15 | TEQ | 2017-12-01 | ANO 500kV substation | Pleasant Hill 500kV substation | 1 | 500 |  | 2546 | ANO - Pleasant Hill 500kV: Replace Substation Equipment | AR |  |  | Planned | 1431807 | Planning w/AFUDC |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-LA | 4605 | 2015-07-30 | 14-EGL-017 | 8751 | 2016-09-15 | TX | 2017-09-01 | Crown Zellerbach 230 kV substation | Crown Zellerbach 138 kV substation | 1 | 230 | 138 | 300 MVA | Add transformer | LA |  |  | Planned | 17190728 | Planning |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-LA | 4605 | 2015-07-30 | 14-EGL-017 | 8753 | 2016-07-05 | SUB | 2017-09-01 | Crown Zellerbach 138 kV substation |  |  | 138 |  | 300 MVA | Construct new substation | LA |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-LA | 4605 | 2015-07-30 | 14-EGL-017 | 8752 | 2016-07-05 | SUB | 2017-09-01 | Crown Zellerbach 230 kV substation |  |  | 230 |  | 300 MVA | Construct new substation | LA |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-LA | 4761 | 2014-12-17 | 14-EGL-022-1 | 9029 | 2016-09-15 | SUB | 2018-04-25 | Willow Glen 500 kV substation |  |  | 500 |  |  | EGSL SPOF Projects: Modify relaying at Willow Glen 500 kV | LA |  |  | Under Construction | 6003861 | Planning |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-LA | 4762 | 2014-12-17 | 14-EGL-022-2 | 9030 | 2016-09-15 | SUB | 2018-06-01 | Fancy Point 500kV substation |  |  | 500 |  |  | EGSL SPOF Projects: Modify relaying at Fancy Point 500kV | LA |  |  | Planned | 440111 | Planning |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-LA | 4763 | 2014-12-17 | 14-EGL-024-1 | 9031 | 2016-09-15 | CB | 2016-12-31 | Jaguar 69 kV substation |  |  | 69 |  |  | Upgrade Circuit Breaker: Jaguar 69 kV 20940-CO | LA |  |  | Under Construction | 970497 |  |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-LA | 4764 | 2014-12-17 | 14-EGL-024-2 | 9032 | 2016-09-15 | CB | 2016-12-31 | Jaguar 69 kV substation |  |  | 69 |  |  | Upgrade Circuit Breaker: Jaguar 69 kV 20905-CO | LA |  |  | Under Construction |  |  |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-LA | 4765 | 2014-12-17 | 14-EGL-024-3 | 9033 | 2016-09-15 | CB | 2016-12-31 | Blount 69 kV substation |  |  | 69 |  |  | Upgrade Circuit Breaker: Blount 69 kV 14105-TC | LA |  |  | Under Construction |  |  |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-LA | 4769 | 2014-12-17 | 12-ELL-004 | 9037 | 2016-07-05 | SUB | 2017-03-31 | Schriever230 kV substation |  |  | 230 |  |  | Construct new substation | LA |  |  | Planned | 13443939 | Planning |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-LA | 4770 | 2014-12-17 | 14-ELL-008-1 | 9038 | 2016-03-30 | CB | 2016-12-31 | Waterford 230 kV substation |  |  | 230 |  |  | Upgrade Circuit Breaker: Waterford 230 kV S7145-CO | LA |  |  | Planned | 1082400 | Planning |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-LA | 4771 | 2014-12-17 | 14-ELL-008-2 | 9039 | 2016-03-30 | CB | 2016-12-31 | Waterford 230 kV substation |  |  | 230 |  |  | Upgrade Circuit Breaker: Waterford 230 kV S7154-CO | LA |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-LA | 4773 | 2014-12-17 | 14-ELL-009-1 | 9041 | 2016-09-15 | TEQ | 2017-03-01 | Ninemile 230 kV |  |  | 230 |  |  | ELL SPOF Projects: Modify relaying at Ninemile 230 kV | LA |  |  | Under Construction | 4036969 | Planning |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-LA | 4774 | 2014-12-17 | 14-ELL-009-2 | 9042 | 2016-09-15 | TEQ | 2017-04-01 | Southport 230 kV |  |  | 230 |  |  | ELL SPOF Projects: Modify relaying at Southport 230 kV | LA |  |  | Under Construction |  |  |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-LA | 4775 | 2014-12-17 | 14-ELL-009-3 | 9043 | 2016-09-15 | TEQ | 2017-06-01 | Labarre 230 kV |  |  | 230 |  |  | ELL SPOF Projects: Modify relaying at Labarre 230 kV | LA |  |  | Under Construction |  |  |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-LA | 4776 | 2014-12-17 | 14-ELL-009-4 | 9044 | 2016-09-15 | TEQ | 2017-02-01 | Harrahan 230 kV |  |  | 230 |  |  | ELL SPOF Projects: Modify relaying at Harrahan 230 kV | LA |  |  | Under Construction |  |  |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-LA | 4778 | 2014-12-17 | 14-ENO-003-1 | 9046 | 2016-09-15 | TEQ | 2016-11-01 | Market Street 230 kV |  |  | 230 |  |  | ELL SPOF Projects: Modify relaying at Market Street 230 kV | LA |  |  | Under Construction |  |  |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-LA | 8284 | 2014-12-17 |  | 20630 | 2016-03-30 | TAP | 2018-12-01 | Tap | Panama |  | 230 |  |  | Tap the Bagatelle - Sorrento line into Panama substation | LA |  |  | Planned | 4145539 |  | Generator | N | N | N | Y
A in MTEP14 | A | South | Entergy-LA | 8284 | 2014-12-17 |  | 20633 | 2016-07-05 | TX | 2017-12-01 | Coly |  |  | 500 | 230 |  | Add second 1200 MVA, 500-230 kV autotransformer at Coly | LA |  |  | Planned | 16670976 |  |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-LA | 8284 | 2014-12-17 |  | 20632 | 2016-09-15 | LN | 2018-12-31 | Richardson | Iberville |  | 230 |  |  | Construct line using 1780 ACSR ~ 11.0 mi. | LA |  | 11 | Planned | 39380000 |  |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-MS | 4614 | 2015-09-10 | 12-EMI-001 | 8767 | 2016-09-15 | LN | 2017-11-15 | Franklin 115 kV substation | McComb 115 kV substation |  | 115 | 115 | 398 MVA | Construct new line | MS |  | 25 | Planned | 33412348 |  |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-MS | 4614 | 2015-09-10 | 12-EMI-001 | 8768 | 2016-03-24 | CB | 2017-11-15 | Franklin 115 kV substation | McComb 115 kV substation |  | 115 |  | 398 MVA | Add substation terminals | MS |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-MS | 4788 | 2014-12-17 | 14-EMI-008-3 | 9056 | 2016-06-29 | CB | 2016-12-31 | Rex Brown 115 kV substation |  |  | 115 |  |  | Upgrade Circuit Breaker: Rex Brown 115 kV J9732-CO | MS |  |  | Under Construction |  |  |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-MS | 4789 | 2014-12-17 | 14-EMI-008-4 | 9057 | 2016-06-29 | CB | 2016-12-31 | Rex Brown 115 kV substation |  |  | 115 |  |  | Upgrade Circuit Breaker: Rex Brown 115 kV J9742-CO | MS |  |  | Under Construction |  |  |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-MS | 4790 | 2014-12-17 | 14-EMI-008-5 | 9058 | 2016-09-15 | CB | 2016-12-31 | Rex Brown 115 kV substation |  |  | 115 |  |  | Upgrade Circuit Breaker: Rex Brown 115 kV J9743-CO | MS |  |  | Under Construction |  |  |  | N | N | N | Y
A in MTEP14 | A | South | Entergy-MS | 4793 | 2014-12-17 | 14-EMI-008-8 | 9061 | 2016-09-15 | CB | 2016-12-31 | Greenville 115 kV substation |  |  | 115 |  |  | Upgrade Circuit Breaker: Greenville 115 kV J9940-CO | MS |  |  | Under Construction |  |  |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 1624 | 2014-12-17 | PR05259, F4004 | 3241 | 2016-09-29 | LN | 2022-06-01 | Portage | Trienda | 2 | 138 |  | 294 | Uprate X-67 Portage - Trienda 138-kV | WI | 3.4 |  | Planned | 2000000 |  |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 1708 | 2014-12-17 | F2105, PRF5915 | 3490 | 2016-06-30 | LN | 2017-01-01 | Fairwater | Mackford Prairie | 1 | 69 |  | 72 MVA | Construct Fairwater-Mackford Prairie 69 kV line | WI |  | 3.5 | Planned | 20400000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 1708 | 2014-12-17 | F2105, PRF5915 | 3491 | 2015-10-19 | LN | 2017-09-26 | Ripon | Metomen | 2 | 69 |  | 59 MVA | Reconfigure the North Randolph-Ripon 69-kV line to form a second Ripon-Metomen 69-kV line and retire the circuit between Metomen and the Mackford Prairie tap | WI | 3.7 |  | Planned |  |  |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 2031 | 2014-12-17 | PR03903, F1670 | 3906 | 2014-12-23 | LNrb | 2018-06-01 | Colley Rd | Enzyme Bio Systems Tap | 1 | 69 |  | 92 | Rebuild Colley Rd-Enzyme Bio Systems Tap (Y-32) 69 kV | WI |  | 0.98 | Planned |  | Engineering |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 2031 | 2014-12-17 | PR03903, F1670 | 7694 | 2014-12-23 | LN | 2018-06-01 | Brick church | Sharon Tap | 1 | 69 |  | 123 | Rebuild Brick Church to Sharon Tap | WI |  | 3.82 | Planned |  | Engineering |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 2031 | 2014-12-17 | PR03903, F1670 | 3909 | 2014-12-23 | LNrb | 2018-06-01 | Clinton Tap | Sharon Tap | 1 | 69 |  | 147 | Rebuild Clinton Tap-Sharon Tap 69 kV | WI |  | 9 | Planned |  | Engineering |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 2031 | 2014-12-17 | PR03903, F1670 | 3908 | 2014-12-23 | LNrb | 2018-06-01 | RC3 (Clinton) | Clinton Tap | 1 | 69 |  | 147 | Rebuild RC3 (Clinton)-Clinton Tap 69 kV | WI |  | 1.55 | Planned |  | Engineering |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 2031 | 2014-12-17 | PR03903, F1670 | 3907 | 2015-07-01 | LNrb | 2018-06-01 | Enzyme Bio Systems Tap | RC3 (Clinton) | 1 | 69 |  | 147 | Rebuild Enzyme Bio Systems Tap-RC3 (Clinton) 69 kV | WI |  | 5.33 | Planned | 36968500 | Engineering |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 2056 | 2014-12-17 | PR03226, F4000 | 3943 | 2016-09-29 | LN | 2017-01-31 | Oak Creek | Pennsylvania | 1 | 138 |  | 404 | Uprate Oak Creek-Pennsylvania (837) 138 kV | WI | 4.53 |  | M2a_Pre-Project Approval | 4000000 |  |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 3096 | 2014-12-17 | PR04463, F3735 | 5421 | 2016-02-15 | LN | 2020-12-31 | Munising | Timber Products | 1 | 69 |  | 37 MVA | Increase ground clearance for the Inland line Munising-Blaney Park 69kV to 167 deg f (37 MVA) clearance | MI | 6.2 |  | Planned | 13000000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 3096 | 2014-12-17 | PR04463, F3735 | 5423 | 2014-10-17 | LN | 2020-12-31 | Seney | Blaney Park | 1 | 69 |  | 37 MVA | Increase ground clearance for the Inland line Munising-Blaney Park 69kV to 167 deg f (37 MVA) clearance | MI | 18 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 3096 | 2014-12-17 | PR04463, F3735 | 5422 | 2014-10-17 | LN | 2020-12-31 | Timber Products | Seney | 1 | 69 |  | 37 MVA | Increase ground clearance for the Inland line Munising-Blaney Park 69kV to 167 deg f (37 MVA) clearance | MI | 28.4 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 3510 | 2016-09-15 | PR04651, F3421 | 6481 | 2016-09-15 | LN | 2019-06-15 | Mukwonago | Edgewood | 1 | 138 |  | 293 | 671K61 Mukwonago-Edgewood 138-kV rebuild | WI | 7.19 |  | Planned | 23121000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 3510 | 2016-09-15 | PR04651, F3421 | 6482 | 2016-09-15 | LN | 2019-06-15 | Edgewood | St. Martins | 1 | 138 |  | 287 | 3013 Edgewood-St. Martins 138-kV rebuild | WI | 7.07 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 3808 | 2014-12-17 | PR04505, F2570 | 7149 | 2015-07-01 | TX | 2019-06-01 | Geneva |  | 1 | 138 | 69 | 100 | New Geneva 138-69 kV Transformer | WI |  |  | Planned | 12155000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 3808 | 2014-12-17 | PR04505, F2570 | 7155 | 2015-07-01 | LN | 2019-06-01 | Twin Lakes | Geneva | 1 | 69 |  | 116 | Construct new Twin Lakes-Geneva 69 kV line with T2-336 | WI | 1 |  | Planned | 7391000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 3808 | 2014-12-17 | PR04505, F2570 | 7154 | 2015-07-01 | LNrc | 2019-06-01 | Richmond Road | Twin Lakes | 1 | 69 |  | 116 | Reconductor Twin Lakes-Richmond 69 kV line with T2-336 | WI | 2.3 |  | Planned | 2675000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 3808 | 2014-12-17 | PR04505, F2570 | 7153 | 2015-07-01 | LNrc | 2019-06-01 | Katzenberg | Richmond Road | 1 | 69 |  | 116 | Reconductor Katzenberg-Richmond 69 kV line with T2-336 | WI | 2.6 |  | Planned | 3024000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 3808 | 2014-12-17 | PR04505, F2570 | 7152 | 2015-07-01 | LN | 2019-06-01 | Geneva | North Lake Geneva | 1 | 138 |  | 293 | Construct new Geneva-North Lake Geneva 138 kV line with T2-477 | WI | 12.5 |  | Planned | 17420000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 3808 | 2014-12-17 | PR04505, F2570 | 7151 | 2015-07-01 | LN | 2019-06-01 | Spring Valley | Geneva | 1 | 138 |  | 293 | Construct new Spring Valley-Geneva 138 kV line with T2-477 | WI | 11.55 |  | Planned | 26567000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 3808 | 2014-12-17 | PR04505, F2570 | 7150 | 2015-07-01 | LNrc | 2019-06-01 | Bain | Spring Valley | 1 | 138 |  | 293 | Reconductor Bain-Spring Valley 138 kV line with T2-477 | WI | 14.45 |  | Planned | 1314000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 3890 | 2014-12-17 | PR05235, F4000 | 7435 | 2015-07-01 | LN | 2021-12-31 | Port Washington | Saukville | 1 | 138 |  | 319 | Reconductor Port Washington-Saukville (762) 138 kV line | WI |  |  | Planned | 2284000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 3891 | 2014-12-17 | PR05236, F4000 | 7436 | 2015-07-01 | LN | 2021-12-31 | Port Washington | Saukville | 1 | 138 |  | 319 | Reconductor Port Washington-Saukville (742) 138 kV line | WI |  |  | Planned | 2843000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 3900 | 2014-12-17 | PR05587, F4003 | 7450 | 2016-06-30 | LN | 2016-12-31 | Bain | Albers | 1 | 138 |  | 285 | Reconductor Bain-Albers (63143) 138 kV line | WI | 3.1 |  | Planned | 1300000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 3904 | 2014-12-17 | PR05672, F4001 | 7457 | 2016-06-30 | LN | 2016-06-10 | McCue | REC Harmony | 1 | 69 |  | 88 | Reconductor McCue-REC Harmony (Y-171) 69 kV line | WI | 1.36 |  | Planned | 3500000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 3904 | 2014-12-17 | PR05672, F4001 | 8362 | 2015-12-28 | LN | 2016-06-10 | Red Hawk Tap | Lamar | 1 | 69 |  | 88 | Reconductor Red Hawk Tap - Lamar 69 kV line | WI | 0.17 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 3904 | 2014-12-17 | PR05672, F4001 | 7458 | 2015-12-28 | LN | 2016-06-10 | REC Harmony | Red Hawk Tap | 1 | 69 |  | 88 | Reconductor REC Harmony-Red Hawk Tap 69 kV line | WI | 2.45 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 4711 | 2014-12-17 | PR04967, F3654 | 8930 | 2016-06-30 | LNrb | 2016-10-17 | Wautoma | A11 Tap | 1 | 69 |  | 79 | Rebuild the 13.1 mile portion of Y-17 (WAU-A11 69 kV) with T2 4/0 Penguin. All structures used will allow operation to 200 deg F normal and 300 deg F emergency | WI | 13.1 |  | Planned | 13600000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 4711 | 2014-12-17 | PR04967, F3654 | 8931 | 2016-06-30 | LNrb | 2016-10-17 | A11 Tap | Montello Tap | 1 | 69 |  | 79 | Rebuild the 6.1 mile portion of line Y-17 (A11-MOO 69 kV) with T2 4/0 Penguin. All structures used will allow operation to 200 deg F normal and 300 deg F emergency | WI | 3.1 |  | Planned |  |  |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 4728 | 2014-12-17 | PR05988 | 8961 | 2015-10-19 | LNrb | 2017-06-01 | University | Whitewater | 1 | 138 |  | 246 | Reconfigure the University area lines of Whitewater - University (4453) 138kV line, Bluff Creek - University (6552) 138kV line and Mukwonago - Whitewater (77353) 138kV line into new lines of Whitewater - University (4453A) 138kV line, Mukwonago - University (77353A) 138kVline and Whitewater - Bluff Creek (6552A) 138kV line | WI |  | 6.2 | Planned |  |  |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 4728 | 2014-12-17 | PR05988 | 8960 | 2015-10-19 | LNrb | 2017-06-01 | University | Mukwanago | 1 | 138 |  | 246 | Reconfigure the University area lines of Whitewater - University (4453) 138kV line, Bluff Creek - University (6552) 138kV line and Mukwonago - Whitewater (77353) 138kV line into new lines of Whitewater - University (4453A) 138kV line, Mukwonago - University (77353A) 138kVline and Whitewater - Bluff Creek (6552A) 138kV line | WI |  | 22.7 | Planned |  |  |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 4728 | 2014-12-17 | PR05988 | 8959 | 2016-06-30 | LNrb | 2017-06-01 | Whitewater | Bluff Creek | 1 | 138 |  | 175 | Reconfigure the University area lines of Whitewater - University (4453) 138kV line, Bluff Creek - University (6552) 138kV line and Mukwonago - Whitewater (77353) 138kV line into new lines of Whitewater - University (4453A) 138kV line, Mukwonago - University (77353A) 138kVline and Whitewater - Bluff Creek (6552A) 138kV line | WI |  | 5.02 | Planned | 5075000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 4731 | 2014-12-17 | PR06093 | 8966 | 2016-06-30 | SUB | 2016-07-01 | Horicon |  |  | 69 |  |  | Replace the 4/0 Copper Main Strin Bus, Jumpers and lugs. In addition to the 336 ACSR Jumpers, 69 kV station Post insulators and bus support clamps. This will increase the bus & bus jumper ratings that are currently limiters and raise the limit to that of | WI |  |  | Planned | 210000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 4731 | 2014-12-17 | PR06093 | 8968 | 2014-10-20 | LNup | 2016-07-01 | Horicon | Horicon Industrial Park | 1 | 69 |  | 64 | Replace the 4/0 Copper Main Strin Bus, Jumpers and lugs. In addition to the 336 ACSR Jumpers, 69 kV station Post insulators and bus support clamps. This will increase the bus & bus jumper ratings that are currently limiters and raise the limit to that of | WI |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 4731 | 2014-12-17 | PR06093 | 8967 | 2014-10-20 | LNup | 2016-07-01 | Horicon | Juneau Tap | 1 | 69 |  | 59 | Replace the 4/0 Copper Main Strin Bus, Jumpers and lugs. In addition to the 336 ACSR Jumpers, 69 kV station Post insulators and bus support clamps. This will increase the bus & bus jumper ratings that are currently limiters and raise the limit to that of | WI |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 4734 | 2014-12-17 | PR06137 | 8980 | 2015-12-28 | CB | 2015-05-04 | Cedar Creek |  |  | 115 |  |  | Cedar Creek 115kV bus tie breaker | WI |  |  | Planned | 2000000 |  |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 4734 | 2014-12-17 | PR06137 | 8979 | 2015-12-28 | CB | 2015-05-04 | Cedar Creek |  |  | 115 |  |  | Cedar Creek - Dewey 115kV line breaker | WI |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 4734 | 2014-12-17 | PR06137 | 8978 | 2015-12-28 | CB | 2015-05-04 | Cedar Creek |  |  | 115 |  |  | Weston - Cedar Creek 115kV line breaker | WI |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 4734 | 2014-12-17 | PR06137 | 8977 | 2014-01-10 | TAP | 2015-06-01 | Cedar Creek | Dewey | 1 | 115 |  | 205 | Loop Weston - Dewey 115kV line into new Cedar Creek substation | WI |  | 15.65 | Planned |  |  |  | N | N | N | Y
A in MTEP14 | A | West | ATC | 4734 | 2014-12-17 | PR06137 | 8976 | 2014-01-10 | TAP | 2015-06-01 | Weston | Cedar Creek | 1 | 115 |  | 205 | Loop Weston - Dewey 115kV line into new Cedar Creek substation | WI |  | 0.25 | Planned |  |  |  | N | N | N | Y
A in MTEP14 | A | West | CFU | 4588 | 2014-12-17 | Univ. | 8730 | 2016-06-14 | SUB | 2017-04-01 | University Ave. | Transformer |  | 161 | 69 | 143 MVA | New Substation | IA |  |  | Under Construction | 5398000 |  |  | N | N | N | Y
A in MTEP14 | A | West | CFU | 4588 | 2014-12-17 | Univ. | 8731 | 2016-06-14 | LN | 2017-04-01 | University Ave | GT to GH tap | 6915 | 69 |  | 143 MVA | 69kV Line and 3 way switch | IA |  | 1.3 | M4_Pre-Construction | 1536500 |  |  | N | N | N | Y
A in MTEP14 | A | West | CFU-PMEU | 4386 | 2015-11-03 | RRHP | 8402 | 2015-11-03 | SUB | 2017-04-01 | Pella West |  |  | 69 |  |  | Reconfiguration of Pella West 69 kV Substation to improve load serving reliability for City of Pella. Substation will be reconfigured from a line breaker to a ring bus scheme. | IA |  |  | Planned | 2360335 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | GRE | 2600 | 2014-12-17 | 20339 | 4611 | 2016-04-27 | LN | 2016-09-23 | Big Sandy | Big Sandy Tap | 1 | 69 |  |  | New Distribution | MN |  | 4 | Planned | 4239175 | Planning |  | N | N | N | NT
A in MTEP14 | A | West | GRE | 4379 | 2016-05-10 | 20451 | 8391 | 2016-06-29 | LN | 2017-04-13 | Quarry | West St. Cloud | 1 | 115 |  | 190 | Build new line from Quarry to West St. Cloud | MN |  |  | Planned | 3250000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | GRE | 4379 | 2016-05-10 | 20451 | 8392 | 2016-06-29 | SUB | 2017-04-13 | West St. Cloud |  |  | 115 |  |  | Install 115 kV breaker and half layout at West St. Cloud | MN |  |  | Planned | 4000000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | GRE-WMU | 4380 | 2015-01-09 | 202647 | 8394 | 2016-09-15 | SUB | 2019-05-01 | Priam |  |  | 115 | 69 |  | Move Willmar 115/69 kV transformer to new Priam 115 kV substation | MN |  |  | Planned | 3000000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | GRE-WMU | 4380 | 2015-01-09 | 202647 | 8395 | 2016-09-15 | LN | 2019-05-01 | Priam | Pennock/Willmar Waste Water | 1 | 69 |  |  | Establish 69 kV outlets from Priam | MN |  | 1.5 | Planned | 1000000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4455 | 2014-12-17 | DAEC Tap Rebuild | 8521 | 2015-06-30 | LN | 2016-12-31 | DAEC Tap | DAEC | 1 | 34 |  | 39 MVA | Rebuild the line to 69kV standards for furture conversion. | IA | 3.32 |  | Planned | 2674264 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4456 | 2014-12-17 | East Nevada St | 8523 | 2016-06-28 | SUB | 2020-12-31 | East Nevada Street | Substation | 1 | 34 |  |  | Add two 69kV breakers at the East Nevada distribution sub to allow for 69kV conversion. | IA |  |  | Planned | 400000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4459 | 2014-12-17 | East IA phase 3 | 8529 | 2016-06-28 | LN | 2018-12-31 | Rome REC | Rome REC Tap |  | 69 |  | 77 MVA | Build a new 69kV line from Rome REC back to the present line. | IA | 2 |  | Planned | 1080000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4459 | 2014-12-17 | East IA phase 3 | 8532 | 2016-06-28 | LN | 2018-12-31 | Marion | Amber |  | 69 |  | 77 MVA | Convert the 34kV line, already built for 69kV, to 69kV operation. | IA |  |  | Planned | 1200000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4459 | 2014-12-17 | East IA phase 3 | 8531 | 2015-12-30 | LN | 2018-12-31 | New Liberty | New Liberty Tap |  | 69 |  | 77 MVA | Build a new 69kV line from New Liberty back to the present line. | IA | 2 |  | Planned | 1080000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4459 | 2014-12-17 | East IA phase 3 | 8530 | 2016-06-28 | LN | 2018-12-31 | Clarence | Clarence REC |  | 69 |  | 77 MVA | Build a new 69kV line from Clarence to Clarence REC | IA | 2 |  | Planned | 1080000 | Planning | Generator | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4461 | 2014-12-17 | Emrld Isle Conv | 8537 | 2016-06-30 | SUB | 2016-09-03 | Marion | 34kV circuit |  | 69 |  |  | Convert the Marion Plant 34kV circuit to 69kV operation | IA |  |  | Under Construction | 1841957 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4462 | 2014-12-17 | Keswick-Victor Conv | 8539 | 2015-12-30 | SUB | 2021-12-30 | Victor Switching | Substation |  | 69 | 34 |  | ITC will add two 69kV breakers and a 69/34kV transformer at the new Victor substation. | IA |  |  | Planned | 3000000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4463 | 2014-12-17 | OtterCk-Fletcher | 8540 | 2015-12-30 | LN | 2019-12-31 | Fletcher | Green Mountain |  | 69 |  | 77 MVA | Retire the 34kV line terminal out of Marshalltown and route the line to the new Fletcher 69kV bus built adjacent to Marshalltown. Convert the 34kV line, already built for 69kV, to 69kV operation. | IA | 6.84 |  | Planned | 240000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4463 | 2014-12-17 | OtterCk-Fletcher | 8545 | 2015-12-30 | LN | 2019-12-31 | Otter Creek | Hubbard Pump Tap |  | 69 |  | 77 MVA | Convert the 34kV line, already built for 69kV, to 69kV operation. | IA | 14.17 |  | Planned |  | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4463 | 2014-12-17 | OtterCk-Fletcher | 8544 | 2015-12-30 | LN | 2019-12-31 | Otter Creek | CB Union |  | 69 |  | 77 MVA | Convert the 34kV line, already built for 69kV, to 69kV operation. | IA | 10.01 |  | Planned |  | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4463 | 2014-12-17 | OtterCk-Fletcher | 8543 | 2015-12-30 | LN | 2019-12-31 | CB Union | Union |  | 69 |  | 77 MVA | Convert the 34kV line, already built for 69kV, to 69kV operation. | IA | 1.05 |  | Planned |  | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4463 | 2014-12-17 | OtterCk-Fletcher | 8542 | 2015-12-30 | LN | 2019-12-31 | Conrad | Union |  | 69 |  | 77 MVA | Convert the 34kV line, already built for 69kV, to 69kV operation. | IA | 12.65 |  | Planned |  | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4463 | 2014-12-17 | OtterCk-Fletcher | 8541 | 2015-12-30 | LN | 2019-12-31 | Conrad | Green Mountain |  | 69 |  | 77 MVA | Convert the 34kV line, already built for 69kV, to 69kV operation. | IA | 11.15 |  | Planned |  | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4465 | 2014-12-17 | Mtwn-StnyPt 161 Conv | 8558 | 2016-06-30 | SUB | 2016-12-31 | Stoney Point | Substation |  | 161 |  |  | Move the 6th Street 161/115kV transfomrer to Stoney Point and retire the 6th Street 161/115kV transformers. Convert sub to 161kV operation. | IA |  |  | Under Construction | 1000000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4465 | 2014-12-17 | Mtwn-StnyPt 161 Conv | 8557 | 2016-06-30 | SUB | 2016-12-31 | Belle Plaine | Substation |  | 161 |  |  | Convert sub to 161kV operation. | IA |  |  | Under Construction | 100000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4465 | 2014-12-17 | Mtwn-StnyPt 161 Conv | 8554 | 2016-06-30 | LN | 2016-12-31 | Belle Plaine | Stoney Point |  | 161 |  | 327 MVA | Convert the 115kV line, already built for 161kV, to 161kV operation. | IA | 27.25 |  | Under Construction |  | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4465 | 2014-12-17 | Mtwn-StnyPt 161 Conv | 8553 | 2016-06-30 | LN | 2016-12-31 | Toledo | Belle Plaine |  | 161 |  | 327 MVA | Convert the 115kV line, already built for 161kV, to 161kV operation. | IA | 16.5 |  | Under Construction |  | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4467 | 2014-12-17 | Fairbank-Oelwein | 8560 | 2016-06-30 | LN | 2019-12-31 | Oelwein | Fairbank |  | 69 |  | 77 MVA | Rebuild 5.5 miles of the Oelwein-Fairbank 69kV line. | IA | 5.5 |  | Planned | 2805000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4704 | 2014-12-17 | Mtown-Parnell-CR | 8919 | 2016-06-30 | LN | 2019-09-02 | Kalona South Tap | Iowa Jct | 1 | 34 |  | 39 MVA | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | IA | 4.92 |  | Planned | 2212000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4704 | 2014-12-17 | Mtown-Parnell-CR | 8918 | 2016-06-30 | LN | 2018-08-03 | Frytown Tap | Kalona South Tap | 1 | 34 |  | 39 MVA | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | IA | 6.02 |  | Planned | 2709000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4704 | 2014-12-17 | Mtown-Parnell-CR | 8917 | 2016-06-30 | LN | 2018-08-03 | Hills | Frytown | 1 | 34 |  | 39 MVA | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | IA | 11.08 |  | Planned | 4986000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4704 | 2014-12-17 | Mtown-Parnell-CR | 8916 | 2016-06-30 | LN | 2018-02-16 | Ferguson REC Tap | Gilman Tap | 1 | 34 |  | 39 MVA | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | IA | 3.75 |  | Planned | 1687500 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4704 | 2014-12-17 | Mtown-Parnell-CR | 8915 | 2016-06-30 | LN | 2020-12-31 | Traer | Dysart | 1 | 34 |  | 39 MVA | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | IA | 8.28 |  | Planned | 3726000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4704 | 2014-12-17 | Mtown-Parnell-CR | 8914 | 2016-06-30 | LN | 2019-05-03 | Sutherland | LeGrand | 1 | 34 |  | 39 MVA | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | IA | 6.27 |  | Planned | 2821500 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4704 | 2014-12-17 | Mtown-Parnell-CR | 8913 | 2016-06-30 | LN | 2018-05-03 | Ferguson | Timber Creek Tap | 1 | 34 |  | 39 MVA | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | IA | 3.75 |  | Planned | 1687500 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4704 | 2014-12-17 | Mtown-Parnell-CR | 8912 | 2016-06-30 | LN | 2017-07-29 | Vining REC Tap | Tama East | 1 | 34 |  | 39 MVA | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | IA | 10.63 |  | Planned | 4783500 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4704 | 2014-12-17 | Mtown-Parnell-CR | 8911 | 2016-06-30 | LN | 2020-12-31 | Belle Plaine Jct | Vining REC Tap | 1 | 34 |  | 39 MVA | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | IA | 12.68 |  | Planned | 5706000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4704 | 2014-12-17 | Mtown-Parnell-CR | 8910 | 2016-06-30 | LN | 2021-12-31 | Benco | Tap | 1 | 34 |  | 39 MVA | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | IA | 1.57 |  | Planned | 706500 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4704 | 2014-12-17 | Mtown-Parnell-CR | 8909 | 2016-06-30 | LN | 2018-02-09 | Belle Plaine Jct | City of Belle Plaine | 1 | 34 |  | 39 MVA | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | IA | 4.8 |  | Planned | 2160000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4704 | 2014-12-17 | Mtown-Parnell-CR | 8908 | 2016-06-30 | LN | 2018-03-16 | Willaimsburg South | Parnell | 1 | 34 |  | 39 MVA | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | IA | 15 |  | Planned | 6750000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4704 | 2014-12-17 | Mtown-Parnell-CR | 8907 | 2016-06-30 | LN | 2018-05-24 | Koszta REC Tap | Belle Plaine Jct | 1 | 34 |  | 39 MVA | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | IA | 5.7 |  | Planned | 2565000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4704 | 2014-12-17 | Mtown-Parnell-CR | 8906 | 2016-06-30 | LN | 2018-05-04 | Willamsbug South | Tap | 1 | 34 |  | 39 MVA | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | IA | 3 |  | Planned | 1350000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4704 | 2014-12-17 | Mtown-Parnell-CR | 8905 | 2016-06-30 | LN | 2018-04-27 | Williamsburg East | Tap | 1 | 34 |  | 39 MVA | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | IA | 2.6 |  | Planned | 1170000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | ITCM | 4704 | 2014-12-17 | Mtown-Parnell-CR | 8904 | 2016-06-30 | LN | 2018-05-03 | Blairstown Tap | Tap | 1 | 34 |  | 39 MVA | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | IA | 2.6 |  | Planned | 1170000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | MDU | 3083 | 2015-03-31 | Dickinson Loop | 5365 | 2014-12-12 | CB | 2018-07-01 | North Dickinson | 2 PCB |  | 115 |  |  | Complete North Dickinson bus | ND |  |  | Planned | 1500000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | West | MDU | 3083 | 2015-03-31 | Dickinson Loop | 5364 | 2013-10-31 | LN | 2018-07-01 | North Dickinson | Dickinson West | 1 | 115 |  | 120 | New line Segment | ND |  | 3 | Planned | 750000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | West | MDU | 4133 | 2015-01-09 | Collins | 7864 | 2015-09-18 | TX | 2017-03-01 | Collins | 115/41.6 kV transformer | 1 | 115 | 41.6 |  | 115/41.6 kV transformer | ND |  |  | Planned | 1500000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | West | MDU | 4134 | 2015-01-09 | South 9th | 7865 | 2015-06-09 | SUB | 2017-06-01 | South 9th | 115/12.47 kV transformer | 1 | 115 | 12.47 | 25 | New substation & transformer | ND |  |  | Planned | 3600000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | West | MDU | 4134 | 2015-01-09 | South 9th | 7866 | 2015-06-09 | LN | 2017-06-01 | South 9th tap | South 9th | 1 | 115 |  | 190 | Double circuit line to the new South 9th substation connecting to the East Bismarck-Sweet Ave 115 kV line | ND |  |  | Planned | 600000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | West | MDU | 4141 | 2015-01-09 | Wishek Reactor | 7875 | 2016-06-01 | IND | 2016-09-30 | Wishek Jct | tertiary reactor |  | 13.8 |  | 15 | 1 X 30 Mvar tertiary reactor | ND |  |  | Planned | 500000 | Engineering |  | N | N | N | Y
A in MTEP14 | A | West | MEC | 4255 | 2015-09-16 | G2676 | 8003 | 2015-12-21 | SUB | 2017-05-01 | Sioux City Airport | Substation |  | 161 | 13 |  | Sioux City Airport Substation | IA |  |  | Planned | 2500000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | MEC | 4594 | 2015-09-16 | G2675 | 8741 | 2016-07-01 | LN | 2017-05-01 | Raun | Sioux City Airport | 1 | 161 |  | 410 | Add Raun-Sioux City Airport 161 kV line | IA |  | 0.1 | Planned | 70000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | MEC | 4594 | 2015-09-16 | G2675 | 8742 | 2016-07-01 | LN | 2017-05-01 | Kellogg | Sioux City Airport | 1 | 161 |  | 410 | Add CF Industries-Sioux City Airport 161 kV line | IA |  | 0.1 | Planned | 70000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | MH, MP | 3831 | 2014-12-17 | GNTL | 7200 | 2014-09-24 | LN | 2020-06-01 | Dorsey | US/MB Border | 1 | 500 |  | 1732 | Dorsey-US/Manitoba Border 500 kV Line | MB |  | 160 | Planned |  |  |  | N | N | N | Y
A in MTEP14 | A | West | MH, MP | 3831 | 2014-12-17 | GNTL | 7622 | 2014-11-18 | SC | 2020-06-01 | Warroad River |  |  | 500 |  | 1732 | New midpoint series compensation station on Dorsey - Iron Range 500 kV Line | MN | 0 | 0 | Planned | 52433712 | Facility Study |  | N | N | N | Y
A in MTEP14 | A | West | MH, MP | 3831 | 2014-12-17 | GNTL | 7202 | 2014-09-24 | SUB | 2020-06-01 | Iron Range |  |  | 500 | 230 | 1200 | New Iron Range 500/230 kV Substation adjacent to existing Blackberry 230/115 kV Substation | MN | 0 | 0 | Planned | 46023004 | Facility Study |  | N | N | N | Y
A in MTEP14 | A | West | MH, MP | 3831 | 2014-12-17 | GNTL | 7201 | 2014-11-18 | LN | 2020-06-01 | US/MB Border | Iron Range | 1 | 500 |  | 1732 | US/Manitoba Border-Iron Range 500 kV Line | MN |  | 220 | Planned | 573207005 | Facility Study |  | N | N | N | Y
A in MTEP14 | A | West | MP | 3831 | 2014-12-17 | GNTL | 20289 | 2015-01-06 | LNrl | 2020-06-01 | Iron Range | various |  | 230 |  |  | Modifications to and reroutes of existing 230 kV and 115 kV lines at Iron Range Substation site | MN | 0 | 2 | Planned | 3891711 | Facility Study |  | N | N | N | Y
A in MTEP14 | A | West | MP | 3831 | 2014-12-17 | GNTL | 20293 | 2015-01-06 | RLY | 2020-06-01 | Hilltop |  |  | 230 |  |  | One 230 kV panel replacement at Hilltop to facilitate interconnection of Iron Range 500/230 kV Substation | MN | 0 | 0 | Planned | 137500 | Facility Study |  | N | N | N | Y
A in MTEP14 | A | West | MP | 3831 | 2014-12-17 | GNTL | 20292 | 2015-01-06 | RLY | 2020-06-01 | Arrowhead |  |  | 230 |  |  | One 230 kV panel replacement at Arrowhead to facilitate interconnection of Iron Range 500/230 kV Substation | MN | 0 | 0 | Planned | 137500 | Facility Study |  | N | N | N | Y
A in MTEP14 | A | West | MP | 3831 | 2014-12-17 | GNTL | 20291 | 2015-01-06 | RLY | 2020-06-01 | Forbes |  |  | 230 |  |  | One 230 kV panel replacement at Forbes to facilitate interconnection of Iron Range 500/230 kV Substation | MN | 0 | 0 | Planned | 137500 | Facility Study |  | N | N | N | Y
A in MTEP14 | A | West | MP | 3831 | 2014-12-17 | GNTL | 20290 | 2015-01-06 | RLY | 2020-06-01 | Blackberry |  |  | 230 |  |  | Two 230 kV panel replacements at Blackberry to facilitate interconnection of Iron Range 500/230 kV Substation | MN | 0 | 0 | Planned | 275000 | Facility Study |  | N | N | N | Y
A in MTEP14 | A | West | MP | 4044 | 2014-12-17 | Canosia Road Substation | 7681 | 2015-06-12 | SUB | 2016-06-30 | Canosia Road | New Substation |  | 115 | 14 | 39.2 | New substation in Arrowhead - Cloquet 115 kV Line | MN | 0 |  | Under Construction | 4868663 | Engineering |  | N | N | N | Y
A in MTEP14 | A | West | MP | 4045 | 2014-12-17 | Embarrass Transformer | 7682 | 2015-05-19 | TX | 2016-10-01 | Embarrass |  | 1 | 115 | 23 | 18.6 | Embarrass 115/23 kV Transformer | MN | 0 | 0 | Planned | 1850000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | MP | 4426 | 2015-01-09 | Hoyt Lakes Substation Modernization | 8457 | 2015-06-10 | BUS | 2017-01-31 | Hoyt Lakes |  |  | 138 |  |  | Bus reconfiguration & equipment replacements | MN | 0 | 0 | Planned | 2500000 | Planning Preliminary |  | N | N | N | Y
A in MTEP14 | A | West | MP | 4426 | 2015-01-09 | Hoyt Lakes Substation Modernization | 20288 | 2015-06-10 | CAP | 2017-01-31 | Hoyt Lakes |  |  | 138 |  | 30 | Hoyt Lakes 30 MVAr cap bank | MN | 0 | 0 | Planned | 500000 | Planning Preliminary |  | N | N | N | Y
A in MTEP14 | A | West | MRES | 4470 | 2016-09-26 | Woodpecker Mitigation | 8563 | 2016-09-26 | LN | 2016-12-31 | Fergus Falls | Silver Lake | 1 | 230 |  |  | Address woodpecker damage and prevent future damage on existing line. | MN |  |  | Planned |  | Planning |  | N | N | N | Y
A in MTEP14 | A | West | MRES | 4470 | 2016-09-26 | Woodpecker Mitigation | 8568 | 2016-09-26 | LN | 2016-12-31 | Detroit Lakes West | Detroit Lakes Industrial | 1 | 115 |  |  | Address woodpecker damage and prevent future damage on existing line. | MN |  |  | Planned |  | Planning |  | N | N | N | Y
A in MTEP14 | A | West | MRES | 4470 | 2016-09-26 | Woodpecker Mitigation | 8567 | 2016-09-26 | LN | 2016-12-31 | Edgetown | Pelican Rapids | 1 | 115 |  |  | Address woodpecker damage and prevent future damage on existing line. | MN |  |  | Planned |  | Planning |  | N | N | N | Y
A in MTEP14 | A | West | MRES | 4470 | 2016-09-26 | Woodpecker Mitigation | 8566 | 2016-09-26 | LN | 2016-12-31 | Audubon | Cormorant Jct. | 1 | 115 |  |  | Address woodpecker damage and prevent future damage on existing line. | MN |  |  | Planned |  | Planning |  | N | N | N | Y
A in MTEP14 | A | West | MRES | 4470 | 2016-09-26 | Woodpecker Mitigation | 8565 | 2016-09-26 | LN | 2016-12-31 | Alexandria Tap | Miltona Tap | 1 | 115 |  |  | Address woodpecker damage and prevent future damage on existing line. | MN |  |  | Planned | 150000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | MRES | 4470 | 2016-09-26 | Woodpecker Mitigation | 8564 | 2016-09-26 | LN | 2016-12-31 | Alexandria - MRES | Grant County | 1 | 115 |  |  | Address woodpecker damage and prevent future damage on existing line. | MN |  |  | Planned |  | Planning |  | N | N | N | Y
A in MTEP14 | A | West | OTP | 4444 | 2015-09-25 | OTP | 8503 | 2015-09-25 | LNup | 2016-12-31 | NERC Alert Facility Ratings for Low Priority | Throughout system |  | 115 |  |  | Verify and remediate facilities as required due to the industry-wide NERC alert | MN,ND,SD |  |  | Planned | 7701028 | Construction |  | N | N | N | Y
A in MTEP14 | A | West | XEL | 4379 | 2016-05-10 | 20451 | 8393 | 2016-06-29 | CB | 2017-04-13 | Quarry |  |  | 115 |  |  | Install 115 kV breaker and half layout at existing Quarry substation | MN |  |  | Planned | 2000000 | Planning |  | N | N | N | Y
A in MTEP14 | A | West | XEL | 4693 | 2014-12-17 |  | 8877 | 2015-06-30 | LNrb | 2016-12-23 | Douglas County | West Union | 1 | 69 |  | 71.7 | Rebuild the Douglas County - West Union 69 kV line to 477 ACSR and transfer Osakis substation load to Douglass County | MN | 6.6 |  | Planned | 3011966 |  |  | N | N | N | Y
A in MTEP14 | A | West | XEL | 4694 | 2014-12-17 |  | 8878 | 2016-06-30 | CAP | 2017-08-01 | Gravel Island |  |  | 161 |  |  | Install two steps of 30 Mvar capacitor banks at Gravel Island substation on the 161 kV bus | WI |  |  | M4_Pre-Construction | 3500000 |  |  | N | N | N | Y
A in MTEP14 | A | West | XEL | 4697 | 2014-12-17 |  | 8881 | 2016-03-28 | LNrc | 2018-11-30 | Split Rock | Nobles County | 1 | 345 |  | 1195 | Reconductor 35 miles to Bundled 477 T-2 ACSR | MN | 35 |  | Planned | 5547376 |  |  | N | N | N | Y
A in MTEP15 | A | Central | AmerenIL | 3689 | 2015-12-28 |  | 6966 | 2013-09-13 | CB | 2016-11-15 | Keystone Substation | Wallace |  | 138 |  |  | Keystone 138-13.8 kV Substation - Replace 138 kV circuit breaker 1396 in the Wallace-Keystone line with a minimum 2000 A continuous 40 kA interrupting circuit breaker | IL |  |  | Planned | 500000 | Planning |  | N | N | N | Y
A in MTEP15 | A | Central | AmerenIL | 4078 | 2015-12-28 | AMRN33 | 7729 | 2015-04-01 | LN | 2016-11-15 | Sandburg | Monmouth | 1 | 138 |  | 280 | Rebuild approx. 4 miles of 477 kcmil ACSR conductor to meet or exceed the 1521 A summer emergency capability of the 1272 kcmil ACSR conductor which makes up the rest of this line. Replace wavetrap at Galesburg Monmouth Substation with equipment capable of carrying 2000 A continuously. | IL | 4 |  | Planned | 4200000 | Budgetary |  | N | N | N | Y
A in MTEP15 | A | Central | AmerenIL | 4079 | 2015-12-28 |  | 7730 | 2014-09-11 | SUB | 2017-06-01 | Huff | Connection for new 138-69 kV Sub |  | 138 | 69 |  | Establish new bulk substation connecting to the Havana-Danvers 138 kV Line 1352 between Powerton Jct. and Lilly Substation. (Tenttatively assume 3-position ring bus.) | IL |  |  | Planned | 3000000 | Planning |  | N | N | N | Y
A in MTEP15 | A | Central | AmerenIL | 4494 | 2015-12-28 |  | 8605 | 2015-03-25 | TX | 2016-12-01 | East Galesburg | Replace 161/138 kV XFMRS |  | 161 | 138 |  | Replace existing parallel 161/138 kV Transformers at East Galesburg with a single 161/138 kV Transformer at Sandburg 345/138 kV Substation. | IL |  |  | Planned | 3681580 | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | Central | AmerenIL | 7825 | 2015-12-28 |  | 20096 | 2015-04-29 | SwSta | 2019-12-01 | Mascoutah Municipal (Hilgard) |  |  | 138 |  |  | Install a 4-breaker 138 kV ring bus (2000 A, 40 kA) at or near the tap to Mascoutah Municipal on the existing Turkey Hill-Ashley 138 kV Line 1482. | IL |  |  | Planned | 5900000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | Central | AmerenIL | 8050 | 2015-12-28 |  | 20344 | 2015-04-01 | TX | 2015-06-01 | Baldwin 345kV |  |  | 345 | 138 | 560 MVA | Replace existing transformer | IL |  |  | Planned | 5650000 | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | Central | AmerenIL | 8054 | 2015-12-28 |  | 20351 | 2015-04-01 | LNrc | 2016-12-01 | Tilden Jct | Sparta |  | 138 |  |  | Reconductor 5.7 miles of line | IL | 5.7 |  | Planned | 2710721 | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | Central | AmerenIL | 8055 | 2015-12-28 |  | 20352 | 2015-04-01 | LNrc | 2016-06-01 | Sparta Tap | Steelville |  | 138 |  |  | Reconductor 7.4 miles of line | IL | 7.4 |  | Planned | 2318247 | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | Central | AmerenIL | 8060 | 2015-12-28 |  | 20485 | 2015-04-01 | LNrc | 2016-12-01 | Fayetteville South Tap | Tilden |  | 138 |  |  | Reconductor 1.5 miles of line | IL | 1.5 |  | Planned | 1500000 | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | Central | AmerenIL | 8134 | 2015-12-28 |  | 20488 | 2015-04-01 | LNrc | 2015-12-01 | Tilden Jct | Tilden |  | 138 |  |  | Reconductor one span of line | IL |  |  | Planned | 175920 | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | Central | AmerenIL | 8137 | 2015-12-28 |  | 20491 | 2015-04-01 | LNrc | 2017-06-01 | Turkey Hill | Mascoutah |  | 138 |  |  | Reconductor 8.5 miles of line | IL | 8.5 |  | Planned | 4250000 | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | Central | AmerenIL | 8581 | 2015-12-28 |  | 20686 | 2016-03-09 | TEQ | 2017-03-02 | Vermillion |  |  | 138 |  |  | Increase of wind farm capacity to 250 MW | IL |  |  | Planned | 48000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | Central | AmerenMO | 7871 | 2015-12-28 |  | 20109 | 2016-06-01 | CB | 2016-12-31 | Keokuk |  |  | 69 |  | 72 | Install new 1200 A, 69 kV position to accommodate new 69 kV line to be constructed by ITC Midwest. | IA |  |  | Planned | 460000 | Engineering |  | N | N | N | NT
A in MTEP15 | A | Central | AmerenMO | 8840 | 2015-12-28 |  | 20747 | 2016-06-02 | LN | 2016-11-14 | Heritage | Hitt | 1 | 161 | 161 | 56 | Extend 0.2 mile 161 kV line from Heritage to Hitt 161-34.5 kV Substation. | MO |  | 0.2 | Planned | 120000 | Planning |  | N | N | N | Y
A in MTEP15 | A | Central | BREC | 3435 | 2015-12-28 | LRP1 | 6338 | 2010-11-15 | LNrc | 2017-12-31 | Rome Junction | West Owensboro | 1 | 69 |  | 72 MVA | reconductor line | KY | 5.8 | 0 | Planned | 440000 | Planning |  | N | N | N | NT
A in MTEP15 | A | Central | BREC | 3436 | 2015-12-28 | LRP2 | 6339 | 2010-11-15 | LN | 2018-12-31 | Wilson | Sacremento | 1 | 69 |  | 72 MVA | new line | KY | 0 | 11 | Planned | 2100000 | Planning |  | N | N | N | NT
A in MTEP15 | A | Central | BREC | 3437 | 2015-12-28 | LRP3 | 6340 | 2010-11-15 | LNrc | 2018-12-31 | Thruston Junction | East Owensboro | 1 | 69 |  | 67 MVA | reconductor line | KY | 0.4 | 0 | Planned | 40000 | Planning |  | N | N | N | NT
A in MTEP15 | A | Central | BREC | 3438 | 2015-12-28 | LRP4 | 6341 | 2010-11-15 | LNrc | 2018-12-31 | Daviess County | Philpot Tap | 1 | 69 |  | 72 MVA | reconductor line | KY | 7.7 | 0 | Planned | 580000 | Planning |  | N | N | N | NT
A in MTEP15 | A | Central | BREC | 3441 | 2015-12-28 | LRP7 | 6344 | 2014-06-10 | LNrc | 2015-12-31 | Olivet Church Road | Olivet Church Road Tap | 1 | 69 |  | 72 MVA | reconductor line | KY | 1.4 | 0 | Planned | 150000 | Planning |  | N | N | N | NT
A in MTEP15 | A | Central | BREC | 3444 | 2015-12-28 | LRP10 | 6347 | 2014-06-10 | TX | 2015-12-31 | Meade County 161 kV | Meade County 69 kV |  | 161 | 69 | 56 MVA | new transformers | KY |  |  | Planned | 4000000 | Planning |  | N | N | N | Y
A in MTEP15 | A | Central | BREC | 9420 | 2015-12-28 |  | 21557 | 2015-11-05 | LN | 2017-03-31 | Coleman EHV | Aleris (LAM1) |  | 161 |  |  | Construction of a 1.7 mile long 161 kV radial circuit from Coleman EHV to serve the 28 MW load at the existing 161/13.8 kV delivery point. | KY |  | 1.7 | Planned | 640000 | Planning |  | N | N | N | Y
A in MTEP15 | A | Central | BREC | 9420 | 2015-12-28 |  | 21562 | 2016-01-12 | TEQ | 2017-03-31 | Coleman EHV |  |  | 161 |  |  | Terminal equipment and breakers will be installed at Coleman EHV 161 kV to accommodate service to the direct-serve Aleris loads (LAM1 & LAM2). | KY |  |  | Planned | 1150000 | Planning |  | N | N | N | Y
A in MTEP15 | A | Central | BREC | 9420 | 2015-12-28 |  | 21561 | 2015-11-05 | SUB | 2017-03-31 | Aleris (LAM2) | Coleman EHV |  | 161 |  |  | This substation will provide the planned 33 MW direct-serve load expansion at Aleris (LAM2). The existing 28 MW direct-serve load will be served from the existing Aleris (LAM1) substation. Both circuits will normally be fed from Coleman EHV 161 kV. In the event of an emergency, existing backup service feeds from the Hancock 161 kV substation remain available. | KY |  |  | Planned | 7000000 | Planning |  | N | N | N | Y
A in MTEP15 | A | Central | BREC | 9420 | 2015-12-28 |  | 21558 | 2015-11-05 | LN | 2017-03-31 | Coleman EHV | Aleris (LAM2) |  | 161 |  |  | Construction of a 2 mile 161 kV circuit to provide service to a new 161/13.8 kV delivery point necessary to serve the expanded load . | KY |  | 2 | Planned | 760000 | Planning |  | N | N | N | Y
A in MTEP15 | A | Central | BREC | 10142 | 2015-12-28 |  | 21472 | 2015-11-17 | TEQ | 2021-01-01 | Coleman |  |  | 345 |  |  | Sub upgrades at Coleman | KY |  |  | Planned | 5232998 | Planning Preliminary |  | N | Y | Y | Y
A in MTEP15 | A | Central | BREC, Vectren | 10142 | 2015-12-28 |  | 21471 | 2016-01-13 | LN | 2021-01-01 | Duff | Coleman |  | 345 |  |  | New Duff-Coleman 345 kV, single circuit. MISO portion is 2 segments - 24.5 and 4 miles, cut into by double circuit PJM section to Rockport | IN,KY |  | 28.5 | Planned | 59117869 | Planning Preliminary |  | N | Y | Y | Y
A in MTEP15 | A | Central | CWLD | 8300 | 2016-07-11 |  | 20634 | 2016-05-25 | LN | 2030-06-01 | Perche | Mill Creek | 1 | 161 |  |  | New 161 kV line from Perche to Mill Creek | MO |  |  | Planned | 12000000 |  |  | N | N | N | Y
A in MTEP15 | A | Central | CWLD | 8300 | 2016-07-11 |  | 20637 | 2016-05-25 | SUB | 2030-06-01 | Mill Creek |  |  | 161 | 13.8 |  | New Mill Creek 161/13.8 kV substation | MO |  |  | Planned | 5000000 |  |  | N | N | N | Y
A in MTEP15 | A | Central | CWLD | 8300 | 2016-07-11 |  | 20636 | 2016-05-25 | LN | 2030-06-01 | McBaine | Mill Creek | 1 | 161 |  |  | New 161 kV line from McBain to Mill Creek | MO |  |  | Planned | 9000000 |  |  | N | N | N | Y
A in MTEP15 | A | Central | CWLD | 8300 | 2016-07-11 |  | 20635 | 2016-05-25 | LN | 2030-06-01 | Grindstone | Mill Creek | 1 | 161 |  |  | New 161 kV line from Grindstone to Mill Creek | MO |  |  | Planned | 6000000 |  |  | N | N | N | Y
A in MTEP15 | A | Central | DEI | 2144 | 2015-12-28 | 604J3062 | 2930 | 2016-03-01 | LNrc | 2017-06-30 | Franklin 230 | Earlywood | 1 | 69 |  | 143 | Franklin 230kV sub to Earlywood sub reconductor 1.06 mile - 69kV - 69165 line with 954ACSR@100C | IN | 1.06 |  | M3_Long Lead Materials | 1170000 | Engineering w/AFUDC |  | N | N | N | NT
A in MTEP15 | A | Central | DEI | 7882 | 2015-12-28 | AMIN1047 | 20111 | 2016-03-01 | LN | 2017-06-01 | Bloomington Rogers St. | Bloomington Dunn St. | 1 | 69 |  | 153 | Construct new 69kV line from Bloomington Rogers St. to Bloomington Dunn St. (also includes Dunn St. bus work - AMIN1046) 954ACSR@100C | IN |  | 3 | M3_Long Lead Materials | 4820000 | Engineering w/AFUDC |  | N | N | N | NT
A in MTEP15 | A | Central | DEI | 7883 | 2015-12-28 | AMIN1093 | 20112 | 2016-03-01 | Dist | 2017-06-02 | Bloomington Downtown | new distribution sub |  | 69 | 12 |  | Construct new 22.4MVA - 69/12kV sub near downtown Bloomington in the new line established by project AMIN1047 / 7882. | IN |  |  | M3_Long Lead Materials | 602000 | Engineering w/AFUDC |  | N | N | N | NT
A in MTEP15 | A | Central | DEI | 7885 | 2015-12-28 | AMIN1052 | 20115 | 2016-08-23 | LNrc | 2017-03-31 | Frankfort Burlington St. | Middlefork | 1 | 69 |  | 153 | Frankfort Burlington St to Middlefork 69kV - 69133 ckt: Reconductor 12.4 miles with 954ACSR@100C | IN | 12.4 |  | M4_Pre-Construction | 6636000 | Engineering w/AFUDC |  | N | N | N | NT
A in MTEP15 | A | Central | DEI | 7903 | 2015-12-28 | AMIN0701 | 20140 | 2015-12-01 | LNrc | 2025-06-01 | Martinsville SE | HE Park Ave | 1 | 69 |  | 153 | Martinsville SE - HE Park Ave 69kV - 6903 ckt: Reconductor 3.4 miles with 954ACSR@100C | IN | 3.4 |  | M1_Final SPM or OOC | 2102000 | Engineering w/AFUDC |  | N | N | N | NT
A in MTEP15 | A | Central | DEI | 7911 | 2015-12-28 | AMIN1146 | 20155 | 2016-02-22 | SUB | 2018-12-31 | Frankfort 230kV |  |  | 230 | 69 | 2000A | Frankfort 230kV: complete 4-brkr ring bus; 69kV: complete 6-brkr ring bus and retire Jefferson Jct with new line terminal for 69kV line to Frankfort Muni. | IN |  |  | M1_Final SPM or OOC | 5109020 | Engineering w/AFUDC |  | N | N | N | NT
A in MTEP15 | A | Central | DEI | 7946 | 2015-12-28 | AMIN1070 | 20197 | 2015-12-01 | LN | 2017-12-31 | Speed | Jeffersonville | 1 | 138 |  | 306 | Loop existing 138kV line from Speed to Clark Maritime to Jeffersonville. Add 2.52 mile 138kV line section from Speed to Memphis Jct and tie into existing 13890 circuit. Add .01 mile 138kV line section from Jeffersonville Jct. to Jeffersonville sub. Install 138kV line terminals at Speed and Jeffersonville. | IN |  | 2.53 | M1_Final SPM or OOC | 5472000 | Engineering w/AFUDC |  | N | N | N | Y
A in MTEP15 | A | Central | DEI | 7953 | 2015-12-28 | AMIN0393T | 20213 | 2016-06-08 | LN | 2016-12-31 | Mohawk Industrial | Mohawk 138 | 1 | 69 |  | 153 | New 1.2 mile 69kV line to complete 69130 ckt. loop through Mohawk Industrial 69/12kV sub. | IN |  | 1.2 | Under Construction | 1309000 | Engineering w/AFUDC |  | N | N | N | NT
A in MTEP15 | A | Central | DEI | 7957 | 2015-12-28 | AMIN1440/AMIN1289 | 20218 | 2016-03-01 | Dist | 2017-06-01 | Kokomo S. Main St. |  |  | 69 | 12 |  | Relocate Kokomo S. Main St. 69/12kV distribution sub to higher ground (rename sub Kokomo Apperson) | IN |  |  | M3_Long Lead Materials | 1261000 | Engineering w/AFUDC |  | N | N | N | NT
A in MTEP15 | A | Central | DEI | 7961 | 2016-06-14 | AMIN1290 | 20225 | 2016-06-14 | CB | 2017-12-31 | Fairview 138 |  |  | 138 |  |  | Fairview 138kV Breaker Replacements: replace OCB 13858, 13854, and relays at line terminals 13854, 13855, 13858 | IN |  |  | M3_Long Lead Materials | 4211000 | Engineering w/AFUDC |  | N | N | N | Y
A in MTEP15 | A | Central | DEI | 7963 | 2015-12-28 | AMIN1291 | 20226 | 2015-12-01 | CB | 2018-12-31 | New Castle 138 |  |  | 138 |  |  | New Castle 138kV Breaker Replacements: replace OCB 13805, 13835, 13842, 13873, 13869-1, 13869-2, and relays at line terminals 13805, 13835, 13842, 13873, 13843 | IN |  |  | M1_Final SPM or OOC | 2516322 | Engineering w/AFUDC |  | N | N | N | Y
A in MTEP15 | A | Central | DEI | 7964 | 2015-12-28 | AMIN1292 | 20227 | 2015-12-01 | CB | 2018-12-31 | Kokomo Highland Park |  |  | 138 | 69 |  | Kokomo Highland Park Equipment: Replace OCB 69230-4, -5, -6, -7, OCB BK 7 CAP, 69kV primary UG cables, relays at terminals 6910, 6911, 6913, 6928, 6992, 13879, 13887, 138kV TRANSFER | IN |  |  | M1_Final SPM or OOC | 3351124 | Engineering w/AFUDC |  | N | N | N | NT
A in MTEP15 | A | Central | DEI | 7969 | 2015-12-28 | AMIN1324 | 20232 | 2015-12-01 | LNup | 2017-12-31 | Edwardsport | Amo |  | 345 |  |  | Edwardsport - Amo 345kV - 34528 ckt. replace intermediate tansient structures with deadend structures - every 2.5 miles (22 structures). | IN |  |  | M1_Final SPM or OOC | 16052359 | Engineering w/AFUDC |  | N | N | N | Y
A in MTEP15 | A | Central | DEI | 7974 | 2015-12-28 | AMIN1322 | 20237 | 2015-12-01 | LNrc | 2018-12-31 | Lafayette 230kV | Attica |  | 230 | 138 |  | Lafayette 230 - Attica 230kV - 23027 ckt: Reconductor 5.4 miles at Lafayette 230 end with 900ACSR-OVAL@100C; also reconductor portions of double-circuited 13877 and 13878 circuits with 954ACSR-OVAL@100C - total of 9.9 miles. | IN | 15.3 |  | M1_Final SPM or OOC | 3684530 | Engineering w/AFUDC |  | N | N | N | Y
A in MTEP15 | A | Central | DEI | 7982 | 2015-12-28 | AMIN1314 | 20251 | 2015-12-01 | LNrc | 2017-12-31 | Advance | Dover | 1 | 69 |  | 100 | Advance - Dover 69kV - 69134 ckt: Rebuild 7.9 mile line with 477ACSR@100C - replacing all structures with steel poles. | IN | 7.9 |  | M1_Final SPM or OOC | 4903384 | Engineering w/AFUDC |  | N | N | N | NT
A in MTEP15 | A | Central | DEI | 7984 | 2015-12-28 | AMIN1283 | 20254 | 2015-12-01 | LNup | 2018-12-31 | Medora | Brownstown | 1 | 69 |  |  | Medora - Brownstown 69kV - 6952 ckt: Rebuild 4.85 mile line transferring existing 477ACSR conductor - replacing all structures with steel poles. | IN | 4.85 |  | M1_Final SPM or OOC | 2590705 | Engineering w/AFUDC |  | N | N | N | NT
A in MTEP15 | A | Central | DEI | 7987 | 2015-12-28 | AMIN1278 | 20257 | 2016-02-02 | LNrc | 2018-12-31 | New Pekin Jct | Salem | 1 | 69 |  | 100 | New Pekin Jct - Salem 69kV - 69153 ckt: Rebuild 9.4 mile line with 477ACSR@100C - replacing all structures with steel poles. | IN | 9.4 |  | M1_Final SPM or OOC | 4028000 | Engineering w/AFUDC |  | N | N | N | NT
A in MTEP15 | A | Central | DEI | 7989 | 2015-12-28 | AMIN1279 | 20259 | 2016-03-01 | LNrc | 2016-12-31 | Edwardsport | Odon Jct | 1 | 69 |  |  | Edwardsport - HE Rogers Jct 69kV - 6951 ckt: Rebuild 9.8 mile line with 477ACSR@100C - replacing all structures with steel poles. (HE Rogers Jct is located between Edwpt and Odon Jct) | IN | 9.8 |  | M4_Pre-Construction | 7391505 | Engineering w/AFUDC |  | N | N | N | NT
A in MTEP15 | A | Central | DEI | 7991 | 2015-12-28 | AMIN1277 | 20261 | 2016-03-01 | LNrc | 2016-12-31 | Rushville | HE Milroy | 1 | 69 |  | 100 | Rushville - HE Milroy 69kV - 6920 ckt: Rebuild 7.2 mile line with 477ACSR@100C - replacing all structures with steel poles. | IN | 7.2 |  | M4_Pre-Construction | 6699202 | Engineering w/AFUDC |  | N | N | N | NT
A in MTEP15 | A | Central | DEI | 7992 | 2015-12-28 | AMIN1281 | 20265 | 2015-12-01 | LNrc | 2018-12-31 | Hillenbrand Jct | Andersonville Jct | 1 | 69 |  | 100 | Hillenbrand Jct - Batesville North - Andersonville Jct 69kV - 6919 ckt: Rebuild 7.93 mile line with 477ACSR@100C - replacing all structures with steel poles. | IN | 7.93 |  | M1_Final SPM or OOC | 6472095 | Engineering w/AFUDC |  | N | N | N | NT
A in MTEP15 | A | Central | DEI | 9246 | 2015-12-28 | TIN1607 | 20849 | 2016-03-01 | LN | 2017-06-01 | Lafayette Southeast | Lafayette South Jct 2 | 1 | 138 |  | 301 | Lafayette SE to new Lafayette S Jct 2 (in existing 13808 ckt.) - build new 138kV - 1.75 mile - 954acsr@100c - 13899 ckt.; add new breaker in Laf SE ring; add (2) line switches at new jct and operate Laf S Jct to Laf S Jct 2 N.O. | IN |  | 1.75 | M3_Long Lead Materials | 3976181 | Engineering w/AFUDC |  | N | N | N | Y
A in MTEP15 | A | Central | DEI | 9247 | 2015-12-28 | TIN1674-AMIN1151 | 20850 | 2016-06-07 | SUB | 2017-06-01 | Lafayette 230kV | bus tie brkr |  | 138 |  |  | Lafayette 230 sub - insert a redundant 138kV bus tie breaker in series with existing breaker; add redundant bus differential relays to both 138kV bus 1 and 2. Scope also includes (5) 138Kv antiquated breaker and relay replacements, disconnect switches and misc buswork. | IN |  |  | M1_Final SPM or OOC | 4500000 | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | Central | DEI, HE | 7940 | 2015-12-28 | AMIN1184 | 20191 | 2016-03-01 | LNrb | 2018-07-31 | Bedford | HE Worthington | 1 | 138 |  | 230 | Bedford - Owensburg - HE Buena Vista - HE Worthington 138kV - 13840 ckt: Reconductor 33 miles with 954ACSR and replace all structures. Also reconductor 2.29 miles of 13823 where it is double circuited with 954ACSR near the Bedford end. Upgrade Bedford 13840 brkr and terminal equipment to 2000A. New ROW will be required. | IN | 35 |  | M3_Long Lead Materials | 36169000 | Engineering w/AFUDC |  | N | N | N | Y
A in MTEP15 | A | Central | HE | 10343 | 2015-12-28 |  | 21569 | 2015-11-16 | SUB | 2016-06-01 | Hubbell |  |  | 138 |  |  | Construct a 138kV ring bus and add a second 138/69kV transformer | IN |  |  | Planned | 10047000 |  |  | N | N | N | Y
A in MTEP15 | A | Central | IPL | 4262 | 2015-12-28 |  | 8040 | 2013-09-12 | LNup | 2016-12-31 | Pritchard | Centerton-Honey Creek-Southport | 1 | 138 |  | 302 | Increase line rating from 242 to 302 MVA | IN | 21.6 |  | Planned |  | Planning |  | N | N | N | Y
A in MTEP15 | A | Central | IPL | 4263 | 2015-12-28 |  | 8041 | 2013-09-12 | LNup | 2016-12-31 | Pritchard | Heartland Crossing-Mooresville | 1 | 138 |  | 242 | Increase line rating from 191 to 242 MVA | IN | 15.8 |  | Planned |  | Planning |  | N | N | N | Y
A in MTEP15 | A | Central | IPL | 4264 | 2015-12-28 |  | 8042 | 2016-03-01 | LN | 2016-12-31 | Pritchard | Franklin Township | 1 | 138 |  | 322 | New 138 kV transmission line rated 322 MVA on spare position of existing double circuit tower line | IN | 23 |  | Under Construction |  | Planning |  | N | N | N | Y
A in MTEP15 | A | Central | IPL | 7701 | 2015-12-28 |  | 20063 | 2016-03-01 | CB | 2016-06-01 | Thompson | Breakers |  | 138 |  |  | Two new breakers | IN |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP15 | A | Central | IPL | 7704 | 2015-12-28 |  | 20065 | 2015-07-09 | CB |  | Rockville | Breaker |  | 345 |  |  | New breaker | IN |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP15 | A | Central | IPL | 7704 | 2015-12-28 |  | 20066 | 2015-07-09 | CB |  | Rockville | Breaker |  | 138 |  |  | New breaker | IN |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP15 | A | Central | IPL | 9402 | 2015-12-28 |  | 20892 | 2015-07-27 | LNup | 2017-07-15 | Guion | Westlane | 40 | 138 |  | 298 | Increase line rating to 298 MVA by increased clearance. | IN | 2.2 |  | Planned |  |  |  | N | N | N | Y
A in MTEP15 | A | Central | PPI | 7881 | 2015-12-28 | 2015-12 | 20113 | 2015-03-12 | LN | 2018-12-31 | Fishhook | Pittsfield | 1 | 138 |  | 229 | 14.5 mile single pole 138 kV line constructed with 795 MCM ACSR conductor. Portions of the line will be double circuited with the Fishhook-Liberty 138 kV line and the Pittsfield-Pittsfield Distribution 69 kV line. | IL |  | 14.5 | Planned | 6887747 | Engineering |  | N | N | N | Y
A in MTEP15 | A | Central | PPI | 7881 | 2015-12-28 | 2015-12 | 20121 | 2015-03-12 | LNrb | 2017-12-01 | Pittsfield | Pittsfield Distribution | 1 | 69 | 69 | 50 | 69 kV Underbuild on portion of Fishhook-Pittsfield 138 kV line. Replace approximately 2.5 miles of 4/0 conductor from Pittsfield-Pittsfield Distribution 69 kV with 336.4 MCM ACSR conductor. | IL | 2.5 |  | Planned | 750000 |  |  | N | N | N | NT
A in MTEP15 | A | Central | PPI | 7889 | 2015-12-28 | 2015-14,35,37 | 20123 | 2015-03-12 | LN | 2019-12-31 | Fishhook 138 kV | Liberty 138 kV |  | 138 | 138 | 229 | Construct 12 mile 138 kV line from Fishhook substation to Liberty substation. | IL |  | 12 | Planned | 5819909 | Engineering |  | N | N | N | Y
A in MTEP15 | A | Central | PPI | 7889 | 2015-12-28 | 2015-14,35,37 | 20125 | 2016-09-09 | TX | 2019-12-31 | St. Anthony 138 kV | St. Anthony 69 kV |  | 138 | 69 | 75 | Replace 50 MVA delta-wye 138/69 kV transformer with 75 MVA wye-wye transformer with LTC. | IL |  |  | Planned | 1251800 | Engineering |  | N | N | N | NT
A in MTEP15 | A | Central | PPI | 7889 | 2015-12-28 | 2015-14,35,37 | 20124 | 2016-09-09 | SUB | 2019-12-31 | Liberty 138 kV | Liberty 69 kV | 1 | 138 | 69 | 75 | New 138/69 kV substation including 75 MVA 138/69 kV transformer. | IL |  |  | Planned | 4653000 | Engineering |  | N | N | N | NT
A in MTEP15 | A | Central | Vectren | 4391 | 2016-05-19 | 2013SIGE5 | 8408 | 2016-05-19 | CAP | 2019-12-31 | Pigeon Creek 69 | Capacitor |  | 69 |  | 15.6 MVAR | Add a 15.6 MVAR cap bank at the Pigeon Creek Sub | IN | 0 | 0 | Planned | 600000 | Planning |  | N | N | N | Y
A in MTEP15 | A | Central | Vectren | 10142 | 2015-12-28 |  | 21473 | 2016-01-13 | TEQ | 2021-01-01 | Duff |  |  | 345 |  |  | Sub upgrades at Duff | IN |  |  | Planned | 3092381 |  |  | N | Y | N | Y
A in MTEP15 | A | East | ITCT | 7891 | 2016-07-14 | ITC_14_020 | 20322 | 2016-07-14 | LNug | 2017-05-01 | Cato | Stone Pool | 1 | 120 |  |  | New 120 kV underground cable to loop in Stone Pool Substation | MI |  |  | Under Construction | 6047000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | ITCT | 7891 | 2016-07-14 | ITC_14_020 | 20455 | 2016-07-14 | RLY | 2017-05-01 | Midtown |  |  | 120 |  |  | Relay Upgrades at Midtown | MI |  |  | M4_Pre-Construction | 54000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | ITCT | 7891 | 2016-07-14 | ITC_14_020 | 20454 | 2016-07-14 | RLY | 2017-05-01 | Cato |  |  | 120 |  |  | Relay upgrades at Cato | MI |  |  | M4_Pre-Construction | 54000 |  |  | N | N | N | Y
A in MTEP15 | A | East | ITCT | 7891 | 2016-07-14 | ITC_14_020 | 20324 | 2016-07-14 | TAP | 2017-05-01 | Stone Pool |  |  | 120 |  |  | New Stone Pool Substation | MI |  |  | M4_Pre-Construction | 4323000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | ITCT | 7891 | 2016-07-14 | ITC_14_020 | 20323 | 2016-07-14 | LNug | 2017-05-01 | Midtown | Stone Pool | 1 | 120 |  |  | New 120 kV underground cable to loop in Stone Pool. | MI |  |  | Under Construction | 6047000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | ITCT | 7892 | 2016-03-22 | ITC_14_028 | 20319 | 2016-03-22 | LN | 2019-06-13 | Hood | Bartlett |  | 120 |  |  | New 120 kV transmission line to loop in Bartlett. | MI |  |  | M2a_Pre-Project Approval | 2490000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | ITCT | 7892 | 2016-03-22 | ITC_14_028 | 20845 | 2016-03-22 | RLY | 2019-06-13 | Bloomfield |  |  | 120 |  |  | Relay Upgrades at Bloomfield | MI |  |  | M2a_Pre-Project Approval | 15000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | ITCT | 7892 | 2016-03-22 | ITC_14_028 | 20844 | 2016-03-22 | RLY | 2019-06-13 | Hood |  |  | 120 |  |  | Relay Upgrades at Hood Substation | MI |  |  | M2a_Pre-Project Approval | 15000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | ITCT | 7892 | 2016-03-22 | ITC_14_028 | 20321 | 2016-03-22 | TAP | 2019-06-13 | Bartlett |  |  | 120 |  |  | New distribution substation | MI |  |  | M2a_Pre-Project Approval | 2910000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | ITCT | 7892 | 2016-03-22 | ITC_14_028 | 20320 | 2016-03-22 | LN | 2019-06-13 | Bloomfield | Bartlett | 1 | 120 |  |  | New 120 kV transmission line to loop in Bartlett Substation | MI |  |  | M2a_Pre-Project Approval | 2490000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | ITCT | 8083 | 2015-12-28 | ITC_14_013 | 20408 | 2016-06-07 | RLY | 2017-06-01 | Cortland |  |  | 120 |  |  | Upgrade limiting relay at Cortland. | MI |  |  | M3_Long Lead Materials | 300000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | ITCT | 8087 | 2016-08-03 | ITC_14_022 | 20411 | 2016-08-03 | CAP | 2018-06-01 | Stratford |  |  | 120 |  |  | 33.3 MVAR capacitor bank at Stratford 120 kV station. | MI |  |  | M2a_Pre-Project Approval | 820000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | ITCT | 8094 | 2015-12-28 | ITC_14_018 | 20422 | 2015-12-23 | TX | 2018-06-01 | Fitz |  | 301 | 345 | 120 |  | Add a 345/120 kV transformer at Fitz Substation | MI |  |  | M2a_Pre-Project Approval | 5500000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | ITCT | 8094 | 2015-12-28 | ITC_14_018 | 20431 | 2015-12-23 | SUB | 2018-06-01 | Fitz |  |  | 345 | 120 |  | Install 345 and 120 kV substation equipment at Fitz to accomodate the installation of the new 345/120 kV transformer and looping the 120 kV Adams to Bunce line into Fitz. | MI |  |  | M2a_Pre-Project Approval | 6500000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | ITCT | 8094 | 2015-12-28 | ITC_14_018 | 20427 | 2015-12-23 | LN | 2018-06-01 | Fitz | Bunce | 1 | 120 |  |  | 120 kV line created by looping the Adams-Bunce 120 kV line into Fitz. This requires approx. 0.1 miles of new double circuit structures in new ROW utilizing 1431 ACSR Conductor. | MI |  | 0.1 | M2a_Pre-Project Approval | 600000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | ITCT | 8094 | 2015-12-28 | ITC_14_018 | 20426 | 2015-12-23 | LN | 2018-06-01 | Adams | Fitz | 1 | 120 |  |  | 120 kV line created by looping the Adams-Bunce 120 kV line into Fitz. This requires approx. 0.1 miles of new double circuit structures in new ROW utilizing 1431 ACSR Conductor. | MI |  | 0.1 | M2a_Pre-Project Approval | 600000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | ITCT | 9245 | 2016-07-05 | ITC_14_023 | 20848 | 2016-07-05 | SUB | 2016-09-02 | Rapson |  |  | 120 |  |  | Add two breakers, disconnects, and relays. | MI |  |  | Under Construction | 1330000 | Engineering | Network | N | Y | N | Y
A in MTEP15 | A | East | ITCT | 9360 | 2016-07-05 | ITC_15_001 | 20874 | 2016-07-05 | SUB | 2018-12-31 | Scio 120/13.2 kV |  |  | 120 | 13.2 |  | Install 2-120 kV line breakers and 1-120 kV section breaker w/ associated disconnects laid out in a straight bus configuration. | MI |  |  | M3_Long Lead Materials | 2775000 | Engineering |  | N | N | N | NT
A in MTEP15 | A | East | ITCT | 9360 | 2016-07-05 | ITC_15_001 | 20876 | 2016-07-05 | LN | 2018-12-31 | Scio | Spruce | 1 | 120 |  |  | New 120 kV line created by constructing approx. 2 miles of 120 kV, double circuit structures in new ROW and looping the existing Lark-Spruce line into Scio. | MI |  | 2 | M3_Long Lead Materials | 3787500 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | ITCT | 9360 | 2016-07-05 | ITC_15_001 | 20875 | 2016-07-05 | LN | 2018-12-31 | Lark | Scio | 1 | 120 |  |  | New 120 kV line created by constructing approx. 2 miles of 120 kV, double circuit structures in new ROW and looping the existing Lark-Spruce line into Scio. | MI |  | 2 | M3_Long Lead Materials | 3787500 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | ITCT | 9362 | 2015-12-28 | ITC_15_005 & ITC_15_006 | 20880 | 2016-08-11 | SUB | 2018-12-31 | Blue 120/41.6 kV |  |  | 120 | 41.6 |  | Install 3-120 kV breakers w/ associated dsconnects in a straight bus configuration, a control house, and all other 120 kV equipment owned by ITCT at Blue substation. | MI |  |  | M3_Long Lead Materials | 2600000 | Engineering |  | N | N | N | NT
A in MTEP15 | A | East | ITCT | 9362 | 2015-12-28 | ITC_15_005 & ITC_15_006 | 21449 | 2016-08-11 | SUBmisc | 2018-12-31 | Lark 120 kV |  |  | 120 |  |  | Upgrade relaying associated with position HI at Lark | MI |  |  | M3_Long Lead Materials | 309000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | ITCT | 9362 | 2015-12-28 | ITC_15_005 & ITC_15_006 | 20887 | 2016-08-11 | LNug | 2018-12-31 | Phoenix | Blue | 2 | 120 |  |  | Construct a 2.6 mile underground line using 2500 XLPE cable between Phoenix and Blue to create the Blue-Phoenix #1 line. | MI |  | 2.6 | M3_Long Lead Materials | 39060000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | ITCT | 9362 | 2015-12-28 | ITC_15_005 & ITC_15_006 | 20886 | 2016-08-11 | LNug | 2018-12-31 | Phoenix | Blue | 1 | 120 |  |  | Construct a 2.6 mile underground line using 2500 XLPE cable between Phoenix and Blue to create the Blue-Phoenix #1 line. | MI |  | 2.6 | M3_Long Lead Materials | 39060000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | ITCT | 9362 | 2015-12-28 | ITC_15_005 & ITC_15_006 | 20885 | 2015-12-23 | LN | 2019-05-01 | Pioneer | State | 2 | 120 |  |  | Construct 2.7 miles of new double circuit structures and string 954 ACSR on both sides between Pioneer and State (formerly "Maize")to create the State (formerly "Maize") - Pioneer #1 and #2 lines. | MI |  | 2.7 | M2a_Pre-Project Approval | 5252000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | ITCT | 9362 | 2015-12-28 | ITC_15_005 & ITC_15_006 | 20884 | 2015-12-23 | LN | 2019-05-01 | Pioneer | State | 1 | 120 |  |  | Construct 2.7 miles of new double circuit structures and string 954 ACSR on both sides between Pioneer and State (formerly "Maize") to create the State (formerly "Maize") - Pioneer #1 and #2 lines. | MI |  | 2.7 | M2a_Pre-Project Approval | 5252000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | ITCT | 9362 | 2015-12-28 | ITC_15_005 & ITC_15_006 | 20883 | 2016-08-11 | SUB | 2018-12-31 | Phoenix 120/41.6 kV |  |  | 120 | 41.6 |  | Install 2-120 kV line breakers and 1-120 kV section breaker at ITC's existing Phoenix substation. Also reterminate the Phoenix end of the Lark-Phoenix circuit to a different bus inside of Phoenix | MI |  |  | M2a_Pre-Project Approval | 2492000 | Engineering |  | N | N | N | NT
A in MTEP15 | A | East | ITCT | 9362 | 2015-12-28 | ITC_15_005 & ITC_15_006 | 20882 | 2015-12-23 | SUB | 2019-05-01 | Pioneer 120/41.6 kV |  |  | 120 | 41.6 |  | Install 2-120 kV line breakers at ITC's existing Pioneer substation | MI |  |  | M2a_Pre-Project Approval | 1428000 | Engineering |  | N | N | N | NT
A in MTEP15 | A | East | ITCT | 9362 | 2015-12-28 | ITC_15_005 & ITC_15_006 | 20881 | 2015-12-23 | SUB | 2019-05-01 | State 120/41.6 kV |  |  | 120 | 41.6 |  | Install 3-120 kV breakers w/ associated dsconnects in a straight bus configuration, a control house, and all other 120 kV equipment owned by ITCT at State (formerly "Maize") substation. | MI |  |  | M2a_Pre-Project Approval | 2420000 | Engineering |  | N | N | N | NT
A in MTEP15 | A | East | ITCT | 9440 | 2015-12-28 | ITC_14_027 | 20901 | 2016-06-07 | LNrl | 2017-12-31 | Waterman | Cato | 1 | 120 |  |  | Relocate a portion of the underground circuit exiting Waterman station | MI |  |  | Under Construction | 8500000 | Engineering Preliminary |  | N | N | N | Y
A in MTEP15 | A | East | ITCT | 9440 | 2015-12-28 | ITC_14_027 | 20905 | 2016-06-07 | LNrl |  | Waterman | DIG-Navarre | 1 | 230 |  |  | Relocate a portion of the overhead circuit exiting Waterman station | MI |  |  | M3_Long Lead Materials |  | Engineering Preliminary |  | N | N | N | Y
A in MTEP15 | A | East | ITCT | 9440 | 2015-12-28 | ITC_14_027 | 20904 | 2016-06-07 | LNrl | 2017-12-31 | Waterman | Zug | 1 | 120 |  |  | Relocate a portion of the overhead circuit exiting Waterman station | MI |  |  | M3_Long Lead Materials |  | Engineering Preliminary |  | N | N | N | Y
A in MTEP15 | A | East | ITCT | 9440 | 2015-12-28 | ITC_14_027 | 20903 | 2016-06-07 | LNrl | 2017-12-31 | Waterman | St. Antoine | 1 | 120 |  |  | Relocate a portion of the underground circuit exiting Waterman station | MI |  |  | Under Construction | 8500000 | Engineering Preliminary |  | N | N | N | Y
A in MTEP15 | A | East | ITCT | 9440 | 2015-12-28 | ITC_14_027 | 20902 | 2016-03-22 | LNrl | 2017-12-31 | Waterman | Frisbie | 1 | 120 |  |  | Relocate portion of the undergound circuit exiting Waterman station | MI |  |  | M3_Long Lead Materials | 8000000 | Engineering Preliminary |  | N | N | N | Y
A in MTEP15 | A | East | METC | 2810 | 2015-12-28 | METC_13_038 | 4941 | 2015-12-23 | LNrb | 2018-12-31 | Delhi | Canal Jct | 1 | 138 |  | 303 MVA | Rebuild 7.2 miles of 4/0 ACSR and 336.4 ACSR to 954 ACSR on new 138 kV structures. | MI | 7.2 |  | M2a_Pre-Project Approval | 7500000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 2810 | 2015-12-28 | METC_13_038 | 8629 | 2015-12-23 | TEQ | 2018-12-31 | Delhi |  |  | 138 |  | 303 MVA | Terminal equipment upgrade at Delhi station. | MI |  |  | M2a_Pre-Project Approval |  |  |  | N | N | N | Y
A in MTEP15 | A | East | METC | 3926 | 2015-12-28 | METC_14_016 | 7488 | 2016-06-07 | TEQ | 2017-06-01 | Dort | Pasadena | 1 | 138 |  |  | Replace/reset relay equipment and replace trainers in the Dort station | MI |  |  | M3_Long Lead Materials | 225000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 4506 | 2015-12-28 | METC_14_018 | 8632 | 2016-06-07 | LNrb | 2018-12-31 | Four Mile | Wealthy Street | 1 | 138 |  | 304 MVA | Rebuild 0.96 miles of 266.8 ACSR + 3/0 Cu, 6.75 miles of 2-3/0 Cu, and 0.49 miles of 795 ACSR conductor utilizing 954 ACSR on new 138 kV structures. Install OPGW along the entire length of the circuit. | MI | 7.71 |  | M3_Long Lead Materials | 8200000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 4506 | 2015-12-28 | METC_14_018 | 8634 | 2016-06-07 | TEQ | 2018-12-31 | Wealthy Street |  |  | 138 |  |  | Station equipment upgrade at Wealthy Street. | MI |  |  | M3_Long Lead Materials | 130000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 4506 | 2015-12-28 | METC_14_018 | 8633 | 2016-06-07 | TEQ | 2018-12-31 | Four Mile |  |  | 138 |  |  | Station equipment upgrade at Four Mile. | MI |  |  | M3_Long Lead Materials | 270000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 4508 | 2015-12-28 | METC_14_038 | 8636 | 2016-06-07 | LNup | 2018-06-01 | Broadmoor | Plaster Creek | 1 | 138 |  | 287 MVA | Remediate the sag on the 795 ACSR from the Broadmoor - Plaster Creek 138 kV circuit to the conductor limit. | MI | 1.1 |  | M3_Long Lead Materials | 190000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 4509 | 2015-12-28 | METC_13_043 | 8637 | 2015-12-23 | LNup | 2017-12-31 | Argenta | Battle Creek | 1 | 345 |  | 1239 MVA | Remediate sag limit to SEMER 2350 Amps. | MI | 27.9 | 0 | M2a_Pre-Project Approval | 2500000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 4509 | 2015-12-28 | METC_13_043 | 8638 | 2015-12-23 | TEQ | 2017-12-31 | Battle Creek |  |  | 345 |  |  | Upgrade terminal equipment at Battle Creek. | MI |  |  | M2a_Pre-Project Approval | 68000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 4524 | 2016-01-04 | METC_14_031 | 8665 | 2016-06-07 | LNup | 2017-12-31 | Emmet | Livingston | 1 | 138 |  |  | Remediate sag on the Emmet - Livingston 138 kV line to bring its rating up to the conductor limit (208 MVA). | MI |  |  | M3_Long Lead Materials | 182000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8066 | 2015-12-28 | METC_14_022 | 20374 | 2016-06-07 | LNrb | 2018-06-01 | Amber | Donaldson Creek | 1 | 138 |  | 199 | Rebuild approx. 19.8 miles of 336 ACSR conductor utilizing 954 ACSR and OPGW on 138kV future double circuit structures. | MI | 19.8 | 0 | M3_Long Lead Materials | 23000000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8067 | 2015-12-28 | METC_14_019 | 20380 | 2016-06-07 | CB | 2017-06-01 | Beals Road |  |  | 138 |  | 430 MVA | Replace the limiting equipment on the Beals Road 138 kV bus tie at positions 500, 505, and 506. | MI | 0 | 0 | M3_Long Lead Materials | 400000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8070 | 2015-12-28 | METC_14_017 | 20388 | 2016-06-07 | TEQ | 2017-06-01 | North Belding | Vergennes | 1 | 138 |  |  | Replace limiting terminal equipment at North Belding. | MI |  |  | M3_Long Lead Materials | 120000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8072 | 2015-12-28 | METC_14_047 | 20394 | 2015-12-23 | LNrb | 2019-12-31 | Riggsville | Port Calcite | 1 | 138 |  |  | Rebuild 45 miles of 336.4 ACSR strung on 138 kV single circuit wood poles installed in 1960. | MI | 45 |  | M2a_Pre-Project Approval | 62048000 | Engineering Preliminary |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8072 | 2015-12-28 | METC_14_047 | 20396 | 2015-12-23 | LNrb | 2019-12-31 | Port Calcite | Rockport | 1 | 138 |  |  | Rebuild 24 miles of 266.8 ACSR strung on 138 kV single circuit wood poles installed in 1958. | MI | 24 |  | M2a_Pre-Project Approval | 34457000 | Engineering Preliminary |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8077 | 2016-04-07 | METC_14_039 | 20418 | 2016-06-07 | LNrb | 2018-12-31 | Vestaburg | Alma | 1 | 138 |  |  | Rebuild the Vestaburg - Alma 138 kV line (approx. 16.7 miles) with new single circuit steel poles using 954 ACSR conductor. Install OPGW along the entire length of the circuit. | MI | 16.7 |  | M3_Long Lead Materials | 18200000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8078 | 2015-12-28 | METC_14_025 | 20401 | 2015-12-23 | CAP | 2017-06-01 | Donaldson Creek |  |  | 138 |  |  | 33.3 MVAR Capacitor | MI |  |  | M2a_Pre-Project Approval | 1200000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8080 | 2015-12-28 | METC_14_027 | 20404 | 2016-06-07 | CAP | 2017-06-01 | Coldwater |  |  | 138 |  |  | Install a 3 x 18 MVAR capacitor and associated station equipment at the 138 kV Coldwater Substation. | MI |  |  | M3_Long Lead Materials | 3900000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8090 | 2015-12-28 | METC_14_035 | 20416 | 2016-06-07 | LNup | 2018-06-01 | Cornell | Blue Water Jct. | 1 | 138 |  |  | Remediate the sag limit to at least 760 A. | MI |  |  | M3_Long Lead Materials | 320000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8091 | 2016-03-22 | METC_14_030 | 20417 | 2016-03-22 | LNup | 2018-06-01 | Donaldson Creek | White Lake | 1 | 138 |  |  | Remediate sag limit. | MI |  |  | M2a_Pre-Project Approval | 360000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8096 | 2015-12-28 | METC_14_036 | 20421 | 2016-06-07 | LNup | 2017-12-31 | Roosevelt | Gaines | 1 | 345 |  |  | Remediate sag limit. | MI |  |  | M3_Long Lead Materials | 380000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8109 | 2015-12-28 | METC_14_032 | 20446 | 2016-06-07 | LNup | 2017-06-01 | Gaylord | Livingston | 1 | 138 |  |  | Remediate the sag limit on the Gaylord - Livingston 138 kV line. | MI |  |  | M3_Long Lead Materials | 75000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8118 | 2015-12-28 | METC_14_040 | 20466 | 2015-12-23 | TEQ | 2018-12-31 | Beecher |  |  | 138 |  |  | Replace overloaded terminal equipment at Beecher. | MI |  |  | M2a_Pre-Project Approval | 350000 | Planning |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8118 | 2015-12-28 | METC_14_040 | 20801 | 2015-12-23 | LNrc | 2018-12-31 | Beecher | Whiting | 1 | 138 |  |  | Relocate the Beecher-Whiting 138 kV line to the open side of the new structures. | MI |  |  | M2a_Pre-Project Approval | 4000000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8118 | 2015-12-28 | METC_14_040 | 20800 | 2015-12-23 | RLY | 2018-12-31 | Morocco |  |  | 138 |  |  | Upgrade relays at Morocco station. | MI |  |  | M2a_Pre-Project Approval | 250000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8118 | 2015-12-28 | METC_14_040 | 20468 | 2015-12-23 | LNrb | 2018-12-31 | Beecher | Samaria | 1 | 138 |  |  | Rebuild the 636 ACSR portion of the Beecher to Samaria 138 kV circuit utilizing 954 ACSR on 138 kV double circuit steel poles. | MI |  |  | M2a_Pre-Project Approval | 21000000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8119 | 2016-08-30 |  | 20470 | 2015-12-28 | LNup | 2017-12-31 | METC Pole Top Switches Additions-Replacement Program - 2017 |  |  | 138 |  |  | Install or replace an existing a new 138 kV, 2-way, full-load-break pole top switch at various tap points across the METC system. | MI |  |  | M2a_Pre-Project Approval | 3600000 |  |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8121 | 2015-12-28 | METC_14_037 | 20472 | 2016-06-07 | LNup | 2018-12-31 | Hackett Jct. | Laundra Jct. | 1 | 138 |  |  | Remediate the sag limit on the Hackett Jct. to Laundra Jct. section of the Bullock to Saginaw River 138 kV circuit. | MI |  |  | M3_Long Lead Materials | 90000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8122 | 2016-08-30 |  | 20474 | 2015-12-28 | LNup | 2018-12-31 | METC Pole Top Switches Additions-Replacement Program |  |  | 138 |  |  | Install or replace an existing a new 138 kV, 2-way, full-load-break pole top switch at various tap points across the METC system. | MI |  |  | M2a_Pre-Project Approval | 3600000 |  |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8124 | 2015-12-28 | METC_14_046 | 20476 | 2016-06-07 | LNrb | 2018-12-31 | Argenta | Morrow | 1 | 138 |  |  | Rebuild approximately 10 miles of existing 138 kV steel lattice towers with wood cross arms to double circuit capable 230 kV construction steel monopoles and string one side with 954 ACSR. | MI | 10.5 |  | M3_Long Lead Materials | 13900000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8126 | 2016-07-14 | METC_15_003 | 20477 | 2016-07-14 | IND | 2016-08-15 | Kenowa |  |  | 345 |  |  | Replace reactor 28R | MI |  |  | Under Construction | 3500000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8127 | 2016-08-30 | METC_14_024 | 20484 | 2015-12-23 | CB | 2017-12-31 | Ludington |  |  | 345 |  |  | Replace Ludington 345 kV circuit breakers 22H9, 24H9, 25H9 and 22F7, 24F7, 25F7 with 345 kV live tank circuit breakers containing 400 OHM pre-insertion resistors. | MI |  |  | M2a_Pre-Project Approval | 8640000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8144 | 2016-03-22 | METC_14_029 | 20521 | 2016-03-22 | TX | 2018-05-31 | Meyer (formerly “Hayes Street”) |  |  | 345 | 138 |  | Install a 345/138 kV transformer at the new Meyer substation. | MI |  |  | M3_Long Lead Materials | 4500000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8144 | 2016-03-22 | METC_14_029 | 20531 | 2016-03-22 | SUB | 2018-05-31 | Tallmadge |  |  | 345 |  |  | Replace 345 kV terminal equipment at Talmadge substation | MI |  |  | M2a_Pre-Project Approval | 140000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8144 | 2016-03-22 | METC_14_029 | 20529 | 2016-03-22 | SUB | 2018-05-31 | Meyer (formerly “Hayes Street”) |  |  | 345 | 138 |  | Construct the Meyer substation and install all 345 and 138 kV terminal equipment to accommodate the new transformer and looping in the Ludington - Tallmadge #2 345 kV, Argenta-Kenowa 345 kV, and Cobb-Tallmadge #1 138 kV circuits. | MI |  |  | M2a_Pre-Project Approval | 20200000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8144 | 2016-03-22 | METC_14_029 | 20528 | 2016-03-22 | LN | 2018-05-31 | Meyer (formerly “Hayes Street”) | Cobb | 1 | 138 |  |  | Construct approx. 0.25 miles of new 138 kV, double circuit structures, and loop the Cobb-Tallmadge #1 138 kV line into Meyer utilizing 954 ACSR conductor. | MI |  | 0.1 | M2a_Pre-Project Approval | 960000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8144 | 2016-03-22 | METC_14_029 | 20527 | 2016-03-22 | LN | 2018-05-31 | Meyer (formerly “Hayes Street”) | Tallmadge | 2 | 138 |  |  | Construct approx. 0.25 miles of new 138 kV, double circuit structures, and loop the Cobb-Tallmadge #1 138 kV line into Meyer utilizing 954 ACSR conductor. | MI |  | 0.1 | M2a_Pre-Project Approval | 900000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8144 | 2016-03-22 | METC_14_029 | 20526 | 2016-03-22 | LN | 2018-05-31 | Meyer (formerly “Hayes Street”) | Kenowa | 1 | 345 |  |  | Construct approx. 0.1 miles of new 345 kV, double circuit structures, and loop the Kenowa - Argenta 345 kV line into Meyer utilizing 2-954 ACSR conductor. | MI |  | 0.1 | M2a_Pre-Project Approval | 1300000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8144 | 2016-03-22 | METC_14_029 | 20525 | 2016-03-22 | LN | 2018-05-31 | Meyer (formerly “Hayes Street”) | Argenta | 1 | 345 |  |  | Construct approx. 0.1 miles of new 345 kV, double circuit structures, and loop the Kenowa - Argenta 345 kV line into Meyer utilizing 2-954 ACSR conductor. Also remediate the sag limit on the Meyer - Argenta 345 kV circuit to a minimum of 1524 MVA. | MI |  | 0.1 | M2a_Pre-Project Approval | 1300000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8144 | 2016-03-22 | METC_14_029 | 20524 | 2016-03-22 | LN | 2018-05-31 | Meyer (formerly “Hayes Street”) | Ludington | 1 | 345 |  |  | Construct approx. 0.1 miles of new 345 kV, double circuit structures, and loop the Ludington-Tallmadge #2 345 kV line into Meyer utilizing 2-954 ACSR conductor. | MI |  | 0.1 | M2a_Pre-Project Approval | 1200000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8144 | 2016-03-22 | METC_14_029 | 20523 | 2016-03-22 | LN | 2018-05-31 | Meyer (formerly “Hayes Street”) | Tallmadge | 1 | 345 |  |  | Construct approx. 0.1 miles of new 345 kV, double circuit structures, and loop the Ludington-Tallmadge #2 345 kV line into Meyer utilizing 2-954 ACSR conductor. Also remediate the sag limit on the Meyer -Tallmadge #1 345 kV circuit to a minimum of 2007 MVA | MI |  | 0.1 | M2a_Pre-Project Approval | 1200000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8170 | 2015-12-28 | METC_13_033 | 20575 | 2016-03-22 | RLY | 2016-12-31 | Leoni | Page Ave | 1 | 138 |  |  | Install the second relay component on the Leoni to Page Ave. 138 kV circuit at Leoni end so that, for faults on the Page Ave. end, the Leoni breaker will trip and clear the fault with one relay component failure. | MI |  |  | M3_Long Lead Materials | 75000 |  |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8171 | 2016-08-16 | METC_13_016 | 20576 | 2016-08-16 | RLY | 2017-06-01 | Croton | Felch Road | 1 | 138 |  |  | 1. Install dual pilot relay protection system on Croton to Felch Road 138 kV circuit so that 3 phase to ground faults on the circuit will be cleared within 7 cycles. 2. Remove the sparing scheme of using Croton 138 kV breaker 500 to spare breaker 388 for Croton to Felch Road 138 kV circuit. 3. Remove Felch Road 138 kV BK 188 Bypassing | MI |  |  | M3_Long Lead Materials | 540000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8460 | 2015-12-28 | METC_14_045 | 20675 | 2016-06-07 | LNup | 2017-12-31 | Hemphill | Sabine | 1 | 138 |  | 180 | Remediate the sag limit on the Sabine - Hemphill 138 kV line to increase its summer emergency rating to the 336 ACSR conductor rating of 208 MVA (871 Amps). | MI |  |  | M3_Long Lead Materials | 140000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8461 | 2015-12-28 | METC-14-043 | 20674 | 2016-06-07 | LNup | 2017-06-01 | Cobb | Sternberg | 1 | 138 |  |  | Remediate the sag limit on the Cobb-Sternberg 138 kV line to bring its rating up to 174 MVA (730 Amp). | MI |  |  | M3_Long Lead Materials | 480000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 8540 | 2015-12-28 | METC_14_044 | 20680 | 2016-06-07 | LNup | 2017-12-31 | Claremont | Layton | 1 | 138 |  |  | Remediate the sag limit on the Claremont-Layton section of the Claremont - Cornell #1 138 kV line to a rating 209 MVA (874 Amps). | MI | 17.2 |  | M3_Long Lead Materials | 520000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 9361 | 2016-03-23 | METC_15_002 | 20877 | 2016-08-15 | SwSta | 2016-10-01 | Green 138 kV |  |  | 138 |  |  | Install 4-138 kV breakers with associated disconnects laid out in a ring bus configuration. | MI |  |  | Under Construction | 4483000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 9361 | 2016-03-23 | METC_15_002 | 20879 | 2016-08-15 | LN | 2016-10-01 | College | Green | 1 | 138 |  |  | New line created by looping the Delhi-College 138 kV circuit into Green. METC will construct approx. 0.1 miles of new double circuit structures to loop the existing line into Green | MI |  | 0.1 | Under Construction | 412000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | METC | 9361 | 2016-03-23 | METC_15_002 | 20878 | 2016-08-15 | LN | 2016-10-01 | Delhi | Green | 1 | 138 |  |  | New line created by looping the Delhi-College 138 kV circuit into Green. METC will construct approx. 0.1 miles of new double circuit structures to loop the existing line into Green | MI |  | 0.1 | Under Construction | 412000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | East | NIPS | 8500 | 2015-12-28 |  | 20678 | 2016-03-15 | BUS | 2018-12-31 | Lagrange | Lagrange |  | 138 | 138 |  | Make necessary upgrades at Lagrange 138kV Substation to create ring bus. | IN |  |  | Planned | 2715000 | Planning |  | N | N | N | Y
A in MTEP15 | A | East | NIPS | 9405 | 2015-12-28 |  | 20896 | 2016-04-28 | SUBmisc | 2018-05-01 | Kosciusko |  |  | 138 |  |  | Replace Line switch and substation Conductor | IN |  |  | Planned | 147845 | Planning |  | N | N | N | Y
A in MTEP15 | A | East | NIPS | 9406 | 2015-12-28 |  | 20897 | 2016-03-15 | SUBmisc | 2018-05-01 | Reynolds |  |  | 138 |  |  | Replace (2) 138kV Switches at Reynolds | IN |  |  | Planned | 112665 | Planning |  | N | N | N | Y
A in MTEP15 | A | East | NIPS | 9461 | 2016-01-05 |  | 20915 | 2015-11-25 | RLY | 2018-12-31 | 17HIPLE |  |  | 138 |  |  | Add Redundant 138kV Bus Differential Relay | IN |  |  | Planned | 50000 | Planning |  | N | N | N | Y
A in MTEP15 | A | East | WPSC | 3567 | 2015-12-28 | HY-WN | 6651 | 2015-09-15 | LNrb | 2017-12-31 | Hersey | Osceola Jct | 1 | 69 |  | 143.4MVA | Rebuild Overloaded line (Peak case) | MI | 4.02 |  | Planned | 2100000 | Budgetary |  | N | N | N | Y
A in MTEP15 | A | East | WPSC | 3567 | 2015-12-28 | HY-WN | 6654 | 2015-09-15 | LNrb | 2017-12-31 | Martiny | Weidman | 1 | 69 |  | 143.4MVA | Rebuild Overloaded line (Peak case) | MI | 8.37 |  | Planned | 4200000 | Budgetary |  | N | N | N | Y
A in MTEP15 | A | East | WPSC | 3567 | 2015-12-28 | HY-WN | 6653 | 2015-09-15 | LNrb | 2017-12-31 | Barryton | Martiny | 1 | 69 |  | 143.4MVA | Rebuild Overloaded line (Peak case) | MI | 1 |  | Planned | 500000 | Budgetary |  | N | N | N | Y
A in MTEP15 | A | East | WPSC | 3567 | 2015-12-28 | HY-WN | 6652 | 2015-09-15 | LNrb | 2017-12-31 | Osceola Jct | Barryton | 1 | 69 |  | 143.4MVA | Rebuild Overloaded line (Peak case) | MI | 9.69 |  | Planned | 4700000 | Budgetary |  | N | N | N | Y
A in MTEP15 | A | East | WPSC | 4086 | 2015-12-28 | FNX-SV | 7739 | 2015-09-15 | LNrb | 2016-12-31 | Fountain Junction | Scottville | 1 | 69 |  | 143.4MVA | Rebuild Overloaded line (Peak case) | MI | 9.15 |  | Planned | 4650000 | Planning |  | N | N | N | Y
A in MTEP15 | A | East | WPSC | 4384 | 2015-12-28 | Airport Xmsn | 8399 | 2014-09-25 | SUB | 2017-12-31 | Airport | Substation Upgrade |  | 138 | 69 |  | 138kV Breaker Replacement and Protective Equipment Upgrade | MI |  |  | Planned | 4100000 | Budgetary |  | N | N | N | Y
A in MTEP15 | A | East | WPSC | 4384 | 2015-12-28 | Airport Xmsn | 21503 | 2015-10-28 | SUB | 2018-12-31 | Airport |  |  | 138 |  |  | Landscaping costs | MI |  |  | Planned | 50000 | Budgetary |  | N | N | N | Y
A in MTEP15 | A | East | WPSC | 4384 | 2015-12-28 | Airport Xmsn | 21502 | 2015-10-28 | SUB | 2017-01-01 | Airport |  |  | 138 |  |  | Airport Substation zoning costs | MI |  |  | Planned | 40000 | Budgetary |  | N | N | N | Y
A in MTEP15 | A | East | WPSC | 7660 | 2015-12-28 | Advance Transmission | 20047 | 2014-11-04 | BUS | 2016-12-31 | Advance Transmission |  |  | 69 |  |  | New 69KV switching station | MI |  |  | Planned | 2250000 | Planning |  | N | N | N | NT
A in MTEP15 | A | East | WPSC | 7661 | 2015-12-28 | Vestaburg Transmission | 20048 | 2016-09-15 | BUS | 2017-12-31 | Vestaburg Transmission |  |  | 69 |  |  | Switch and bus upgrades, including a sparing scheme addition | MI |  |  | Planned | 170000 | Planning |  | N | N | N | NT
A in MTEP15 | A | East | WPSC | 7662 | 2015-12-28 | Atlanta Transmission | 20049 | 2016-09-15 | BUS | 2017-12-31 | Atlanta Transmission |  |  | 69 |  |  | Replace equipment | MI |  |  | Planned | 250000 | Budgetary |  | N | N | N | NT
A in MTEP15 | A | East | WPSC | 7663 | 2015-12-28 | Gaylord OCB | 20050 | 2016-09-15 | BUS | 2017-12-31 | Gaylord OCB |  |  | 69 |  |  | Replace breaker and upgrade control system | MI |  |  | Planned | 300000 | Planning |  | N | N | N | NT
A in MTEP15 | A | East | WPSC | 8220 | 2016-08-30 | CV-WC Line Raise | 20608 | 2014-10-30 | LNup | 2016-05-31 | Casnovia | White Cloud |  | 69 |  |  | 1.93 miles of line has been requested by GLE to be raised to accommodate distribution underbuild. This project will rebuild a total of 2.5 miles to gradually tie the new taller poles into the existing line. The existing conductor is planned to be used for this project. | MI | 2.5 |  | Planned | 800000 | Budgetary |  | N | N | N | NT
A in MTEP15 | A | East | WPSC | 8221 | 2015-12-28 | Airport Line Mods | 20609 | 2014-10-30 | LN | 2017-12-31 | Airport 138kV & 69kV |  |  | 138 | 69 |  | This project will construct the line modifications required to route lines into the new Airport station. | MI |  |  | Planned | 1000000 | Budgetary |  | N | N | N | NT
A in MTEP15 | A | East | WPSC | 8380 | 2015-12-28 | Advance Line Mods | 20653 | 2014-11-04 | LN | 2016-12-31 | Advance Transmission |  |  | 69 |  |  | Line modifications to support the Advance Transmission station project | MI |  |  | Planned | 1250000 | Budgetary |  | N | N | N | NT
A in MTEP15 | A | South | AECC | 8320 | 2015-12-28 |  | 20638 | 2016-05-26 | SwSta | 2017-10-01 | EAI El Dorado - Monticello East 115 kV line |  |  | 115 |  |  | Switching station needed to tap Entergy line | AR |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP15 | A | South | AECC | 8320 | 2015-12-28 |  | 20640 | 2016-05-26 | SUB | 2017-10-01 | 115 kV radial tap |  |  | 115 | 13.2 |  | Hermitage 115/13.2 kV substation | AR |  |  | Planned |  |  |  | N | N | N | NT
A in MTEP15 | A | South | AECC | 8320 | 2015-12-28 |  | 20639 | 2016-05-26 | LN | 2017-10-01 | EAI El Dorado - Monticello East 115 kV line | Hermtage 115/13.2 kV substation |  | 115 |  |  | 1.6 miles of 115 kV line | AR |  |  | Planned | 2060000 |  |  | N | N | N | Y
A in MTEP15 | A | South | AECC | 8341 | 2015-12-28 |  | 20645 | 2015-07-09 | TX | 2015-08-01 | Corning North 115kV |  |  | 115 |  |  | Installing a second transformer at Corning North. Due to a possible line conversion in the area by EAI in the very near future (2020 or sooner), the second transformer have a 161/115kV dual wound high side. | AR |  |  | Planned | 1500000 | Scoping |  | N | N | N | Y
A in MTEP15 | A | South | AECC | 8342 | 2015-12-28 |  | 20646 | 2015-07-09 | LN | 2015-08-01 | Pocahontas East | Industrial Park |  | 161 |  |  | 3.5 mile radial tap from the current Pocahontas East substation to the new Industrial Park 161/24.9kV substation. | AR |  | 3.5 | Planned | 2500000 | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | South | AECC | 8342 | 2015-12-28 |  | 20648 | 2015-07-09 | RLY | 2015-08-01 | Pocahontas East |  |  | 161 |  |  | AECC is installing an in-line breaker on the East side of the Pocahontas East substation. This breaker is intended to provide protection to Entergy's Jim Hill to Water Valley SPA 161kV Transmission Line. | AR |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP15 | A | South | AECC | 8342 | 2015-12-28 |  | 20647 | 2015-07-09 | Dist | 2015-08-01 | Industrial Park |  |  | 161 |  |  | New 30MVA 161/24.9kV distribution substation | AR |  |  | Planned | 2250000 | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | South | AECC | 8400 | 2015-12-28 |  | 20658 | 2016-08-15 | SwSta | 2017-04-01 | Tap EAI El Dorado to Monticello 115kV line |  |  | 115 |  |  | 3 position ring bus | AR |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP15 | A | South | AECC | 8400 | 2015-12-28 |  | 20660 | 2016-08-15 | SUB | 2017-04-01 | 115 kV transmission line |  |  | 115 | 69 |  | 115/69 kV substation | AR |  |  | Planned |  |  |  | N | N | N | NT
A in MTEP15 | A | South | AECC | 8400 | 2015-12-28 |  | 20659 | 2016-08-15 | LN | 2017-04-01 | Tap EAI El Dorado to Monticello 115kV line |  |  | 115 |  |  | 13 mile 115kV line | AR |  | 13 | Planned | 6400000 |  |  | N | N | N | Y
A in MTEP15 | A | South | AECC | 8402 | 2016-09-20 |  | 20661 | 2016-09-20 | LN | 2019-12-01 | Camden South |  |  | 115 |  |  | 7 mile 115kV transmission line from existing Camden South delivery point/substation to the proposed Camden West substation. | AR |  | 7 | Planned | 3950000 |  |  | N | N | N | Y
A in MTEP15 | A | South | AECC | 8402 | 2016-09-20 |  | 20662 | 2016-09-20 | SUB | 2019-12-01 | 115kV line |  |  | 115 | 13.2 |  | 115/13.2 kV substation | AR |  |  | Planned |  |  |  | N | N | N | NT
A in MTEP15 | A | South | AECC | 8420 | 2016-02-22 |  | 20664 | 2016-02-22 | LN | 2017-12-01 | Pocahontas North | Ingram |  | 161 |  |  | 7 mile radial 161kV transmission line from Entergy's Pocahontas North station to the new Clay County Ingram substation | AR |  | 7 | Planned | 3611500 | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | South | AECC | 8420 | 2016-02-22 |  | 20665 | 2016-02-22 | Dist | 2017-12-01 | Ingram |  |  | 161 | 24.9 |  | new 161/25kV substation with initial projected load of 12,000kW. Uncertain at the moment of the transformer size. Will likely be a 12/16/20 MVA. | AR |  |  | Planned | 2250000 | Engineering Preliminary |  | N | N | N | NT
A in MTEP15 | A | South | AECC | 8480 | 2015-12-28 |  | 20676 | 2015-07-09 | LN | 2017-01-01 | Marmaduke 161 kV | Gainesville | 1 | 161 |  | 57.7 MVA | 10-mile, 336 ACSR 26/7 161 kV transmission line. | AR |  |  | Planned | 2000000 | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | South | AECC | 8480 | 2015-12-28 |  | 20677 | 2015-07-09 | Dist | 2017-01-01 | Gainesville |  |  | 161 | 13.2 | 12/16/20 MVA | 161/13.2 kV distribution substation | AR |  |  | Planned | 5000000 | Planning Preliminary |  | N | N | N | NT
A in MTEP15 | A | South | CLECO | 7988 | 2015-12-28 | 15-ELL-001 | 20260 | 2016-09-15 | SUB | 2018-06-01 | Bayou Vista 230 | Bayou Vista 138 kV | 1 | 230 | 138 | 500 MVA | CLECO will expand Bayou Vista substation to 230 kV and install 230-138 kV autotransformer | LA |  |  | Planned |  | Planning |  | N | N | N | Y
A in MTEP15 | A | South | CLECO | 8980 | 2015-12-28 |  | 20867 | 2015-07-10 | BUS | 2015-10-30 | West Fork |  |  | 230 |  |  | Replace the Existing 230 kV high side bus at West Fork with a 3 terminal Ring bus with Breakers. | LA |  |  | Under Construction | 2308708 | Budgetary |  | N | N | N | Y
A in MTEP15 | A | South | CLECO | 9042 | 2015-12-28 |  | 20864 | 2015-07-10 | CB | 2015-10-01 | Coughlin |  |  | 138 |  |  | Replace Breakers 8000, 8128, 8006, 8115, 8009 due to available fault current exceeding the short circuit rating of the existing breakers. | LA |  |  | Under Construction | 725008 | Budgetary |  | N | N | N | Y
A in MTEP15 | A | South | CLECO | 9340 | 2015-12-28 |  | 20873 | 2015-07-17 | SUB | 2016-12-01 | Longville |  |  | 138 |  |  | Build a new 138 kV substation Longville tapped into the Deridder to Nelson 138 kV line. 18.3 miles from Deridder & 24.3 miles from Nelson. | LA |  |  | Planned | 4400000 | Budgetary |  | N | N | N | Y
A in MTEP15 | A | South | CLECO | 9421 | 2015-12-28 |  | 20898 | 2015-07-28 | SUB | 2017-06-01 | Plaisance | Veazie | 1 | 138 |  |  | New substation tapped into the Plaisance to Veazie 138 kV line | LA |  |  | Planned | 4360000 | Budgetary |  | N | N | N | Y
A in MTEP15 | A | South | CLECO | 9421 | 2015-12-28 |  | 20900 | 2015-07-28 | LN | 2017-06-01 | Plaisance | Veazie | 1 | 138 |  |  | Build 138 kV line from existing transmission line to customers location 0.7 miles. | LA |  | 0.7 | Planned | 1040000 | Budgetary |  | N | N | N | Y
A in MTEP15 | A | South | CLECO, Entergy-LA | 7988 | 2015-12-28 | 15-ELL-001 | 20258 | 2016-09-15 | LN | 2018-06-01 | Terrebonne 230 kV | Bayou Vista 230 kV | 1 | 230 |  | 640 | Construct approximately 30.33 miles from Terrebonne to Bayou Vista 230 kV line using conductor ACSS 954 cardinal rated at 640 MVA. | LA |  | 30.33 | Planned | 75900000 | Planning |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-AR | 4666 | 2015-12-28 | 12-EAI-014 | 8847 | 2016-09-14 | LNrc | 2019-12-01 | Mabelvale 115 kV Substation | Bryant 115 kV Substation | 1 | 115 |  | 390 MVA | Reconductor Line | AR | 5 |  | Planned | 6371120 | Planning |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-AR | 4666 | 2015-12-28 | 12-EAI-014 | 21439 | 2016-09-14 | LNrb | 2019-12-01 | Bryant | Bryant South | 1 | 115 |  |  | 115 kV line | AR |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-AR | 4669 | 2016-02-16 | 11-EAI-015 | 8850 | 2016-06-03 | LNcnv | 2019-05-01 | Jim Hill 161 kV substation | Datto 161 kV Substation | 1 | 161 |  | 363 MVA | rebuild line and convert from 115kV to 161kV operation | AR | 39.3 |  | Planned | 43729766 | Planning |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-AR | 4669 | 2016-02-16 | 11-EAI-015 | 8851 | 2016-06-03 | CB | 2019-05-01 | Datto 161 kV Substation |  | 1 | 161 |  | 363MVA | Install breakers at Datto | AR |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-AR | 7925 | 2015-12-28 | 14-EAI-026 | 20180 | 2016-09-15 | LN | 2016-10-15 | Black Rock 69kV substation (AECC) | Imboden 69kV substation | 1 | 69 |  |  | Construct 0.4 mile 69kV transmission line from Black Rock 69kV substation to Imboden 69 kV substation. | AR |  | 0.4 | Under Construction | 3133719 | Engineering Preliminary |  | N | N | N | NT
A in MTEP15 | A | South | Entergy-AR | 7925 | 2015-12-28 | 14-EAI-026 | 20181 | 2016-09-15 | CB | 2016-10-15 | Black Rock 69kV Substation (AECC) |  |  | 69 |  |  | new 69kV circuit breaker to be added at Black Rock 69kV substation. | AR |  |  | Under Construction |  |  |  | N | N | N | NT
A in MTEP15 | A | South | Entergy-AR | 7928 | 2015-12-28 | 15-EAI-002 | 20198 | 2016-09-15 | SUB | 2017-11-15 | New EHV 500kV substation |  |  | 500 | 161 |  | Build a 500/161kV substation where the ISES - Dell 500kV line crosses the Jonesboro-Hergett and Hergett-Trumann West 161kV lines. Cut the 500kV line and the two 161kV lines into the new station. 500kV bus needs to be a 4 breaker ring bus and the terminals need to be layed out such that the two 500kV lines do not share a common breaker. | AR |  |  | Under Construction | 74965393 |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-AR | 7928 | 2015-12-28 | 15-EAI-002 | 20208 | 2016-09-15 | LNrb | 2017-11-15 | Hergett 161kV substation | Trumann West 161kV substation | 1 | 161 |  | 363MVA | Rebuild the Hergett - new EHV 161kV substation - Trumann West 161kV line to a minimum rating of 1300A or 363MVA. | AR | 8.3 |  | Under Construction |  |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-AR | 7928 | 2015-12-28 | 15-EAI-002 | 20207 | 2016-09-15 | LNrb | 2017-11-15 | Jonesboro 161KV substation | Jonesboro (SPA) 161kV substation | 1 | 161 |  | 544MVA | rebuild the Jonesboro - Jonesboro (SPA) 161 kV line to a minimum rating of 1950 A or 544MVA. | AR | 0.9 |  | Under Construction |  |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-AR | 7928 | 2015-12-28 | 15-EAI-002 | 20205 | 2016-09-15 | TEQ | 2017-11-15 | New EHV 161kV substation | Jonesboro 161kV substation | 1 | 161 |  | 363MVA | Upgrade terminal equipment on the Hergett - new EHV station - Jonesboro 161 kV line to achieve a rminimum rating of 1300A or 363MVA. | AR |  |  | Under Construction |  |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-AR | 7928 | 2015-12-28 | 15-EAI-002 | 20203 | 2016-09-15 | TEQ | 2017-11-15 | Hergett 161kV substation | New EHV 161kv substation | 1 | 161 |  | 363MVA | replace terminal equipment on teh Hergett - new EHV station - Jonesboro 161kV line to achieve a minimum rating of 1300 A or 363MVA. | AR |  |  | Under Construction |  |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-AR | 7928 | 2015-12-28 | 15-EAI-002 | 20200 | 2016-09-15 | TX | 2017-11-15 | New EHV 500kV substation | New EHV 161kV substation |  | 500 | 161 | 800 | Install an 800MVA 500/161kV autotransformer (10%Z on 480MVA base.) | AR |  |  | Under Construction |  |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-AR | 7928 | 2015-12-28 | 15-EAI-002 | 20199 | 2016-09-15 | SUB | 2017-11-15 | New EHV 161kV substation |  |  | 500 | 161 |  | Build a 500/161 kV station where the ISES -Dell 500kV line crosses the Jonesboro-Hergett and Hergett - Trumann West 161kV lines. Cut the 500kV line and the two 161kV linesinto the new station. Install an 800MVA 500/161kV auto transformer. | AR |  |  | Under Construction |  |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-AR | 8680 | 2015-12-28 | 15-EAI-008 | 20729 | 2016-09-15 | TAP | 2016-09-20 | Conway Middle Road |  |  | 161 |  |  | New 161 kV substation | AR |  |  | Under Construction | 786000 | Planning |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-AR | 8681 | 2015-12-28 | 15-EAI-009 | 20730 | 2016-09-15 | SUB | 2016-11-01 | Jefferson Industrial |  |  | 115 |  |  | New 115 kV substation | AR |  |  | Under Construction | 5257000 | Facility Study |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-AR | 8860 | 2015-12-28 | 14-EAI-020-9 | 20764 | 2016-09-15 | CB | 2016-12-01 | Paragould |  |  | 115 |  |  | New circuit bkr | AR |  |  | Planned | 256005 | Engineering |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-LA | 4604 | 2015-12-28 | 14-EGL-016 | 8749 | 2016-09-15 | LNrc | 2017-02-24 | Port Hudson 69 kV substation | Zachary REA substation | 1 | 69 |  | 143 MVA | Reconductor Line | LA | 5.76 |  | Under Construction | 11202000 | Planning |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-LA | 4604 | 2015-12-28 | 14-EGL-016 | 8750 | 2016-09-15 | TEQ | 2017-02-24 | Port Hudson 69 kV substation | Zachary REA substation | 1 | 69 |  | 143 MVA | Upgrade terminal equipment | LA |  |  | Under Construction |  | Planning |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-LA | 4606 | 2015-12-28 | 14-EGL-004 | 8754 | 2016-09-15 | TX | 2019-03-01 | Fancy Point 500 kV substation | Fancy Point 230 kV substation | 2 | 500 | 230 | 1200 MVA | Add transformer | LA |  |  | Planned | 92000000 | Planning |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-LA | 4630 | 2015-12-28 | 11-EGL-018 | 8793 | 2016-09-15 | LNrc | 2017-06-01 | Francis 69 kV substation | Marydale 69 kV substation | 1 | 69 |  | 105 MVA | Reconductor Line | LA | 7.47 |  | Planned | 13283208 | Planning |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-LA | 7919 | 2015-12-28 | 15-EGL-002 | 20174 | 2016-09-15 | CAP | 2016-12-01 | Vincent 230 kV |  |  | 230 |  |  | "NERC TPL-001-4 Reliability Standards and Entergy's Planning Guidelines. Low voltages will occur at the Boudoin, Calcasieu, Pecan Grove, Vincent, Graywood, and Solac 230 kV substations during the single contingency (P1-2) breaker to breaker loss of either Carlyss to Boudoin, Boudoin to Calcasieu, or Calcasieu to Pecan Grove 230 kV line. This project will provide the needed voltage support in the area to mitigate the single contingency events." | LA |  |  | Planned | 1324421 | Planning |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-LA | 7923 | 2015-12-28 | 15-EGL-005 | 20178 | 2016-09-15 | LNrc | 2017-06-01 | Lake Charles Bulk 69 kV | Chlomal 69 kV | 1 | 69 |  | 117 MVA | "NERC TPL-001-4 Reliability Standards and Entergy's Planning Guidelines. The Lake Charles Bulk to Chlomal 69 kV line will exceed its thermal rating during the single contingency (P1-2) breaker to breaker loss of the Calcasieu to Pecan Grove 230 kV line or the Lake Charles Bulk to East Broad 69 kV line. This project will result in an increase in the thermal rating of the circuit by upgrading line conductor and station equipment at Lake Charles Bulk." | LA | 3.07 |  | Planned | 2905700 | Planning Preliminary |  | N | N | N | NT
A in MTEP15 | A | South | Entergy-LA | 7923 | 2015-12-28 | 15-EGL-005 | 20236 | 2016-09-15 | TEQ | 2017-06-01 | Lake Charles Bulk |  |  | 69 |  | 117 MVA | LC Bulk-Cholmal Upgrade 600 A switches to 1200 A and upgrade line conductor. | LA |  |  | Planned |  | Planning |  | N | N | N | NT
A in MTEP15 | A | South | Entergy-LA | 7948 | 2015-12-28 | 15-EGL-009 | 20202 | 2016-09-15 | LNrc | 2017-06-01 | 335346 Scott 69 | 335435 Carencro 69 | 1 | 69 |  | 143 MVA | "NERC TPL-001-4 Reliability Standards and Entergy's Planning Guidelines. The Scott to Carencro 69 kV line will exceed its thermal rating during the single contingency (P1-2) breaker to breaker loss of the Champagne to Sunset 69 kV line. This project will result in an increase in the thermal rating of the circuit by upgrading line conductor and relay settings at Carencro." | LA | 6.84 |  | Planned | 6822535 | Planning |  | N | N | N | NT
A in MTEP15 | A | South | Entergy-LA | 7988 | 2015-12-28 | 15-ELL-001 | 20262 | 2016-09-15 | SUB | 2018-06-01 | Terrebonne |  |  | 230 |  |  | Breakers and switches addition to accomodate new line | LA |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-LA | 8585 | 2015-12-28 | 15-EGL-016 | 20690 | 2016-09-15 | SwSta | 2018-03-18 | Rhodes 500kV Substation |  |  | 500 |  |  | Construction of a new 500 kV, 3000 A, three breaker ring bus switching station west of Nelson on the Nelson to Hartburg 500 kV line. | LA |  |  | Under Construction | 28070000 |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-LA | 8586 | 2015-12-28 | 15-EGL-017-01 | 20691 | 2016-09-15 | SUB | 2018-03-18 | TBD |  |  | 500 | 230 | 1200 MVA | Construct a new 500-230 kV substation west of the existing Carlyss 230 kV substation. This includes the installation of a new 500-230 kV, 1200 MVA autotransformer bank at the new 500-230 kV bulk station comprised of (3) single phase units. | LA |  |  | Under Construction | 31530000 |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-LA | 8587 | 2015-12-28 | 15-EGL-017-02 | 20692 | 2016-09-15 | LN | 2018-03-18 | Rhodes | TBD | 1 | 500 |  | 2598 MVA | Construct approximately 11.5 miles of new 500 kV transmission line from the new Rhodes 500 kV switching station to a new 500-230 kV bulk station west of the existing Carlyss 230 kV substation. | LA |  | 7 | Under Construction | 43000000 |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-LA | 8588 | 2015-12-28 | 15-EGL-017-03 | 20693 | 2016-09-15 | LN | 2018-03-18 | TBD | Carlyss | 1 | 230 |  | 1195 MVA | Construct approximately 1.5 miles of new 230 kV transmission line from the new 500-230 kV bulk substation west of Carlyss to the existing Carlyss 230 kV substation. | LA |  | 4 | Under Construction | 8690000 |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-LA | 8589 | 2015-12-28 | 15-EGL-018 | 20694 | 2016-03-30 | CB | 2018-03-18 | Carlyss |  |  | 230 |  |  | Expand the existing Carlyss 230 kV substation into a breaker and a half operating scheme. Replace the underrated 230 kV breakers with ones having sufficient short circuit interrupting due to the increase in fault currents. The breakers to be replaced are: 8775-IC 13145-CO 13150-CO 13155-CO 13480-CO 13500-CO 13580-CO | LA |  |  | Under Construction | 14050000 |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-LA | 8589 | 2015-12-28 | 15-EGL-018 | 20696 | 2016-03-30 | BUS | 2018-03-18 | Carlyss |  |  | 230 |  |  | Expand the existing Carlyss 230 kV substation into a breaker and a half operating scheme. Replace the underrated 230 kV breakers with ones having sufficient short circuit interrupting due to the increase in fault currents. The breakers to be replaced are: 8775-IC 13145-CO 13150-CO 13155-CO 13480-CO 13500-CO 13580-CO | LA |  |  | Under Construction |  |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-LA | 8590 | 2015-12-28 | 15-EGL-019 | 20695 | 2016-09-15 | LN | 2018-03-18 | Carlyss | Solac | 1 | 230 |  | 779 MVA | Construct approximately 12 miles of new 230 kV transmission line from Carlyss to the Solac 230 kV substation. The line will be designed and routed to accommodate a future cut-in into the Calcasieu substation. Add a 230 kV line bay terminal at Carlyss and the Solac 230 kV substation to facilitate the termination of the new line. | LA |  | 12 | Under Construction | 33160000 |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-LA | 9284 | 2015-12-28 | 15-ELL-006 | 20862 | 2016-03-30 | CAP | 2017-08-31 | Bayou Verret |  |  | 230 |  |  | Install two 40.7 MVAR 230 kV cap banks at Bayou Verret substation. | LA |  |  | Planned | 1684477 |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-LA | 9285 | 2015-12-28 | 15-ELL-005 | 20863 | 2016-07-05 | LNrb | 2019-06-01 | Waterford | Vacherie | 1 | 230 |  |  | Reconductor Waterford to Vacherie 230 kV line. | LA |  |  | Planned | 19732950 |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-MS | 7898 | 2015-12-28 | 15-EMI-001 | 20135 | 2016-06-29 | SUBmisc | 2016-12-31 | Greenville |  |  | 115 |  |  | Upgrade 600A switches to minimum 810A rating (conductor) | MS |  |  | Under Construction | 463871 | Planning |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-MS | 7901 | 2015-12-28 | 15-EMI-002 | 20137 | 2016-03-24 | RLY | 2016-12-01 | Natchez SES |  |  | 115 |  |  | upgrade relaying and CTs at Natchez on line 168 and 169 | MS |  |  | Planned | 796791 | Planning |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-MS | 7901 | 2015-12-28 | 15-EMI-002 | 20138 | 2016-03-24 | RLY | 2016-12-01 | Natchez |  |  | 115 |  |  | Upgrade relaying and CTs on line 168 and 169 | MS |  |  | Planned |  | Planning |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-TX | 4617 | 2015-12-28 | 13-ETI-013 | 8771 | 2016-09-15 | LNrc | 2017-05-01 | Egypt 138 kV Substatiion | Panorama 138 kV Substation | 1 | 138 |  | 287 MVA | Reconductor Line | TX | 1.16 |  | Under Construction | 3347942 |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-TX | 4617 | 2015-12-28 | 13-ETI-013 | 8772 | 2016-09-15 | TEQ | 2017-05-01 | Panorama 138 kV Substation |  |  | 138 |  | 287 MVA | Upgrade Terminal Equipment | TX |  |  | Under Construction |  |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-TX | 4653 | 2015-12-28 | 11-ETI-038 | 21600 | 2016-09-15 | IND | 2017-12-01 | Port Neches |  |  | 138 |  |  | Install reactor on Sabine Bay Line 516 | TX |  |  | Planned | 4358791 | Planning |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-TX | 7947 | 2015-12-28 | 11-ETI-002 | 21599 | 2016-09-15 | IND | 2017-12-01 | Sabine |  |  | 138 |  |  | Install Reactor at Sabine on the Port Neches bay | TX |  |  | Planned | 4363775 | Planning |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-TX | 8582 | 2015-12-28 | 15-ETI-007-01 | 20687 | 2016-03-30 | SVC | 2016-10-03 | Alden |  |  | 138 |  | +200/-100 MVAR | Add a 200 MVAR SVC at the existing Alden 138 kV substation. | TX |  |  | Under Construction | 31593000 |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-TX | 8583 | 2015-12-28 | 15-ETI-007-02 | 20688 | 2016-07-05 | CAP | 2016-10-03 | Oakridge |  |  | 138 |  | 25.1 | Add a 25.1 MVAR Capacitor bank to the Oakridge 138 kV bus. | TX |  |  | Planned | 912000 |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-TX | 9241 | 2015-12-28 | 15-ETI-019 | 20856 | 2016-09-15 | SUB | 2016-12-01 | Deer Lake | Fish Creek | 1 | 138 |  |  | New 138 kV substation between Fish Creek and Spring Branch on line number 96. | TX |  |  | Planned | 675157 | Planning |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-TX | 9242 | 2015-12-28 | 15-ETI-020 | 20855 | 2016-09-15 | SUB | 2016-11-01 | Wildcat | Nitro | 1 | 69 |  |  | New 69 kV substation between South Beaumont and Nitro on line 98. | TX |  |  | Under Construction | 5159000 |  |  | N | N | N | NT
A in MTEP15 | A | South | Entergy-TX | 9280 | 2015-12-28 | 15-ETI-016 | 20858 | 2016-03-30 | TX | 2020-06-01 | Cypress 500 | Cypress 138 | 2 | 500 | 138 |  | 2nd Cypress 500/138 kV Auto. | TX |  |  | Planned | 14392680 |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-TX | 9281 | 2015-12-28 | 15-ETI-014 | 20859 | 2016-09-15 | LNrb | 2018-08-31 | Cleveland | Tarkington | 1 | 138 |  |  | Reconductor 9.3 miles and upgrade all related equipment. | TX |  |  | Planned | 9451175 |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-TX | 9282 | 2015-12-28 | 15-ETI-015-1 | 20860 | 2016-03-30 | LNrc | 2017-06-01 | South Beaumont | Carroll St | 1 | 138 |  |  | Reconductor 3.3 miles and upgrade all related equipment | TX |  |  | Planned | 1636587 |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-TX | 9283 | 2015-12-28 | 15-ETI-015-2 | 20861 | 2016-03-30 | LNrc | 2017-06-01 | South Beaumont | Carroll St | 2 | 138 |  |  | Reconductor 3.3 miles and upgrade all related equipment. | TX |  |  | Planned | 1767746 |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-TX | 9460 | 2015-12-28 | 15-ETI-001 | 20909 | 2016-09-15 | TX | 2017-11-01 | South Beaumont 138 | South Beaumont 69 | 1 | 138 | 69 | 200 | Upgrade Transformer to 200 MVA | TX |  |  | Planned | 16559809 |  |  | N | N | N | NT
A in MTEP15 | A | South | Entergy-TX | 9460 | 2015-12-28 | 15-ETI-001 | 20911 | 2016-03-30 | BUS | 2017-11-01 | South Beaumont 138 |  |  | 138 |  |  | Reconfigure station | TX |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-TX | 9460 | 2015-12-28 | 15-ETI-001 | 20910 | 2016-03-30 | TX | 2017-11-01 | South Beaumont 138 | South Beaumont 69 | 2 | 138 | 69 | 200 | Upgrade Auto to 200 MVA | TX |  |  | Planned |  |  |  | N | N | N | NT
A in MTEP15 | A | South | Entergy-TX | 9482 | 2015-12-28 | 15-ETI-023 | 20916 | 2016-03-30 | LN | 2019-06-01 | China 230 | Stowell 230 | 1 | 230 |  |  | New 230 kV line from China to Stowell | TX |  |  | Planned | 57300000 | Planning |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-TX | 9482 | 2015-12-28 | 15-ETI-023 | 20917 | 2016-03-30 | TX | 2019-06-01 | Stowell 230 | Stowell 138 | 1 | 230 | 138 | 400 | 230/138 kV Auto Transformer | TX |  |  | Planned |  | Planning |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-TX | 10487 | 2016-01-06 | 15-ETI-024; 15-ETI-025 | 21596 | 2015-12-17 | TX | 2020-06-01 | Grimes 345 | Grimes 230 | 2 | 345 | 230 |  | Install 2nd 345/230 Auto | TX |  |  | Planned | 121920000 | Planning |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-TX | 10487 | 2016-01-06 | 15-ETI-024; 15-ETI-025 | 21598 | 2016-07-05 | LNrc | 2019-06-01 | Newton Bulk | Leach | 1 | 138 |  |  | Rebuild Newton Bulk to Leach 138 kV line | TX |  |  | Planned | 33900000 | Planning |  | N | N | N | Y
A in MTEP15 | A | South | Entergy-TX | 10487 | 2016-01-06 | 15-ETI-024; 15-ETI-025 | 21597 | 2015-12-17 | LN | 2020-06-01 | Grimes | Lewis Creek | 1 | 230 |  |  | New 230 kV line from Grimes to Lewis Creek | TX |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP15 | A | South | ETEC | 8208 | 2015-12-28 | PRJ 07 | 20596 | 2016-01-12 | LN | 2017-12-31 | TBD | TBD |  | 138 |  |  | Cut into Tarkington-Long John 138 kV line and extend line to Luce Bayou substation. | TX |  |  | Planned | 10800000 |  |  | N | N | N | Y
A in MTEP15 | A | South | ETEC | 8208 | 2015-12-28 | PRJ 07 | 20597 | 2016-01-12 | SUB | 2017-12-31 | TBD |  |  | 138 |  |  | Install new Luce Bayou 138 kV in-and-out substation. | TX |  |  | Planned | 5500000 |  |  | N | N | N | Y
A in MTEP15 | A | South | LAFA | 8820 | 2015-12-28 |  | 20743 | 2015-08-21 | TX | 2018-12-31 | Pont Des Mouton |  |  | 230 | 69 |  | 230-69 autotransformer to feed new 69kv station | LA |  |  | Planned | 3750000 | Planning |  | N | N | N | NT
A in MTEP15 | A | South | LAFA | 8820 | 2015-12-28 |  | 20745 | 2015-08-21 | SUB | 2018-12-31 | Northeast |  |  | 69 |  |  | Station to alleviate distribution loading. | LA |  |  | Planned | 4250000 | Planning |  | N | N | N | NT
A in MTEP15 | A | South | LAFA | 8820 | 2015-12-28 |  | 20744 | 2015-08-21 | LN | 2018-12-31 | Pont Des Mouton | Northeast |  | 69 |  |  | New 69kv line from Pont Des Mouton to Peck stations. | LA |  |  | Planned | 2500000 | Planning |  | N | N | N | NT
A in MTEP15 | A | South | SMEPA | 8120 | 2016-09-26 |  | 20518 | 2016-07-01 | LNrb | 2016-10-31 | Ellisville | Glade GOAB | 1 | 69 |  | 71 | Rebuild L18 (Ellisville - Glade GOAB) using 759 ACSR conductor and 48-fiber OPGW. | MS | 4.63 |  | Planned | 1242195 | Planning |  | N | N | N | NT
A in MTEP15 | A | South | SMEPA | 8120 | 2016-09-26 |  | 20520 | 2016-09-26 | LNrb | 2017-04-30 | Glade GOAB | Cleo | 1 | 69 |  | 71 | Rebuild L18A (Glade GOAB - Cleo) using 795 ACSR conductor with 48-fiber OPGW. | MS | 6.03 |  | Planned | 1617805 | Planning |  | N | N | N | NT
A in MTEP15 | A | South | SMEPA | 8560 | 2016-02-03 |  | 20682 | 2016-07-01 | LNcnv | 2018-08-01 | Waynesboro | Missionary | 1 | 230 |  | 501 MVA | Convert Waynesboro - Missionary 161kV line to 230kV operation. | MS | 38.31 |  | Planned | 500000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | South | SMEPA | 8560 | 2016-02-03 |  | 20703 | 2016-07-01 | LNrb | 2020-09-01 | Homewood | Missionary |  | 161 |  | 296 | Rebuild existing 69kV lines from span from Homewood - Missionary using double circuit provisions for the addition of the 161kV path from Homewood - Missionary. | MS | 19.5 |  | Planned | 6825000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | South | SMEPA | 8560 | 2016-02-03 |  | 20702 | 2016-07-01 | LN | 2020-02-01 | Homewood | Missionary | 1 | 161 |  | 296 | Add additional 161kV circuit to existing double circuit line. | MS | 31 |  | Planned | 3410000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | South | SMEPA | 8560 | 2016-02-03 |  | 20701 | 2016-09-26 | BUS | 2017-12-31 | Homewood |  |  | 161 |  |  | Add 161kV Bay with Breaker at Homewood. | MS |  |  | Planned | 545000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | South | SMEPA | 8560 | 2016-02-03 |  | 20700 | 2016-07-01 | BUS | 2018-06-01 | Missionary |  |  | 161 |  |  | Add 161kV breaker to existing bay at Missionary substation. | MS |  |  | Planned | 165000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | South | SMEPA | 8560 | 2016-02-03 |  | 20699 | 2016-07-01 | SUB | 2018-06-01 | Missionary |  |  | 230 | 161 | 250 MVA | Add 230/161kV Transformer (250 MVA) at existing SMEPA owned Missionary substation. | MS |  |  | Planned | 2900000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | South | SMEPA | 8560 | 2016-02-03 |  | 20698 | 2016-07-01 | SUB | 2018-06-01 | Waynesboro - Missionary | Laurel East - Enterprise |  | 230 |  |  | Add 230kV Bay with Breakers at switching station. | MS |  |  | Planned | 2680000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | South | SMEPA | 8560 | 2016-02-03 |  | 20697 | 2016-07-01 | SwSta | 2018-06-01 | Waynesboro - Missionary | Laurel East - Enterprise |  | 230 |  |  | Tap the existing SMEPA owned Waynesboro - Missionary and MPCo owned Laurel East - Enterprise lines at the point of intersection and construct a 230kV switching station. | MS |  |  | Planned | 365000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | South | SMEPA | 8560 | 2016-02-03 |  | 20685 | 2016-07-01 | BUS | 2018-06-01 | Waynesboro |  |  | 230 |  |  | Add 230kV bay with breaker at Waynesboro (Create Ring Bus Configuration) | MS |  |  | Planned | 670000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | South | SMEPA | 8560 | 2016-02-03 |  | 20684 | 2016-07-01 | BUS | 2018-06-01 | Waynesboro |  |  | 230 |  |  | Add 230kV Breaker to existing bay at Waynesboro | MS |  |  | Planned | 230000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | South | SMEPA | 8560 | 2016-02-03 |  | 20683 | 2016-07-01 | BUS | 2018-06-01 | Missionary |  |  | 230 |  |  | Add 230kV Bay with Breaker at Missionary | MS |  |  | Planned | 670000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | South | SMEPA | 9000 | 2015-12-28 |  | 20792 | 2016-07-01 | LNrb | 2016-07-15 | Benndale | Benndale GT | 1 | 69 |  |  | Rebuild line using 795 ACSR and 48-fiber OPGW. | MS | 1.2 |  | Planned | 370000 | Planning |  | N | N | N | NT
A in MTEP15 | A | South | SMEPA | 9020 | 2016-09-26 |  | 20793 | 2016-09-26 | LNrb | 2017-12-31 | Wiggins GOAB | Big Level | 1 | 69 |  |  | Rebuild the existing Big Level - Wiggins GOAB 69kV line using 795 ACSR conductor and 48-fiber. | MS | 8.4 |  | Planned | 1875000 | Planning |  | N | N | N | NT
A in MTEP15 | A | West | ATC | 3159 | 2015-12-28 | PR03817 | 5547 | 2016-09-29 | LN | 2017-12-31 | West Middleton | Timberlane Tap | 1 | 69 |  | 84 | Uprate West Middleton to Timberlane Tap 69 kV Line | WI | 1.8 |  | Planned | 2000000 | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 3159 | 2015-12-28 | PR03817 | 5548 | 2013-09-10 | LN | 2018-12-31 | Timberlane Tap | Stage Coach | 1 | 69 |  | 88 | Uprate Timberlane Tap to Stage Coach 69 kV Line | WI | 2.4 |  | Planned |  | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 4353 | 2015-12-28 | PR05933 | 8328 | 2016-03-29 | SUB | 2017-12-01 | Creekview |  |  | 138 |  |  | New 138kV Creekview substation | WI |  |  | Planned | 16000000 | Planning |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 4353 | 2015-12-28 | PR05933 | 8330 | 2016-03-29 | LN | 2017-12-01 | Creekview | South Fond Du Lac | 1 | 138 |  | 246 | Loop Forward Energy Center - South Fond Du Lac 138kV line into new Creekview SS | WI | 13.2 |  | Planned |  | Planning |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 4353 | 2015-12-28 | PR05933 | 8329 | 2016-03-29 | LN | 2017-12-01 | Forward Energy Center | Creekview | 1 | 138 |  | 246 | Loop Forward Energy Center - South Fond Du Lac 138kV line into new Creekview SS | WI | 7.58 |  | Planned |  | Planning |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 4419 | 2015-12-28 | PR05948 | 8439 | 2013-12-12 | TEQ | 2016-06-01 | Sunset Point | Ellinwood | 1 | 138 |  | 246 | Uprate Sunset Point - Ellinwood (SPTG311) 138kV line at Sunset Point from 795 Drake ACSR and 500 Cu37 jumpers with 2156 ACSR Bluebird | WI |  |  | Planned | 109000 |  |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 4421 | 2015-12-28 | PR06011 | 8441 | 2016-09-29 | LN | 2017-07-01 | Elkhorn | Williams Bay | 1 | 138 |  | 197 | Loop Elkhorn - Brick Church (X-44) 138kV line into Williams Bay | WI | 7.67 |  | Planned | 875000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 4421 | 2015-12-28 | PR06011 | 8444 | 2015-01-14 | CB | 2017-07-01 | Williams Bay |  |  | 138 |  |  | Add line breaker to Brick Church - Williams Bay (X-44) 138kV line at Williams Bay | WI |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 4421 | 2015-12-28 | PR06011 | 8443 | 2016-09-29 | CB | 2017-07-01 | Williams Bay |  |  | 138 |  |  | Add line breaker to Elkhorn - Williams Bay (X-44) 138kV line at Williams Bay | WI |  |  | Planned | 3575000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 4421 | 2015-12-28 | PR06011 | 8442 | 2015-01-14 | LN | 2017-07-01 | Brick Church | Williams Bay | 1 | 138 |  | 188 | Loop Elkhorn - Brick Church (X-44) 138kV line into Williams Bay | WI | 6.62 |  | Planned |  |  |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 4422 | 2015-12-28 | PR05969 | 8445 | 2016-06-30 | TX | 2016-08-19 | Brillion Iron Works |  | 1 | 138 | 69 | 60 | New 138/69kV transformer at new Brillion Iron Works substation | WI |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 4422 | 2015-12-28 | PR05969 | 8451 | 2016-06-30 | LN | 2016-08-19 | Forest Junction | Glenview | 1 | 138 |  | 174 | Uprate Forest Junction - Glenview (E-57) 138kV line | WI | 4.62 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 4422 | 2015-12-28 | PR05969 | 8450 | 2016-06-30 | LN | 2016-08-19 | Brillion Iron Works | Brillion Iron Works Arc | 1 | 69 |  | 87 | Brillion Iron Works - Brillion Iron Works Arc 69kV line arc furnace service | WI |  | 0.11 | Planned |  | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 4422 | 2015-12-28 | PR05969 | 8449 | 2016-06-30 | LN | 2016-08-19 | Glenview | Brillion Iron Works | 1 | 69 |  | 39 | Expand Glenview - Brillion Iron (M-65) 69kV line to the new Brillion Iron Works 69kV bus | WI | 0.95 |  | Planned |  |  |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 4422 | 2015-12-28 | PR05969 | 8448 | 2016-06-30 | LN | 2016-08-19 | Glenview | Brillion Iron Works | 1 | 138 |  | 174 | Loop Shoto - Glenview (L-90) 138kV line into Brillion Iron Works | WI | 1.09 |  | Planned |  |  |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 4422 | 2015-12-28 | PR05969 | 8447 | 2016-06-30 | LN | 2016-08-19 | Shoto | Brillion Iron Works | 1 | 138 |  | 105 | Loop Shoto - Glenview (L-90) 138kV line into Brillion Iron Works | WI | 22.43 |  | Planned | 12500000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 4422 | 2015-12-28 | PR05969 | 8446 | 2016-06-30 | SUB | 2016-08-19 | Brillion Iron Works |  |  | 138 |  |  | New Brillion Iron Works (BIW) substation | WI |  |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 4732 | 2015-12-28 | PR06105 | 8969 | 2016-06-30 | LN | 2018-12-01 | Ogden St. | Bayshore | 1 | 69 |  | 123 | Construct a new 69kV line from Ogden St. - Bayshore | WI |  | 0.54 | Planned | 10400000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 4732 | 2015-12-28 | PR06105 | 8973 | 2016-06-30 | CB | 2018-12-01 | Ogden St. |  |  | 69 |  |  | Odgen St. - Bayshore 69kV breaker | WI |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 4732 | 2015-12-28 | PR06105 | 8972 | 2016-06-30 | CB | 2018-12-01 | Ogden St. |  |  | 69 |  |  | Odgen St. - Wells St. 69kV breaker | WI |  |  | Planned |  |  |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 4732 | 2015-12-28 | PR06105 | 8971 | 2016-06-30 | LNrb | 2018-12-01 | 2nd St. | Fiber swtiching structure | 1 | 69 |  | 123 | Rebuild 2nd St. - Fiber switching structure (N-14) 69kV | WI | 0.59 |  | Planned |  |  |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 4732 | 2015-12-28 | PR06105 | 8970 | 2016-06-30 | LNrb | 2018-12-01 | Bayshore | 2nd St. | 1 | 69 |  | 123 | Rebuild Bayshore - 2nd St. (N-14) 69kV | WI | 0.15 |  | Planned |  |  |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 7601 | 2015-12-28 | PR06199 | 20036 | 2016-03-30 | Remove | 2016-07-01 | Lakehead Portage |  |  | 69 |  |  | Remove 16 Mvar mobile capacitor bank at Lakehead Portage 69 kV | WI |  |  | Planned | 3400000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 7602 | 2015-12-28 | PR05440 | 20037 | 2014-11-25 | LNup | 2019-10-31 | Bunker Hill | Kelly | 1 | 115 |  | 145 | Rerate Bunker Hill - Kelly 115 kV as part of Blackbrook/Bunker Hill retirment (PR05440) | WI | 19.47 |  | Planned | 4800000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 7603 | 2015-12-28 | PR05440 | 20038 | 2014-09-08 | Remove | 2019-11-01 | Blackbrook |  |  | 115 |  |  | Retire Blackbrook 115 kV station | WI |  |  | Planned | 25200000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 7603 | 2015-12-28 | PR05440 | 20044 | 2014-09-08 | LNrb | 2019-11-01 | Roehring Rd | Pine | 1 | 115 |  | 145 | Rebuild M-13b Pine - Roehring Rd 115 kV with double circuit structures | WI | 10.89 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 7603 | 2015-12-28 | PR05440 | 20043 | 2014-09-08 | LNrb | 2019-11-01 | Roehring Rd | Kelly | 1 | 115 |  | 145 | Rebuild M-13a Kelly - Roehring Rd 115 kV | WI | 19.47 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 7603 | 2015-12-28 | PR05440 | 20042 | 2014-09-08 | LNrb | 2019-11-01 | Roehring Rd | Antigo | 1 | 115 |  | 145 | Rebuild A-313b Antigo - Roehring Rd 115kV | WI | 5.85 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 7603 | 2015-12-28 | PR05440 | 20041 | 2014-09-08 | LNrb | 2019-11-01 | Roehring Rd | Gardner Park | 1 | 115 |  | 145 | Rebuild A-313a Gardner Park - Roehring Rd 115kV with double circuit structures | WI | 34.33 |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 7603 | 2015-12-28 | PR05440 | 20040 | 2014-09-08 | SwSta | 2019-11-01 | Roehring Rd |  |  | 115 |  |  | Build new 115 kV 4 position ring bus named Roehring Rd | WI |  |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 7603 | 2015-12-28 | PR05440 | 20039 | 2014-09-08 | Remove | 2019-11-01 | Bunker Hill |  |  | 115 |  |  | Retire Bunker Hill 115 kV station | WI |  |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 7741 | 2015-12-28 | PR06198 WO:600800 F4314 | 20069 | 2016-03-29 | CAP | 2016-12-15 | Dellwood |  |  | 69 |  |  | Add 8.17 Mvar capacitor bank at Dellwood 69 kV station | WI |  |  | Planned | 3100000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 7741 | 2015-12-28 | PR06198 WO:600800 F4314 | 20070 | 2016-03-29 | Remove | 2016-12-15 | McKenna |  |  | 69 |  |  | Remove 15.3 Mvar mobile capacitor bank from McKenna station. | WI |  |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 7780 | 2015-12-28 | PR6489 | 20086 | 2016-09-29 | TX | 2017-03-01 | Esker View |  | 1 | 138 | 24.9 | 32 | Build 138/24.9 kV distribution transformer | WI |  |  | Planned | 4500000 | Engineering |  | N | N | N | NT
A in MTEP15 | A | West | ATC | 7981 | 2015-12-28 | PR05258 | 20252 | 2016-09-29 | CB | 2016-12-31 | Beardsley St |  |  | 69 |  |  | Add breakers at Beardsley St to sectionalize J-10 | WI |  |  | Planned | 2500000 |  |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 8065 | 2015-12-28 | PR07164, WO601615, F4693 | 20373 | 2015-07-24 | LNrb | 2020-12-31 | Pleasant Prairie | New Sub | 1 | 345 |  | 1146 | Loop Arcadian - Pleasant Prairie (PLPL81) 345 kV into new New Sub switching station | WI | 0 | 0.8 | Planned |  | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 8065 | 2015-12-28 | PR07164, WO601615, F4693 | 20378 | 2015-07-24 | SwSta | 2020-12-31 | New Sub |  |  | 345 |  |  | New 345 kV New Sub switching station | WI |  |  | Planned |  | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 8065 | 2015-12-28 | PR07164, WO601615, F4693 | 20377 | 2015-07-24 | LNrb | 2020-12-31 | Libertyville | New Sub | 1 | 345 |  | 1201 | Loop Zion - Libertyville (2224) 345 kV into new New Sub switching station | IL | 0 | 2 | Planned |  | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 8065 | 2015-12-28 | PR07164, WO601615, F4693 | 20376 | 2016-03-30 | LNrb | 2020-12-31 | Zion | New Sub | 1 | 345 |  | 1201 | Loop Zion - Libertyville (2224) 345 kV into new New Sub switching station | IL | 0 | 2 | Planned | 52000000 | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 8065 | 2015-12-28 | PR07164, WO601615, F4693 | 20375 | 2015-07-24 | LNrb | 2020-12-31 | Arcadian | New Sub | 1 | 345 |  | 928 | Loop Arcadian - Pleasant Prairie (PLPL81) 345 kV into new New Sub switching station | WI | 14.8 | 0.8 | Planned |  | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 8071 | 2015-12-28 |  | 20389 | 2016-09-29 | LN | 2023-12-31 | Plains | National | 1 | 138 |  | 294 | New 138 kV line from Plains - National | MI | 0 | 57 | Planned | 124602000 | Planning |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 8660 | 2015-12-28 | PR07030 | 20719 | 2016-06-30 | TX | 2020-09-01 | Somers |  | 2 | 138 | 24.9 | 66 | 2nd Somers distribution transformer | WI |  |  | Planned | 2800000 | Planning Preliminary |  | N | N | N | NT
A in MTEP15 | A | West | ATC | 8660 | 2015-12-28 | PR07030 | 20721 | 2016-06-30 | CB | 2020-09-01 | Albers |  |  | 138 |  |  | New line breaker from Albers to Somers. | WI |  |  | Planned |  | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 8660 | 2015-12-28 | PR07030 | 20720 | 2016-06-30 | CB | 2020-09-01 | Albers |  | 1 | 138 |  |  | New line breaker for Bain - Albers | WI |  |  | Planned |  | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 9080 | 2015-12-28 |  | 20810 | 2016-09-29 | CB | 2018-12-31 | W. Marinette |  | 2 | 138 |  |  | Install high and low side breakers on existing 138/69 kV transformer on circuit 2. | WI |  |  | Planned | 4500000 | Planning |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 9080 | 2015-12-28 |  | 20812 | 2016-09-29 | CB | 2018-12-31 | W. Marinette |  | 1 | 138 |  |  | Install W. Marinette 138-69 kV transformer high-side protection on circuit 1. | WI |  |  | Planned |  | Planning |  | N | N | N | Y
A in MTEP15 | A | West | ATC | 9081 | 2015-12-28 |  | 20811 | 2016-06-30 | LNrc | 2018-03-01 | Depere | Glory Rd | 1 | 138 |  | 290 | Reconductor R122 De Pere - Glory Road 138 kV underground and overhead lines. | WI | 1.14 |  | Planned | 736000 | Planning |  | N | N | N | Y
A in MTEP15 | A | West | DPC | 7664 | 2015-12-28 |  | 20663 | 2016-09-08 | LNrb | 2017-04-21 | Briggs Road | La Crosse Tap switch | 1 | 161 |  | 414 | DPC will rebuild the existing 161 kV line following existing ROW between the Briggs Road substation to the 3-way switch called La Crosse Tap that looks towards Genoa, XEL La Crosse and XEL Briggs Road | WI | 13.3 | 0 | Planned | 12000000 | Planning |  | N | N | N | Y
A in MTEP15 | A | West | GRE | 3782 | 2015-12-28 | 20425 | 7085 | 2016-09-08 | LN | 2016-10-27 | Long Lake | Mantrap | 1 | 115 |  | 142 | 115 kV line | MN | 0.33 | 6.25 | Planned | 4463269.15 | Planning |  | N | N | N | Y
A in MTEP15 | A | West | GRE | 4377 | 2015-12-28 | 202497 | 8889 | 2016-06-29 | CB | 2016-11-03 | Yankee Doodle North | Yankee Doodle South | 1 | 115 |  |  | Install bus tie breaker to allow closure of normally open point | MN |  |  | Planned | 891673.78 | Planning |  | N | N | N | Y
A in MTEP15 | A | West | GRE | 7894 | 2015-12-28 | 202989 | 20131 | 2016-04-14 | LN | 2017-10-02 | Stockade |  | 1 | 115 | 115 |  | GRE proposes to tap the GRE-owned Wakefield ? Big Swan 115 kV line and build a new, ~6 mile, 115 kV transmission to the proposed pumping station. | MN |  | 6 | Planned | 3812779 | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | West | GRE | 7899 | 2015-12-28 | 202988 | 20136 | 2016-09-15 | LN | 2017-10-19 | Cedar Lake Pumping Station |  | 1 | 115 | 115 |  | Install a transmission line to connect to MVEC?s Cedar Lake pump station sub. Line to be built to 115kV specs but initially energized at 115kV. Line length is undetermined at this point. 6 miles are assumed. | MN |  | 6 | Planned | 4989151.97 | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | West | GRE | 7912 | 2015-12-28 | 202919 | 20152 | 2016-09-15 | LNrb | 2021-05-01 | Bass Lake | Lawndale | 1 | 115 | 115 |  | Construct two miles of 115 kV line with 795 ACSS conductor from the 3 way switch to the high side structure of new Wright Hennepin Electric Cooperative?s Lawndale #2 distribution substation. | MN | 2 |  | Planned | 2000000 | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8042 | 2015-12-28 | Burl Sourth Sub | 20325 | 2015-01-23 | LN | 2016-12-31 | Burlington South |  |  | 69 |  |  | ITC will build new 69kV line taps for the new Burlington South Alliant Energy distribution sub. | IA |  |  | Planned | 60000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8043 | 2015-12-28 | Cust Interconnet Blanket | 20326 | 2014-12-02 | LN | 2017-12-31 | Blanket for Customer Interconnections under $1 million for 2017 | Throughout system |  | 345 | 69 |  | These projects are being done at the request of an interconnection customer in order to facilitate new load, re-distribute existing load, improve the performance of the sub-transmission and distribution systems, or to accommodate a new Transmission-to-Transmission connection request. | IA,MN,IL |  |  | Planned | 2400000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8043 | 2015-12-28 | Cust Interconnet Blanket | 20327 | 2014-12-02 | LN | 2018-12-31 | Blanket for Customer Interconnections under $1 million for 2018 | Throughout system |  | 345 | 69 |  | These projects are being done at the request of an interconnection customer in order to facilitate new load, re-distribute existing load, improve the performance of the sub-transmission and distribution systems, or to accommodate a new Transmission-to-Transmission connection request. | IA,MN,IL |  |  | Planned | 2400000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8048 | 2015-12-28 | Cntrl Enclosure Blanket | 20337 | 2015-12-29 | SUB | 2016-12-31 | Cntrl Enclosure Blanket for 2016 | Throughout system |  | 345 | 69 |  | Replace control enclosures due to age & condition | IA,MN,IL |  |  | Under Construction | 1860000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8049 | 2015-12-28 | NERC Com Mitigation | 20341 | 2015-12-29 | SUB | 2016-12-31 | NERC Com Mitigation for 2016 | Throughout system |  | 345 | 69 |  | New proposed NERC Reliability Standards will also impact the need to upgrade substations equipment to meet the standards. NERC Reliability Standards continue to evolve and issues like relay encroachment/loadability, scheme redundancy, protective relay testing, fault recording and stability analysis upgrades continually are being identified. | IA,MN,IL |  |  | Under Construction | 180000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8051 | 2015-12-28 | NRUC/ERUC | 20346 | 2015-12-29 | SUB | 2016-12-31 | Normal & Emergeny Retirement Unit Change-out for 2016 | Throughout system |  | 345 | 69 |  | The need for replacing miscellaneous aged, broken, or failed equipment in the field ? primarily in substations. Equipment replacements identified from maintenance inspections, such as batteries, field capacitors, control building HVAC units, transformer t | IA,MN,IL |  |  | Under Construction | 9000000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8053 | 2015-12-28 | Poor Performing Ckts | 20387 | 2015-12-29 | LN | 2016-12-31 | Poor Performing Circuits for 2016 | Throughout system |  | 69 | 34 |  | Rebuild poor performing circuits that have been identified as a system reliability issue | IA,MN,IL |  |  | Under Construction | 4800000 | Engineering |  | N | N | N | NT
A in MTEP15 | A | West | ITCM | 8057 | 2015-12-28 | SCADA Blanket | 20358 | 2015-12-29 | SUB | 2016-12-31 | SCADA Blanket for 2016 | Throughout system |  | 345 | 69 |  | Perform SCADA upgrades | IA,MN,IL |  |  | Under Construction | 360000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8058 | 2015-12-28 | Signage Blanket | 20362 | 2015-12-29 | LN | 2016-12-31 | Signage Blanket for 2016 | Throughout system |  | 345 | 69 |  | Add pole signage to transmission towers and poles that are not currently numbered to aid field personnel in troubleshooting activities and performing scheduled inspections and maintenance. | IA,MN,IL |  |  | Under Construction | 1200000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8074 | 2015-12-28 | Fairfax Cap | 20398 | 2015-01-20 | CAP | 2017-06-30 | Fairfax | Capacitor |  | 161 |  | 42 MVAR | Add a 42 MVAR 161 kV capacitor bank and new breaker at Fairfax substation. | IA |  |  | Planned | 1687896 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8086 | 2015-12-28 | Radio 69kV Cap | 20409 | 2015-12-29 | CAP | 2016-02-29 | Radio | Capacitor |  | 69 |  | 13.2 MVAR | Add a 13.2MVAR 69kV capacitor bank | IA |  |  | Under Construction | 524804 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8088 | 2015-12-28 | Hiawatha Cap | 20412 | 2015-01-20 | CAP | 2018-12-31 | Hiawatha | Capacitor |  | 161 |  | 42 MVAR | Move the 115kV cap bank and change the size to a 42MVAR 161kV cap bank at Hiawatha. | IA |  |  | Planned | 193795.2 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8093 | 2015-12-28 | PCI 161/69kV TRF | 20420 | 2015-01-21 | TX | 2016-12-31 | PCI | Transformer | 2 | 161 | 69 | 200 | Add a 200 MVA 161/69 kV transformer at Prairie Creek Industrial substation. | IA |  |  | Planned | 3617594 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8106 | 2015-12-28 | Hrn Lk Sub & Cap | 20437 | 2016-01-12 | CAP | 2019-12-31 | Heron Lake | Capacitor |  | 161 |  | 42 MVAR | Install two 21MVAR 161kV cap banks | MN |  |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8106 | 2015-12-28 | Hrn Lk Sub & Cap | 20440 | 2016-01-12 | SUB | 2019-12-31 | Heron Lake | Substation |  | 161 | 69 |  | Rebuild the Heron Lake 161kV to a ring bus (convertable to bkr and 1/2) | MN |  |  | Planned | 16929252 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8125 | 2015-12-28 | Anita-Grand Jct Rblds ph1 | 20478 | 2016-06-28 | LN | 2017-12-31 | Anita | Thompson | 1 | 69 |  |  | Rebuild 34kV to 69kV(operate at 34kV until 69kV/dist subs are ready) | IA | 17.6 |  | Planned | 11159322 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8128 | 2015-12-28 | Anita-Grand Jct Rblds ph2 | 20490 | 2015-01-21 | LN | 2017-12-31 | Redfield | Panora REC Tap | 1 | 69 |  |  | Build new 69 kV line (operate at 34kV until 69kV/dist subs are ready) | IA | 10 |  | Planned | 8852758.8 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8128 | 2015-12-28 | Anita-Grand Jct Rblds ph2 | 20502 | 2016-06-28 | LN | 2019-12-31 | Bagley | Perry | 1 | 69 |  |  | Rebuild 34kV to 69kV(operate at 34kV until 69kV/dist subs are ready) | IA | 19 |  | Planned | 11841000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8129 | 2015-12-28 | Anita-Grand Jct Rblds ph3 | 20511 | 2015-01-21 | LN | 2018-12-31 | Jefferson WCC | Scranton Distribution | 1 | 69 |  |  | Rebuild 34kV to 69kV(operate at 34kV until 69kV/dist subs are ready) | IA | 14.5 |  | Planned | 11837228.4 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8132 | 2015-12-28 | Anita-Grand Jct Rblds ph4 | 20516 | 2015-01-21 | LN | 2019-12-31 | Bagley Jct | Scranton | 1 | 69 |  |  | Rebuild 34kV to 69kV(operate at 34kV until 69kV/dist subs are ready) | IA | 16 |  | Planned | 8104200 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8150 | 2015-12-28 | Belle Plaine Conv | 20534 | 2015-01-20 | SUB | 2025-12-31 | Belle Plaine | Substation |  | 161 | 69 |  | Add four 69kV breakers that are needed at Belle Plaine and add a 100MVA 161/69kV transformer. | IA |  |  | Planned | 4891935.6 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8150 | 2015-12-28 | Belle Plaine Conv | 20724 | 2015-01-20 | SUB | 2025-12-31 | 34.5kV substation retirements |  |  | 34.5 |  |  | Retire the 34.5kV substation equipment that is no longer needed. | IA |  |  | Planned | 600000 | Engineering |  | N | N | N | NT
A in MTEP15 | A | West | ITCM | 8150 | 2015-12-28 | Belle Plaine Conv | 20537 | 2015-01-20 | SwSta | 2025-12-31 | Haven | Switch Station |  | 69 | 69 | 143 MVA | Haven Three (3) Terminal 69kV Switch Station | IA |  |  | Planned | 3043446 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8150 | 2015-12-28 | Belle Plaine Conv | 20536 | 2015-01-20 | SwSta | 2025-12-31 | Belle Plaine South (River Valley) | Switch Station |  | 69 | 69 | 143 MVA | Belle Plaine South (now named River Valley) Three (3) Terminal 69kV Switch Station | IA |  |  | Planned | 3043446 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8150 | 2015-12-28 | Belle Plaine Conv | 20535 | 2014-09-15 | TX | 2025-12-31 | Belle Plaine | Transformer |  | 161 | 69 | 100 MVA | Add a 161/69kV 100MVA transformer at Belle Plaine | IA |  |  | Planned |  | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8151 | 2015-12-28 | B Plaine-Vinton-Traer | 20538 | 2015-01-21 | SUB | 2025-12-31 | Vinton | Substation |  | 69 |  | 143 MVA | Two additional 69kV breakers are needed at the Vinton substation. | IA |  |  | Planned | 1164487.2 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8151 | 2015-12-28 | B Plaine-Vinton-Traer | 20539 | 2015-01-21 | SUB | 2025-12-31 | Traer | Substation |  | 69 |  | 143 MVA | One additional 69kV breaker is needed at the Traer substation. | IA |  |  | Planned | 768123.6 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8152 | 2015-12-28 | Conroy-Parnell Conv | 20542 | 2015-01-21 | SUB | 2025-12-31 | Parnell | Substation |  | 161 | 69 |  | Three 69kV breakers are needed at the Parnell Substation. | IA |  |  | Planned | 3812623.2 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8152 | 2015-12-28 | Conroy-Parnell Conv | 20543 | 2014-09-15 | TX | 2025-12-31 | Parnell | Transformer | 1 | 161 | 69 | 100 MVA | A new 161/69kV 100MVA transformer is needed at the Parnell Substation. | IA |  |  | Planned |  | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8153 | 2015-12-28 | Parnell-Keswick Conv | 20544 | 2015-01-21 | SwSta | 2025-12-31 | Keswick | Switch Station |  | 69 |  | 143 MVA | Add a Keswick 3 terminal switch station | IA |  |  | Planned | 2931082.8 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8154 | 2015-12-28 | Fairfax-Marengo Conv | 20545 | 2014-12-02 | SUB | 2025-12-31 | Fairfax | Substation |  | 69 |  |  | Two 69kV breakers are needed at the Fairfax Substation. | IA |  |  | Planned | 1278863 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8154 | 2015-12-28 | Fairfax-Marengo Conv | 20728 | 2015-01-21 | LN | 2025-12-31 | various 34.5kV | various 34.5kV |  | 34.5 |  |  | retire 34.5kV lines that are no longer needed | IA |  |  | Planned | 974404.8 | Engineering |  | N | N | N | NT
A in MTEP15 | A | West | ITCM | 8154 | 2015-12-28 | Fairfax-Marengo Conv | 20727 | 2015-01-21 | SUB | 2025-12-31 | various 34.5 kV subs |  |  | 34.5 |  |  | retire 34.5kV subs | IA |  |  | Planned | 180000 | Engineering |  | N | N | N | NT
A in MTEP15 | A | West | ITCM | 8154 | 2015-12-28 | Fairfax-Marengo Conv | 20546 | 2014-12-02 | SUB | 2025-12-31 | Marengo | Substation |  | 69 |  |  | Four 69kV breakers need to be installed at the Marengo Substation. | IA |  |  | Planned | 4198943 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8155 | 2015-12-28 | Mtown-Tama-Laurel Conv | 20547 | 2015-01-21 | SUB | 2025-12-31 | Fletcher | Substation |  | 69 |  |  | One (1) 69kV Terminal at Fletcher Substation | IA |  |  | Planned | 367443.6 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8155 | 2015-12-28 | Mtown-Tama-Laurel Conv | 20726 | 2015-01-21 | LN | 2025-12-31 | new switch stations |  |  | 69 |  |  | Perform the 69kV line work for new switch stations for the conversion. | IA |  |  | Planned | 600060 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8155 | 2015-12-28 | Mtown-Tama-Laurel Conv | 20549 | 2015-01-21 | SwSta | 2025-12-31 | Laurel | Switch Station |  | 69 |  |  | Three 69kV breakers and one 69kV bus tie breaker are needed at the Laurel switch station. | IA |  |  | Planned | 2817202.8 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8155 | 2015-12-28 | Mtown-Tama-Laurel Conv | 20548 | 2015-01-21 | SwSta | 2025-12-31 | Tama Paper | Switch Station |  | 69 |  |  | Three 69kV line breakers and one 69kV bus tie breaker are needed at the Tama Breaker Substation. | IA |  |  | Planned | 2817202.8 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8157 | 2015-12-28 | J233 Mtown Upgrades | 20551 | 2014-09-15 | SUB | 2015-12-31 | Marshalltown | Substation |  | 161 |  | 558 MVA | Three new terminals are needed at the Marshalltown substation to accommodate interconnection to the generating facilities 3 GSUs. | IA |  |  | Planned | 3850000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8158 | 2015-12-28 | DAEC Switch Station | 20552 | 2016-06-30 | SwSta | 2017-03-31 | DAEC | Switch Station |  | 69 |  |  | Construct a new three (3) terminal, three (3) breaker 69 kV switch station northwest of the city of Palo, Iowa in order to eliminate the coordination and system protection issues. The existing Vinton ? DAEC ? Hiawatha 69 kV transmission lines will need to be tapped and re-routed into the new substation. | IA |  |  | Planned | 3062831 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8160 | 2015-12-28 | Morgan Valley-Beverly 345 | 20554 | 2016-06-29 | SwSta | 2021-05-01 | Morgan Valley | Switch Station |  | 345 | 345 |  | Add a new Morgan Valley 345kV three terminal switch station on the Duane Arnold-Tiffin 345kV line. | IA |  |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8160 | 2015-12-28 | Morgan Valley-Beverly 345 | 20737 | 2016-06-29 | CAP | 2021-05-01 | Beverly | Capacitor |  | 69 |  | 33 MVAR | Add a 33 MVAR cap on the Beverly 69kV bus | IA |  |  | Planned |  | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8160 | 2015-12-28 | Morgan Valley-Beverly 345 | 20559 | 2016-06-29 | SUB | 2021-05-01 | Beverly | Substation |  | 345 | 161 |  | Add a new Beverly 345/161kV substation adjacent to the existing Beverly 161kV sub. Add a 161kV terminal at the existing Beverly sub to tie to the low side (161kV) of the new 345/161kV substation. | IA |  |  | Planned | 14864540.4 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8160 | 2015-12-28 | Morgan Valley-Beverly 345 | 20558 | 2016-06-29 | TX | 2021-05-01 | New Beverly 345/161kV | Substation | 1 | 345 | 161 | 450 MVA | New Beverly 345/161kV 450MVA autotransformer | IA |  |  | Planned |  | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8160 | 2015-12-28 | Morgan Valley-Beverly 345 | 20557 | 2016-06-29 | SUB | 2021-05-01 | New Beverly 345/161 kV | Substation |  | 345 | 161 |  | Add a new Beverly 345/161kV substation adjacent to the existing Beverly 161kV sub. | IA |  |  | Planned |  | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8160 | 2015-12-28 | Morgan Valley-Beverly 345 | 20555 | 2016-06-29 | LN | 2021-05-01 | Morgan Valley | New Beverly 345/161kV | 1 | 345 |  |  | Add a new 6.5 mile 345 kV line from the new Morgan Valley Switchstation to a new 345/161 kV substation adjacent to the existing Beverly 161/69/34.5 kV substation. | IA |  | 6.5 | Planned | 23292051.6 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8161 | 2015-12-28 | Amers-Doud ph1 | 20562 | 2014-12-02 | LN | 2016-12-31 | Ames Mine | Ames NADC | 1 | 69 |  |  | Buiid Ames Mine NADC 69lV | IA |  |  | Planned | 2004000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8162 | 2015-12-28 | Ames-Doud ph2 | 20563 | 2015-08-28 | LNcnv | 2017-12-31 | Ames Mine | New Ames 69kV Substation | 1 | 69 |  |  | Converrt the line from Ames Mine to the new Ames 69kV Substation to 69kV operation. | IA | 1.9 |  | Planned |  | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8164 | 2015-12-28 | Ames-Barilla Conv | 20565 | 2015-01-21 | SwSta | 2017-12-31 | new Ames | Substation |  | 69 |  |  | Construct a new 4 terminal switch station | IA |  |  | Planned | 6255831.6 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8164 | 2015-12-28 | Ames-Barilla Conv | 20725 | 2015-01-21 | LN | 2017-12-31 | Boone Jct | Barilla | 1 | 34.5 |  |  | Retire 0.4 miles | IA |  |  | Planned | 132000 | Engineering |  | N | N | N | NT
A in MTEP15 | A | West | ITCM | 8164 | 2015-12-28 | Ames-Barilla Conv | 20566 | 2015-08-28 | LNcnv | 2017-12-31 | new Ames Substation | Barilla | 1 | 69 |  |  | Convert the line from the new Ames Substation to Barilla to 69kV operation. Ames Ckt 4930 - reterminate Ames tap. | IA | 5.1 |  | Planned | 705000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8166 | 2015-12-28 | Vinton-Hiawath Conv | 20568 | 2015-12-30 | SUB | 2016-08-05 | Hiawatha | Substation |  | 69 |  |  | Add a 69kV terminal at the Hiawatha sub | IA |  |  | Under Construction | 554400 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8166 | 2015-12-28 | Vinton-Hiawath Conv | 20569 | 2015-12-30 | SUB | 2016-08-05 | Vinton | Substation |  | 69 |  |  | Add a 69kV terminal at Vinton | IA |  |  | Under Construction | 554400 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8167 | 2015-12-28 | Doud-Ames Conv ph1 | 20570 | 2016-06-30 | SUB | 2016-07-19 | Doud | Substation |  | 161 | 69 |  | The existing 69 kV terminals at Boone Jct will be re-terminated to breaker positions at Doud. A 161/69 kV transformer will be installed at Doud, and the existing 161/69 kV transformer at Boone Jct. will be removed. | IA |  |  | Under Construction | 5496000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8167 | 2015-12-28 | Doud-Ames Conv ph1 | 20572 | 2016-06-30 | LN | 2016-07-19 | Doud | Squaw Valley REC | 1 | 69 |  |  | Convert the line from Doud to Squaw Valley REC to 69kV operation. | IA | 8.6 |  | Under Construction | 633000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8167 | 2015-12-28 | Doud-Ames Conv ph1 | 20571 | 2016-06-30 | TX | 2016-07-19 | Doud | Transformer | 1 | 161 | 69 | 100 MVA | Add a Doud 161/69kV transformer | IA |  |  | Under Construction |  | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | ITCM | 8168 | 2015-12-28 | Doud-Ames Conv ph2 | 20573 | 2015-12-30 | LN | 2017-03-31 | Squaw Valley REC | Ames Transmission |  | 69 |  |  | Convet the line to 69kV operation | IA | 6.5 |  | Planned | 1380600 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | MEC | 8020 | 2015-12-28 |  | 20294 | 2016-09-16 | LN | 2019-12-01 | Pleasant Corner | Beacon | 1 | 161 |  | 410 MVA | New 161 kV Line from Pleasant Corner to Beacon | IA | 0 | 16 | Planned | 14500000 | Planning |  | N | N | N | Y
A in MTEP15 | A | West | MEC | 8020 | 2015-12-28 |  | 20295 | 2016-09-16 | TEQ | 2019-12-01 | Beacon |  |  | 161 |  | 2000A | New 161 kV Line Terminal at the Beacon Substation | IA |  |  | Planned | 765000 | Planning |  | N | N | N | Y
A in MTEP15 | A | West | MEC | 8028 | 2016-06-30 |  | 20304 | 2016-07-01 | TX | 2023-06-01 | Hastings |  |  | 161 | 69 | 125 MVA | Replace the Hastings transformer with a 125 MVA transformer. | IA |  |  | Planned | 2000000 | Planning |  | N | N | N | NT
A in MTEP15 | A | West | MEC | 8030 | 2015-12-28 |  | 20305 | 2016-03-21 | LN | 2017-06-01 | Clarksville East | Waverly West | 1 | 69 |  |  | New 69 kV Line from Clarksville East to Waverly West. Retire Clarksville East - Waverly Junction. | IA | 0 | 3 | Planned | 2600000 | Planning |  | N | N | N | NT
A in MTEP15 | A | West | MEC | 8035 | 2015-12-28 |  | 20372 | 2016-03-21 | TEQ | 2017-04-01 | Sub 78 |  |  | 161 |  |  | Replace limiting terminal equipment | IA |  |  | Planned | 207000 | Planning |  | N | N | N | Y
A in MTEP15 | A | West | MEC | 8036 | 2015-12-28 |  | 20371 | 2016-03-21 | TEQ | 2017-04-01 | Sub 56 |  |  | 161 |  |  | Replace limiting terminal equipment. | IA |  |  | Planned | 91000 | Planning |  | N | N | N | Y
A in MTEP15 | A | West | MEC | 8037 | 2015-12-28 | 02307 & 02309 | 20430 | 2016-04-06 | CB | 2017-11-15 | Sub 93 |  |  | 345 |  | 3000A | Replace Sub 93 345 kV circuit breakers 954 and 964 with new 3,000 Amp breakers. | IA |  |  | Planned | 853000 | Planning |  | N | N | N | Y
A in MTEP15 | A | West | MEC | 8038 | 2015-12-28 | G7141 | 20381 | 2016-07-01 | LNup | 2017-06-01 | Sub S | Sub G & Sub R |  | 69 |  | 1200 A | Replace two 69 kV line switches near Sub 41 on the G-R-S 3-terminal 69 kV line. | IL | 3.5 |  | Planned | 153000 | Planning |  | N | N | N | NT
A in MTEP15 | A | West | MEC | 8039 | 2016-09-16 | G7154 | 20379 | 2016-09-14 | LNup | 2020-11-01 | Sub R | GRS Tap |  | 69 |  | 119 MVA | Rebuild the 69 kV line from Sub R to the three way GRS tap (FAC N38) in Rock Island. Replace underground cable and upgrade overhead section as needed to match cable rating. | IL | 1.55 | 0 | Planned | 3325000 | Planning |  | N | N | N | NT
A in MTEP15 | A | West | MEC | 8059 | 2015-12-28 |  | 20364 | 2016-03-30 | CB | 2017-12-01 | DPS |  |  | 69 |  | 2000A | Replace eight 69 kV circuit breakers and associated 69 kV switches at DPS Substation | IA |  |  | Planned | 850000 | Planning |  | N | N | N | NT
A in MTEP15 | A | West | MEC | 8340 | 2015-12-28 |  | 20642 | 2016-03-30 | LNrc | 2015-06-15 | Ashawa | Army Post Road | 1 | 161 |  | 410 | Reconductor and rebuild the 161 kV line from Ashawa to Army Post Road with T-2 556.5 MCM ACSR conductor. | IA | 4.28 | 0 | Planned | 1977833 | Planning |  | N | N | N | Y
A in MTEP15 | A | West | MEC | 8340 | 2015-12-28 |  | 20644 | 2016-03-30 | LNrc | 2017-06-15 | Willow Creek | Greenfield Plaza | 1 | 161 |  | 410 | Rebuild and reconductor the Willow Creek to Greenfield Plaza 161 kV line with T-2 556.5 MCM ACSR conductor. | IA | 4.78 | 0 | Planned | 1850000 | Planning |  | N | N | N | Y
A in MTEP15 | A | West | MEC | 8340 | 2015-12-28 |  | 20643 | 2015-07-09 | LNrc | 2014-06-15 | Army Post | Willow Creek | 1 | 161 |  | 410 | Rebuild and reconductor 1.0 mile of 161 kV line from Army Post to Willow Creek with T-2 556.5 MCM ACSR conductor. | IA | 1 | 0 | Planned | 390000 | Planning |  | N | N | N | Y
A in MTEP15 | A | West | MEC | 8740 | 2015-12-28 |  | 20739 | 2016-03-30 | LN | 2016-12-01 | Brooks | Adams County | 1 | 161 |  | 410 | New 10-mile 161 kV line from Brooks Substation to Adams County Substation. | IA | 0 | 10 | Planned | 7500000 | Planning |  | N | N | N | Y
A in MTEP15 | A | West | MEC | 8740 | 2015-12-28 |  | 20740 | 2016-03-30 | SUB | 2016-12-01 | Brooks |  |  | 161 |  | 2000 | Add two new 161 kV line circuit breakers at the existing Brooks Substation to terminate the 161 kV lines from Clarinda and Adams County Substations. | IA |  |  | Planned | 1750000 | Planning |  | N | N | N | Y
A in MTEP15 | A | West | MEC | 8880 | 2015-12-28 |  | 20768 | 2015-07-09 | TX | 2015-05-01 | Sycamore | Sycamore | 1 | 161 | 69 | 167 | Replace failed transformer AG8T1 | IA | 0 | 0 | Planned | 1645000 | Planning |  | N | N | N | NT
A in MTEP15 | A | West | MEC | 9160 | 2015-12-28 |  | 20829 | 2016-09-30 | CAP | 2015-04-19 | Hastings |  |  | 69 |  |  | Reduce reactive capability of the 69 kV capacitor bank at Hastings Substation from 33.6 MVAR to 21.6 MVAR. Voltage step change upon switching the bank is too large during certain outage conditions. | IA |  |  | Planned | 51657 | Planning |  | N | N | N | NT
A in MTEP15 | A | West | MP | 7995 | 2015-12-28 | Maturi 115/23 kV Transformer | 20268 | 2015-05-13 | TX | 2015-12-31 | Maturi |  | 1 | 115 | 23 | 18.6 | New 115/23 kV transformer | MN | 0 | 0 | Planned | 1426000 | Scoping |  | N | N | N | Y
A in MTEP15 | A | West | MP | 7998 | 2015-12-28 | Dog Lake Expansion | 20278 | 2015-03-20 | CB | 2017-12-31 | Dog Lake |  |  | 115 |  |  | Add three new breakers plus bus expansion at existing Dog Lake Substation | MN | 0 | 0 | Planned | 2100000 | Engineering Preliminary |  | N | N | N | Y
A in MTEP15 | A | West | MP | 7998 | 2015-12-28 | Dog Lake Expansion | 20281 | 2015-03-20 | LN | 2017-12-31 | Badoura | Dog Lake | 1 | 115 |  |  | Extend line to expanded Dog Lake Substation | MN | 0 | 0.1 | Planned | 330000 | Engineering Preliminary |  | N | N | N | Y
A in MTEP15 | A | West | MP | 7998 | 2015-12-28 | Dog Lake Expansion | 20280 | 2015-03-20 | LN | 2017-12-31 | Verndale | Dog Lake | 1 | 115 |  |  | Extend line to expanded Dog Lake Substation | MN | 0 | 0.1 | Planned | 330000 | Engineering Preliminary |  | N | N | N | Y
A in MTEP15 | A | West | MP | 7998 | 2015-12-28 | Dog Lake Expansion | 20279 | 2015-03-20 | LN | 2017-12-31 | Scearcyville | Dog Lake | 1 | 115 |  |  | Extend line to expanded substation | MN | 0 | 0.5 | Planned | 330000 | Engineering Preliminary |  | N | N | N | Y
A in MTEP15 | A | West | MP | 7999 | 2015-12-28 | Straight River Substation | 20282 | 2015-06-10 | SUB | 2016-10-01 | Straight River |  |  | 115 | 34.5 | 10 | New 115/34.5 kV Substation | MN | 0 | 0 | Planned | 2140000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | MP | 7999 | 2015-12-28 | Straight River Substation | 20821 | 2015-06-10 | Dist | 2016-10-01 | Straight River | Park Rapids Pump Station |  | 34.5 |  | 20 | 34.5 kV feeder extension from Straight River to pump station | MN |  | 0.1 | Planned | 50000 | Engineering |  | N | N | N | NT
A in MTEP15 | A | West | MP | 7999 | 2015-12-28 | Straight River Substation | 20283 | 2015-06-10 | TAP | 2016-10-01 | Straight River |  |  | 115 |  |  | Tap in Hubbard - Blueberry 115 kV Line | MN | 0 | 0.1 | Planned | 620000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | MP | 8000 | 2015-12-28 | 16 Line Relocation | 20284 | 2015-04-02 | LNrl | 2018-05-01 | Arrowhead | 16L Tap | 1 | 115 |  | 55 | Relocate line segment | MN | 0 | 3 | Planned | 4740000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | MP | 8001 | 2015-12-28 | Enbridge East | 20285 | 2015-05-12 | TAP | 2015-10-01 | Enbridge East | New Line Tap | 1 | 115 |  |  | New line tap in Stinson - Gary 115 kV line | WI | 0 | 0.25 | Planned | 802541 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | MP | 8002 | 2015-12-28 | Enbridge South Sub | 20286 | 2015-06-12 | TAP | 2015-07-15 | South | New Line Tap | 1 | 115 |  |  | New line tap in existing Nemadji Tap (part of Gary - Stinson 115 kV Line) | WI | 0 | 0.1 | Under Construction | 1229500 | Construction |  | N | N | N | Y
A in MTEP15 | A | West | MP | 8003 | 2015-12-28 | Hawthorne II | 20287 | 2015-05-12 | TAP | 2015-12-31 | Hawthorne | Rebuilt Line Tap | 1 | 161 |  |  | Rebuild existing Hawthorne Tap in Stinson - Gordon 161 kV Line | WI | 0 | 0.1 | Planned | 530000 | Engineering Preliminary |  | N | N | N | Y
A in MTEP15 | A | West | MP | 9060 | 2015-12-28 | Forbes Transformer | 20802 | 2015-05-08 | TX | 2016-10-01 | Forbes |  |  | 230 | 115 | 373 | Addition of a second 230/115 kV Transfomer to relieve loading off the existing 230/115 kV under post contingent events. | MN |  |  | Planned | 4000000 | Planning |  | N | N | N | Y
A in MTEP15 | A | West | MP | 9061 | 2015-12-28 |  | 20803 | 2015-05-08 | CB | 2016-10-01 | Minntac |  |  | 230 |  |  | Adding 3 additional cirucit breakers and associated equipment to change the existing substation into a ring bus design. | MN |  |  | Planned | 3000000 | Planning |  | N | N | N | Y
A in MTEP15 | A | West | MP | 9061 | 2015-12-28 |  | 20804 | 2015-05-08 | LNrl | 2016-10-01 | Minntac | Forbes |  | 230 |  |  | Relocating line entrance at Minntac substation to fit into new ring bus design. | MN |  |  | Planned | 1000000 | Planning |  | N | N | N | Y
A in MTEP15 | A | West | MP | 9062 | 2015-12-28 | Maturi Transformer Replacement | 20805 | 2015-05-08 | TX | 2016-05-01 | Maturi |  | 1 | 115 | 34.5 | 18.6 | Transformer swap | MN | 0 | 0 | Planned | 400000 | Planning |  | N | N | N | NT
A in MTEP15 | A | West | MP | 9063 | 2015-12-28 | Hat Trick | 20806 | 2015-05-08 | LN | 2016-12-31 | Hat Trick | Laskin | 1 | 115 |  | 98 | Extend existing 115 kV line to new substation | MN | 0 | 0.1 | Planned | 499000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | MP | 9063 | 2015-12-28 | Hat Trick | 20808 | 2015-05-08 | SUB | 2016-12-31 | Hat Trick |  |  | 115 | 23 | 39.2 | New 115/23 kV Substation | MN | 0 | 0 | Planned | 4836850 | Engineering |  | N | N | N | NT
A in MTEP15 | A | West | MP | 9063 | 2015-12-28 | Hat Trick | 20807 | 2015-05-08 | LN | 2016-12-31 | Hat Trick | 37 Line Tap | 1 | 115 |  | 98 | Extend existing line to new substation | MN | 0 | 0.1 | Planned | 499000 | Engineering |  | N | N | N | Y
A in MTEP15 | A | West | OTP | 8240 | 2015-12-28 |  | 20614 | 2015-09-22 | TX | 2016-10-31 | Jamestown 345 |  |  | 345 | 115 | 336 MVA | Replace existing 345/115/41.6 kV transformers #1 and #2 at Jamestown with two larger 336 MVA transformers. | ND |  |  | Planned | 7000000 | Planning |  | N | N | N | Y
A in MTEP15 | A | West | OTP | 8240 | 2015-12-28 |  | 21468 | 2015-10-13 | SUB | 2016-10-31 | Jamestown 345 |  |  | 345 |  |  | Install 345 kV Breaker as a tie breaker between the transformers. | ND |  |  | Planned | 1700000 | Planning | Network | N | Y | Y | Y
A in MTEP15 | A | West | OTP | 8240 | 2015-12-28 |  | 21440 | 2015-09-22 | SUB | 2016-10-31 | Jamestown 345kV |  |  | 115 |  |  | Install 115 kV ring bus breaker and bus work. | ND |  |  | Planned | 850000 | Planning |  | N | N | N | Y
A in MTEP15 | A | West | OTP | 8281 | 2016-09-14 |  | 20627 | 2016-09-14 | SUB | 2018-07-31 | Donaldson 115 | Drayton 115 |  | 115 |  |  | Add a new 115 kV breaker at Donaldson to the Donaldson to Drayton 115 kV line to improve reliability of area loads. This breaker will reduce fault exposure to Donaldson loads by 17 miles and improve operations, maintenance, and relaying flexibility at Donaldson. | MN |  |  | Planned | 370000 | Planning Preliminary |  | N | N | N | Y
A in MTEP15 | A | West | XEL | 8075 | 2015-12-28 |  | 20395 | 2016-09-19 | SUB | 2016-12-30 | Lake Bavaria |  |  | 115 |  |  | Install new distribution substation | MN |  |  | Under Construction | 1153304 | Scoping |  | N | N | N | Y
A in MTEP15 | A | West | XEL | 8079 | 2015-12-28 |  | 20403 | 2015-05-21 | LNrb | 2019-06-01 | Madelia Switching Station | Village of Madelia | 1 | 69 |  |  | Rebuild 3.6 miles of 69 kV line from Madelia Switching Station to Village of Madelia to 336 ACSR | MN | 3.6 |  | Planned | 1594000 | Scoping |  | N | N | N | NT
A in MTEP15 | A | West | XEL | 8097 | 2015-12-28 |  | 20425 | 2016-06-30 | SUB | 2016-10-07 | Poplar Lake |  |  | 161 |  |  | Install 161 kV 20 MVAR reactor at Poplar Lake substation | WI |  |  | Planned | 2339744 | Scoping |  | N | N | N | Y
A in MTEP15 | A | West | XEL | 8107 | 2016-09-01 |  | 20444 | 2015-05-21 | SUB | 2019-01-01 | Yankee |  |  | 115 | 34.5 |  | Install a 3rd 115/34.5 kV transformer at Yankee, cut over the Buffalo Ridge feeder 321 and serve from Yankee, add 115 kV breakers at Yankee | MN |  |  | Planned | 4000000 | Planning |  | N | N | N | NT
A in MTEP15 | A | West | XEL | 8113 | 2015-12-28 |  | 20449 | 2016-09-29 | SUB | 2018-12-01 | Ward County |  |  | 230 | 115 |  | New 230/115 kV substation near Minot, ND | ND |  |  | Planned | 12186000 | Scoping |  | N | N | N | Y
A in MTEP15 | A | West | XEL | 8113 | 2015-12-28 |  | 20453 | 2016-09-29 | LN | 2018-12-01 | Ward County | McHenry | 1 | 230 |  | 500 | New 230 kV line from Ward County - McHenry | ND |  | 20 | Planned | 26775100 | Scoping |  | N | N | N | Y
A in MTEP15 | A | West | XEL | 8117 | 2015-12-28 |  | 20471 | 2016-06-30 | LNrb | 2023-09-30 | Ward County | Souris | 1 | 115 |  | 230 | Rebuild the 115 kV line between Ward County and Souris | ND | 7 |  | Planned | 7200000 | Scoping |  | N | N | N | Y
A in MTEP15 | A | West | XEL | 8117 | 2015-12-28 |  | 20473 | 2016-06-30 | LNrb | 2023-09-30 | Ward County | Souris | 2 | 115 |  | 230 | Rebuild the 115 kV line between Ward County and Souris | ND | 7 |  | Planned | 7200000 | Scoping |  | N | N | N | Y
A in MTEP15 | A | West | XEL | 8142 | 2015-12-28 |  | 20508 | 2016-06-30 | TX | 2017-12-01 | Stone Lake |  |  | 161 | 69 | 112 | Upgrade 161-69 kV transformer to 112 MVA | WI |  |  | Planned | 2227000 | Scoping |  | N | N | N | NT
A in MTEP15 | A | West | XEL | 8149 | 2015-12-28 |  | 20540 | 2016-06-30 | LN | 2018-12-01 | New Sub (South) | New Sub (North) | 1 | 69 |  |  | New 69 kV line tapping the existing Stinson - Bayfront 115 kV line to a new substation near Bayfield | WI |  | 20 | Planned | 14500000 | Planning |  | N | N | N | NT
A in MTEP15 | A | West | XEL | 8149 | 2015-12-28 |  | 20561 | 2016-06-30 | LNrb | 2018-12-01 | Cornucopia | Bayfield Tap | 1 | 69 |  |  | Rebuild Cornucopia - Bayfield Tap 34.5 kV to 69 kV using 477 ACSR | WI | 18 |  | Planned | 11000000 | Planning |  | N | N | N | NT
A in MTEP15 | A | West | XEL | 8149 | 2015-12-28 |  | 20560 | 2016-06-30 | SUB | 2018-12-01 | New Sub (North) |  |  | 69 | 34.5 |  | New 69/34.5 kV line near Bayfield Tap. Includes one 3 MVAR 34.5 kV cap bank. | WI |  |  | Planned | 2800000 | Planning |  | N | N | N | NT
A in MTEP15 | A | West | XEL | 8149 | 2015-12-28 |  | 20556 | 2016-06-30 | LNrb | 2018-12-01 | Iron River | Herbster | 1 | 69 |  |  | Rebuild Iron River - Herbster 34.5 kV to 69 kV using 477 ACSR | WI | 25 |  | Planned | 6500000 | Planning |  | N | N | N | NT
A in MTEP15 | A | West | XEL | 8149 | 2015-12-28 |  | 20541 | 2016-06-30 | SUB | 2018-12-01 | New Sub (South) |  |  | 115 | 69 |  | New 115/69 kV substation on the Stinson - Bayfront 115 kV line | WI |  |  | Planned | 5200000 | Planning |  | N | N | N | NT
A in MTEP15 | A | West | XEL | 8780 | 2015-12-28 |  | 20798 | 2015-04-29 | SUB | 2018-06-01 | Bailey Road |  |  | 345 | 115 |  | New substation tapping Red Rock-A.S. King 345 kV line | MN |  |  | Planned | 29000000 | Scoping |  | N | N | N | Y
A in MTEP15 | A | West | XEL | 8780 | 2015-12-28 |  | 20799 | 2016-06-30 | TX | 2018-06-01 | Bailey Road |  | 9 | 345 | 115 |  | Bailey Road 345/115 transformer #9 | MN |  |  | Planned | 5500000 |  |  | N | N | N | Y
B | B | East | ITCT | 1850 | 2014-01-31 |  | 3732 | 2014-01-31 | LN | 2020-12-31 | Hancock | Wixom | 1 | 230 |  |  | New Line resulting from Quaker-Wixom cut into Hancock | MI |  |  | Proposed |  |  |  | N | N | N | Y
B | B | East | ITCT | 1850 | 2014-01-31 |  | 3734 | 2014-01-31 | TX | 2020-12-31 | Hancock 230/120 kV | Transformer | 1 | 230 | 120 |  | New Transformer | MI |  |  | Proposed | 9000000 |  |  | N | N | N | Y
B | B | East | ITCT | 1850 | 2014-01-31 |  | 3733 | 2014-01-31 | LN | 2020-12-31 | Hancock | Quaker | 1 | 230 |  |  | New Line resulting from Quaker-Wixom cut into Hancock | MI |  |  | Proposed |  |  |  | N | N | N | Y
B | B | West | ATC | 1946 | 2013-02-18 |  | 20582 | 2014-09-16 | TX | 2024-06-01 | Spring Green |  | 2 | 138 | 69 | 100 | Install a 2nd Spring Green 138-69 kV Transformer | WI |  |  | Proposed | 5578636 | Engineering |  | N | N | N | Y
B | B | West | GRE, ITCM | 1741 | 2011-12-13 |  | 2235 | 2012-06-27 | LN | 2013-12-31 | Storden (Cottonwood County) | Dotson | 1 | 161 |  | 446 | New line | MN | 26 |  | Proposed | 16379839 | Planning | Network | N | Y | N | Y
B | B | West | ITCM | 1741 | 2011-12-13 |  | 3292 | 2012-06-27 | LNrb | 2013-12-31 | Heron Lake | South Storden | 1 | 161 |  | 440 | Rebuild line to higher capacity | MN |  |  | Proposed | 6818660 | Planning | Network | N | Y | N | Y
B | B | West | ITCM | 1741 | 2011-12-13 |  | 4028 | 2012-06-27 | LN | 2013-12-31 | South Storden | Cottonwood County | 1 | 161 |  |  |  | MN |  |  | Proposed | 4092575 | Planning | Network | N | Y | N | Y
B | B | West | ITCM | 1741 | 2011-12-13 |  | 4027 | 2012-06-27 | COM | 2013-12-31 | Communication System Upgrades |  |  | 161 |  |  |  | MN |  |  | Proposed | 400000 | Planning | Network | N | Y | N | Y
B | B | West | ITCM | 1741 | 2011-12-13 |  | 4026 | 2012-06-27 | SUB | 2013-12-31 | Heron Lake Substation |  |  | 161 |  |  |  | MN |  |  | Proposed | 4195530 | Planning | Network | N | Y | N | Y
B | B | West | ITCM | 1741 | 2011-12-13 |  | 4025 | 2012-06-27 | SUB | 2013-12-31 | Cottonwood County substation |  |  | 161 |  |  |  | MN |  |  | Proposed | 4833216 | Planning | Network | N | Y | N | Y
B in MTEP10 | B | East | ITCT | 1856 | 2014-01-31 |  | 3743 | 2016-03-17 | LN | 2030-12-31 | Jewell | Pontiac | 1 | 345 |  |  | Cut Pontiac-Greenwood-Belle River into Jewell creating Pontiac-Jewell and Jewell-Belle River-Greenwwod | MI |  |  | Proposed | 2600000 |  |  | N | N | N | Y
B in MTEP10 | B | East | ITCT | 1856 | 2014-01-31 |  | 3744 | 2016-03-17 | LN | 2030-12-31 | Jewell | Belle River - Greenwood Jct | 1 | 345 |  |  | Cut Pontiac-Greenwood-Belle River into Jewell creating Pontiac-Jewell and Jewell-Belle River-Greenwwod | MI |  |  | Proposed | 2600000 |  |  | N | N | N | Y
B in MTEP10 | B | East | ITCT | 2932 | 2015-03-25 |  | 5104 | 2015-03-25 | LN | 2020-06-01 | St Antoine | Essex | 1 | 120 |  |  | Construct 2nd underground cable from St Antoine to Essex (5.1 miles). | MI |  | 5.1 | Proposed | 54800000 |  |  | N | N | N | Y
B in MTEP10 | B | East | METC | 3210 | 2014-01-31 |  | 5953 | 2014-01-31 | LN | 2016-06-01 | Vanderbilt | Riggsville |  | 138 |  |  | Rebuild 30.3 miles of 138 kV 266 ACSR to 954 ACSR FDC 230 kV construction. | MI | 30.3 |  | Proposed | 33254000 |  |  | N | N | N | Y
B in MTEP10 | B | West | ITCM | 1746 | 2011-12-13 |  | 3549 | 2012-03-26 | LNrb | 2014-12-31 | Fox Lake | Rutland | 1 | 161 |  | 446/446 MVA | Rebuild existing line | MN | 17 |  | Proposed | 11900000 | Planning |  | N | N | N | Y
B in MTEP10 | B | West | ITCM | 1746 | 2011-12-13 |  | 3553 | 2012-03-26 | LNrb | 2018-12-31 | Hayward | Adams | 1 | 161 |  | 446/446 MVA | Rebuild existing line | MN | 36.39 |  | Proposed | 25480000 | Planning |  | N | N | N | Y
B in MTEP10 | B | West | ITCM | 1746 | 2011-12-13 |  | 3552 | 2012-03-26 | LNrb | 2016-12-31 | Winnebago | Hayward | 1 | 161 |  | 446/446 MVA | Rebuild existing line | MN | 49.09 |  | Proposed | 34370000 | Planning |  | N | N | N | Y
B in MTEP10 | B | West | ITCM | 1746 | 2011-12-13 |  | 3551 | 2012-03-26 | LNrb | 2017-12-31 | Lakefield Jct | Fox | 1 | 161 |  | 446/446 MVA | Rebuild existing line | MN | 22.3 |  | Proposed | 15610000 | Planning |  | N | N | N | Y
B in MTEP10 | B | West | ITCM | 1746 | 2011-12-13 |  | 3550 | 2012-03-26 | LNrb | 2015-12-31 | Rutland | Winnebago | 1 | 161 |  | 446/446 MVA | Rebuild existing line | MN | 14.6 |  | Proposed | 10220000 | Planning |  | N | N | N | Y
B in MTEP11 | B | Central | AmerenMO | 2973 | 2014-11-17 |  | 5174 | 2014-11-17 | SUB | 2022-12-01 | Mason-Carrollton-8 | Connection to Howard Bend 138-12 kV Sub | 1 | 138 |  | 478 | Howard Bend 138-12 kV Substation - Provide 138 kV ring bus connection from Mason-Carrollton-8 138 kV line to new Howard Bend Substation. Install 1-138 kV, 2000 A PCB at Carrollton Substation as a bus-tie. | MO |  |  | Proposed | 1371000 | Planning |  | N | N | N | Y
B in MTEP11 | B | East | METC | 1815 | 2014-01-31 |  | 3649 | 2014-01-31 | LNrb | 2020-06-01 | Chase | Mecosta | 1 | 138 |  | 108 | Rebuild 7.2 miles (230 kV construction, operate at 138 kV) | MI | 7.2 |  | Proposed | 8900000 | Planning |  | N | N | N | Y
B in MTEP11 | B | West | MEC | 3215 | 2016-09-14 | T6242 | 6089 | 2016-09-14 | CAP | 2030-06-01 | Sub 49 | Capacitor |  | 161 |  | 50 | Sub 49 161 kV 50 MVAr Capacitor | IL |  |  | Proposed | 840000 | Planning |  | N | N | N | Y
B in MTEP11 | B | West | MEC | 3266 | 2013-09-15 | T6164 | 6085 | 2013-09-15 | LNrb | 2024-06-01 | Sub 56 | Sub 89 | 1 | 161 |  | 314 | Sub 56-89 161 kV line uprate | IA | 22 |  | Proposed | 680000 | Planning |  | N | N | N | Y
B in MTEP12 | B | Central | AmerenIL | 2290 | 2015-09-11 |  | 4206 | 2015-09-11 | LN | 2023-06-01 | Joppa | 2nd. 345/161 kV Transformer |  | 345 | 161 | 560 | Install 2nd. 345/161 kV, 560 MVA Transformer | IL |  |  | Proposed |  |  |  | N | N | N | Y
B in MTEP12 | B | Central | AmerenIL | 3336 | 2012-03-06 |  | 6201 | 2013-09-13 | LN | 2020-06-01 | Gilman | Watseka | 1 | 138 |  | 322 | Reconductor to 1600 A summer emergency capability | IL | 15.21 |  | Proposed | 4763000 | Planning |  | N | N | N | Y
B in MTEP12 | B | Central | AmerenIL | 3342 | 2014-11-17 |  | 6207 | 2014-11-17 | LN | 2025-06-01 | Diamond Star | McClean County Sw. Station | 1 | 138 |  | 160 | Diamond Star Tap-McClean County section of McClean-Washington Street 138 kV Line 1544 - Verify hardware capable of operations at 120 degrees C on 5.04 miles of 477 kcmil ACSR conductor. | IL | 5.04 |  | Proposed | 240000 | Planning |  | N | N | N | Y
B in MTEP12 | B | Central | AmerenIL | 3687 | 2016-07-11 |  | 6964 | 2014-06-04 | CB | 2017-06-01 | North Decatur | Clinton Route 54 |  | 138 |  |  | North Decatur 138-34 kV Substation - Replace 138 kV Breakers 1313, 1350, and 1566W in the North Decatur-Clinton Route 54, North Decatur-Latham-1350, and North Decatur-Latham-1566 138 kV lines with minimum 2000 A continuous 40 kA interrupting circuit break | IL |  |  | Proposed | 500000 | Planning |  | N | N | N | Y
B in MTEP12 | B | Central | AmerenIL | 3703 | 2016-08-15 |  | 6953 | 2016-08-15 | SUB | 2022-12-01 | New Berlin Sub. |  |  | 138 | 69 | 112 | Install new 112 MVA, 138-69 kV Substation. Connect to Auburn, North-Jacksonville Industrial 138 kV Line 1306. | IL |  |  | Proposed |  |  |  | N | N | N | Y
B in MTEP12 | B | Central | AmerenMO | 3701 | 2012-03-06 | AMRN25 | 6946 | 2013-09-13 | LN | 2023-06-01 | Joachim | Cotter Creek | 1 | 138 |  | 240 | Extend 138 kV line from Joachim to Cotter Creek 138-34.5 kV substation as initial 138 kV supply to Cotter Creek sub. | MO |  |  | Proposed | 11880110 | Engineering |  | N | N | N | Y
B in MTEP12 | B | Central | AmerenMO | 3701 | 2012-03-06 | AMRN25 | 6948 | 2013-09-13 | LN | 2023-06-01 | Olympian Village | Cotter Creek | 1 | 138 |  | 240 | Extend 138 kV line from Olympian Village to Cotter Creek 138-34.5 kV Substation | MO |  |  | Proposed | 13385390 | Engineering |  | N | N | N | Y
B in MTEP12 | B | Central | AmerenMO | 3701 | 2012-03-06 | AMRN25 | 6947 | 2013-09-13 | SUB | 2023-06-01 | Olympian Village Sub |  |  | 138 |  | 478 | Olympian Village Switching Station - Establish 138 kV Breaker Station in Joachim-St. Francois-2 138 kV line (3-2000 A PCBs) as source of second 138 kV supply to Cotter Creek Substation. | MO |  |  | Proposed | 5965140 | Engineering |  | N | N | N | Y
B in MTEP12 | B | Central | AmerenMO | 3708 | 2012-03-06 |  | 6960 | 2011-09-15 | TX | 2018-06-01 | Fountain Lake Sub. | Install 2nd. 138-12.5 kV Xfmr |  | 138 | 12.5 | 45 | Fountain Lake Substation - Install 2nd. 138-12.5 kV Transformer. | MO |  |  | Proposed |  |  |  | N | N | N | Y
B in MTEP12 | B | East | ITCT | 1295 | 2014-01-31 |  | 2124 | 2014-01-31 | LN | 2018-06-01 | Quaker 120 | To Drexel to Southfield 120 |  | 120 |  |  | Rebuild the existing Quaker to Drexel to Southfield circuit utilizing 1431 ACSR conductor on double circuit 230 kV towers and add a second Quaker to Southfield circuit on this new tower line | MI | 7.35 |  | Proposed | 25500000 |  |  | N | N | N | Y
B in MTEP12 | B | East | ITCT | 1295 | 2014-01-31 |  | 5485 | 2014-01-31 | LN | 2018-06-01 | Quaker 120 | Southfield 120 |  | 120 |  |  | Rebuild the existing Quaker to Drexel to Southfield circuit utilizing 1431 ACSR conductor on double circuit 230 kV towers and add a second Quaker to Southfield circuit on this new tower line | MI |  | 7.35 | Proposed | 25550000 |  |  | N | N | N | Y
B in MTEP12 | B | East | ITCT | 2933 | 2014-01-31 |  | 5105 | 2016-09-14 | LNrc | 2020-12-31 | Superior | Wayne | 1 | 120 |  |  | Reconductor a ~10.5 mile-long portion of the Superior – Wayne 120 kV line that is comprised of 477 ACSR conductor only utilizing 795 ACSR conductor and replace the 477 ACSR line entrance at Wayne station. | MI | 10.5 |  | Proposed |  |  |  | N | N | N | Y
B in MTEP12 | B | East | ITCT | 3589 | 2014-01-31 |  | 6683 | 2014-01-31 | LNrb | 2018-06-01 | Lee | Lake Huron Pumping Jct. | 1 | 120 |  |  | Rebuild approximately 5.4 miles of 267 ACSR conductor to 954 ACSR | MI | 5.4 |  | Proposed | 5000000 |  |  | N | N | N | Y
B in MTEP12 | B | East | ITCT | 3589 | 2014-01-31 |  | 6684 | 2014-06-13 | LNrb | 2018-06-01 | Lake Huron Pumping Jct. | Menlo | 1 | 120 |  |  | Rebuild approximately 6.4 miles of 267 ACSR conductor to 954 ACSR | MI | 6.4 |  | Proposed | 6200000 |  |  | N | N | N | Y
B in MTEP12 | B | East | METC | 3137 | 2014-01-31 |  | 5515 | 2014-01-31 | LN | 2017-12-31 | Bard Road | Warren | 1 | 138 |  |  | Rebuild approximately 19.6 miles of the Warren to Bard Road 138 kV circuit to 230 kV double circuit construction using 954 ACSR. One side would be energized at 138kV, with the other side left vacant for future use. | MI | 19.6 |  | Proposed | 27800000 |  |  | N | N | N | Y
B in MTEP12 | B | East | METC | 3582 | 2014-01-31 |  | 6675 | 2014-01-31 | LNrb | 2017-06-01 | Bullock | Summerton | 1 | 138 |  |  | Rebuild the entire circuit between Bullock and Summerton to 954 ACSR on single-circuit, 138 kV steel pole structures | MI | 25.5 |  | Proposed | 20000000 | Planning |  | N | N | N | Y
B in MTEP12 | B | East | METC | 3594 | 2014-11-04 |  | 6693 | 2014-11-04 | TEQ | 2018-12-31 | Tittabawassee |  |  | 345 |  |  | Replace 345kV station equipment in rows 34 and 36 at Tittabawassee. | MI |  |  | Proposed | 3500000 |  |  | N | N | N | Y
B in MTEP12 | B | West | OTP | 3659 | 2016-06-28 | OTP | 6820 | 2016-06-14 | TX | 2018-11-01 | Roberts County 115/69/41.6 kV Substation | 115/41.6 transformer | 1 | 115 | 41.6 | 34 MVA | 115/41.6 transformer | SD |  |  | Proposed | 2000000 | Planning |  | N | N | N | Y
B in MTEP12 | B | West | OTP | 3661 | 2016-06-28 | OTP | 6822 | 2014-03-24 | TX | 2017-12-31 | Grenville 69/41.6 kV Substation | 69/41.6 transformer |  | 69 | 41.6 | 10 MVA | 69/41.6 transformer | SD |  |  | Proposed | 450000 | Proposed |  | N | N | N | Y
B in MTEP12 | B | West | OTP | 3661 | 2016-06-28 | OTP | 6823 | 2014-03-24 | TX | 2017-12-31 | Grenville | Pickeral Lake | 1 | 41.6 |  | 34 MVA | Build a new 2-mile 41.6 kV line to connect OTP and EREPC systems | SD |  | 2 | Proposed | 250000 | Proposed |  | N | N | N | Y
B in MTEP12 | B | West | OTP | 3664 | 2016-06-28 | OTP | 6826 | 2015-05-11 | LN | 2018-12-31 | Mooreton | Roberts Jct. | 1 | 41.6 |  | 34 MVA | New 41.6kv Line 16 miles | ND |  | 16 | Proposed | 3800000 |  |  | N | N | N | Y
B in MTEP13 | B | Central | AmerenIL | 4069 | 2012-09-15 |  | 7716 | 2016-09-09 | SUB | 2020-06-01 | Stallings Sub | Install 1-138 kV breaker |  | 138 |  |  | Install 138 kV, 2000 A bus-tie breaker. | IL |  |  | Proposed | 897220 | Engineering |  | N | N | N | Y
B in MTEP13 | B | Central | AmerenIL | 4071 | 2014-11-17 | AMRN31 | 7718 | 2014-11-17 | LN | 2025-06-01 | Cottage Hills | Wanda | 1 | 138 |  | 160 | Increase clearances to ground on 5.63 miles of 477 kcmil ACSR between Cottage Hills and Wanda to permit operation at 120 degrees C. in the Wood River-Stallings 138 kV Line. | IL | 5.63 |  | Proposed | 4504000 | Planning |  | N | N | N | Y
B in MTEP13 | B | Central | AmerenIL | 4071 | 2014-11-17 | AMRN31 | 7720 | 2014-11-17 | SUB | 2025-06-01 | Cottage Hills | Upgrade terminal equipment on Cottage Hills-Wanda |  | 138 |  | 160 | Replace or reconnect 600 A CTs and replace an 800 A PCB at Cottage Hills with equipment capable of carrying 1200 A continuously. | IL |  |  | Proposed | 500000 | Planning |  | N | N | N | Y
B in MTEP13 | B | Central | AmerenIL | 4071 | 2014-11-17 | AMRN31 | 7719 | 2014-11-17 | LN | 2025-06-01 | Stallings | Wanda |  | 138 |  | 314 | Reconductor 6.01 miles of 477 kcmil ACSR in the Stallings-Wanda section with conductor capable of carrying 1600 A under summer emergency conditions. | IL | 6.01 |  | Proposed | 6000000 | Planning |  | N | N | N | Y
B in MTEP13 | B | Central | AmerenMO | 4067 | 2015-09-11 |  | 7714 | 2015-09-11 | LN | 2018-06-01 | Meramec | Watson | 2 | 138 |  | 240 | Reconductor to 1600 A summer emergency capability. | MO | 3.7 |  | Proposed | 2107484 | Engineering |  | N | N | N | Y
B in MTEP13 | B | Central | AmerenMO | 4075 | 2014-11-17 |  | 7724 | 2014-11-17 | LN | 2024-06-01 | Sioux | Huster | 3 | 138 |  | 314 | Reconductor 5.9 miles of 954 kcmil ACSR with conductor capable of carrying 1600 A under summer emergency conditions. Replace 1200 A terminal equpment (dixconnect switches, CT's, bus conductor) at Huster with equipment capable of carrying 1600 A or better. | MO | 5.9 |  | Proposed | 5900000 | Planning |  | N | N | N | Y
B in MTEP13 | B | East | METC | 4346 | 2015-11-13 |  | 8321 | 2016-07-14 | LNrb | 2018-12-31 | Karn | Garfield | 1 | 138 |  | 330 | Rebuild the 33.5 mile copper portion of the Karn to Garfield circuit using single circuit 138kV structures and 954 ACSR conductor. Mitigate several additional points of interest on the remaining portions (795 and 1431 ACSR). Replace station equipment at | MI | 33.5 |  | Proposed | 39500000 | Engineering |  | N | N | N | Y
B in MTEP13 | B | West | GRE | 4012 | 2016-06-30 | 20326 | 7645 | 2016-06-30 | Dist | 2020-12-31 | Hardy Lake |  |  | 115 |  |  | GRE will build new Crow Wing Power 115 KV Hardy Lake Substation | MN |  | 0.1 | Proposed | 207500 | Planning |  | N | N | N | Y
B in MTEP13 | B | West | GRE | 4013 | 2012-09-11 | 20334 | 7646 | 2016-06-30 | Dist | 2026-05-02 | Air Lake |  |  | 115 |  |  | GRE will build new Dakota Electric 115 kv South Air Lake substation. | MN |  | 0 | Proposed | 864000 | Planning |  | N | N | N | Y
B in MTEP13 | B | West | GRE | 4015 | 2014-12-19 | 20414 | 7648 | 2014-12-19 | Dist | 2027-12-31 | Le Homme Dieu |  |  | 115 |  |  | GRE will convert Runestone's LeHommeDieu 69 kV distribution sub to 115 kV | MN | 0.5 |  | Proposed | 365000 | Planning |  | N | N | N | Y
B in MTEP13 | B | West | GRE | 4016 | 2016-06-30 | 20507 | 7649 | 2016-06-30 | Dist | 2022-05-31 | Cashel |  |  | 115 |  |  | GRE will convert Agralite Cashel 41.6 kV distribution sub to 115 kV | MN | 1 |  | Proposed | 625000 | Planning |  | N | N | N | Y
B in MTEP13 | B | West | MEC | 4252 | 2012-09-15 | G4083 | 8001 | 2012-09-15 | SUB | 2015-06-30 | Neal North | Breaker |  | 161 |  |  | Neal North:161 kV Breaker Replacements | IA |  |  | Proposed | 325000 | Planning |  | N | N | N | Y
B in MTEP13 | B | West | MP | 3756 | 2015-05-07 | Wrenshall | 7021 | 2015-06-10 | SUB | 2020-12-31 | Wrenshall | Substation Equipment |  | 115 | 69 | 28 | Add breakers and a 115/69 kV transformer | MN |  |  | Proposed | 3000000 | Planning |  | N | N | N | Y
B in MTEP13 | B | West | MP | 4295 | 2015-06-10 | HVDC Valve Hall Replacement | 8219 | 2015-06-10 | HVDC | 2020-12-31 | Arrowhead | Valve hall upgrade |  | 250 |  | 550 | Replace valve hall at Arrowhead terminal, +/- 250 kV | MN |  |  | Proposed | 37500000 | Planning |  | N | N | N | Y
B in MTEP13 | B | West | MP | 4295 | 2015-06-10 | HVDC Valve Hall Replacement | 8220 | 2015-06-10 | HVDC | 2020-12-31 | Square Butte | Valve hall upgrade |  | 250 |  | 550 | Replace valve hall at Square Butte terminal, +/- 250 kV | ND |  |  | Proposed | 37500000 | Planning |  | N | N | N | Y
B in MTEP14 | B | Central | AmerenIL | 4489 | 2014-12-17 |  | 8600 | 2013-09-13 | LN | 2018-11-15 | Fargo | Radnor | 1347 | 138 |  | 240 | Rebuild Fargo-Pioneer-1347 138 kV line between Fargo and Radnor. Tentative 1600 A summer emergency target rating. | IL | 3 |  | Proposed | 3000000 | Planning |  | N | N | N | Y
B in MTEP14 | B | Central | AmerenMO | 4498 | 2014-12-17 | AMRN45 | 8611 | 2013-09-13 | LN | 2020-06-01 | Berntie | Jim Hill | 1 | 161 |  | 399 | Construct approximately 20 miles of 161 kV line between Jim Hill Plant and Berntie Substation in southeast, Missouri. The new line should have a 2000 A summer emergency rating. | MO |  | 20 | Proposed | 24000000 | Planning |  | N | N | N | Y
B in MTEP14 | B | Central | AmerenMO | 4498 | 2014-12-17 | AMRN45 | 8613 | 2013-09-13 | CB | 2020-06-01 | Jim Hill | Install 161 kV Breaker |  | 161 |  |  | Install 161 kV Breaker at Jim Hill | MO |  |  | Proposed | 500000 | Planning |  | N | N | N | Y
B in MTEP14 | B | Central | AmerenMO | 4498 | 2014-12-17 | AMRN45 | 8612 | 2013-09-13 | CB | 2020-06-01 | Berntie | Install 161 kV Ring Bus |  | 161 |  |  | Construct 161 kV ring bus at Berntie Substation | MO |  |  | Proposed | 6000000 | Planning |  | N | N | N | Y
B in MTEP14 | B | East | METC | 1795 | 2014-12-17 | METC_13_037 | 3604 | 2013-09-13 | LNrb | 2016-12-31 | David Jct. | Bingham | 1 | 138 |  | 303 MVA | Rebuild approximately 19miles of 336.4 ACSR from the Bingham - David Jct. 138 kV section to 954 ACSR on new 138 kV future double circuit structures. | MI | 19 |  | Proposed | 19000000 | Engineering |  | N | N | N | Y
B in MTEP14 | B | East | METC | 3922 | 2014-12-17 | METC_13_039 | 7484 | 2014-06-13 | LNrb | 2016-12-31 | Alpine Jct. | Cannon Jct. | 1 | 138 |  | 257 MVA | Rebuild 8.4 miles of 336 ACSR utilizing 954 ACSR on new 138 kV structures. | MI | 8.4 |  | Proposed | 8200000 | Engineering |  | N | N | N | Y
B in MTEP14 | B | East | METC | 4510 | 2014-12-17 | METC_13_044 | 8639 | 2014-06-13 | LNrb | 2017-12-31 | Morrow | Battle Creek | 1 | 138 |  | 388 MVA | Rebuild 22 miles of Morrow - Battle Creek138kV to 954 ACSR on future double circuit 138kV towers. | MI | 22 | 0 | Proposed | 24200000 | Engineering |  | N | N | N | Y
B in MTEP14 | B | East | METC | 4510 | 2014-12-17 | METC_13_044 | 8640 | 2014-06-13 | TEQ | 2017-12-31 | Morrow |  |  | 138 |  |  | Upgrade terminal equipment at Morrow. | MI |  |  | Proposed | 440000 | Engineering |  | N | N | N | Y
B in MTEP14 | B | East | METC | 4511 | 2016-07-05 | METC_13_046 | 8641 | 2016-07-05 | LNrb | 2019-12-31 | Verona | Foundry | 1 | 138 |  | 287 MVA | Rebuild 21 miles of the Verona - Foundry 38kV circit to 1431 ACSR. | MI | 21 | 0 | Proposed | 16000000 | Engineering |  | N | N | N | Y
B in MTEP14 | B | East | METC | 4511 | 2016-07-05 | METC_13_046 | 8642 | 2016-07-05 | TEQ | 2019-12-31 | Verona |  |  | 138 |  |  | Upgrade terminal equipment at Verona. | MI |  |  | Proposed | 21000 | Engineering |  | N | N | N | Y
B in MTEP14 | B | East | WPSC | 4383 | 2016-03-30 | Bradley Xmsn | 8398 | 2016-09-15 | SUB | 2022-12-31 | Bradley | Substation Upgrade |  | 138 | 69 |  | 138kV Breaker Replacement and Protective Equipment Upgrade | MI |  |  | Proposed | 4000000 | Budgetary |  | N | N | N | Y
B in MTEP14 | B | East | WPSC | 4383 | 2016-03-30 | Bradley Xmsn | 21506 | 2016-09-15 | SUB | 2022-12-31 | Bradley |  |  | 138 |  |  | Bradley Landscaping | MI |  |  | Proposed | 100000 | Budgetary |  | N | N | N
B in MTEP14 | B | East | WPSC | 4383 | 2016-03-30 | Bradley Xmsn | 21505 | 2016-09-15 | SUB | 2021-12-31 | Bradley |  |  | 138 |  |  | Bradley Zoning | MI |  |  | Proposed | 50000 |  |  | N | N | N
B in MTEP14 | B | East | WPSC | 4383 | 2016-03-30 | Bradley Xmsn | 21504 | 2015-10-28 | SUB | 2017-01-01 | Bradley |  |  | 138 |  |  | Bradley station land | MI |  |  | Proposed | 500000 | Planning |  | N | N | N
B in MTEP14 | B | South | SMEPA | 4439 | 2015-04-03 | LRTPS11-RP2102 | 8475 | 2014-09-22 | LN | 2021-06-01 | Tap Point | Morrow | 1 | 161 |  | 296 | New 161kV Line (Tap existing Purvis - Lumberton 161kV Line) w/OPGW | MS |  | 3 | Proposed | 1050000 | Planning |  | N | N | N | Y
B in MTEP14 | B | South | SMEPA | 4439 | 2015-04-03 | LRTPS11-RP2102 | 8479 | 2014-09-22 | TEQ | 2021-06-01 | Morrow |  |  | 161 |  |  | Add 161kV Breaker @ Morrow | MS |  |  | Proposed | 165000 | Planning |  | N | N | N | Y
B in MTEP14 | B | South | SMEPA | 4439 | 2015-04-03 | LRTPS11-RP2102 | 8478 | 2014-09-22 | LNup | 2021-06-01 | Purvis | Lumberton | 1 | 161 |  |  | Uprate Purvis to Lumberton 161kV line to 296MVA w/OPGW | MS | 1 |  | Proposed | 123200 | Planning |  | N | N | N | Y
B in MTEP14 | B | South | SMEPA | 4439 | 2015-04-03 | LRTPS11-RP2102 | 8477 | 2014-09-22 | TAP | 2021-06-01 | Tap Point |  |  | 161 |  |  | New 161kV Switching Station @ Tap Point w/ 3 breakers | MS |  |  | Proposed | 1950000 | Planning |  | N | N | N | Y
B in MTEP14 | B | South | SMEPA | 4439 | 2015-04-03 | LRTPS11-RP2102 | 8476 | 2015-07-13 | LN | 2021-06-01 | Tap Point | Morrow |  | 161 |  |  | New 161kV Transmission Line Right of Way | MS |  | 3 | Proposed | 210000 | Planning | Generator | N | N | N | Y
B in MTEP14 | B | South | SMEPA | 4440 | 2015-04-03 | LRTPS11-RP2106 | 8480 | 2014-09-22 | TEQ | 2021-06-01 | Lumberton |  |  | 161 |  |  | Add 161kV breaker at Lumberton 161kV substation | MS |  |  | Proposed | 180000 | Planning |  | N | N | N | Y
B in MTEP14 | B | South | SMEPA | 4440 | 2015-04-03 | LRTPS11-RP2106 | 8490 | 2014-09-22 | SwSta | 2021-06-01 | Big Level |  |  | 161 |  |  | Big Level 161kV switching station w/3 breakers | MS |  |  | Proposed | 1950000 | Planning |  | N | N | N | Y
B in MTEP14 | B | South | SMEPA | 4440 | 2015-04-03 | LRTPS11-RP2106 | 8489 | 2014-09-22 | SwSta | 2021-06-01 | Stillmore |  |  | 161 |  |  | Stillmore 161kV switching station w/3 breakers | MS |  |  | Proposed | 1950000 | Planning |  | N | N | N | Y
B in MTEP14 | B | South | SMEPA | 4440 | 2015-04-03 | LRTPS11-RP2106 | 8488 | 2014-09-22 | Dist | 2021-06-01 | Big Level |  |  | 161 |  |  | Convert Big Level distribution substation to 161kV | MS |  |  | Proposed | 1600000 | Planning |  | N | N | N | Y
B in MTEP14 | B | South | SMEPA | 4440 | 2015-04-03 | LRTPS11-RP2106 | 8487 | 2014-09-22 | Dist | 2021-06-01 | Stillmore |  |  | 161 |  |  | Convert Stillmore distribution substation to 161kV | MS |  |  | Proposed | 1600000 | Planning |  | N | N | N | Y
B in MTEP14 | B | South | SMEPA | 4440 | 2015-04-03 | LRTPS11-RP2106 | 8486 | 2014-09-22 | LNrb | 2021-06-01 | Stillmore | Wiggins GOAB | 1 | 161 |  | 296 | Rebuild Line 37C (Stillmore - Wiggins GOAB) at 161kV w/OPGW | MS | 7.22 |  | Proposed | 2093800 | Planning |  | N | N | N | Y
B in MTEP14 | B | South | SMEPA | 4440 | 2015-04-03 | LRTPS11-RP2106 | 8485 | 2014-09-22 | LNrb | 2021-06-01 | Benndale GT | Benndale | 1 | 161 |  | 296 | Rebuild Line 35A (Benndale GT - Benndale) at 161kV w/OPGW | MS | 1.3 |  | Proposed | 377000 | Planning |  | N | N | N | Y
B in MTEP14 | B | South | SMEPA | 4440 | 2015-04-03 | LRTPS11-RP2106 | 8484 | 2014-09-22 | LNrb | 2021-06-01 | Wiggins GOAB | Big Level | 1 | 161 |  | 296 | Rebuild Lines 37A & 37B (Wiggins GOAB - Big Level) at 161kV w/OPGW | MS | 8.5 |  | Proposed | 2465000 | Planning |  | N | N | N | Y
B in MTEP14 | B | South | SMEPA | 4440 | 2015-04-03 | LRTPS11-RP2106 | 8483 | 2014-09-22 | LN | 2021-06-01 | Wiggins GOAB | Stillmore |  | 161 |  |  | New 161kV Transmission Line Right of Way | MS |  | 8 | Proposed | 560000 | Planning |  | N | N | N | Y
B in MTEP14 | B | South | SMEPA | 4440 | 2015-04-03 | LRTPS11-RP2106 | 8482 | 2014-09-22 | LN | 2021-06-01 | Wiggins | Stillmore | 1 | 161 |  | 296 | New 161kV line to Stillmore w/OPGW | MS |  | 8 | Proposed | 2800000 | Planning |  | N | N | N | Y
B in MTEP14 | B | South | SMEPA | 4440 | 2015-04-03 | LRTPS11-RP2106 | 8481 | 2014-09-22 | TEQ | 2021-06-01 | Benndale |  |  | 161 |  |  | Add 161kV breaker at Benndale 161kV substation | MS |  |  | Proposed | 180000 | Planning |  | N | N | N | Y
B in MTEP14 | B | South | SMEPA | 4441 | 2015-04-03 | LRTPS11-RP2607 | 8491 | 2014-09-22 | TAP | 2026-06-01 | Tap Point |  |  | 161 |  |  | New 161kV Switchyard (Tap L171) w/ breakers | MS |  |  | Proposed | 1950000 | Planning |  | N | N | N | Y
B in MTEP14 | B | South | SMEPA | 4441 | 2015-04-03 | LRTPS11-RP2607 | 8498 | 2014-09-22 | TEQ | 2026-06-01 | State Line |  |  | 69 |  |  | Additional 69kV breaker | MS |  |  | Proposed | 120000 | Planning |  | N | N | N | Y
B in MTEP14 | B | South | SMEPA | 4441 | 2015-04-03 | LRTPS11-RP2607 | 8497 | 2014-09-22 | TEQ | 2026-06-01 | State Line |  |  | 69 |  |  | Additional 69kV bay w/ breaker | MS |  |  | Proposed | 440000 | Planning |  | N | N | N | Y
B in MTEP14 | B | South | SMEPA | 4441 | 2015-04-03 | LRTPS11-RP2607 | 8496 | 2014-09-22 | TX | 2026-06-01 | State Line |  |  | 161 | 69 | 50 | New 161/69kV, 100 MVA transformer | MS |  |  | Proposed | 1810000 | Planning |  | N | N | N | Y
B in MTEP14 | B | South | SMEPA | 4441 | 2015-04-03 | LRTPS11-RP2607 | 8495 | 2014-09-22 | TEQ | 2026-06-01 | State Line |  |  | 161 |  |  | New 161kV bay w/ breaker | MS |  |  | Proposed | 1635000 | Planning |  | N | N | N | Y
B in MTEP14 | B | South | SMEPA | 4441 | 2015-04-03 | LRTPS11-RP2607 | 8494 | 2014-09-22 | SwSta | 2026-06-01 | State Line |  |  | 161 |  |  | New 161kV Switchyard at State Line | MS |  |  | Proposed | 315000 | Planning |  | N | N | N | Y
B in MTEP14 | B | South | SMEPA | 4441 | 2015-04-03 | LRTPS11-RP2607 | 8493 | 2014-09-22 | LN | 2026-06-01 | Tap Point | State Line |  | 161 |  | 296 | New 161kV Transmission Line Right of Way | MS |  | 19 | Proposed | 1330000 | Planning |  | N | N | N | Y
B in MTEP14 | B | South | SMEPA | 4441 | 2015-04-03 | LRTPS11-RP2607 | 8492 | 2014-09-22 | LN | 2026-06-01 | Tap Point | State Line | 1 | 161 |  | 296 | New 161kV Transmission Line w/ OPGW adder | MS |  | 19 | Proposed | 6650000 | Planning |  | N | N | N | Y
B in MTEP14 | B | West | ATC, MP | 3832 | 2015-05-07 | Iron Range - Arrowhead 345 kV | 7203 | 2013-07-24 | LN | 2025-12-31 | Blackberry | Transformer | 1 | 500 | 345 | 1200 | Blackberry 1200 MVA 500/345 kV transformer | MN |  |  | Proposed |  |  |  | N | N | N | Y
B in MTEP14 | B | West | ATC, MP | 3832 | 2015-05-07 | Iron Range - Arrowhead 345 kV | 7206 | 2013-07-24 | LN | 2025-12-31 | Blackberry | Arrowhead | 2 | 345 |  | 1219 | Blackberry - Arrowhead 345 kV line (Ckt 2) | MN |  | 60 | Proposed |  |  |  | N | N | N | Y
B in MTEP14 | B | West | ATC, MP | 3832 | 2015-05-07 | Iron Range - Arrowhead 345 kV | 7205 | 2013-07-24 | LN | 2025-12-31 | Blackberry | Arrowhead | 1 | 345 |  | 1219 | Blackberry - Arrowhead 345 kV line (Ckt 1) | MN |  | 60 | Proposed | 220481656.22 | Planning |  | N | N | N | Y
B in MTEP14 | B | West | ATC, MP | 3832 | 2015-05-07 | Iron Range - Arrowhead 345 kV | 7204 | 2013-07-24 | LN | 2025-12-31 | Blackberry | Transformer | 2 | 500 | 345 | 1200 | Blackberry 1200 MVA 500/345 kV transformer | MN |  |  | Proposed |  |  |  | N | N | N | Y
B in MTEP14 | B | West | GRE | 4376 | 2016-06-30 | 202496 | 8381 | 2016-06-30 | LNrc | 2020-04-29 | Parkwood | Crooked Lake | 1 | 115 |  | 300+ | Reconductor line | MN | 3.36 |  | Proposed | 500000 | Planning |  | N | N | N | Y
B in MTEP14 | B | West | MDU | 3082 | 2014-12-17 | NW Bism | 5362 | 2013-10-31 | CB | 2017-06-01 | NW Bismarck | 3 PCB |  | 115 |  |  | Create a ring bus | ND |  |  | Proposed | 3050000 | Engineering |  | N | N | N | Y
B in MTEP14 | B | West | MP | 2548 | 2014-12-17 | Duluth 230 kV Project | 4564 | 2014-09-12 | TX | 2026-12-31 | Hilltop |  | 2 | 230 | 115 | 187 | Hilltop Transformer #2 | MN | 0 | 0 | Proposed | 3000000 | Planning Preliminary | Network | N | Y | N | Y
B in MTEP14 | B | West | MP | 2548 | 2014-12-17 | Duluth 230 kV Project | 4565 | 2014-09-12 | LNcnv | 2026-12-31 | Arrowhead | Hilltop | 1 | 230 |  | 470 | Upgrade 115 kV line to 230 kV | MN | 9 |  | Proposed | 3000000 | Planning Preliminary | Network | N | Y | N | Y
B in MTEP14 | B | West | MP | 3856 | 2015-06-10 | HVDC 750 MW | 7379 | 2015-06-10 | LNup | 2020-12-31 | Square Butte | Arrowhead | 1 | 250 |  | 750 | Structure upgrades on existing +/- 250 V HVDC line to achieve 750 MW capacity | ND,MN | 465 |  | Proposed | 10000000 | Planning |  | N | N | N | Y
B in MTEP14 | B | West | MP | 3856 | 2015-06-10 | HVDC 750 MW | 20820 | 2015-06-10 | HVDC | 2020-12-31 | Square Butte |  |  | 250 |  | 750 | Replace valve hall at Square Butte HVDC terminal +/-250kV HVDC | ND |  |  | Proposed | 37500000 | Planning |  | N | N | N
B in MTEP14 | B | West | MP | 3856 | 2015-06-10 | HVDC 750 MW | 20819 | 2015-06-10 | HVDC | 2020-12-31 | Arrowhead |  |  | 250 |  | 750 | Replace valve hall at Arrowhead HVDC terminal +/-250kV HVDC | MN |  |  | Proposed | 37500000 | Planning |  | N | N | N
B in MTEP14 | B | West | MP | 3856 | 2015-06-10 | HVDC 750 MW | 7383 | 2015-06-10 | TEQ | 2020-12-31 | Arrowhead | HVDC Terminal Equipment | 1 | 250 |  |  | Arrowhead HVDC terminal equipment upgrades; +/- 250 V | MN |  |  | Proposed | 15000000 | Planning |  | N | Y | N | Y
B in MTEP14 | B | West | MP | 3856 | 2015-06-10 | HVDC 750 MW | 7382 | 2015-06-10 | TX | 2020-12-31 | Arrowhead | Converter Transformers | 1 | 250 | 230 | 750 | Twelve 75 MVA converter transformers at Arrowhead; +/- 250 V | MN |  |  | Proposed | 42500000 | Planning |  | N | N | N | Y
B in MTEP14 | B | West | MP | 3856 | 2015-06-10 | HVDC 750 MW | 7381 | 2015-06-10 | TEQ | 2020-12-31 | Square Butte | HVDC Terminal Equipment | 1 | 250 |  |  | Square Butte HVDC terminal equipment upgrades; +/- 250 V | ND |  |  | Proposed | 15000000 | Planning |  | N | N | N | Y
B in MTEP14 | B | West | MP | 3856 | 2015-06-10 | HVDC 750 MW | 7380 | 2015-06-10 | TX | 2020-12-31 | Square Butte | Converter Transformers | 1 | 250 | 230 | 750 | Twelve 75 MVA converter transformers at Square Butte; +/- 250 V | ND |  |  | Proposed | 42500000 | Planning |  | N | N | N | Y
B in MTEP14 | B | West | MPC, OTP | 4232 | 2014-09-18 | OTP, MPC | 7985 | 2016-01-27 | SUB | 2024-11-15 | Winger 230 kV | Winger 230 kV |  | 230 |  |  | Winger Sub Expansion, Add 230 kV Breakers & Termination for New Line | MN |  |  | Proposed | 2000000 | Planning |  | N | N | N | Y
B in MTEP14 | B | West | MPC, OTP | 4232 | 2014-09-18 | OTP, MPC | 7988 | 2016-01-27 | LN | 2024-11-15 | Winger 230 kV | Thief River 230 kV | 1 | 230 |  | 452 | Winger-Thief River 230 kV New Transmission Line | MN |  | 47 | Proposed | 20000000 | Planning |  | N | N | N | Y
B in MTEP14 | B | West | MPC, OTP | 4232 | 2014-09-18 | OTP, MPC | 7987 | 2016-01-27 | TX | 2024-11-15 | Thief River 230 kV | Thief River 230 kV |  | 230 | 115 | 187 | Thief River 230/115 kV Add New 187 MVA Transformer | MN |  |  | Proposed | 5000000 | Planning |  | N | N | N | Y
B in MTEP14 | B | West | MPC, OTP | 4232 | 2014-09-18 | OTP, MPC | 7986 | 2016-01-27 | SUB | 2024-11-15 | Thief River 230 kV | Thief River 230 kV |  | 230 |  |  | Thief River Sub Expansion, Add 230 kV Breakers & Termination for New Line | MN |  |  | Proposed | 1000000 | Planning |  | N | N | N | Y
B in MTEP15 | B | Central | AmerenIL | 3010 | 2015-03-19 | AMRN13 | 5219 | 2014-09-11 | LN | 2030-06-01 | Baldwin | Heritage | 1 | 345 |  | 1793 | Baldwin-Grand Tower-N.W. Cape (Heritage) 345 kV - Construct 69 miles of 3000 A summer emergency capability. Install a 560 MVA, 345/138 kV transformer at Grand Tower | IL |  | 69 | Proposed |  | Planning |  | N | N | N | Y
B in MTEP15 | B | Central | AmerenIL | 3010 | 2015-03-19 | AMRN13 | 5220 | 2014-08-27 | TX | 2030-06-01 | Grand Tower Plant | Install 345/138 kV Xfmr | 1 | 345 | 138 | 560 | Install a 560 MVA, 345/138 kV transformer at Grand Tower | IL |  |  | Proposed | 5000000 | Planning |  | N | N | N | Y
B in MTEP15 | B | Central | AmerenIL | 7802 | 2015-11-24 |  | 20089 | 2015-11-24 | LNrc | 2026-06-01 | West Frankfort, East | West Frankfort | 1 | 138 |  | 322 | Reconductor 5.25 miles of 1272 kcmil ACSR conductor with conductor capable of carrying 1600 A under summer emergency conditions. Replace bus conductor at West Frankfort, East with conductor having capability equal to or greater than the new line conductor. | IL |  |  | Proposed |  |  |  | N | N | N
B in MTEP15 | B | Central | AmerenIL | 7821 | 2016-06-02 |  | 20091 | 2016-06-02 | CAP | 2020-06-01 | Kickapoo |  |  | 34.5 |  |  | Install --2-7.2 Mvar, 34.5 kV capacitor banks and PCBs. | IL |  |  | Proposed |  |  |  | N | N | N
B in MTEP15 | B | Central | AmerenIL | 7826 | 2015-03-19 |  | 20097 | 2014-08-29 | CB | 2019-12-01 | Turkey Hill |  |  | 138 |  |  | Install 138 kV bus tie breaker. Needed: 1-138 kV, 2000 A (minimum), 40 kA PCB. | IL |  |  | Proposed |  |  |  | N | N | N
B in MTEP15 | B | Central | AmerenIL | 7861 | 2015-03-19 |  | 20101 | 2015-11-05 | CB | 2019-06-01 | Effingham Northwest |  |  | 138 |  |  | Install 2-138 kV, 2000 A, 40 kA PCBs, one on each 138 kV line position. Upgrade bus conductor to 2000 A continuous capability. | IL |  |  | Proposed |  |  |  | N | N | N
B in MTEP15 | B | Central | AmerenIL | 7863 | 2015-03-19 |  | 20103 | 2014-12-05 | SUB | 2020-12-01 | Tilden |  |  | 138 |  |  | Establish a 5 position 138 kV ring bus for 4-138 kV lines and 1-138/34.5 kV transformer. | IL |  |  | Proposed |  |  |  | N | N | N
B in MTEP15 | B | Central | AmerenMO | 7862 | 2014-12-05 |  | 20102 | 2016-09-09 | SUB | 2020-12-01 | Buick Smelter |  |  | 161 | 4 |  | Relocate substation. Remove existing substation, install 2 motor-operated 161 kV switches and 2 customer owned and installed 161 kV circuit switchers. Make provisions for the addition of a third 161-4 kV transformer. | MO |  |  | Proposed |  |  |  | N | N | N
B in MTEP15 | B | Central | BREC | 3440 | 2014-09-16 | LRP6 | 6343 | 2010-11-15 | TX | 2024-12-31 | Reid EHV 161 kV | Reid EHV 69 kV |  | 161 | 69 | 56 MVA | new transformer | KY |  |  | Proposed | 5000000 | Planning |  | N | N | N | Y
B in MTEP15 | B | Central | PPI | 7888 | 2015-04-28 | 2015-19,20,41 | 20120 | 2015-07-09 | LN | 2016-12-31 | Geneseo Plant | JCE Geneseo |  | 69 | 69 | 50 | Construct 0.2 mile 69 kV transmission line to connect Geneseo plant substation to the Geneseo Jo-Carroll Energy substation to provide a network connection. | IL |  | 0.2 | Proposed | 289300 |  |  | N | N | N
B in MTEP15 | B | Central | PPI | 7888 | 2015-04-28 | 2015-19,20,41 | 20797 | 2015-11-05 | LN |  | MEC Sub 39 | JCE Ladwig | 1 | 69 |  | 50 | New 11 mile 69 kV line to provide network feed for Jo-Carroll Energy and the City of Geneseo | IL |  |  | Proposed |  |  |  | N | N | N
B in MTEP15 | B | Central | PPI | 7888 | 2015-04-28 | 2015-19,20,41 | 20122 | 2015-07-09 | LNcnv | 2016-12-31 | Ladwig | JCE Geneseo | 1 | 69 | 69 | 35 | Convert existing 34.5 kV line to 69 kV. Existing line is built to 69 kV specifications. | IL | 7.62 |  | Proposed |  |  |  | N | N | N
B in MTEP15 | B | Central | Vectren | 4395 | 2014-10-06 | 2013SIGE9 | 8412 | 2016-05-19 | CAP | 2019-12-31 | Northeast 69 | Capacitor |  | 69 |  |  | Remove existing cap banks from the tertiary winding of the 138/69 kV transformer at Northeast sub, and install equivalent cap banks on the 69 kV bus with breakers | IN | 0 | 0 | Proposed | 450000 | Planning |  | N | N | N | Y
B in MTEP15 | B | Central | Vectren | 4396 | 2016-05-18 | 2013SIGE10 | 8413 | 2016-05-19 | LN | 2020-12-31 | Scott Township 138 | Toyota 138 | 75-2 | 138 |  | 287 MVA | Install new approx. 13 mile 138 kV line | IN | 0 | 13 | Proposed | 13000000 | Planning |  | N | N | N | Y
B in MTEP15 | B | Central | Vectren | 4397 | 2014-10-06 | 2013SIGE11 | 8414 | 2014-10-01 | LNrb | 2020-12-31 | Leonard Rd. 69 | St. Phillips 69 | 31 | 69 |  | 103 MVA | Rebuild and reconductor approx. 6.8 miles | IN | 6.78 | 0 | Proposed | 5100000 | Planning |  | N | N | N | Y
B in MTEP15 | B | Central | Vectren | 4398 | 2014-10-06 | 2013SIGE12 | 8415 | 2014-10-01 | LNrb | 2021-12-31 | Northeast 69 | Sunbeam Tap 69 | 52-1 | 69 |  | 103 MVA | Rebuild and reconductor approx. 3 miles | IN | 2.95 | 0 | Proposed | 2250000 | Planning |  | N | N | N | Y
B in MTEP15 | B | Central | Vectren | 4399 | 2016-05-19 | 2013SIGE13 | 8416 | 2016-05-19 | SUB | 2023-12-31 | Newtonville 161 | Bus reconfig. |  | 161 |  | 335 MVA | Convert existing 161 kV bus to a ring bus configuration | IN | 0 | 0 | Proposed | 1000000 | Planning |  | N | N | N | Y
B in MTEP15 | B | East | ITCT | 3943 | 2014-12-02 |  | 7505 | 2015-04-29 | TEQ | 2018-12-31 | Navarre |  | 1 | 230 | 120 |  | Increase the CT ratio on the low-side breaker of the Navarre 230/120 kV Transformer #201. | MI |  |  | Proposed |  |  |  | N | N | N | Y
B in MTEP15 | B | East | ITCT | 4520 | 2015-04-22 | ITC_14_001 | 8652 | 2014-12-03 | SUB | 2018-06-01 | Mortar Creek |  |  | 345 |  | N/A | The Mortar Creek 345 kV switching substation. | MI |  |  | Proposed | 17100000 | Engineering |  | N | N | N | Y
B in MTEP15 | B | East | ITCT | 4520 | 2015-04-22 | ITC_14_001 | 8658 | 2014-09-15 | LN | 2018-06-01 | Mortar Creek | Monroe | 2 | 345 |  | 1748 MVA | Loop the Monroe #2 circuit into Mortar Creek. | MI |  |  | Proposed | 1000000 | Engineering |  | N | N | N | Y
B in MTEP15 | B | East | ITCT | 4520 | 2015-04-22 | ITC_14_001 | 8657 | 2014-09-15 | LN | 2018-06-01 | Mortar Creek | Lenawee - Milan | 1 | 345 |  | 1814 MVA | Loop the Lenawee - Milan circuit into Mortar Creek. | MI |  |  | Proposed | 1000000 | Engineering |  | N | N | N | Y
B in MTEP15 | B | East | ITCT | 4520 | 2015-04-22 | ITC_14_001 | 8656 | 2014-09-15 | LN | 2018-06-01 | Mortar Creek | Majestic | 1 | 345 |  | 953 MVA | Loop the Majestic circuit into Mortar Creek. | MI |  |  | Proposed | 1000000 | Engineering |  | N | N | N | Y
B in MTEP15 | B | East | ITCT | 4520 | 2015-04-22 | ITC_14_001 | 8655 | 2014-09-15 | LN | 2018-06-01 | Mortar Creek | Lemoyne | 1 | 345 |  | 953 MVA | Loop the Lemoyne circuit into Mortar Creek. | MI |  |  | Proposed | 1000000 | Engineering |  | N | N | N | Y
B in MTEP15 | B | East | ITCT | 4520 | 2015-04-22 | ITC_14_001 | 8654 | 2014-09-15 | LN | 2018-06-01 | Mortar Creek | Monroe | 1 | 345 |  | 1315 MVA | Loop Monroe circuit into Mortar Creek. | MI |  |  | Proposed | 1000000 | Engineering |  | N | N | N | Y
B in MTEP15 | B | East | ITCT | 4520 | 2015-04-22 | ITC_14_001 | 8653 | 2014-09-15 | LN | 2018-06-01 | Mortar Creek | Bayshore | 1 | 345 |  | 1262 MVA | Loop the Bayshore circuit into Mortar Creek. | MI |  |  | Proposed | 1000000 | Engineering |  | N | N | N | Y
B in MTEP15 | B | East | ITCT | 4520 | 2015-04-22 | ITC_14_001 | 20382 | 2014-12-03 | RLY | 2018-06-01 | Majestic |  |  | 345 |  |  | Upgrade relays at the Majestic station. | MI |  |  | Proposed | 450000 | Engineering |  | N | N | N
B in MTEP15 | B | East | ITCT | 4520 | 2015-04-22 | ITC_14_001 | 20383 | 2014-09-15 | RLY | 2018-06-01 | Monroe |  |  | 345 |  |  | Upgrade relays at Monroe station. | MI |  |  | Proposed | 400000 | Engineering |  | N | N | N
B in MTEP15 | B | East | ITCT | 8068 | 2015-04-22 | ITC_13_061 | 20384 | 2014-09-15 | LNup | 2017-12-31 | Brownstown | Monroe | 2 | 345 |  | 1756 MVA | Remediate the sag limit on the Brownstown to Monroe 2 345 kV line to increase its summer emergency rating to a minimum of 1793 MVA / 3000 Amps. | MI | 18.2 | 0 | Proposed | 1200000 | Engineering |  | N | N | N
B in MTEP15 | B | East | ITCT | 8069 | 2015-04-22 | ITC_13_056 | 20385 | 2014-09-15 | LNup | 2018-12-31 | Lemoyne | Majestic | 1 | 345 |  |  | Remediate the sag limit on the Lemoyne - Majestic 345 kV line. | MI |  |  | Proposed | 2500000 | Engineering |  | N | N | N
B in MTEP15 | B | East | ITCT | 8099 | 2015-04-22 | ITC_14_014 | 20442 | 2014-09-15 | LNrb | 2018-12-31 | Lincoln | Northeast/Northwest | 1 | 120 |  |  | Rebuild 2.95 miles of 477 ACSR to 1431 ACSR on new Double circuit towers. | MI |  |  | Proposed | 4000000 | Engineering |  | N | N | N
B in MTEP15 | B | East | ITCT | 8099 | 2015-04-22 | ITC_14_014 | 20443 | 2014-09-15 | TEQ | 2018-12-31 | Lincoln |  |  | 120 |  |  | Replace 2 line enterences at Lincoln Substation. | MI |  |  | Proposed | 200000 | Engineering |  | N | N | N
B in MTEP15 | B | East | METC | 1804 | 2014-12-02 |  | 3620 | 2014-11-17 | TEQ | 2018-12-31 | Marquette | Substation Equipment |  | 138 |  |  | upgrade station equipment (relaying at Marquette) | MI |  |  | Proposed |  |  |  | N | N | N | Y
B in MTEP15 | B | East | METC | 3927 | 2015-07-22 | METC_14_026 | 7489 | 2014-11-14 | TEQ | 2017-12-31 | Karn | Saginaw River | 1 | 138 |  |  | Replace limiting equipment from the Saginaw River 138 kV station. | MI |  |  | Proposed | 2800000 | Engineering |  | N | N | N | Y
B in MTEP15 | B | East | METC | 4525 | 2015-04-22 | METC_14_015 | 8666 | 2014-11-10 | TX | 2018-12-31 | Goss |  |  | 345 | 138 |  | Install a second 345/138 kV transformer at Goss | MI |  |  | Proposed | 4490000 | Engineering |  | N | N | N | Y
B in MTEP15 | B | East | METC | 4525 | 2015-04-22 | METC_14_015 | 8667 | 2014-11-10 | SUB | 2018-12-31 | Goss |  |  | 345 | 138 |  | Install new and upgrade existing station equipment at Goss. | MI |  |  | Proposed | 4810000 | Engineering |  | N | N | N | Y
B in MTEP15 | B | East | METC | 8123 | 2015-04-22 | METC_14_028 | 20475 | 2014-12-05 | TX | 2018-12-31 | Weeds Lake |  |  | 345 | 138 |  | Add a 2nd 345/138 kV transformer at Weeds Lake substation | MI |  |  | Proposed | 4500000 | Engineering |  | N | N | N
B in MTEP15 | B | East | METC | 8123 | 2015-04-22 | METC_14_028 | 20681 | 2015-07-13 | RLY | 2018-12-31 | Argenta |  |  | 345 |  |  | Upgrade line relaying at Argenta 345 kV station. | MI |  |  | Proposed | 250000 | Engineering |  | N | N | N
B in MTEP15 | B | East | METC | 8123 | 2015-04-22 | METC_14_028 | 20483 | 2014-12-05 | SUB | 2018-12-31 | Weeds Lake |  |  | 345 | 138 |  | Add 345 and 120 kV station equipment required to accomodate the new 345/138 kV transformer #2 and looping in the Argenta to Twin Branch 345 kV line. | MI |  |  | Proposed | 11750000 | Engineering |  | N | N | N
B in MTEP15 | B | East | METC | 8123 | 2015-04-22 | METC_14_028 | 20481 | 2014-12-05 | LN | 2018-12-31 | Weeds Lake | Twin Branch | 1 | 345 |  |  | Install approx 0.1 miles of new 345 kV double circuit structures, and use 2x954 ACSR to loop Agenta-Twin Branch 345 kV into Weeds Lake to create the Twin Branch(AEP) to Weeds Lake #1 circuit | MI |  | 0.1 | Proposed | 500000 | Engineering |  | N | N | N
B in MTEP15 | B | East | METC | 8123 | 2015-04-22 | METC_14_028 | 20479 | 2014-12-05 | LN | 2018-12-31 | Weeds Lake | Argenta | 2 | 345 |  |  | Install approx 0.1 miles of new 345 kV double circuit structures, and use 2x954 ACSR to loop Agenta-Twin Branch 345 kV into Weeds Lake to create the Argenta to Weeds Lake #2 circuit | MI |  | 0.1 | Proposed | 500000 | Engineering |  | N | N | N
B in MTEP15 | B | East | METC | 8130 | 2015-04-22 | METC_13_049 | 20497 | 2014-12-01 | TX | 2018-12-31 | Pere Marquette |  |  | 345 | 230 |  | Install a 345/230 kV transformer at Pere Marquette substation. | MI |  |  | Proposed | 4655000 | Engineering Preliminary |  | N | N | N
B in MTEP15 | B | East | METC | 8130 | 2015-04-22 | METC_13_049 | 20505 | 2014-12-01 | LN | 2018-12-31 | Keystone | Pere Marquette | 1 | 230 |  |  | Construct the new, approx. 75 mile, 230 kV transmission line between Pere Marquette and Keystone Substations | MI | 29.4 | 46.4 | Proposed | 66020000 | Engineering Preliminary |  | N | N | N
B in MTEP15 | B | East | METC | 8130 | 2015-04-22 | METC_13_049 | 20504 | 2014-12-01 | SUB | 2018-12-31 | Pere Marquette |  |  | 345 | 230 |  | Install all 230 and 345 kV terminal equipment associated with the new 345/230 kV transformer and the new 230 kV Pere Marquette to Keystone line. | MI |  |  | Proposed | 11561000 | Engineering Preliminary |  | N | N | N
B in MTEP15 | B | East | METC | 8130 | 2015-04-22 | METC_13_049 | 20503 | 2014-12-01 | SUB | 2018-12-31 | Keystone |  |  | 230 | 138 |  | Install all 230 and 138 kV terminal equipment associated with the new 230/138 kV transformer and the new 230 kV Pere Marquette to Keystone line. | MI |  |  | Proposed | 5595000 | Engineering Preliminary |  | N | N | N
B in MTEP15 | B | East | METC | 8130 | 2015-04-22 | METC_13_049 | 20499 | 2014-12-01 | TX | 2018-12-31 | Keystone |  |  | 230 | 138 |  | Install a 230/138 kV transformer at Keystone substation. | MI |  |  | Proposed | 2367000 | Engineering Preliminary |  | N | N | N
B in MTEP15 | B | East | NIPS | 8026 | 2014-12-01 |  | 20299 | 2014-11-26 | TX | 2017-12-31 | 17DEKALB 138 | 17DEKALB 69 | 1 | 138 | 69 | 112 | Upgrade to 112 MVA Transformer | IN |  |  | Proposed | 2700000 | Planning |  | N | N | N
B in MTEP15 | B | East | NIPS | 8026 | 2014-12-01 |  | 20301 | 2014-11-26 | LNup | 2017-12-31 | 17DEKALB | 05AUBURN | 1 | 138 |  | 54 | Rating Increase | IN |  |  | Proposed |  | Actual |  | N | N | N
B in MTEP15 | B | East | WPSC | 8222 | 2016-03-30 | Bradley line mods | 20610 | 2016-09-15 | LN | 2022-12-31 | Bradley 138kV & 69kV |  |  | 138 | 69 |  | Construction to support the upgrade of the Airport 138kV and 69kV station. | MI |  |  | Proposed | 1000000 | Budgetary |  | N | N | N
B in MTEP15 | B | East | WPSC | 8360 | 2015-03-30 | Alba New Station | 20649 | 2016-09-15 | SUB | 2022-12-31 | Alba |  |  | 138 | 69 |  | The Alba transmission tie station represents the oldest tie on the Wolverine system. It is located on a small parcel of leased property with limited expansion capability. The existing station shall be replaced with a new in/out transmission line design, three (3) breaker substation, modern control house, metering, protection relaying and a 50 or 90MVA, 138/69kV tie transformer, dependent upon load requirements. | MI |  |  | Proposed | 4000000 | Budgetary |  | N | N | N
B in MTEP15 | B | East | WPSC | 8361 | 2015-03-30 | Alba Line Mods | 20650 | 2016-09-15 | LN | 2022-12-31 | Alba |  |  | 138 | 69 |  | This project will address 138kV transmission line and structure reconfiguration costs associated with construction of the new Alba transmission substation, so that the 138kV ITC/METC looped transmission line segments can successfully enter and leave the substation | MI |  |  | Proposed | 1000000 | Budgetary |  | N | N | N
B in MTEP15 | B | South | CLECO | 7993 | 2015-04-01 |  | 20267 | 2015-07-09 | LNrc | 2024-05-01 | Rodemacher | East Leesville | 1 | 230 |  | 628 | Reconductor Rodemacher to East Leesville 230 kV line with Cardinal 954 ACSS/TW/HS285 | LA | 38.28 |  | Proposed | 10000000 | Planning |  | N | N | N
B in MTEP15 | B | South | Entergy-TX | 4799 | 2015-09-11 | 13-ETI-021 | 9067 | 2015-09-28 | SUB | 2021-06-01 | Dishman 230 kV Substation |  |  | 230 |  |  | Construct new substation | TX |  |  | Proposed | 10500000 |  |  | N | N | N | Y
B in MTEP15 | B | South | SMEPA | 8141 | 2015-04-03 |  | 20510 | 2014-09-15 | LNrb | 2026-06-01 | Hoy | Sharon GOAB | 1 | 69 |  | 126 | Rebuild L16 (Hoy - Sharon GOAB 69kV) using 795 ACSR with 161kV insulation and double circuit provisions. | MS | 3.98 |  | Proposed | 1273600 | Planning |  | N | N | N
B in MTEP15 | B | South | SMEPA | 8143 | 2015-04-03 |  | 20515 | 2014-09-15 | LNrb | 2026-06-01 | Foxworth | Pickwick GOAB | 1 | 69 |  | 126 | Rebuild L45A (Foxworth - Pickwick GOAB) using 795 ACSR conductor. | MS | 7.07 |  | Proposed | 2050300 | Planning |  | N | N | N
B in MTEP15 | B | West | ATC | 1718 | 2016-09-15 | F2081 | 3504 | 2016-09-15 | TX | 2026-06-01 | Custer | Transformer | 1 | 138 | 69 | 100 MVA | Install a 138/69 kV transformer at Custer substation | WI |  |  | Proposed | 4904268 |  |  | N | N | N | Y
B in MTEP15 | B | West | ATC | 1719 | 2016-09-15 | F2081 | 3505 | 2016-09-15 | LN | 2026-12-31 | Shoto | Custer | 1 | 138 |  | 290 MVA | Construct a Shoto-Custer 138 kV line | WI |  | 9.94 | Proposed | 22938000 |  |  | N | N | N | Y
B in MTEP15 | B | West | ATC | 3678 | 2014-09-10 | NP-Package1 | 6900 | 2014-03-31 | SUB | 2050-12-31 | Roberts |  |  | 138 |  |  | New 138 kV Sub at Roberts | MI |  |  | Proposed | 5300000 | Planning |  | N | N | N | Y
B in MTEP15 | B | West | ATC | 3678 | 2014-09-10 | NP-Package1 | 6909 | 2014-03-31 | LN | 2050-12-31 | Forsyth | Munising | 1 | 138 |  | 348 | Rebuild Forsyth-Munising 138 kV line | MI |  | 50 | Proposed | 75000000 | Planning |  | N | N | N | Y
B in MTEP15 | B | West | ATC | 3678 | 2014-09-10 | NP-Package1 | 6908 | 2014-03-31 | LN | 2050-12-31 | Pine River | Straits |  | 138 |  | 348 | Terminal work for conversion of double circuit 69kV line from Pine River to Straits to operate both circuits at 138 kV | MI |  |  | Proposed | 750000 | Planning |  | N | N | N | Y
B in MTEP15 | B | West | ATC | 3678 | 2014-09-10 | NP-Package1 | 6899 | 2014-03-31 | SUB | 2050-12-31 | Seney |  |  | 138 |  |  | New 138 kV Sub at Seney | MI |  |  | Proposed | 5300000 | Planning |  | N | N | N | Y
B in MTEP15 | B | West | ATC | 3678 | 2014-09-10 | NP-Package1 | 6898 | 2014-03-31 | TX | 2050-12-31 | Roberts |  | 1 | 138 | 69 | 60 | New 138/69 kV Transformer at Roberts | MI |  |  | Proposed | 2300000 | Planning |  | N | N | N | Y
B in MTEP15 | B | West | ATC | 3678 | 2014-09-10 | NP-Package1 | 6897 | 2014-03-31 | TX | 2050-12-31 | Seney |  | 1 | 138 | 69 | 60 | New 138/69 kV Transformer at Seney | MI |  |  | Proposed | 2300000 | Planning |  | N | N | N | Y
B in MTEP15 | B | West | ATC | 3678 | 2014-09-10 | NP-Package1 | 6896 | 2014-03-31 | LN | 2050-12-31 | Seney | Roberts | 1 | 138 |  | 348 | New 138kV line from Seney-Roberts | MI |  | 20 | Proposed | 22500000 | Planning |  | N | N | N | Y
B in MTEP15 | B | West | ATC | 3678 | 2014-09-10 | NP-Package1 | 6895 | 2014-03-31 | LN | 2050-12-31 | Munising | Seney | 1 | 138 |  | 348 | Rebuild Munising-Seney 138kV line on new ROW | MI |  | 30 | Proposed | 37500000 | Planning |  | N | N | N | Y
B in MTEP15 | B | West | ATC | 3678 | 2014-09-10 | NP-Package1 | 6907 | 2014-03-31 | SUB | 2050-12-31 | new sub near Pine River |  |  | 138 |  |  | New 138 kV Sub near Pine River | MI |  |  | Proposed | 4500000 | Planning |  | N | N | N | Y
B in MTEP15 | B | West | ATC | 3678 | 2014-09-10 | NP-Package1 | 6906 | 2014-03-31 | TX | 2050-12-31 | Pine River |  | 1 | 138 | 69 | 60 | New 138/69 kV Transformer at Pine River | MI |  |  | Proposed | 2300000 | Planning |  | N | N | N | Y
B in MTEP15 | B | West | ATC | 3678 | 2014-09-10 | NP-Package1 | 6905 | 2014-03-31 | SUB | 2050-12-31 | new sub near 9-Mile |  |  | 138 |  |  | New 138 kV Sub near 9-Mile | MI |  |  | Proposed | 5300000 | Planning |  | N | N | N | Y
B in MTEP15 | B | West | ATC | 3678 | 2014-09-10 | NP-Package1 | 6904 | 2014-03-31 | TX | 2050-12-31 | 9-Mile |  | 1 | 138 | 69 | 60 | New 138/69 kV Transformer at 9-Mile | MI |  |  | Proposed | 2300000 | Planning |  | N | N | N | Y
B in MTEP15 | B | West | ATC | 3678 | 2014-09-10 | NP-Package1 | 6903 | 2014-03-31 | LN | 2050-12-31 | 9-Mile | Pine River | 2 | 138 |  | 174 | Rebuild 9-Mile to Pine River as double circuit 138 kV (Operated as one 69 and one 138kV line), Circuit 2 | MI |  | 25 | Proposed | 15000000 | Planning |  | N | N | N | Y
B in MTEP15 | B | West | ATC | 3678 | 2014-09-10 | NP-Package1 | 6902 | 2014-03-31 | LN | 2050-12-31 | 9-Mile | Pine River | 1 | 138 |  | 348 | Rebuild 9-Mile to Pine River as double circuit 138 kV (Operated as one 69 and one 138kV line), Circuit 1 | MI |  | 25 | Proposed | 15000000 | Planning |  | N | N | N | Y
B in MTEP15 | B | West | ATC | 3678 | 2014-09-10 | NP-Package1 | 6901 | 2014-03-31 | LN | 2050-12-31 | Roberts | 9-Mile | 1 | 138 |  | 348 | Rebuild and Convert 69kV line from Roberts to 9-Mile to 138 kV operation | MI |  | 50 | Proposed | 67500000 | Planning |  | N | N | N | Y
B in MTEP15 | B | West | ATC | 3838 | 2014-09-10 | NP Project | 6914 | 2014-03-31 | LN | 2050-12-31 | Plains | National | 1 | 345 |  | 1204 | New 345 kV line from Plains-National | MI |  | 60 | Proposed | 144400000 | Planning |  | N | N | N | Y
B in MTEP15 | B | West | ATC | 3838 | 2014-09-10 | NP Project | 7250 | 2014-03-31 | LN | 2019-06-01 | Presque Isle | Tilden | 1 | 138 |  |  | Loop Presque Isle-Tilden 138 into new National Substation and uprate National-Tilden portion | WI |  |  | Proposed | 600000 | Planning |  | N | N | N | Y
B in MTEP15 | B | West | ATC | 3838 | 2014-09-10 | NP Project | 6918 | 2014-03-31 | TX | 2050-12-31 | National |  | 2 | 345 | 138 | 500 | New 345/138kV Transformer at National | MI |  |  | Proposed | 8400000 | Planning |  | N | N | N | Y
B in MTEP15 | B | West | ATC | 3838 | 2014-09-10 | NP Project | 6917 | 2014-03-31 | TX | 2050-12-31 | National |  | 1 | 345 | 138 | 500 | New 345/138kV Transformer at National | MI |  |  | Proposed | 8400000 | Planning |  | N | N | N | Y
B in MTEP15 | B | West | ATC | 3838 | 2014-09-10 | NP Project | 6916 | 2014-03-31 | SUB | 2050-12-31 | National |  |  | 345 |  |  | New 345kV sub near National | MI |  |  | Proposed | 19000000 | Planning |  | N | N | N | Y
B in MTEP15 | B | West | ATC | 7580 | 2014-09-10 | PR06427 | 20003 | 2014-07-07 | IND | 2018-06-01 | Werner West |  |  | 138 |  |  | Install new 25 Mvar inductor at Werner West 138 kV | WI |  |  | Proposed | 1524446 | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7581 | 2014-09-10 | PR06425 | 20004 | 2014-07-07 | IND | 2018-06-01 | Forest Junction |  |  | 138 |  |  | Install new 25 Mvar inductor at Forest Jct 138 kV | WI |  |  | Proposed | 1762635 | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7584 | 2015-01-14 | PR04986 | 20018 | 2015-01-14 | LNrb | 2022-12-31 | New Holstein | St Nazianz | 1 | 69 |  | 79 | Rebuild New Holstein - St Nazianz 69 kV | WI | 10.16 |  | Proposed | 15941421 | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7584 | 2015-01-14 | PR04986 | 20019 | 2015-01-14 | LNrb | 2022-12-31 | St Nazianz | Custer | 1 | 69 |  | 79 | Rebuild St Nazianz - Custer 69 kV | WI | 11.18 |  | Proposed |  | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7585 | 2014-09-18 | PR06370 | 20020 | 2014-07-07 | TX | 2023-06-01 | Colley Rd |  | T32 | 138 | 69 | 93 | Install new 138/69 kV 100 MVA transformer | WI |  |  | Proposed | 9944381 | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7586 | 2014-09-18 | PR05856 | 20021 | 2014-07-07 | TX | 2019-06-01 | Atlantic |  | 2 | 138 | 69 | 80 | Install new 138/69 kV 100 MVA transformer | WI |  |  | Proposed | 9043283 | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7586 | 2014-09-18 | PR05856 | 20032 | 2014-07-07 | TEQ | 2019-06-01 | Atlantic |  |  | 69 |  |  | Replace 138kV bus strain insulators | WI |  |  | Proposed |  | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7586 | 2014-09-18 | PR05856 | 20031 | 2014-07-07 | TEQ | 2019-06-01 | Atlantic |  |  | 69 |  |  | Replace 69kV bus strain insulators | WI |  |  | Proposed |  | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7586 | 2014-09-18 | PR05856 | 20030 | 2014-07-07 | CB | 2019-06-01 | Atlantic |  |  | 69 |  |  | Replace 69kV breaker 841 for asset renewal | WI |  |  | Proposed |  | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7586 | 2014-09-18 | PR05856 | 20029 | 2014-07-07 | CB | 2019-06-01 | Atlantic |  |  | 69 |  |  | Replace 69kV breaker 775 for asset renewal | WI |  |  | Proposed |  | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7586 | 2014-09-18 | PR05856 | 20028 | 2014-07-07 | CB | 2019-06-01 | Atlantic |  |  | 69 |  |  | Replace 69kV breaker 773 for asset renewal | WI |  |  | Proposed |  | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7586 | 2014-09-18 | PR05856 | 20027 | 2014-07-07 | CB | 2019-06-01 | Atlantic |  |  | 69 |  |  | New Portage 69kV line breaker | WI |  |  | Proposed |  | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7586 | 2014-09-18 | PR05856 | 20026 | 2014-07-07 | CB | 2019-06-01 | Atlantic |  |  | 69 |  |  | New Winona69 69kV line breaker | WI |  |  | Proposed |  | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7586 | 2014-09-18 | PR05856 | 20025 | 2014-07-07 | TEQ | 2019-06-01 | Atlantic |  |  | 69 |  |  | New switch around new 69kV breaker and existing switch to create second 69kV bus | WI |  |  | Proposed |  | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7586 | 2014-09-18 | PR05856 | 20024 | 2014-07-07 | CB | 2019-06-01 | Atlantic |  |  | 69 |  |  | new Atlantic 69 kV circuit breaker to create second 69kV bus | WI |  |  | Proposed |  | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7586 | 2014-09-18 | PR05856 | 20023 | 2014-07-07 | TEQ | 2019-06-01 | Atlantic |  |  | 138 |  |  | New 138kV bus for high side of new transformer | WI |  |  | Proposed |  | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7586 | 2014-09-18 | PR05856 | 20022 | 2014-07-07 | CB | 2019-06-01 | Atlantic |  |  | 138 |  |  | new Atlantic 138 kV circuit breaker | WI |  |  | Proposed |  | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7762 | 2014-09-18 | PR06460 | 20073 | 2014-09-10 | LNrb | 2023-12-31 | Harrison | Harrison Tap | 1 | 69 |  | 52 | Rebuild Y-19 from Harrison to Harrison Tap 69 kV | WI | 5.04 |  | Proposed |  | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7762 | 2014-09-18 | PR06460 | 20078 | 2014-09-10 | LNrb | 2023-12-31 | Wautoma Tap | Wautoma | 1 | 69 |  | 51 | Rebuild Y-19 Wautoma Tap - Wautoma | WI | 2.79 |  | Proposed |  | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7762 | 2014-09-18 | PR06460 | 20077 | 2014-09-10 | LNrb | 2023-12-31 | A15 | Wautoma Tap | 1 | 69 |  | 79 | Rebuild Y-19 A15 - Wautoma Tap | WI | 3.24 |  | Proposed |  | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7762 | 2014-09-18 | PR06460 | 20076 | 2014-09-10 | LNrb | 2023-12-31 | Wild Rose | A15 | 1 | 69 |  | 79 | Rebuild Y-19 Wild Rose - A15 | WI | 3.62 |  | Proposed |  | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7762 | 2014-09-18 | PR06460 | 20075 | 2014-09-10 | LNrb | 2023-12-31 | Wild Rose Tap | Wild Rose | 1 | 69 |  | 79 | Rebuild Y-19 from Wild Rose Tap - Wild Rose | WI | 2.79 |  | Proposed |  | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7762 | 2014-09-18 | PR06460 | 20074 | 2014-09-10 | LNrb | 2023-12-31 | Harrison Tap | Wild Rose Tap | 1 | 69 |  | 79 | Rebuild Y-19 from Harrison Tap - Wild Rose Tap | WI | 13.3 |  | Proposed |  | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7763 | 2014-09-18 | PR06467 | 20079 | 2014-09-10 | LNrb | 2023-12-31 | McKenna | A13 | 1 | 69 |  | 69 | Rebuild Y-47 McKenna - A13 | WI | 7.68 |  | Proposed |  | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7763 | 2014-09-18 | PR06467 | 20080 | 2014-09-10 | LNrb | 2023-12-31 | A13 | Castle Rock | 1 | 69 |  | 53 | Rebuild Y-47 A13 - Castle Rock | WI | 0.82 |  | Proposed |  | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7764 | 2016-08-11 | PR06465 | 20081 | 2014-09-10 | LNrb | 2023-12-31 | Wautoma | WC5 (ACEC Richford) | 1 | 69 |  | 79 | Rebuild Y-49 Wautoma - ACEC Richford | WI | 8.25 |  | Proposed |  | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7764 | 2016-08-11 | PR06465 | 20082 | 2014-09-10 | LNrb | 2023-12-31 | WC5 (ACEC Richford) | Chaffee Creek | 1 | 69 |  | 64 | Rebuild Y-49 ACEC Richford - Chaffee Creek | WI | 4.78 |  | Proposed |  | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7765 | 2014-09-18 | PR06467 | 20083 | 2014-09-10 | LNrb | 2023-12-31 | McKenna | A07 | 1 | 69 |  | 69 | Rebuild Y-145 McKenna - A07 | WI | 5.29 |  | Proposed |  | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7765 | 2014-09-18 | PR06467 | 20085 | 2014-09-10 | LNrb | 2023-12-31 | Lincoln Pumping Sta. Tap | Lincoln Pumping Sta. | 1 | 69 |  | 79 | Rebuild Y-145 Lincoln Pumping Sta. Tap - Lincoln Pumping Sta. | WI | 0.13 |  | Proposed |  | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 7765 | 2014-09-18 | PR06467 | 20084 | 2014-09-10 | LNrb | 2023-12-31 | A07 | Lincoln Pumping Station Tap | 1 | 69 |  | 79 | Rebuild Y-145 A07 - Lincoln Pumping Station Tap | WI | 1.19 |  | Proposed |  | Engineering |  | N | N | N
B in MTEP15 | B | West | ATC | 8073 | 2014-09-15 |  | 20390 | 2016-09-29 | LNup | 2023-12-01 | Plains | Arnold | 1 | 138 |  | 205 | Uprate 78652 Plains - Arnold 138 kV line | MI | 29 |  | Proposed | 43720000 | Planning |  | N | N | N
B in MTEP15 | B | West | ATC | 8073 | 2014-09-15 |  | 20392 | 2016-09-29 | TX | 2023-12-01 | Plains |  | 2 | 345 | 138 | 500 | Install a second 345/138 kV transformer at Plains Substation | MI |  |  | Proposed |  | Planning |  | N | N | N
B in MTEP15 | B | West | ATC | 8073 | 2014-09-15 |  | 20391 | 2016-09-29 | TX | 2023-12-01 | Plains |  | 1 | 345 | 138 | 500 | Upgrade existing 345/138 kV transformer at Plains Substation with a 500 MVA transformer | MI | 0 | 0 | Proposed |  | Planning |  | N | N | N
B in MTEP15 | B | West | ATC | 8076 | 2015-11-23 |  | 20718 | 2016-09-29 | LNcnv | 2023-12-01 | High Falls | Crivitz | 1 | 138 |  | 233 | Convert High Falls - Crivitz 69 kV line to create a Thunder - Crivitz 138 kV line | WI | 13 |  | Proposed |  |  |  | N | N | N
B in MTEP15 | B | West | ATC | 8076 | 2015-11-23 |  | 20717 | 2016-09-29 | LN | 2023-12-01 | Thunder | Plains | 1 | 345 |  | 1219 | Loop Morgan - Plains 345 into Thunder to create a new Thunder - Plains 345 kV line | WI |  | 40 | Proposed |  |  |  | N | N | N
B in MTEP15 | B | West | ATC | 8076 | 2015-11-23 |  | 20716 | 2016-09-29 | LN | 2023-12-01 | Morgan | Plains | 1 | 345 |  | 1219 | Loop Morgan - Plains 345 into Thunder to create a new Morgan - Thunder 345 kV line | WI |  | 31 | Proposed |  | Planning Preliminary |  | N | N | N
B in MTEP15 | B | West | ATC | 8076 | 2015-11-23 |  | 20715 | 2016-09-29 | LN | 2023-12-01 | Morgan | Thunder | 1 | 138 |  | 316 | New 138 kV line from Morgan - Thunder | WI |  | 31 | Proposed | 105000000 | Planning Preliminary |  | N | N | N
B in MTEP15 | B | West | ATC | 8076 | 2015-11-23 |  | 20714 | 2016-09-29 | TX | 2023-12-01 | Thunder |  | 1 | 138 | 69 | 100 | Install a new 138/69 kV transformer at Thunder Substation | WI |  |  | Proposed |  |  |  | N | N | N
B in MTEP15 | B | West | ATC | 8076 | 2015-11-23 |  | 20713 | 2016-09-29 | TX | 2023-12-01 | Thunder |  | 1 | 345 | 138 | 500 | Install a new 345/138 kV transformer at Thunder Substation | WI |  |  | Proposed |  |  |  | N | N | N
B in MTEP15 | B | West | ATC | 8082 | 2015-10-01 |  | 20407 | 2014-09-19 | LNrc | 2020-12-01 | Highway V | Preble | 1 | 138 |  | 220 | Reconductor X154 Highway V - Preble 138 kV line | WI | 2 |  | Proposed | 6000000 | Planning |  | N | N | N
B in MTEP15 | B | West | ATC | 8084 | 2014-09-15 |  | 20410 | 2014-09-19 | LNup | 2020-12-01 | Highway 8 | Clear Lake | 1 | 115 |  | 145 | Uprate Q95 Highway 8 - Clear Lake 115 kV line | WI | 21 |  | Proposed | 24000000 | Planning |  | N | N | N
B in MTEP15 | B | West | ATC | 8089 | 2015-01-14 |  | 20413 | 2016-02-04 | LNcnv | 2021-12-01 | Lakota | Mass | 1 | 138 |  | 139 | Convert the existing 69-kV line from Conover-Mass to 138-kV operation, replace existing conductor with a larger one, reterminate the line at the Lakota Road Substation instead of Conover | WI,MI | 58 |  | Proposed | 100000000 | Planning Preliminary |  | N | N | N
B in MTEP15 | B | West | ATC | 8089 | 2015-01-14 |  | 20415 | 2016-02-04 | SUB | 2021-12-01 | Mass |  |  | 138 | 69 | 100 | Modify the existing Mass Substation to accommodate 138-kV buswork and a new 138/69-kV transformer | MI |  |  | Proposed |  | Planning Preliminary |  | N | N | N
B in MTEP15 | B | West | ATC | 8089 | 2015-01-14 |  | 20414 | 2016-02-04 | LNcnv | 2021-12-01 | Mass | Winona | 1 | 138 |  | 139 | Convert the existing 69-kV line from Mass-Winona to 138-kV operation, replace existing conductor with a larger one | MI | 10.5 |  | Proposed |  | Planning Preliminary |  | N | N | N
B in MTEP15 | B | West | ATC | 8263 | 2014-11-04 | PR06463 FP:4485 WO:601142 | 20621 | 2014-10-07 | LNrb | 2021-12-31 | WWR | NSC | 1 | 69 |  | 69 | Rebuild Y-45 with new conductor. | WI | 0.22 |  | Proposed |  |  |  | N | N | N
B in MTEP15 | B | West | ATC | 8263 | 2014-11-04 | PR06463 FP:4485 WO:601142 | 20625 | 2014-10-07 | LNrb | 2021-12-31 | RUDT | RUD | 1 | 69 |  | 79 | Rebuild Y-45 with new conductor. | WI | 5.37 |  | Proposed |  |  |  | N | N | N
B in MTEP15 | B | West | ATC | 8263 | 2014-11-04 | PR06463 FP:4485 WO:601142 | 20624 | 2014-10-07 | LNrb | 2021-12-31 | NSC | NSCT | 1 | 69 |  | 79 | Rebuild Y-45 with new conductor. | WI | 0.82 |  | Proposed |  |  |  | N | N | N
B in MTEP15 | B | West | ATC | 8263 | 2014-11-04 | PR06463 FP:4485 WO:601142 | 20623 | 2014-10-07 | LNrb | 2021-12-31 | RUDT | SGL | 1 | 69 |  | 69 | Rebuild Y-45 with new conductor. | WI | 5.29 |  | Proposed | 18667906 | Planning |  | N | N | N
B in MTEP15 | B | West | ATC | 8263 | 2014-11-04 | PR06463 FP:4485 WO:601142 | 20622 | 2014-10-07 | LNrb | 2021-12-31 | NSC | RUDT | 1 | 69 |  | 69 | Rebuild Y-45 with new conductor. | WI | 5.47 |  | Proposed |  |  |  | N | N | N
B in MTEP15 | B | West | ATC | 8440 | 2014-11-11 | PR04970 | 20666 | 2014-11-11 | LNrc | 2019-12-31 | Oak Creek | Hayes | 1 | 138 |  | 194 | reconductor the 4/0 Cu section of 811 Oak Creek-Hayes with T2-477 | WI | 12.85 |  | Proposed | 13743440 | Planning |  | N | N | N
B in MTEP15 | B | West | ATC | 8441 | 2014-11-11 | PR04202 | 20667 | 2014-11-11 | SUB | 2016-12-31 | Escanaba |  |  | 69 |  |  | New 69 kV Escanaba Switching Station | MI |  |  | Proposed | 5616000 | Planning |  | N | N | N
B in MTEP15 | B | West | ATC | 8441 | 2014-11-11 | PR04202 | 20669 | 2014-11-11 | TX | 2016-12-31 | Escanaba |  | 2 | 69 | 12.47 | 28 | Escanaba T2 | MI |  |  | Proposed |  |  |  | N | N | N
B in MTEP15 | B | West | ATC | 8441 | 2014-11-11 | PR04202 | 20668 | 2014-11-11 | TX | 2016-12-31 | Escanaba |  | 1 | 69 | 12.47 | 28 | Escanaba T1 | MI |  |  | Proposed |  |  |  | N | N | N
B in MTEP15 | B | West | ATC | 8444 | 2015-01-14 |  | 20672 | 2015-01-14 | LNrb | 2020-12-31 | First Ave | Sawyer | 1 | 69 |  | 68 | Replace UG Cable from 1st Ave-Sawyer 69 kV line | WI | 1 |  | Proposed |  |  |  | N | N | N
B in MTEP15 | B | West | ATC | 8620 | 2015-01-07 |  | 20709 | 2015-01-07 | LN | 2018-12-12 | Howards Grove | Erdman | 1 | 138 |  | 294 | Build new Howards Grove - Erdman 138 kV line. | WI |  | 6.6 | Proposed |  |  |  | N | N | N
B in MTEP15 | B | West | ATC | 8641 | 2015-01-08 | PR7009 | 20712 | 2015-01-08 | CAP | 2023-06-01 | Boscobel |  | 1 | 69 |  |  | Add a second 8.16 MVAR capacitor. | WI |  |  | Proposed | 1394539 | Planning |  | N | N | N
B in MTEP15 | B | West | GRE | 2632 | 2014-12-19 | 20385 | 4643 | 2014-12-19 | LN | 2022-11-30 | Onigum | Birch Lake | 1 | 115 |  | 140 | Onigum 115 kV conversion, Birch Lake 115 kV breaker and deadend | MN | 9.45 |  | Proposed | 5300000 |  |  | N | N | N | Y
B in MTEP15 | B | West | ITCM | 8111 | 2015-05-29 | CR-N Liberty Upgrades | 20458 | 2015-01-23 | LN | 2024-12-31 | Tharp | North Liberty | 1 | 161 | 69 | 446 MVA | New 161-69 kV double circuit line from Tharp to new North Liberty 161/69 kV Substation | IA |  | 9.5 | Proposed | 21125552.4 | Engineering |  | N | N | N
B in MTEP15 | B | West | ITCM | 8111 | 2015-05-29 | CR-N Liberty Upgrades | 20736 | 2015-01-23 | LN | 2024-12-31 | Conroy | Homestead | 1 | 69 | 69 | 77 MVA | Build a new Conroy to Homestead 69kV line. | IA |  | 5 | Proposed | 7479482.4 | Engineering |  | N | N | N
B in MTEP15 | B | West | ITCM | 8111 | 2015-05-29 | CR-N Liberty Upgrades | 20735 | 2015-01-23 | SwSta | 2024-12-31 | Heartland | Switch Station |  | 69 | 69 |  | ITC will add a new Heartland switch station with 3 terminals. | IA |  |  | Proposed | 3979449.6 | Engineering |  | N | N | N
B in MTEP15 | B | West | ITCM | 8111 | 2015-05-29 | CR-N Liberty Upgrades | 20469 | 2015-01-23 | SUB | 2022-12-31 | Fairfax | Terminal |  | 161 |  | 558 MVA | Fairfax substation 161 kV bus position addition | IA |  |  | Proposed | 904827.6 | Engineering |  | N | N | N
B in MTEP15 | B | West | ITCM | 8111 | 2015-05-29 | CR-N Liberty Upgrades | 20467 | 2015-01-23 | LN | 2019-12-31 | Rose Hollow | Heartland | 1 | 69 | 69 | 140 MVA | Build a new Rose Hollow - Heartland 69 kV line (double circuit with CIPCO owned 161kV) | IA |  | 9 | Proposed | 14929987.2 | Engineering |  | N | N | N
B in MTEP15 | B | West | ITCM | 8111 | 2015-05-29 | CR-N Liberty Upgrades | 20465 | 2015-01-23 | LN | 2022-12-31 | Tharp | Fairfax | 1 | 161 | 161 | 446 MVA | New 161 kV line from Fairfax to Tharp. | IA |  | 8 | Proposed | 17897122.8 | Engineering |  | N | N | N
B in MTEP15 | B | West | ITCM | 8111 | 2015-05-29 | CR-N Liberty Upgrades | 20464 | 2015-01-23 | SwSta | 2024-12-31 | Conroy | Substation |  | 69 | 69 |  | ITC will install a new Conroy 69 kV switch station with 3 terminals. | IA |  |  | Proposed | 3979449.6 | Engineering |  | N | N | N
B in MTEP15 | B | West | ITCM | 8111 | 2015-05-29 | CR-N Liberty Upgrades | 20463 | 2015-01-23 | TX | 2019-12-31 | Rose Hollow | Transformer | 1 | 161 | 69 | 150 MVA | Rose Hollow new 150 MVA 161/69 kV transformer | IA |  |  | Proposed |  | Planning Preliminary |  | N | N | N
B in MTEP15 | B | West | ITCM | 8111 | 2015-05-29 | CR-N Liberty Upgrades | 20459 | 2015-01-23 | SUB | 2019-12-31 | Rose Hollow | Substation |  | 161 | 69 |  | Rose Hollow 161 kV bus position addition, 69kV terminal addition, and 161/69kV tranformer upgrade. | IA |  |  | Proposed | 4186710 | Engineering |  | N | N | N
B in MTEP15 | B | West | ITCM | 8842 | 2015-03-19 | Quad-Rock Ck 345 | 20759 | 2016-01-08 | LN | 2024-12-31 | Quad Cities | Rock Creek | 2 | 345 |  | 1246 MVA | Build the Quad Cities to Rock Creek 345kV line to double circuit and add 345kV terminals at both substations. | IA,IL |  |  | Proposed |  |  |  | N | N | N
B in MTEP15 | B | West | ITCM | 8843 | 2015-03-19 | Rock Creek 2nd 345/161kV | 20760 | 2016-01-08 | TX | 2024-12-31 | Rock Creek |  |  | 345 | 161 | 450 MVA | Add a 2nd 345/161kV 450MVA transformer at Rock Creek. | IA |  |  | Proposed |  |  |  | N | N | N
B in MTEP15 | B | West | ITCM | 8844 | 2015-03-19 | Albany-Galena 161kV Rebuild | 20761 | 2015-03-13 | LNrb | 2024-12-31 | Albany | York | 1 | 161 |  | 446 MVA | Rebuild Albany-York161kV to 446MVA. | IL | 15.04 |  | Proposed |  |  |  | N | N | N
B in MTEP15 | B | West | ITCM | 8844 | 2015-03-19 | Albany-Galena 161kV Rebuild | 20763 | 2015-03-13 | LNrb |  | Savanna | Galena | 1 | 161 |  | 446 MVA | Rebuild Savanna to Galena 161kV to 446 MVA. | IL | 29.16 |  | Proposed |  |  |  | N | N | N
B in MTEP15 | B | West | ITCM | 8844 | 2015-03-19 | Albany-Galena 161kV Rebuild | 20762 | 2015-03-13 | LNrb |  | York | Savanna | 1 | 161 |  |  | Rebuild York to Savanna 161kV to 446 MVA. | IL | 8.65 |  | Proposed |  |  |  | N | N | N
B in MTEP15 | B | West | MEC | 8023 | 2015-04-09 |  | 20297 | 2015-03-10 | LNrc |  | Hills | Sub E (Iowa City) | 1 | 161 |  | 410 MVA | Reconductor 161 kV line | IA | 6.6 |  | Proposed | 4000000 | Planning |  | N | N | N
B in MTEP15 | B | West | MEC | 8114 | 2015-04-09 |  | 20451 | 2016-09-14 | LNup | 2018-06-01 | SubA | Sub 84 |  | 69 |  | 72 | Replace structures to increase line clearance and rating. | IA | 8.6 |  | Proposed | 225000 | Planning |  | N | N | N | NT
B in MTEP15 | B | West | MP | 7913 | 2015-05-07 |  | 20154 | 2015-04-02 | LNrc | 2019-11-01 | Little Falls | St. Stephen Tap | 1 | 115 |  | 144 | Little Falls - Langola Tap - (Future) St. Stephen Tap reconductor with 636 ACSR @ 75C | MN | 17.57 | 0 | Proposed | 6800000 | Planning |  | N | N | N | Y
B in MTEP15 | B | West | MPC, OTP | 4237 | 2014-09-12 | OTP, MPC | 7994 | 2014-09-12 | SUB | 2021-11-15 | Hensel 115 kV | Hensel 115 kV | 1 | 115 |  |  | Hensel 115 kV Sub Expansion | ND |  |  | Proposed | 500000 | Planning |  | N | N | N | Y
B in MTEP15 | B | West | MPC, OTP | 4237 | 2014-09-12 | OTP, MPC | 7996 | 2014-09-12 | LN | 2021-11-15 | Hensel 115 kV | Drayton 115 kV | 1 | 115 |  | 147 | Hensel-Drayton 115 kV New 22 miles Transmission Line | ND |  | 22 | Proposed | 5000000 | Planning |  | N | N | N | Y
B in MTEP15 | B | West | MPC, OTP | 4237 | 2014-09-12 | OTP, MPC | 7995 | 2014-09-12 | SUB | 2021-11-15 | Drayton 115 kV | Drayton 115 kV | 1 | 115 |  |  | Drayton 115 kV Sub Expansion | ND |  |  | Proposed | 1000000 | Planning |  | N | N | N | Y
B in MTEP15 | B | West | OTP | 4236 | 2015-03-20 | OTP | 7993 | 2014-03-24 | TX | 2020-11-15 | Ortonville 115/41.6 kV | Ortonville 115/41.6 kV | 1 | 115 | 41.6 | 40 | Ortonville 115/41.6 kV 40 MVA Transformer Replacement | MN |  |  | Proposed | 1000000 | Planning |  | N | N | N | Y
B in MTEP15 | B | West | OTP | 8085 | 2016-09-14 |  | 20432 | 2015-03-20 | LN | 2020-11-15 | GRE Kerkhoven 115kV | OTP Kerkhoven 115 kV | 1 | 115 | 12.5 | 102 | Add a new 115 kV - 1 mile - 266 ACSR transmission line from GRE Kerkhoven to OTP Kerkhoven Town. | MN |  | 1 | Proposed | 600000 | Planning Preliminary |  | N | N | N | Y
B in MTEP15 | B | West | OTP | 8085 | 2016-09-14 |  | 20433 | 2015-03-20 | SUB | 2020-11-15 | GRE Kerkhoven 115 kV | OTP Kerkhoven 115/12.5 |  | 115 | 12.5 | 10MVA | Building new substation due to town conversion from existing 41.6 kV line to 115 to 12.5kV. Transformer 10MVA | MN |  | 4 | Proposed | 1100000 | Planning Preliminary |  | N | N | N | Y
Note on T3: Upgraded or on existing rights of way